standard input (SI)

DESIGNER/CONSULTANT:

cONSULTANT PROJECT MANAGER:

DEPARTMENT PROJECT MANAGER:

fINAL SUBMISSION DATE:

| Revisions to 2007 SI: |
| --- |
| date | BDC | Description / reason |
| JAN 19 2017 | BDC17S-02 | REVISION TO SUBSECTION 107.04 |
| JAN 18 2017 | BDC16S-10 | REVISION TO SUBPART 203.03.01 |
| DEC 21 2016 | BDC16S-07 | Revision to Subpart 610.03.01 and 610.03.02 |
| DEC 16 2016 | BDC16S-08 | Revision to Subpart 202.03.03 |
| DEC 15 2016 |  | Revision to Subpart 912.04.01 |
| nov 04 2016 | BDC16S-05 | Revision to Subpart 106.07.02 |
| Sep 22 2016 | BDC15S-13 | Revision to Section 503 |
| Sep 12 2016 | BDC16S-02 | Revision to Subparts/Subsections 159.03.06, 159.04, 610.03.02, and 610.04 |
| AUG 24 2016 | BDC16S-03 | Revision to Subparts/Subsections/Section 101.03, 159.03.02, 701.03.02, 701.03.03, 701.03.06, 701.03.07, 701.03.15, 701.04, 704, and 1001.04 |
| AUG 15 2016 | BDC16S-01R | Revision to Subsection 102.04 |
| JUL 29 2016 | BDC16S-01 | Revision to Subsection 102.04 |
| JUL 15 2016 | BDC15S-09 | Addition of new Subpart 108.07.03 to the 2007 SI |
| Feb 17 2016 | BDC15S-14 | Addition of new Subsection 106.10 and Revision to Subsection 108.01 |
| Feb 08 2016 | BDC15S-08 | Addition of new Subpart 105.01.03 |
| Nov 23, 2015 | BDC15S-11 | Revision to Subpart 610.03.07 and subsection 610.04 |
| OCT 28, 2015 | BDC14S-05 | Revision to Subparts/Subsections/division 507, 507.02.01, 507.03.06, 507.04, 509, 509.01, 509.03.01, 509.04, 906.04.01, 906.07 and 913.03.01 |
| Jul 30, 2015 | BDC15S-06 | Revision to Subparts 511.03.01, 606.03.02, 903.02.04, 903.06.02, 904.01.01, 904.01.02, 904.02.02, 904.03.01, 904.03.02, 904.04.02, 905.01.03, 906.04.05, Subsections 906.01, 908.03, 915.05, and Test Method NJDOT C-2 |
| Jun 30, 2015 | BDC15S-07 | Revision to Subparts 401.03.03, 404.03.01 and 406.03.01 |
| Jun 02 2015 |  | Revision to Subpart 403.03.01 d &E and 406.03.01 E |
| May 20 2015 | BDC14S-11 | Revision to Subparts 159.02.01 and 159.03.02 and addition of Subsection 913.04 |
| Apr 22 2015 | BDC15S-03 | Revision to Subpart 504.03.02 |
| Apr 08 2015 | BDC15S-04 | Deletion of the FHWA Attachment No. 5(A) |
| Mar 30 2015 | BDC15S-02 | Revision to Subpart 610.03.07 and Subsection 610.04 |
| Mar 26 2015 | BDC15S-01 | Addition of new Division 420 (PAVEMENT PRESERVATION TREATMENTS) to the 2007 Standard Specification, revision to Subpart 504.02.01; and Subsection 901.07 and addition of Subsections 902.09, 902.10 and Section 1012 |
| Jan 26 2015 | BDC14S-13 | Revision to Subparts 453.03.01 and 453.03.02 |
| Oct 31 2014 | BDC14S-04 | Revision to Subpart 202.03.07 |
| Oct 30 2014 | BDC14S-12 | Revision to Test Method B-3 |
| Sep 26 2014 | BDC14S-10 | Revision to Subpart 152.03.02 |
| Aug 29 2014 | BDC14S-07 | Revision to Subparts/Subsections 401.02.01, 401.03.02, 401.03.03, 401.04, 403.02.02, 403.03.01, 403.04, 404.03.01, 406.03.01, 902.01.01, 902.02.01, 902.02.02, 902.02.03, 902.02.04, 902.03.01, 902.04.01, 902.04.02, 902.04.03, 902.05.01, 902.05.02, 902.05.03, 902.06.01 and 902.06.03. Addition of Subpart 902.01.05 and Subsections 902.07 and 902.08 |
| Aug 15 2014 | BDC14S-09 | Revision to Subsection 102.01 |
| jun 25 2014 | BDC14S-08 | Revision to the State Attachment No. 1 |
| Jun 20 2014 | BDC14S-06 | Revision to Subsection 109.06 |
| may 08 2014 | BDC14S-02 | Revision to Subsection 102.04 and Subpart 108.07.02 |
| Feb 28 2014 | BDC14S-01 | Revision to Subpart 202.03.07 |
| Feb 04 2014 | -------------- | Revision to 105.07.01(B) 3, Bureau of Electrical Maintenance, Central region ADDRESS has been changed. |
| Jan 24 2014 | BDC13S-14 | Revision to Subparts/Subsections 106.03, 106.07, 904.01.02, 904.01.06, 904.02.02, 904.02.06, 904.03.02, 904.03.06, 904.04.02, 904.04.06, 905.01, 909.02.01, 909.02.02, 913.01.01, 913.01.02, 913.01.03, 913.01.04, and 913.01.05 |
| JAN 15 2014 | -------------- | Revision to subpart 65X.03.01(A) updated the list of JCP&L approved Subcontractors, and The Links for civil rights forms have been revised. |
| Dec 18 2013 | BDC13S-13 | Revision to Subsections/Subparts 101.01, 102.09, 102.10, 102.15, 108.10, 108.20, 152.03.01, 156.03.01 and 159.03.02 |
| Nov 21 2013 | BDC13S-11 | Revision to Subpart 610.03.07 and Subsection 610.04 |
| Sept 18 2013 | -------------- | Revision to Subpart 159.03.06, Subsection 159.04 and 610.02.01 (Renamed items per BDC13S-08) |
| Sept 17 2013 | -------------- | Revision IN THE INSTRUCTIONAL TEXT OF subsection 106.09 |
| Aug 19 2013 | BDC13S-08 | Revision to Subparts/Subsection 610.03.01, 610.03.02, 610.04, 912.03.01, and 912.03.02 |
| Aug 12 2013 | BDC13S-10 | Revision to Subpart 404.03.01 |
| July 30 2013 | BDC12S-04 | Revision to Subparts/Subsections 159.02.01, 159.03.02, 159.04, 611.01, 611.02, 611.03.02, and 611.04 |
| Jun 26 2013 | BDC13S-09 | Revision to Subparts 912.03.01, 912.03.02 and 912.04.01 |
| JUN 10 2013 | BDC13S-04 | Revision to Subparts 105.07.01, 159.03.02, 701.03.01, 701.03.15, 704.02.01, 704.03.01, 704.03.02, 704.03.03, 704.03.04, 704.03.05, 704.03.06, 704.03.07, 704.03.08, 704.03.09, and Subsection 918.01 |
| May 13 2013 | BDC13S-07 | Revision to Subsection 105.05 |
| Apr 19 2013 | BDC13S-06 | Revision to Subpart 903.03.05 |
| Mar 08 2013 | BDC13S-05 | Revision to Subpart 159.03.08 |
| Mar 01 2013 | BDC13S-01 | Revision to Subparts 155.03.01 and 156.03.01 |
| Feb 22 2013 | BDC12S-15 | Revision to Subparts 203.03.01, 401.03.03, 401.03.04, 401.04, 402.03.02, 403.03.01, 902.02.04, 902.07.02 and 902.07.04 |
| Feb 15 2013 | BDC12S-10 | Revision to Subpart 159.03.06 and Subsection 159.04 |
| JAN 28 2013 | BDC13S-03 | Revision to the FHWA Attachment No. 4 |
| Jan 18 2013 | BDC13S-02 | Revision to Subsection 102.10 |
| Dec 17 2012 | BDC12S-08 | Revision to Subsection 509.04 |
| NOV 21 2012 | BDC12S-14 | Revision to Subparts/Subsection 506.03.03, 506.04 and 507.03.06 |
| Oct 12 2012 | BDC12S-12 | Revision to Subparts 201.03.01 and 202.03.03 |
| Sep 28 2012 | BDC12S-11 | Revision to Subsection 601.04 |
| Sep 21 2012 | BDC12S-13 | Revision to Subsections 151.04, 152.04, 157.04 and 160.04 |
| aUG 30 2012 | -------------- | Revision to THE CONTACT INFORMATION FOR REGIONAL Materials engineer’s office IN THE INSTRUCTIONAL TEXT OF subsection 156.03 |
| July 20 2012 | BDC12S-09 | Revision to the Federal Attachment No.1 (Form FHWA-1273) |
| may 29 2012 | BDC12S-07 | Revision to Subsections 101.01, 101.03, 104.03 and 109.05 |
| may 02 2012 | BDC12S-03 | Revision to subpart 401.03.03 and Test Method R-1 |
| Apr 20 2012 | BDC12S-02 | Revised Attachments to the Special Provisions for the FHWA & Wholly State Funded Projects |
| MAr 30 2012 | BDC12s-06 | Revision to Subsection 109.09, Subparts 155.03.01 and 156.03.01 |
| feb 14 2012 | bdc11s-13 | Revision to Subparts/Subsections 151.03.01, 152.03.01, 155.03.03 and 155.04 subsections 651.04, 652.04 and 653.04 |
| JAN 12 2012 | bdc12s-01 | Revision to subsection 101.04 |
| Dec 12 2011 | bdc11s-12 | Revision to subsections 651.04, 652.04 and 653.04 |
| nov 15 2011 | bdc11s-03 | Revision to subsections 102.04, 505.03, 506.03, 509.03, and 554.04 |
| Oct 25 2011 | bdc11s-10 | Revision to Subsections/Subparts 108.14, 155.03.01, 157.04, 158.03.02, and 159.04 |
| aug 26 2011 | BDC11S-08 | Revision to Subparts 401.03.05, 902.03.03, 902.04.03, 902.06.03, and 903.05.04 |
| Aug 12 2011 | BDC11S-09 | Revision to the State Attachment No. 1 |
| July 11 2011 | BDC11S-06 | Revision to Subparts 607.03.02, 607.03.04, 610.03.04 and Subsection 611.02 |
| Jun 17 2011 | BDC11S-07 | Revision to subpart 160.03.01 |
| Jun 10 2011 | BDC11S-05 | addition of new to subsection 107.17 |
| May 25 2011 | -------------- | Revision to subsections/subpart 105.05, 107.09 , 608.02.01 and 608.03.06 |
| Apr 10 2011 | -------------- | Revision to subpart 65X.03.01(A) updated the list of JCP&L approved Subcontractors |
| Mar 30 2011 | BDC11S-01 | Revision to Subsections/Subparts 303.03.01, 401.02.01, 401.03.01, 401.03.02, 401.03.03, 402.01, 402.02.01, 402.02.02, 402.04, 404.03.01, 902.02.02, 902.03.02, 902.03.03, 902.04.03, 902.05.01, 902.05.02, 902.05.03, 902.06.03, 1009.01; and test method B-8. Added Subpart 402.03.02, Section 406, Subsections 902.07, 902.08 & 1009.03 and test methods B-10, B-11 and B-12 |
| Mar 23 2011 | BDC11S-02 | Revision to subpart 152.03.01 |
| DEC 29 2010 | BDC10S-08 | Revision to Subsections 105.05, 106.04, 108.09, 159.03, 159.04, 512.04, 701.03, 701.04, 704.02, 704.03, 704.04, 918.01, 1001.04 and 1001.05 |
| DEC 22 2010 | BDC10S-12 | Revision to Subsections 105.07, 108.11, 152.04, 153.03, 155.03, and 157.03 |
| Nov 16 2010 | BDC10S-10 | Revision to Subsections 609.03, 609.04, & 913.01 |
| Nov 05 2010 | BDC10S-11 | Revision to Subsection 106.03 |
| Oct 14 2010 | BDC10S-02 | Revision to Section 608 and Subsection 919.15 |
| sep 10 2010 | bdc10S-09 | Revision to Subsections152.03, 201.03, 507.03, 509.03, 905.01, & 1011.03 |
| Jun 04 2010 | BDC10S-07 | Revision to Subsections 107.12 & 108.01 |
| May 18 2010 | BDC10S-05 | Revision to Subsections 105.07, 153.03, & 157.03 |
| Apr 26 2010 | BDC10S-04 | Revision TO SUBPART 156.03.05 |
| Apr 16 2010 | -------------- | Revision TO 104.03.09, 109.07 & 607.03.01 (D) |
| Apr 09 2010 | bdc09s-01 | Revision to Subsections 612.02, 612.03, 612.04, & 911.02 |
| Mar 31 2010 | BDC10S-06 | Revision to the FHWA Attachment No. 1 (FHWA-1273) |
| Mar 29 2010 | BDC10S-01 | Revision to Subsection 507.04 and Subpart 905.03.03 |
| Mar 17 2010 | BDC10S-03 | Revision to Subsection 901.11 |
| mar 10 2010 | -------------- | Revision to subpart 65X.03.01(A) updated & REORGANIZED the list of JCP&L approved Subcontractors and instructions |
| Jan 26 2010 | BDC09S-11 | revision to subsections 508.02 & 508.04 and addition of new Subparts 508.03.03 & 909.02.09 |
| jan 19 2010 | bdc09s-12 | Revision to Subsection 108.06 |
| Dec 07 2009 | BDC09S-08 | revision to subsections 159.03.02, 609.03.01, 610.03.06, &911.03 |
| Nov 24 2009 | BDC09S-10 | Revision to the State Attachment No. 1 |
| Oct 09 2009 | BDC09S-09 | Revision to Subsection 101.01 |
| Sep 21 2009 | -------------- | Revision to 654.03.01 & instructions for JCP&L based on QIA-46 |
| Aug 13 2009 | BDC09S-07 | Revision TO SUBPART 160.03.01 |
| Jun 15 2009 | BDC09S-06 | Revision to Subsections 912.03 & 912.04 |
| May 29 2009 | BDC09S-05 | Revision to Subsection 102.03 |
| May 18 2009 | BDC09S-04 | Revision to FHWA and State Attachments |
| Apr 16 2009 | BDC09S-03R | Revision to Subsection 101.01 of the 2007 Standard Input |
| Mar 30 2009 | BDC09S-03 | Revision to Subsection 101.01 of the 2007 Standard Input |
| feb 17 2009 | bdc08s-02 | revision to subsections 101.04, 102.02, 102.04, 104.03, 105.07, 107.04, 107.09, 107.11, 107.12, 108.02, 108.08, 108.19, 108.20, 152.03, 159.02, 159.03, 159.03, 159.04, 160.03, 160.03, 201.03, 202.02, 453.03, 502.03, 503.03, 506.03, 507.04, 511.02, 513.02, 513.03, 606.03, 610.04, 652.03, Section 654, 701.03, 701.03, 701.04, 704.03, 704.03, 704.03, 704.03, 704.03, 704.03, 811.03, 903.03, 904.01, 904.02, 905.01, 911.02, 914.04, 1001.04, & 1001.05 |

SPECIAL PROVISIONS

1**************************************************************************************************************************1

include PROJECT DESCRIPTION AS SHOWN ON THE KEY sheet, AND FEDERAL PROJECT NUMBER (CONSTRUCTION) WHEN APPLICABLE.

subject matter expert (Sme) CONTACT – project manager

1**************************************************************************************************************************1

AUTHORIZATION OF CONTRACT

1**************************************************************************************************************************1

INclude THE FOLLOWING FOR fhwa funded projects

The Contract is authorized by the provisions of Title 27 of the Revised Statutes of New Jersey and supplements thereto, and Title 23 of the United States Code - Highways.

1**************************************************************************************************************************1

*****OR*****

1**************************************************************************************************************************1

INclude THE FOLLOWING FOR wholly state funded projects

The Contract is authorized by the provisions of Title 27 of the Revised Statutes of New Jersey and supplements thereto.

1**************************************************************************************************************************1

SPECIFICATIONS TO BE USED

The 2007 Standard Specifications for Road and Bridge Construction, of the New Jersey Department of Transportation as amended herein will govern the construction of this Project and the execution of the Contract.

These Special Provisions consist of the following:

1**************************************************************************************************************************1

complete and include the following

Pages 1 to ___ inclusive.

1**************************************************************************************************************************1

1**************************************************************************************************************************1

INclude THE FOLLOWING FOR fhwa funded projects

General wage determinations issued under Davis-Bacon and related acts, published by US Department of Labor, may be obtained from the Web Determinations online web site at http://www.wdol.gov/dba.aspx#0  Select state, county and construction type heading: HIGHWAY where the Project is to be performed then click Search.

Pay the prevailing wage rates determined by the United States Secretary of Labor and the New Jersey Department of Labor.  If the prevailing wage rate prescribed for any craft by the United States Secretary of Labor is not the same as the prevailing wage rate prescribed for that craft by the New Jersey Department of Labor, pay the higher rate.

State wage rates may be obtained from the New Jersey Department of Labor & Workforce Development (Telephone:  609-292-2259) or by accessing the Department of Labor & Workforce Development’s web site at http://lwd.dol.state.nj.us/labor/wagehour/wagehour_index.html. The State wage rates in effect at the time of award are part of this Contract, pursuant to Chapter 150, Laws of 1963 (N.J.S.A. 34:11-56.25 et seq.).

If an employee of the Contractor or subcontractor has been paid a rate of wages less than the prevailing wage, the Department may suspend the Work, and declare the Contractor in default.

The following FHWA funded project Attachments that are located at the end of these Special Provisions:"

1.	Required Contract Provisions, Federal-Aid Construction Contracts (Form FHWA-1273).

2.	Standard Federal Equal Employment Opportunity Construction Contract Specifications (Executive Order 11246).

3.	Notice of Requirement for Affirmative Action to Ensure Equal Employment Opportunity (Executive Order 11246).

4.	State of New Jersey Equal Employment Opportunity for Contracts Funded by FHWA.

2**************************************************************************************2

5.	Emerging Small Business Enterprise Utilization Attachment, FHWA Funded Contracts.

OR

5.	Disadvantaged Business Enterprise Utilization Attachment, FHWA Funded Contracts

The ESBE/DBE goals request form and classification codes worksheet are available at

http://www.state.nj.us/transportation/eng/documents/procedures/doc/ESBE-DBEGoalsRequest2012.doc

http://www.state.nj.us/transportation/eng/documents/procedures/xls/WorkClassD2012.xls

e-mail the completed form and worksheet along with a copy of the Engineer’s Estimate to THE BUREAU OF CONSTRUCTION SERVICES at CSPD@dot.state.nj.us

allow AT LEAST 10 days for CONSTRUCTION SERVICES to respond with a determination on which attachments (FHWA ATTAchment NO. 5 for ESBE or FHWA attachment NO. 5 for DBE) is to be used for the project.

upon receiving the information, fill in the blank (GOALS FOR THIS PROJECT) on the appropriate FHWA attachment LOCATED at the end of these special provisions.

delete the inappropriate fhwa ATTACHMENT

sme CONTACT – Office of Civil Rights, Contract Compliance

2**************************************************************************************2

2**************************************************************************************2

6.	Equal Employment Opportunity Special Provisions.

Follow instructions and fill out the training request form at

http://www.state.nj.us/transportation/eng/documents/procedures/doc/TraineeRequest2012.doc

submit request to the Civil Rights, Contract Compliance at least 10 days in advance, by e-mailing, CIVIL RIGHTS Contract compliance at: cr.contcompl@dot.state.nj.us . Obtain required information.

upon receiving the information, fill in the blanks on fhwa attachment no.6 (training special provisions) located at the end of these special provisions.

sme CONTACT – Office of Civil Rights, Contract Compliance

2**************************************************************************************2

7.	Special Contract Provisions for Investigating, Reporting, and Resolving Employment Discrimination and Sexual Harassment Complaints.

list here & include additional project specific ATTACHMENTS required for the project at the end of these Special Provisions, SUCH AS ASBESTOS ABATEMENT

The following additional project specific Attachments are located at the end of these Special Provisions:

1.

1**************************************************************************************************************************1

1**************************************************************************************************************************1

INclude THE FOLLOWING FOR wholly state funded projects

State wage rates may be obtained from the New Jersey Department of Labor & Workforce Development (Telephone:  609-292-2259) or by accessing the Department of Labor & Workforce Development’s web site at http://lwd.dol.state.nj.us/labor/wagehour/wagehour_index.html The State wage rates in effect at the time of award are part of this Contract, pursuant to Chapter 150, Laws of 1963 (N.J.S.A. 34:11-56.25 et seq.).

If an employee of the Contractor or subcontractor has been paid a rate of wages less than the prevailing wage, the Department may suspend the Work, and declare the Contractor in default.

The following Wholly State funded project Attachments that are located at the end of these Special Provisions:"

1.	State of New Jersey Equal Employment Opportunity Special Provisions for Construction Contracts Funded by Wholly or partially State Funds.

2.	Payroll Requirements for 100 Percent State Projects.

3.	Americans with Disabilities Act for 100 Percent State Funded Contracts.

2**************************************************************************************2

4.	Small Business Enterprise Utilization Attachment for 100% State Funded Contracts.

The SBE goals request form and classification codes worksheet are available at

http://www.state.nj.us/transportation/eng/documents/procedures/doc/SBEGoalsRequest2012.doc

http://www.state.nj.us/transportation/eng/documents/procedures/xls/WorkClassD2012.xls

e-mail the completed form and worksheet along with a copy of the Engineer’s Estimate to THE BUREAU OF CONSTRUCTION SERVICES at CSPD@dot.state.nj.us

allow AT LEAST 10 days for CONSTRUCTION SERVICES to respond.

upon receiving the information, fill in the blank (V.	SMALL BUSINESS GOALS FOR THIS PROJECT) on STATE attachment NO. 4 LOCATED at the end of these special provisions.

sme CONTACT – Office of Civil Rights, Contract Compliance

2**************************************************************************************2

list here & include additional project specific ATTACHMENTS required for the project at the end of these Special Provisions, SUCH AS ASBESTOS ABATEMENT

The following additional project specific Attachments are located at the end of these Special Provisions:

1.

1**************************************************************************************************************************1

Division 100 – General Provisions

Section 101 – General Information

101.01  Introduction

1**************************************************************************************************************************1

BDC13S-13 dated Dec 18, 2013

complete and include the funding dollar amounts with the appropriate state and/or federal fiscal year for PROJECTs with advanced construction (MULTI-YEAR) FUNDING.

sme contact – project manager

THE FOLLOWING IS ADDED:

2**************************************************************************************2

3************************************************3

INclude THE FOLLOWING FOR fhwa funded projects

Pursuant to NJSA 27:1B-21.6 and USC (United States Code) Title 23 Section 115, the Department intends to enter into a contract for the advancement of the Project.  However, sufficient funds for the Project may not have been appropriated, and only amounts appropriated by law may be expended.  Payment under the Contract is restricted to the amounts appropriated for a fiscal year (FY).

3************************************************3

*****OR*****

3************************************************3

INclude THE FOLLOWING FOR wholly state funded projects

Pursuant to NJSA 27:1B-21.6, the Department intends to enter into a contract for the advancement of the Project.  However, sufficient funds for the Project may not have been appropriated, and only amounts appropriated by law may be expended.  Payment under the Contract is restricted to the amounts appropriated for a fiscal year (FY).

3************************************************3

2**************************************************************************************2

Governing bodies have no legal obligation to make such an appropriation.  There is no guarantee that additional funds will be appropriated.  Failure by governing bodies to appropriate additional funds will not constitute a default under, or a breach of, the Contract.  However, if the Department terminates the Contract or suspends work because funds have not been appropriated, the parties to the Contract will retain their rights for suspension and termination as provided in 108.13, 108.14 and 108.15; except as indicated below.

Do not expend or cause to be expended any sum in excess of the amount allocated in the current fiscal year's Capital Program (as specified below).  The Department will notify the Contractor when additional funding has been appropriated.  Any expenditure by the Contractor which exceeds the amount appropriated is at the Contractor's risk and the Contractor waives its right to recover costs in excess of that appropriated amount.

The approved _____ Capital Program has an item with $ _____ million for the construction of the Project.

2**************************************************************************************2

INCLUDE ALL APPROPRIATE STATEMENT(S)

The Department anticipates that _____ million dollars in additional funds will be provided during State FY _____.

The Department anticipates that the balance of the funds necessary to complete the Project will be provided during State FY _____.

The Department anticipates that _____ million dollars in additional funds will be provided during Federal FY ____.

The Department anticipates that the balance of the funds necessary to complete the Project will be provided during Federal FY _____.

2**************************************************************************************2

The Federal FY begins October 1 of the previous calendar year and the State FY begins July 1 of the previous calendar each year.

1**************************************************************************************************************************1

101.03  Terms

The following terms are changed.

1**************************************************************************************************************************1

pavement structure.  The combination of pavement, base courses, and when specified, a subbase course, placed on a subgrade to support the traffic load and distribute it to the roadbed (see Figure 101-1).  These various courses are defined as follows:

1.	pavement.  One or more layers of specified material of designed thickness at the top of the pavement structure.

2.	base course.  One or more layers of specified material of designed thickness placed on the subgrade or subbase.

3.	subbase.  One or more layers of specified material of designed thickness placed on the subgrade.

1**************************************************************************************************************************1

The following term Is aDDed.

1**************************************************************************************************************************1

BDC16s-03 dated Aug 24, 2016

ITS commissioning.  Completion of Level A testing of an Intelligent Transportation System per 704.03.01. This does not constitute Acceptance by the Department of the work.

1**************************************************************************************************************************1

101.04  Inquiries Regarding the Project

1**************************************************************************************************************************1

include the following for all projects

1.	Before Award of Contract.

2**************************************************************************************2

BDC08s-02 dated Feb 17, 2009

the first paragraph is changed to:

Submit inquiries and/or view other questions/answers by following the format prescribed on the project’s electronic bidding web page.

2**************************************************************************************2

2**************************************************************************************2

BDC12s-01 dated JAN 12, 2012

the second paragraph is changed to:

The deadline for submitting inquiries is 12:00 noon, 7 days before the opening of bids.

2**************************************************************************************2

2.	After Award of Contract.

2**************************************************************************************2

SELECT the APPROPRIATE REGIONAL OFFICE

sme contact – Construction Management

North Region

Ms. Chrissa Roessner, Regional Construction Engineer

200 Stierli Court

Mt. Arlington, NJ  07856-1322

Telephone:  973-601-6670

*****OR*****

Central Region

Mr. Robert Parker, Regional Construction Engineer

1035 Parkway Avenue

Trenton, NJ  08625

Telephone:  732-625-4207

*****OR*****

South Region

Mr. Donald S. Matlack, Regional Construction Engineer

One Executive Suite Route 70 West

Cherry Hill, NJ  08002-4106

Telephone: 856-486-6615

*****OR*****

SELECT the CONTACT If Transportation Systems Management (TSM) LEAD ITS PROJECT

Mr. Wasif Mirza, Director of MSE

1035 Parkway Avenue

Trenton, NJ 08625

Telephone: 609-530-2549

2**************************************************************************************2

1**************************************************************************************************************************1

Section 102 – Bidding Requirements and Conditions

102.01  Qualification to Bid

1**************************************************************************************************************************1

BDC14s-09 dated aug 15, 2014

second criteria is changed to:

2.	Before the receipt of the bid or accompanying the bid, the Bidder has disclosed ownership as required by N.J.S.A. 52:25-24.2.

1**************************************************************************************************************************1

102.02  Bidder Registration and Downloading of the Proposal Documents

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

THE last SENTENCE OF THE first PARAGRAPH IS CHANGED TO:

The Bidder shall not alter or in any way change the software.

1**************************************************************************************************************************1

102.03  Revisions Before Submitting a Bid

1**************************************************************************************************************************1

BDC09s-05 dated May 29, 2009

the second paragraph is changed to:

The Bidder shall acknowledge all addenda posted through the Department’s website.  The addenda acknowledgement folder is included in the Department’s electronic bidding file.  The Department has the right to reject the bid if the Bidder has not acknowledged all addenda posted.

1**************************************************************************************************************************1

102.04  Examination of Contract and Project Limits

1**************************************************************************************************************************1

2**************************************************************************************2

BDC11s-03 dated Nov 15, 2011

THE FOLLOWING IS ADDED AFTER THE second PARAGRAPH:

The structures and the location(s) of lead paint, if any, are listed in the Special Provisions.

3************************************************3

Complete and include following information

The following is a list of structures and the location(s) of lead paint:

| Structure #/Location | Lead Paint Location(s) |
| --- | --- |

3************************************************3

2**************************************************************************************2

1.	Evaluation of Subsurface and Surface Conditions.

2**************************************************************************************2

BDC08s-02 dated Feb 17, 2009

complete and include International Roughness Index (IRI) values of the existing roadway

sme contact – Pavement & Drainage management and technology

THE FOLLOWING IS ADDED:

|  | International Roughness Index (IRI) values of the existing roadway |
| --- | --- |
| Route | Direction | Mile Post | Existing IRI Value |
|  |  | From | To |  |

This information is the latest available IRI data of the right most through lane from the Pavement Management Unit.  The pavement information shown herein was obtained by the Department and is made available to the authorized users only that they may have access to the same information available to the Department.  It is presented in good faith, but is not intended as a substitute for investigations, interpretation or judgment of such authorized users.

2**************************************************************************************2

2**************************************************************************************2

complete and include the pavement core record form

and provide a copy to

Pavement & Drainage management and technology

NEW JERSEY DEPARTMENT OF TRANSPORTATION

PAVEMENT CORE RECORD

PROJECT/ROUTE & SECTION: ___________________________________________________________

DRILLER: ______________________________________________________________________________

INSPECTOR: ____________________________________________________________________________

COUNTY/TOWNSHIP: ____________________________________________________________________

DATE STARTED: _____________	DATE COMPLETED: _________________

| CORE NUMBER | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| ROUTE |  |  |  |  |  |
| DIRECTION (N, E, S, W) |  |  |  |  |  |
| MILE POST (MP or Station) |  |  |  |  |  |
| LANE NO. (Left to Right) |  |  |  |  |  |
| SHOULDER (Inside or Outside) |  |  |  |  |  |
| CORE DIAMETER (Inches) |  |  |  |  |  |
| TOTAL CORE DEPTH (Inches) |  |  |  |  |  |
| CORE DRILLED TO |  |  |  |  |  |
| SURFACE TYPE (AC/PC) |  |  |  |  |  |
| AC THICKNESS (Inches) |  |  |  |  |  |
| PC THICKNESS (Inches) |  |  |  |  |  |

* Lane 1 is the left lane in the direction of travel.

The pavement information shown herein was used by the Department for design and estimate purposes.

2**************************************************************************************2

1**************************************************************************************************************************1

2.	Utility Agreements.

1**************************************************************************************************************************1

BDC14S-02 dated May 08, 2014

The last sentence is deleted.

1**************************************************************************************************************************1

3.	Existing Plans and As-Builts.

1**************************************************************************************************************************1

BDC16S-01R dated AUGUST 15, 2016

Entire part is change to:

The Department will provide a list of existing structures bearing structure numbers within the Project on the Plans.  The Department will list the existing plans including structural plans, contour maps and as-built plans used in the development of the Contract in the Special Provisions.  The Bidder may download the existing plans including structural plans, contour maps and as-built plans of Department-owned facilities through the electronic bidding process along with the Proposal documents.  The Bidder shall obtain plans of municipality-owned or county-owned facilities through the municipality or county.  The Bidder shall verify information obtained from the existing documents with regard to its application to bidding and performing the Contract.

2**************************************************************************************2

THE DESIGNER MUST REQUEST THAT THE PROJECT MANAGER (PM) SUBMIT A COMPLETED EDU-2 FORM, VIA EMAIL, TO THE ENGINEERING DOCUMENTS UNIT TO OBTAIN PDF FILES FOR ALL PLANS TO BE USED IN DESIGNING THE PROJECT. THE DESIGNER WILL RECEIVE THESE FILES FROM THE PM.  LATER, AT LEAST 15 DAYS BEFORE FINAL DESIGN SUBMISSION, THE DESIGNER MUST PROVIDE PDF FILES TO the PM WITH A LIST AND ONE COPY OF ALL PLANS USED IN  DESIGNING THE PROJECT, FOR THEIR POSTING ON THE ELECTRONIC BIDDING SITE.

SME CONTACT – PROJECT MANAGER

2**************************************************************************************2

2**************************************************************************************2

Existing Plans including structural plans, contour maps and as-built plans used are as follows:

2**************************************************************************************2

1**************************************************************************************************************************1

102.09  Proposal Bond

1**************************************************************************************************************************1

BDC13S-13 dated Dec 18, 2013

THE fifth PARAGRAPH is CHANGED TO:

The Department will not accept Proposal Bonds that do not comply in all respects with the provisions of N.J.A.C. 16:44-7.3(e) and that are not substantiated by a valid power of attorney executed by the Surety.

1**************************************************************************************************************************1

102.10  Submission of Bids

1**************************************************************************************************************************1

BDC13S-13 dated Dec 18, 2013

THE second PARAGRAPH is CHANGED TO:

The Bidder shall ensure delivery of its bid with all required components and attachments, including, but not limited to the following:

1.	Schedule of Items.

2.	Proposal Electronic Bidding File with Bidder’s Certification.

3.	For wholly State funded contracts, acknowledgement of compliance with the registrations specified in 102.01.

4.	For wholly State funded contracts, acknowledgement of compliance with N.J.S.A. 19:44A-20.13, et seq.

5.	Proposal Bond form.

6.	Other related documents as specified in the Contract.

7.	On the Disclosure of Investment Activities in Iran (Form DC-16) provided by the Department, certify pursuant to N.J.S.A. 52:32-58, that neither the bidder, nor one of its parents, subsidiaries, and/or affiliates (as defined in N.J.S.A. 52:32-56(e)(3)), is listed on the Department of the Treasury's List of Persons or Entities Engaging in Prohibited Investment Activities in Iran and that neither is involved in any of the investment activities set forth in N.J.S.A. 52:32-56(f).  If the bidder is unable to so certify, the bidder shall provide a detailed and precise description of such activities to the Department.

1**************************************************************************************************************************1

102.15  Disqualification of Bidders

1**************************************************************************************************************************1

BDC13S-13 dated Dec 18, 2013

part (10) is changed to:

10.	Disqualification, suspension, or debarment of an individual, firm, partnership, corporation, or any combination as required by N.J.A.C. 16:44-11.1.

1**************************************************************************************************************************1

Section 104 – Scope of Work

104.03.03  Types of Changes

3.	Changes in the Character of Work.

a.	Differing Site Condition.

1**************************************************************************************************************************1

BDC12s-07 dated mAY 29, 2012

The second paragraph is changed to:

The Department will make payment for increased costs resulting from a Type 1 or Type 2 Differing Site Condition as a change in the character of work; however, the Department will not consider making payment for a differing site condition unless the resulting change in cost exceeds $7,500. Except, if the Contractor incurs cost as the result of multiple differing site conditions, with the cost of each separate differing site condition having a value of at least $1,500 but not more than $7,500, the Department will consider making payment for such costs if the aggregate cost of the multiple differing site conditions exceeds $7,500.  If the change in cost exceeds these amounts, the Department will base the modification on the total cost of the change, and the Department will not deduct the threshold amount of $7,500 from the cost of the change.

1**************************************************************************************************************************1

104.03.04  Contractual Notice

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

the second paragraph is changed to:

Immediately provide written notice to the RE of a circumstance that is believed to be a change to the Contract.  If notice is not provided on Contractual Notice (Form DC-161), include the following in the initial written notice:

1.	A statement that this is a notice of a change.

2.	The date when the circumstances believed to be a change were discovered.

3.	A detailed and specific statement describing the nature and circumstances of the change.

4.	If the change will or could affect costs to the Department.

5.	If the change will or could affect Contract Time as specified in 108.11.01.C.

In addition to the hard copy of the notice, email the notice to the RE.  It is not necessary to attach listed documents to the email.

1**************************************************************************************************************************1

104.03.08  Force Account

1**************************************************************************************************************************1

BDC12s-07 dated mAY 29, 2012

7.	Equipment.

a.	Contractor-Owned Equipment.

part 1 is changed to:

1	The Department will calculate the “rental” hourly rates by dividing the monthly rate by 176.  The Department will not use weekly, daily, or hourly rates.  The Department will apply rental hourly rates for every hour the equipment is in active use, except that for any 30-day period, the Department will limit the total amount paid for each piece of equipment to a maximum of the monthly rate.

The following part is added:

6.	The Department will make payment for costs for transporting equipment to and from the work site, if said costs are solely required as a direct result of the Force Account activity.

the second paragraph is changed to:

The payment established is full payment for all equipment costs, including the cost of fuel, repairs, maintenance, depreciation, storage and incidentals.

10.	Subcontractors.

The second paragraph is changed to:

The Department will make payment for markup on subcontracted work at the rate of 5 percent applied on the total amount of all costs for subcontracted force account work up to $500,000 and 2% applied on the total amount of all costs for subcontracted force account work over $500,000.

1**************************************************************************************************************************1

104.03.09  Delay Damages

1.	Non-Productive Activity.

e.	Equipment.

1**************************************************************************************************************************1

dated Apr 16, 2010

The first sentence is changed to:

If as the result of the delay, equipment cannot be used for any active work, and is directed by the RE to remain on the work site during the delay, the Department will make payment as specified in 104.03.08.7.a.5.

1**************************************************************************************************************************1

Section 105 – Control of Work

105.01  Authority of the Department

1**************************************************************************************************************************1

BDC15S-08 dated feb 08, 2016

THE FOLLOWING new subpart IS ADDED:

105.01.03 Contractor Performance Evaluation

Pursuant to N.J.A.C. 16:44-1 et seq., the Department will assign Performance Evaluation ratings to determine the Contractor’s Work Classification Limit.

The RE will perform a Contractor Performance Evaluation using the Department’s form DC-83 that is current at the time of bid.  The Department’s form DC-83 is available at http://www.state.nj.us/transportation/eng/forms/.  The RE will perform the Contractor Performance Evaluation at the end of the annual rating period, which extends from January 1 through December 31, if the value of work performed is at least 25% of the Total Adjusted Contract Price or has a value of more than $1 million.  If a Project is completed prior to the end of the regular annual rating period, the RE will perform the Contractor Performance Evaluation when the Department initiates a Certificate of Completion.  The Department may extend the rating period or decide to not perform a Contractor Performance Evaluation Rating at its sole discretion, and will provide the Contractor with written notification of a decision to extend a rating period or to not perform a Contractor Performance Evaluation Rating.  The RE will provide the Contractor with the breakdown and weighting of the Quality/Contract Compliance subcategories at the preconstruction conference.  The Contractor Performance Evaluation process is not an administrative process and is contractual in nature.

Meet with the RE to review the Contractor Performance Evaluation rating when requested by the RE.  A protest regarding the Performance Evaluation rating will be resolved through the Rating Review meeting process specified in this Subpart and not through the Contractual Claim Resolution Process specified in Subsection 107.12.

The Contractor may only protest a Contractor Performance Evaluation rating of less than 70.  If the Contractor receives a Contractor Performance Evaluation rating of less than 70, the Contractor may protest the assigned rating by submitting a request for a Rating Review meeting with the Department Manager as specified in Subsection 101.04 (2) of the Special Provisions, responsible for the administration of the construction.  Submit a written request for a Rating Review meeting to the Department Manager within 15 days of receiving the Contractor Performance Evaluation Rating from the RE.  Provide with the request for a Rating Review Meeting a specific and detailed statement of the reasons for the protest and provide a copy of any documents that the Contractor wants the Department to consider. The Contractor waives its right to protest a Contractor Performance Evaluation Rating if it does not submit a written request for a Rating Review meeting within 15 days of  the Contractor’s receipt of the Contractor Performance Evaluation Rating.

The Department Manager will schedule and hold a meeting to review the Contractor’s Performance Evaluation with the Contractor and hear the Contractor’s protest within 30 days of receiving the Contractor’s request for a Rating Review meeting.  The Department Manager will issue a written decision upholding or adjusting the Performance Evaluation rating within 10 days of conducting the Rating Review meeting.

1**************************************************************************************************************************1

105.05  Working Drawings

1**************************************************************************************************************************1

BDC13S-07 dated may 13, 2013

the second PARAGRAPH is CHANGED TO:

Ensure that working drawing submissions also conform to the Department design manuals and other Department standards for the proposed work.  After Award, the Department will provide additional formatting information, the number of copies required, and the address of the receiving designated design unit.

the third PARAGRAPH is CHANGED TO:

Submit working drawings on 22 × 36-inch sheets.  The Department may approve the use of 8-1/2 x 11 inch sheet on a case by case basis.  Submit design calculations required for the working drawings on 8-1/2 × 11-inch paper.  Submit 7 copies of the working drawings to the designated design unit for review with a copy of the transmittal letter to the RE. For railroad-carrying structures, submit 4 additional copies to the designated design unit. Submit an additional copy for each outside testing agency or authority involved in the Project.

the NINTH PARAGRAPH is CHANGED TO:

Submit working drawings for certification or approval as specified in Table 105.05-1.  This list is not all inclusive.  Ensure that the working drawings submitted for approval are signed and sealed by a Professional Engineer.  The working drawings submitted for certification are not required to be signed and sealed by a Professional Engineer unless they alter the original Contract

TABLE 105.05-1 is CHANGED TO:

| Table 105.05 1 – Working Drawing Submission Category |
| --- |
| Certified | Approved |
| Breakaway I-Beam GA Sign Support Posts | Catalog Cuts (related to landscape Items) |
| Bridge Drainage | Change in Structural Steel Details |
| Bridge Railing and Fencing Anchorage System | Change of Prestressed Concrete Strand Patterns |
| Catalog Cuts | Demolition Plans |
| Composite Piles | Erection Plans |
| DMS Sign Support Structure | High Load Multi-Rotational (HLMR) Bearings |
| DMS Standard Ground Mounted | Isolation Bearings |
| Elastomeric Bearings Pads | ITS System Drawings, including Block Diagrams |
| Electrical Items Not Pre-Qualified | Machinery and Electrical Items for Movable Bridges |
| Expansion Deck Joint Assembly Systems | Mechanically Stabilized Earth (MSE) Walls |
| Modular Expansion Joint Assembly | Other work shown on the Plans as conceptual |
| Precast Prestressed Concrete Beams and Piles Fabrication | Precast Concrete Arch Structures |
| Reinforced Elastomeric Bearings | Precast Concrete Box Culverts |
| Sign Legends | Prefabricated Modular Walls |
| Sign Support Structures | Stay-In-Place Forms |
| Structural Steel Fabrication | Temporary Sheeting and Cofferdams |
|  | Temporary Shielding |
|  | Temporary Structures |
|  | Value Engineering Plans |

the first paragraph under part 1 of tenth PARAGRAPH IS changed to:

1.	Certified Working Drawings.  For working drawings requiring certification, include 2 blank blocks directly above the title block.  Designate one block for design unit certification, and designate the other block for the Contractor’s approval stamp and a signed statement stating that the Contract has not been altered.  The Department will require 30 days for review and certification or rejection and return of certified working drawings.

1**************************************************************************************************************************1

1**************************************************************************************************************************1

complete and include the following if the DEPARTMENT will REQUIRE less or more than 30 days to review and certify, or reject and return, working drawings. provide a justification to increased time frames and obtain project manager’s approval.

sme contact – Structural Engineering

1.	Certified Working Drawings.

the last sentence of the FIRST paragraph is changed to:

The Department will require ___days for review and certification or rejection and return of certified working drawings.

1**************************************************************************************************************************1

1**************************************************************************************************************************1

complete and include the following if the DEPARTMENT will REQUIRE less or more than 45 days to review and approve, or reject and return, working drawings. provide a justification to increased time frames and obtain project manager’s approval.

sme contact – Structural Engineering

2.	Approved Working Drawings.

the last sentence of the FIRST paragraph is changed to:

The Department will require ___days for review and approval or rejection and return of working drawings.

1**************************************************************************************************************************1

105.07.01  Working in the Vicinity of Utilities

A.	Initial Notice.

1**************************************************************************************************************************1

list all utility companies located within the project limits.

include ADDRESSes and email ADDRESSes of contact personnel.

sme contact – project manager

1**************************************************************************************************************************1

B.	Locating Existing Facilities.

1**************************************************************************************************************************1

2**************************************************************************************2

part (2) is changed to:

BDC13S-04 dated JUN 10, 2013

2.	For the Department’s fiber optic network, Obtain and complete the fiber optic markout request form as specified in the Special Provisions.  Submit a fiber optic markout request form to the Traffic Operations location specified in the Special Provisions for the markout.  The Traffic Operations will complete the markout within 15 days of the receipt.  Provide the RE a copy of the markout, and maintain the markout until construction operations in the vicinity of the Department’s fiber optic network are completed.

Fiber Optic Markout Form is available at:

http://www.state.nj.us/transportation/eng/elec/ITS/requests.shtm

2**************************************************************************************2

2**************************************************************************************2

SELECT the APPROPRIATE TRAFFIC OPERATIONS OFFICE(s)

for Sussex, Passaic, Bergen, essex, Morris, warren, Hunterdon, Somerset, union, Hudson, and middlesex counties

Bureau of Traffic Operations, North Region (TOCN)

670 River Drive

Elmwood Park, NJ 07407-1347

Telephone: 732-697-7360

*****OR*****

For Mercer, Monmouth, Ocean, Burlington, Camden, Gloucester, Atlantic, Salem, Cumberland, and Cape May counties

Bureau of Traffic Operations, South Region (TOCS)

1 Executive Campus-Route 70 West

Cherry Hill, NJ 08002-4106

Telephone: 856-486-6650

2**************************************************************************************2

3.

2**************************************************************************************2

SELECT the APPROPRIATE electrical OFFICE(s)

Bureau of Electrical Maintenance, North Region

200 Stierli Court

Mt. Arlington, NJ  07856-1322

Telephone:  973-770-5065

*****OR*****

3************************************************3

Feb 04 2014

NJDOT

Central Region Electrical

1035 Parkway Avenue

4 th Floor E&O Bldg.

CN 600

Trenton, NJ 08625

Telephone:  732-625-4350

3************************************************3

*****OR*****

Bureau of Electrical Maintenance, South Region

One Executive Campus Route 70 West

Cherry Hill, NJ  08002-4106

Telephone: 856-486-6627

2**************************************************************************************2

2**************************************************************************************2

BDC13S-04 dated JUN 10, 2013

SELECT THE APPROPRIATE TRAFFIC OPERATIONS OFFICE FROM #2 ABOVE, IN ADDITION, WHEN FACILITIES OTHER THAN FIBER OPTIC EXIST; SELECT OTHER ITS CONTACT FROM BELOW AS NECESSARY

For Weigh in Motion and Traffic Volume systems contact:

Transportation Data and Safety Unit

PO Box 600

Trenton, NJ 08625

609-530-3508

For RoadWAY Weather Information Systems contact:

Permits, Electrical Maintenance & Claims Unit

PO Box 600

Trenton, NJ 08625

609-530-5728

2**************************************************************************************2

1**************************************************************************************************************************1

C.	Protection of Utilities.

1**************************************************************************************************************************1

2**************************************************************************************2

complete and include THE FOLLOWING WHEN a railroad is located within the project limits.

sme contact – project manager

| Location | Speed | Number Per Day | Time |
| --- | --- | --- | --- |

2**************************************************************************************2

2**************************************************************************************2

BDC13S-04 dated JUN 10, 2013

the second PARAGRAPH is changed to:

Protect and support existing Department electrical and ITS facilities and ensure that there is no interruption of service.  Use hand tools only while working within two feet of the fiber optic network.  At least 30 days before beginning the work, submit a plan to the RE for approval showing the method of support and protection.  When access to Traffic Operation Centers, communication hubs, ITS cabinets or any other ITS facilities is required to perform work, submit a request for access to ITS facilities.  Ensure that the request for access is made at least five working days before any work is scheduled, using the online form as specified in the Special Provisions.

http://www.state.nj.us/transportation/eng/elec/ITS/access.shtm

2**************************************************************************************2

2**************************************************************************************2

BDC10S-05 dated May 18, 2010

THE fourth PARAGRAPH is CHANGED TO:

Access within railroad right-of-way is restricted.  Before beginning work within the railroad ROW or on railroad facilities, obtain the railroad’s written approval for access, the method of construction, and the schedule of the work.  Provide a copy of the submittal and approval to the RE.  Comply with the railroad’s requirements for working within the railroad right-of-way.

2**************************************************************************************2

2**************************************************************************************2

BDC10S-05 dated May 18, 2010

the FOLLOWING IS ADDED TO the SIXTH PARAGRAPH

Ensure that the work is performed following the railroad’s access and safety restrictions.

2**************************************************************************************2

1**************************************************************************************************************************1

105.07.02  Work Performed by Utilities

1**************************************************************************************************************************1

BDC10S-12 dated Dec 22, 2010

complete and include the following for all utility companies that are affected by the project for the advance notice requirements. ensure number of (day/s) advanced notice are based on Calendar days as related to the schedule

provide these affected utility companies with a compact disc containing electronic files of plans & Special provisions

| Company Name & Address | Contact Person | Number of Day/s Advance Notice |
| --- | --- | --- |

2**************************************************************************************2

list work per stage to be performed by the utility companies. include a general description of the WORK to be performed by the company and provide company TIME FRAME to Mobilize on site and to perform the work. ensure work duration (day/s) are based on Calendar days as related to the schedule. include seasonal restrictions for the work. ensure that any staging and multiple company coordination is properly accounted for in all contract documents.

| Stage # _______ |  |  |  |
| --- | --- | --- | --- |
| Utility Company Name | Work Description | Work Duration (Day/s) | Restrictions |
|  | Stage Total | _______________ |

2**************************************************************************************2

1**************************************************************************************************************************1

Section 106 – Control of Material

106.02  Department-Furnished Material

1**************************************************************************************************************************1

include the type of materials and their location

1**************************************************************************************************************************1

106.03  Foreign Materials

1**************************************************************************************************************************1

1.	Wholly State-Funded Projects

2**************************************************************************************2

BDC13s-14 dated jan 24, 2014

FOR A WHOLLY STATE-FUNDED PROJECT WHICH HAS FEDERAL FUNDS IN AN ASSOCIATED PROJECT COVERED BY THE SAME NEPA (National Environmental Policy Act) DOCUMENT, INCLUDE THE FOLLOWING:

sme contact – project manager

the entire text IS changed to:

Due to the requirements of MAP-21 (Moving Ahead for Progress in the 21st Century Act), comply with the Federal Aid Project requirements specified under Subpart 2.

2**************************************************************************************2

2**************************************************************************************2

BDC10s-11 dated Nov 05, 2010

THE FOLLOWING is added AFTER THE FIRST PARAGRAPH:

For steel and iron products incorporated into the Project, provide a certification from the manufacturer stating the country where the steel or iron product was melted and manufactured including application of coatings which protect or enhance the value of the material.  Ensure that 4 copies of the manufacturer’s certification are provided with each delivery of steel and iron products.  Retain 1 copy and submit 3 copies to the RE.  Ensure that the certification includes, materials description, quantity of material represented by the certification, country of manufacture, and notarized signature of a person having legal authority to bind the supplier.  If a Certification of Compliance as specified in 106.07 contains a statement regarding the country of manufacture, a separate certification is not necessary.

2**************************************************************************************2

1**************************************************************************************************************************1

106.04  MATERIALS QUESTIONNAIRE

1**************************************************************************************************************************1

BDC10s-08 dated dec 29, 2010

THE LAST SENTENCE OF THE FIRST PARAGRAPH IS changed to:

For ITS systems as specified in Section 704, obtain approval of system working drawings including individual components and Electrical material instead of submitting a materials questionnaire.

1**************************************************************************************************************************1

106.07.01 Certification of Compliance

1**************************************************************************************************************************1

BDC13s-14 dated jan 24, 2014

the entire text IS CHANGED TO:

Submit manufacturer’s Certifications of Compliance stating that the materials and/or assemblies fully comply with the requirements of the Contract when required by the Contract or requested by the Department.

Ensure that Manufacturer’s Certification of Compliance contains the following information:

- Project Name.

- Name of the Contractor.

- Material description.

- Quantity of material represented by the certification.

- Means of identifying the consignment, such as label marking or seal number.

- Date and method of shipment.

- A statement that the material conforms to the Contract material requirements and that representative samples have been sampled and tested.

- If the submission is for an assembly of materials, a statement that the assembly conforms to the Contract.

- Signature of a person having legal authority to bind the supplier.

- Typed or printed name of the person who signed the certification.

Before incorporating the materials into the Project, obtain 3 copies of the manufacturer's Certifications of Compliance for materials, components, and manufactured items that are accepted by certification. Retain 1 copy and submit 2 copies to the RE. With the Certification of Compliance, provide a transmittal identifying the Item for which it is submitted. For products that contain steel or iron, attach additional documents as required by the certification procedures as specified in 106.07.02. The Contractor may submit the Certifications of Compliance electronically to the RE in a scanned document. Include the transmittal and all backup documentation in the scanned document.

The Department has the right to sample and test materials or assemblies accepted on the basis of Certifications of Compliance at any time. The Department will reject materials or assemblies, whether in place or not, if found not to be in conformance with the Contract requirements.

The Department will not make payment for an Item for which material is accepted on the basis of a Certification of Compliance until the RE has received the required Certification of Compliance and has inspected and accepted the material or assembly.

1**************************************************************************************************************************1

106.07.02 Certification for Iron and Steel

1**************************************************************************************************************************1

BDC16s-05 dated nov 04, 2016

the entire text IS CHANGED TO:

A.	Precast Concrete Steel and Concrete Pipe Certification of Compliance.  For precast concrete and concrete pipe items, a Buy America Compliance Plan is required to confirm that the material meets the Buy America requirements as specified in 106.03.  The ME will periodically audit compliance with the program at the precast plant.  If the precast concrete item is not inspected by ME, submit a Certification of Compliance for the precast concrete item as required in 106.07.01.  When a Certification of Compliance is submitted, ensure that the Certification of Compliance contains a statement that the reinforcing steel used in the precast concrete item complies with the Buy America requirements as specified in 106.03

B.	Step Certification of Compliance.  For products that contain steel or iron components and are not covered in 106.07.02.A, step Certification of Compliance is required to confirm that the item meets the Buy America requirements as specified in 106.03.  A step certification is a process under which each handler (e.g., supplier, fabricator, manufacturer, processor, coating facility) of the iron and steel components certifies that the steel and iron components were of domestic origin and that their step in the process was domestically performed.

Every step in the process from melting to coating must be performed in the United States in order for the steel or iron component to be considered domestic and must be documented by step certification. If a domestic source for a steel or iron component cannot be found, submit a request for waiver to the Department. Do not purchase non-domestic steel or iron components without the express written consent of the Department.

Ensure that 3 copies of the Contractor’s Certification of Compliance (Form DC-17) and the step Certifications of Compliance are provided for items containing steel or iron. Retain 1 copy and submit 2 copies to the RE. The Contractor may submit the DC-17 and the step certifications electronically in a scanned document.

Ensure that step Certifications of Compliance contain the following information:

- Name of the Company supplying the material.

- Name and location of the Company the material was shipped to.

- Material description.

- Quantity of material represented by the Certification.

- Means of identifying the consignment, such as label marking or seal number.

- Date and method of shipment.

- A statement that the material conforms to the Contract material requirements and to the Buy America requirements in 106.03.

- A statement that all steel or iron components in the material or assembly were “melted and manufactured in the US”, unless there is non-domestic steel or iron in the material or assembly.

- If there is non-domestic steel or iron in the assembly, describe in detail the non-domestic steel or iron material and the quantity. Attach a copy of the Department’s approval for the use of non-domestic steel or iron components.

- Signature of a person having legal authority to bind the supplier.

- Typed or printed name of the person who signed the certification.

The Department will not make payment for work containing steel or iron materials until the RE has received the required DC-17 and step Certifications of Compliance, has inspected and accepted the material or assembly.

1**************************************************************************************************************************1

106.09  Substitutes for Proprietary Items

1**************************************************************************************************************************1

2**************************************************************************************2

Contact the appropriate smes to determine if a substitute proprietary item or the name of a particular supplier will not be permitted for a work. specify in the appropriate subsection where the intended work is specified, as follows:

2**************************************************************************************2

2**************************************************************************************2

include “No substitution is permitted” statement in the appropriate subsection when a substitution in such work is not permitted

for example: if a proprietary fence material is needed, then include the “No substitution is permitted” statement in subsection 605.02.01.

2**************************************************************************************2

1**************************************************************************************************************************1

1**************************************************************************************************************************1

BDC15s-14 dated Feb 17, 2016

THE FOLLOWING new section IS ADDED:

106.10  USE OF UNITED STATES FLAG VESSELS

For Federal-Aid projects, comply with the Cargo Preference Act of 1954 as amended (46 U.S.C. 1241(b)) and the requirements of 46CFR381. Use privately owned United States-flag commercial vessels to ship at least 50 percent of the gross tonnage (computed separately for dry bulk carriers, dry cargo liner and tankers) whenever shipping any equipment, material or commodities pursuant to this contract to the extent such vessels are available at fair and reasonable rates for United States-flag commercial vessels, and ensure that within 20 days following the date of loading for shipments originating within the United States, or within 30 working days following the date of loading for shipments originating outside the United States, submit a legible copy of a rated “on-board” commercial ocean bill-of-lading in English for each shipment of cargo to the RE and to the Division of National Cargo, Office of Market Development, Maritime Administration, Washington, DC 20590 in accordance with 46 CFR 381.7(a)-(b).

1**************************************************************************************************************************1

Section 107 – Legal Relations

107.04  New Jersey Contractual Liability Act

1**************************************************************************************************************************1

bdc17s-02 DATED JAN 19, 2017

the fourth paragraph is changed to:

For purposes of determining the date of “completion of the contract” pursuant to N.J.S.A. 59:13-5, “completion of the contract” occurs on the date that the Contractor provides written notice to the Department of acceptance of the Proposed Final Certificate or conditional acceptance of the Proposed Final Certificate or the 30th day after the Department issues the Proposed Final Certificate, whichever event occurs first.

1**************************************************************************************************************************1

107.09  Independent Contractor

1**************************************************************************************************************************1

dated May 25, 2011

the entire subsection is changed to:

The relationship of the Contractor to the State is that of an independent contractor. Conduct business consistent with such status.  Do not hold out or claim to be an officer or employee of the Department by reason hereof.  Do not make a claim, demand, or application to or for the rights or privileges applicable to an officer or employee of the Department, including, but not limited to, Workers Compensation Insurance, unemployment insurance benefits, social security coverage, or retirement membership or credit.

1**************************************************************************************************************************1

107.11 RISKS ASSUMED BY THE CONTRACTOR

1.	Damage Caused by the Contractor.

The following is added:

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

For projects within the limits noted below, the designer shall include the following additional clause with the respective limits for that project.  If working within the vicinity of the Turnpike, Garden State parkway, or Atlantic City Expressway, note those also.

Rt 38 MP 0.5 to 9.5

RT 42 mp 6.3 to 13.3

Rt 70 MP 0.0 to 5.4

I-80 MP 57.5 to 68.3

I-295 MP 40.6 to 67.79

I-95 MP 0.58 to 8.77

I-195 MP 0.00 to 6.25

For any damages by the Contractor to the fiber optic network along Route _____, MP _____, also notify the G4S Technology LLC at 877-637-2344 within two hours.  Only G4S Technology LLC will be allowed to complete repairs on that respective section of the fiber optic network.  Directly pay G4S Technology LLC within 30 days from the receipt of G4S Technology LLC’s invoice for such repairs, and provide the RE with a copy of the transmittal letter.  If the Contractor does not make payment within 30 days, the Department may recover the costs incurred for repairs from the Contract.

1**************************************************************************************************************************1

107.12.01  Satisfying the Notice Requirements

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

THE FOLLOWING IS ADDED TO THE second PARAGRAPH:

Upon request, provide the RE with 3 copies of all documentation submitted in support of the claim.

1**************************************************************************************************************************1

107.12.02  Steps

3.	Step III, Claims Committee.

1**************************************************************************************************************************1

BDC10s-07 dated Jun 04, 2010

THE second paragraph is changed to:

The Claims Committee will not review a claim or combination of claims valued less than $250,000 until after the receipt of conditional release as specified in 109.11.  If the Contract is 75 percent complete or greater as measured by Contract Time or Total Adjusted Contract Price, the Claims Committee will not review a claim or combination of claims valued more than $250,000 until after receipt of conditional release as specified in 109.11.  If the Claims Committee does not review a claim or combination of claims before Completion, the Claims Committee will review the claim or combination of claims at a single session of the Claims Committee after the receipt of the conditional release as specified in 109.11 and all claims have been reviewed at Steps I and II of the Claims Resolution Process.  When reviewing a combination of claims, the Claims Committee will not review any individual claim valued less than $20,000.

1**************************************************************************************************************************1

1**************************************************************************************************************************1

BDC11s-05 dated Jun 10, 2011

THE FOLLOWING subsection is ADDED

107.17 Communication with the News Media

Do not communicate with the news media or issue a news release without obtaining a prior written approval from the Department.

1**************************************************************************************************************************1

Section 108 – Prosecution and Completion

108.01  Subcontracting

1**************************************************************************************************************************1

include details, in the appropriate sections, regarding: SPECIALIZED KNOWLEDGE, experience, CRAFTSMANSHIP, and/OR EQUIPMENT required. the subcontractor must be qualified to perform certain SPECIALTY items (such as: segmental bridge, drilled shafts, blasting, ETC.).

1**************************************************************************************************************************1

1.	Values and Quantities.

1**************************************************************************************************************************1

THE FOLLOWING IS ADDED to first PARAGRAPH

1.

list “SPECIALTY ITEMS"

items MAY BE CONSIDERED “SPECIALITY ITEMS” DUE TO SPECIAILIZED KNOWLEDGE, CRAFTSMANSHIP, OR EQUIPMENT REQUIRED TO perform THE WORK. obtain APPROVAL of appropriate sme.

2**************************************************************************************2

select one of the following.

There are no Specialty Items in this Project.

*****OR*****

Specialty Items are as listed below:

3************************************************3

sme contact – GEOTECHnical engineering

Drilling and blasting.

3************************************************3

3************************************************3

Select appropriate item(s).

sme contact – TRAFFIC SIGNAL AND SAFETY ENGINEERING

Above ground highway lighting items.

*****AND/OR*****

Above ground sign lighting items.

***** AND/OR *****

Above and below bridge deck lighting items.

***** AND/OR *****

Electrical wire items.

3************************************************3

3************************************************3

sme contact – Mobility and Systems Engineering (MSE).

ITS items, except for foundations, standards, and junction boxes.

3************************************************3

3************************************************3

list additional “specialty items”

as approved by the sme

3************************************************3

2**************************************************************************************2

1**************************************************************************************************************************1

1**************************************************************************************************************************1

BDC10s-07 dated Jun 04, 2010

THE third PARAGRAPH IS CHANGED TO:

If a partial quantity of work for a unit price Item is subcontracted, the Department will determine the value of the work subcontracted by multiplying the price of the Item by the quantity of units to be performed by the subcontractor.

THE fourth PARAGRAPH IS CHANGED TO:

If only a portion of work of an Item is subcontracted, the Department will determine the value of work subcontracted based on the value of the work subcontracted as indicated in the subcontract agreement and as shown in a breakdown of cost submitted by the Contractor.

1**************************************************************************************************************************1

3.	Subcontract Requirements.  Ensure that subcontract agreements include the following Contract provisions:

a.	Federal Aid Projects.

1**************************************************************************************************************************1

BDC15s-14 dated Feb 17, 2016

The following part is added:

14.	Subsection 106.10 as amended or supplemented.

1**************************************************************************************************************************1

108.02  Commencement of Work

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

The Subpart 4 in the first paragraph is changed to:

4.	Progress schedule as specified in 153.03

1**************************************************************************************************************************1

108.06  Night Operations

2.	Visibility Requirements for Workers and Equipment.

1**************************************************************************************************************************1

BDC09s-12 dated Jan 19, 2010

the first paragraph  is changed to:

Ensure that workers wear a 360° high-visibility retroreflective safety garment meeting ANSI/ISEA Class 3, Level 2 standards.

1**************************************************************************************************************************1

108.07.02  Changes to the Traffic Control Plan (TCP)

1**************************************************************************************************************************1

BDC14S-02 dated May 08, 2014

THE FIRST SENTENCE IN THE FIRST PARAGRAPH IS CHANGED TO:

Submit requests for changes to the TCP to the RE for approval at least 30 days before the change is needed.

1**************************************************************************************************************************1

1**************************************************************************************************************************1

BDC15S-09 dated Jul 15, 2016

include the following if lane rental is necessary otherwise delete.

sme CONTACT – Traffic operations (to obtain allowable hours)

sme CONTACT – Road user solutions (to obtain rental rate)

THE FOLLOWING new subpart IS ADDED:

108.07.03  Lane Rental

Lane and shoulder closures are restricted to the schedule provided in the Traffic Control Details of the plans, and as specified in Subpart 108.07.01.  The Contractor may extend the allowable hours for lane and shoulder occupancy as provided by Table 108.07.03-1 with the RE’s written approval.  Submit a written request to the RE to rent lanes and shoulders for an extended period at least 14 days prior to the anticipated use.  In the request, provide the following information:

1.	Route, Direction and milepost limits

2.	Closure Description (Lane type/shoulder):

3.	Date(s)/Days

4.	Start Time(s)

5.	Finish Time(s)

6.	Reason

7.	Calculation of Lane Rental Cost for each closure

The Department will assess the lane rental charge for each hour the Contractor occupies a lane in accordance with Table 108.07.03-1.  If the Contractor does not occupy the lane during the extended hours, the Department will not assess a lane rental charge.  If the Contractor occupies the lane for fewer hours than requested, the Department will only assess a lane rental charge for the time that the Contractor has actually occupied the lane.  If the Contractor occupies a lane for a portion of an hour, the Department will round the occupancy time to the next highest half hour.

The Department will assess a lane rental charge for lane and/or shoulder occupancy of the roadway at the rates provided in Table 108.07.03-1.

2**************************************************************************************2

complete and include the appropriate Lane rental Charge information.

sme CONTACT – Traffic operations (to obtain allowable hours)

sme CONTACT – road user solutions (to obtain rental rate)

| Table 108.07.03-1 |
| --- |
| Lane Rental availability & charge |
| ROADWAY | DIRECTION | CLOSURE DESCRIPTION | CLOSURE TIME | RENTAL RATE |
|  |  |  | Day(s) | Start Time | Finish Time |  |
|  |  |  |  | Hours | Hours | $ per hour |

2**************************************************************************************2

Do not occupy a lane or shoulder beyond the RE’s approved extension of the allowable hours for lane and shoulder occupancy.  If the Contractor’s lane closure exceeds the allowable time period, the Department will assess Lane Occupancy Charges in accordance with Section 108.08.

1**************************************************************************************************************************1

108.08  Lane Occupancy Charges

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

THE second PARAGRAPH IS CHANGED TO:

The RE will keep record of each occurrence as well as the cumulative amount of time that a lane is kept closed beyond the lane closure schedule and provide the record to the Contractor.  The Department will calculate the lane occupancy charge by multiplying the length of time of the delayed opening, in minutes, by the rate of $10 per minute per lane, unless otherwise specified in the Special Provisions.  The total amount per day for the lane occupancy charge that the Department will collect will not exceed $10,000.00.

2**************************************************************************************2

include appropriate Lane Occupancy Charge information.

sme CONTACT – value Management

THE FOLLOWING IS ADDED:

The rate to calculate the Lane Occupancy Charge is as follows:

| Description | Rate |
| --- | --- |

2**************************************************************************************2

1**************************************************************************************************************************1

108.09  MAINTENANCE WITHIN THE PROJECT LIMITS

1**************************************************************************************************************************1

BDC10s-08 dated dec 29, 2010

The FOLLOWING IS ADDED to the first PARAGRAPH:

6.	Access to ITS devices and their respective controllers and meter cabinets is maintained throughout the duration of the project.

1**************************************************************************************************************************1

108.10  Contract Time

1**************************************************************************************************************************1

BDC13S-13 dated Dec 18, 2013

2**************************************************************************************2

complete and include the following WHEN dates are specified.

delete A, if not applicable and re-Assign Appropiate letter to the remaining statements

SME CONTACT – Construction Management and

regional construction engineer

A.	Complete all work required for Interim Completion for ____________on or before __________.

B.	Complete all work required for Substantial Completion on or before __________.

C.	Achieve Completion on or before __________.

2**************************************************************************************2

*****OR*****

2**************************************************************************************2

complete and include the following WHEN a number of DAYS are specified.

delete A, if not applicable and re-Assign Appropiate letter to the remaining statements

SME CONTACT – Construction Management and regional construction engineer

for Transportation Systems Management (tsm) lead its projects, contact mse for the need of its burn-in period for its system testing.

SME CONTACT – Mobility and Systems Engineering (MSE)

A.	Complete all work required for Interim Completion for ____________ in _______ days.

B.	Complete all work required for Substantial Completion in _______ days.

C.	Achieve Completion in _______ days.

2**************************************************************************************2

*****OR*****

2**************************************************************************************2

complete and include the following WHEN a number of WORKING DAYS are specified.

delete Appropriate part(S), if not applicable and re-Assign Appropiate letter to the remaining statements

SME CONTACT – Construction Management and regional construction engineer

for tsm lead its projects, contact mse for the need of its burn-in period for its system testing.

SME CONTACT – Mobility and Systems Engineering (MSE)

A.	Complete all work required for Interim Completion for ____________ in _______ working days.

B.	Complete all work required for Substantial Completion in _______ working days.

C.	Achieve Completion in _______ working days.

2**************************************************************************************2

1**************************************************************************************************************************1

108.11.01  Extensions to Contract Time

B.	Types of Delays.

1.	Non-Excusable Delays.

1**************************************************************************************************************************1

BDC10S-12 dated Dec 22, 2010

THE FOLLOWING IS ADDED:

For work performed by Utilities, delays up to 30 percent of the estimated duration specified in 105.07.02 are considered non-excusable.  The duration includes both the advance notice and the completion of the work by the Utility.

For delays caused by Railroads, delays up to 30 percent of the estimated availability specified in 105.07 are considered non-excusable.

1**************************************************************************************************************************1

2.	Excusable, Non-Compensable Delays.

1**************************************************************************************************************************1

b.	Utilities.

2**************************************************************************************2

BDC10S-12 dated Dec 22, 2010

THE FOLLOWING IS ADDED:

For delays caused by Railroads, when the availability to access is reduced by more than 30 percent greater than the estimated availability specified in 105.07.

2**************************************************************************************2

2**************************************************************************************2

include the following, IF the project DURATION is less than 1 year, and amount of duration of utility work performed by utility company is minor. Subject to review and approval of SME

sme contact – Project manager

THE last PARAGRAPH is CHANGED TO:

If approved excusable, non-compensable delays exceed a total of 90 days, the time in excess of 90 days will become excusable and compensable as specified in 108.11.01.B.3.

2**************************************************************************************2

1**************************************************************************************************************************1

108.12  Right-Of-Way Restrictions

1**************************************************************************************************************************1

complete and include THE FOLLOWING WHEN RoW has not been secured for those parcels. provide anticipated dates of availability.

sme contact – Project manager

The Department has not obtained the following Right-of-Way parcels; the anticipated availability dates are provided:

Properties and Vacation/Availability Dates

| Demolition and/ or Parcel No | Approximate Baseline Station | Offset/Direction | Date |
| --- | --- | --- | --- |

1**************************************************************************************************************************1

108.14  Default and Termination of Contractor’s Right to Proceed

1**************************************************************************************************************************1

2**************************************************************************************2

complete and include the following if start of work is restricted by department action

sme contact – Project manager

List (1) of the first PARAGRAPH is changed to:

1.	Fails to begin construction operations within __ days of execution of the Contract.

2**************************************************************************************2

2**************************************************************************************2

BDC11s-10 dated oct 25, 2011

The following is added after the 2nd paragraph:

If the Department directs the Surety to complete the Contract, and the Surety elects to use a completion-contractor to perform the Work, the Surety must promptly submit to the Department a request for approval of the proposed completion-contractor as a subcontractor as per Section 108.01.  The Department has the right to reject a request by the Surety to use the Contractor as the completion-contractor, either directly or under the direction of a consultant to the Surety.  In addition, the Department has the right to reject a request by the Surety to contract with employees of the Contractor, directly or under the direction of a consultant to the Surety, to complete the Contract. The Department’s right to reject contained in this paragraph is based on the sole discretion of the Department.

2**************************************************************************************2

1**************************************************************************************************************************1

108.19  Completion and Acceptance

THE FOLLOWING IS ADDED:

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

include specification prior to the final Design submission for Incentive Payment.

if no incentive payment for early completion is to be specified include the following:

sme CONTACT – value Management

No Incentive Payment for Early Completion is specified for this project.

1**************************************************************************************************************************1

108.20  Liquidated Damages

1**************************************************************************************************************************1

BDC13S-13 dated Dec 18, 2013

obtain road user cost

sme CONTACT – value Management

obtain construction engineering cost

sme CONTACT – Construction Management

select APPROPRIATE condition from the following list

Liquidated damages are as follows:

2**************************************************************************************2

complete and include the following.

delete Appropriate part(S), if not applicable and re-Assign Appropiate letter to the remaining statements

A.	For each day that the Contractor fails to complete the work as specified in Subsection 108.10 of these Special Provisions, for Interim Completion, the Department will assess liquidated damages in the amount of $______.

use only the road user cost.

B.	For each day that the Contractor fails to complete the work as specified in Subsection 108.10 of these Special Provisions, for Substantial Completion, the Department will assess liquidated damages in the amount of $______.

use the total cost of the road user and construction engineering costs.

C.	For each day that the Contractor fails to achieve Completion as specified in Subsection 108.10 of these Special Provisions, the Department will assess liquidated damages in the amount of $_____.

Use only the construction engineering cost divided by 2.

2**************************************************************************************2

2**************************************************************************************2

THE FOLLOWING IS ADDED:

When the Contractor may be subjected to more than one rate of liquidated damages established in this Section, the Department will assess liquidated damages at the higher rate.

2**************************************************************************************2

1**************************************************************************************************************************1

Section 109 – Measurement and Payment

109.01  Measurement of Quantities

THE SECOND PARAGRAPH IS CHANGED TO:

The Department will designate Items as Measured Items or as Proposal Items by having a suffix of M or P in the Item number respectively.  The Department will measure quantities of Measured Items for payment.

109.02  Scope of Payment

THE THIRD SENTENCE OF THE FIRST PARAGRAPH IS CHANGED TO:

The Department will not make additional or separate payment for work or portion of work unless specifically provided for in the “Measurement and Payment” Subsection.

109.05  Estimates

1**************************************************************************************************************************1

2**************************************************************************************2

BDC12s-07 dated mAY 29, 2012

the second paragraph is changed to:

The RE will provide a summary of the Estimate to the Contractor. Before the issuance of each payment, certify, on forms provided by the Department, that:

- Each subcontractor or supplier has been paid the amount due from the previous progress payment and shall be paid the amount due from the current progress payment and that full payment for any retainage withheld from a subcontractor has been or will be made within 30 days after the subcontractor’s work has been satisfactorily completed; or

- There exists a valid basis under the terms of the subcontractor's or supplier's contract to withhold payment from the subcontractor or supplier, and therefore payment is withheld.

2**************************************************************************************2

2**************************************************************************************2

INclude THE FOLLOWING FOR WHOLLY Landscape projects

sme contact – landscape architecture

THE ninth PARAGRAPH IS CHANGED TO:

In the first Estimate following installation of all landscape work, the Department will reduce the retainage withheld to one percent of the total adjusted Contract price, excluding subcontracted work on Federally funded projects, unless it has been determined by the Department that the withholding of additional retainage is required.  If retainage is held in cash withholdings, the reduction is to be accomplished by payment under the next Estimate.  If retainage is held in bonds, the Department will authorize a reduction in the escrow account.

2**************************************************************************************2

2**************************************************************************************2

BDC12s-07 dated mAY 29, 2012

The Tenth paragraph is changed to:

The RE has the right to not process an Estimate when, in the judgment of the RE, the Work is not performed or proceeding as specified in the Contract or following the Department giving the Contractor and Surety notice of default as specified in 108.14.

2**************************************************************************************2

1**************************************************************************************************************************1

109.06  Materials Payments and Storage

1**************************************************************************************************************************1

BDC14s-06 dated Jun 20, 2014

THE text before the list under the first PARAGRAPH is CHANGED TO:

The Contractor may request payment for the cost of materials, including the storage cost, not incorporated into the Work.  If approved by the RE, the Department will make payment for the cost of materials, including storage costs if such payment exceeds $25,000; however, the amount of payment may not exceed 85 percent of the bid price for the associated Item.  The Department will not make payment for such materials until the RE is satisfied that:

1**************************************************************************************************************************1

109.07  Bonds Posted in Lieu of Retainages

1**************************************************************************************************************************1

dated APR 16, 2010

THE FIRST PARAGRAPH IS CHANGED TO:

The Contractor may deposit negotiable bonds of the State or any of its political subdivisions, which have been approved by the Department, in an escrow account to secure release of all or a portion of the retainage withheld as specified in 109.05.  Establish the account under the provisions of an escrow agreement to be entered into between the Contractor, the Department, and a bank located in the State that is an authorized depository with a trust department.  Pay the charges of the bank for services rendered according to the terms and conditions of the escrow agreement.

1**************************************************************************************************************************1

109.09  Audits

1**************************************************************************************************************************1

BDC12s-06 dated mar 30, 2012

THE FOLLOWING IS ADDED:

Pursuant to N.J.S.A. 52:15C-14(d), relevant records of private vendors or other persons entering into contracts with the Department are subject to audit or review by the New Jersey Office of the State Comptroller.  Therefore, the Contractor shall maintain all documentation related to products, transactions or services under the Contract for a period of five years from the date of final payment.  Such records shall be made available to the New Jersey Office of the State Comptroller upon request.

1**************************************************************************************************************************1

Division 150 – Contract Requirements

Section 151 – Performance Bond and Payment Bond

151.03.01 Performance Bond and Payment Bond

1**************************************************************************************************************************1

BDC11s-13 dated Feb 14, 2012

the last SENTENCE OF THE first paragraph is changed to:

Submit the broker’s fees, the certified rate schedule, paid invoices and the report of execution for the bond to the RE.

1**************************************************************************************************************************1

151.04  Measurement and Payment

1**************************************************************************************************************************1

BDC12s-13 dated sep 21, 2012

THE FOLLOWING ITEM’s pay unit IS revised to:

Item	Pay Unit

PERFORMANCE BOND AND PAYMENT BOND	dollar

1**************************************************************************************************************************1

Section 152 – Insurance

152.03.01  Owner’s and Contractor’s Protective Liability Insurance

A.	Policy Requirements.

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

THE fourth SENTENCE of the first paragraph IS CHANGED TO:

Ensure that policies are underwritten by companies with a current A.M. Best rating of A- with a Financial Size Category of VII or better.

1**************************************************************************************************************************1

B.	Types

1.	Comprehensive General Liability Insurance.

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

If JCP&L related utility work is to be performed, add the following:

the following is added:

Ensure the policy names JCP&L, its officers, employees and agents as additional insured.

1**************************************************************************************************************************1

2.	Comprehensive Automobile Liability Insurance.

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

If JCP&L related utility work is to be performed, add the following:

the following is added:

Ensure the policy names JCP&L, its officers, employees and agents as additional insured.

1**************************************************************************************************************************1

3.	Owner’s and Contractor’s Protective Liability Insurance.

1**************************************************************************************************************************1

BDC11s-02 dated Mar 23, 2011

the entire text is changed to:

Procure a separate Owner’s and Contractor’s Protective Liability Insurance Policy with a minimum limit of liability in the amount of $4,000,000 per occurrence as a combined single limit for bodily injury and property damage.  Ensure the policy is endorsed to include Severability of Interest/Separation of Insureds clause.  Ensure the policy names the State, its officers, employees, and agents as additional insured.  Provide documentation from the insurance company that indicates the cost of the Owner’s and Contractor’s Protective Liability Insurance Policy.

Ensure the policy is endorsed to include per project aggregate.

1**************************************************************************************************************************1

5.	Excess Liability Insurance.

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

If JCP&L related utility work is to be performed, add the following:

the following is added:

Ensure the policy names JCP&L, its officers, employees and agents as additional insured.

1**************************************************************************************************************************1

6.	Marine Liability Insurance.

1**************************************************************************************************************************1

BDC13S-13 dated Dec 18, 2013

the entire text is changed to:

If construction operations require the Contractor to use a boat, procure Marine Liability Insurance with a minimum limit of liability in the amount of $2,000,000 per occurrence.  Ensure the policy is endorsed to include:

1.	Personal injury.

2.	Contractual liability.

3.	Waiver of Subrogation for all claims and suits, including recovery of any applicable deductibles.

4.	Per project aggregate.

Ensure the policy names the State, its officers, employees, and agents as additional insured.

1**************************************************************************************************************************1

152.03.02  Railroad Protective Liability Insurance

1**************************************************************************************************************************1

2**************************************************************************************2

BDC10s-09 dated sep 10, 2010

The following is added to the first paragraph:

Ensure the policy is endorsed to include per project aggregate.

2**************************************************************************************2

2**************************************************************************************2

BDC14s-10 dated sep 26, 2014

THE third PARAGRAPH IS CHANGED TO:

Ensure the policy is endorsed to include Severability of Interest/Separation of Insureds clause.  Submit the policy for railroad protective liability insurance and endorsements to the Comprehensive General Liability Insurance to the railroad company for approval.  The Department will list the name and address of the railroad company representative in the Special Provisions.  Construction operations will not be permitted on railroad property before approval of insurance by the railroad company.  Reconcile all policy requirements to the satisfaction of the railroad company and the RE.

2**************************************************************************************2

2**************************************************************************************2

iNCLUDE THE FOLLOWING WHEN RAILROAD INSURANCE IS REQUIRED.

sme contact – project manager

Procure and maintain insurance coverage for the following railroad(s):

3************************************************3

include THE APPROPRIATE RAILROAD(S).

National Railroad Passenger Corporation (AMTRAK)

*****and/OR*****

Consolidated Rail Corporation (CONRAIL)

*****and/OR*****

New Jersey Transit Rail Operations

*****and/OR*****

New York Susquehanna & Western Railway Corporation (NYS&W)

3************************************************3

2**************************************************************************************2

2**************************************************************************************2

list the name and address of the railroad company representative

2**************************************************************************************2

2**************************************************************************************2

complete and include THE PERCENTAGE OF PROJECT COST WITHIN RAILROAD ROW

It is estimated that ___ percent of the Project cost is located within or adjacent to the railroad right-of-way.

2**************************************************************************************2

1**************************************************************************************************************************1

152.03.03  Pollution Liability Insurance

1**************************************************************************************************************************1

BDC10s-09 dated sep 10, 2010

Subpart 9 is ADDed to the third PARAGRAPH:

9.	Per project aggregate.

1**************************************************************************************************************************1

152.04  Measurement and Payment

1**************************************************************************************************************************1

2**************************************************************************************2

BDC12s-13 dated sep 21, 2012

THE FOLLOWING ITEMs’ pay units are revised to:

Item	Pay Unit

OWNER’S AND CONTRACTOR’S PROTECTIVE LIABILITY INSURANCE	dollar

RAILROAD PROTECTIVE LIABILITY INSURANCE	dollar

POLLUTION LIABILITY INSURANCE	dollar

2**************************************************************************************2

2**************************************************************************************2

BDC10S-12 dated Dec 22, 2010

THE LAST PARAGRAPH IS CHANGED TO:

The Department will make initial payment for Owner’s and Contractor’s Protective Liability Insurance, Railroad Protective Liability Insurance, and Pollution Liability Insurance at the lesser of the bid amount, or actual costs as documented from paid invoices.  If the Bid amount is greater than the amount indicated on the documented paid invoices, the Department will make payment for any remainder, up to the Bid amount, with the final monthly Estimate.

2**************************************************************************************2

1**************************************************************************************************************************1

Section 153 – Progress Schedule

1**************************************************************************************************************************1

Choose “Bar Chart Progress Schedule and Updates” only if total contract price is below 2 million dollars and the construction duration is less than 9 months. confirm with the department

sme contact – project manager

1**************************************************************************************************************************1

153.03.01  CPM Progress Schedule

1**************************************************************************************************************************1

2**************************************************************************************2

BDC10S-05 dated May 18, 2010

THE third PARAGRAPH IS CHANGED TO:

The Contractor may propose alternate staging.  Ensure that proposed alternate staging does not interfere with work done by Others without written concurrence from the affected Others.  The Department may reject the proposed alternate staging if it causes an increase to the cost of work done by Others.  The Contractor is responsible for the cost of changes or additional work required as a result of completing the work according to the proposed alternate staging.

2**************************************************************************************2

2**************************************************************************************2

BDC10S-12 dated Dec 22, 2010

1.	Preliminary Schedule Submission.

The second PARAGRAPH IS changed to:

The RE may require 3 color paper copies of the preliminary schedule, Gantt Chart, as specified in 153.03.02.2.e, and a network diagram (PERT) printed on 36 ( 22-inch plans detailing the activity relationships.

2.	Baseline Schedule Submission.

THE last SENTENCE OF THE first PARAGRAPH IS CHANGED TO:

The RE may require the Contractor to submit 3 color paper copies of the baseline schedule.

The second PARAGRAPH part 3 IS changed to:

3.	The RE may require 3 color paper copies of the tabular reports, as specified in 153.03.02.2, and a printed network diagram (PERT) on 36 ( 22-inch sheets detailing the activity relationships.

2**************************************************************************************2

1**************************************************************************************************************************1

153.03.02  CPM Progress Schedule Updates

1**************************************************************************************************************************1

2**************************************************************************************2

THE last PARAGRAPH IS CHANGED TO:

If the project falls behind schedule for nonexcusable delays, so that the schedule indicates that the Work will not be completed by the Completion date, as specified in 108.10, take the necessary steps to improve progress.  Under such circumstances, the RE may direct the Contractor to increase the number of shifts, begin overtime operations, work extra days including weekends and holidays, and supplement its construction plant.  Furthermore, the RE may require the Contractor to submit for approval a recovery schedule showing how the Contractor proposes to meet the directed acceleration.

2**************************************************************************************2

2**************************************************************************************2

BDC10S-12 dated Dec 22, 2010

2.	Tabular Reports.

THE FIRST SENTENCE OF THE first PARAGRAPH IS CHANGED TO:

The RE may require 3 color paper copies of the longest path sort, total float sort, responsibility sort, area sort, and Gantt chart.

2**************************************************************************************2

1**************************************************************************************************************************1

153.03.03  Bar Chart Progress Schedule and Updates

A.	Schedule.

1**************************************************************************************************************************1

2**************************************************************************************2

BDC10S-12 dated Dec 22, 2010

THE third SENTENCE OF THE third PARAGRAPH IS CHANGED TO:

Provide 3 color paper copies of a bar chart progress schedule or similar type that is acceptable to the RE for approval as follows:

2**************************************************************************************2

2**************************************************************************************2

THE FOLLOWING IS ADDED:

If the project falls behind schedule for nonexcusable delays, so that the schedule indicates that the Work will not be completed by the Completion date, as specified in 108.10, take the necessary steps to improve progress.  Under such circumstances, the RE may direct the Contractor to increase the number of shifts, begin overtime operations, work extra days including weekends and holidays, and supplement its construction plant.  Furthermore, the RE may require the Contractor to submit for approval a recovery schedule showing how the Contractor proposes to meet the directed acceleration.

2**************************************************************************************2

1**************************************************************************************************************************1

153.04  Measurement and Payment

THE third paragraph is changed to:

If the Contractor’s CPM Progress Schedule update is not approved by the date of the progress meeting for the following update, the Department will assess liquidated damages to recover the Department’s increased administrative costs.  The Department will assess damages for each delinquent update as follows:

Section 155 – Construction Field Office

155.03.01  Field Office

1**************************************************************************************************************************1

BDC11s-10 dated oct 25, 2011

provide THE project specific items.

complete and include the following list.

sme contact – Construction Management

4.	Communication Equipment.

a.	Telephones.  Provide ___ cordless phones with auto-switching.

c.	Cell Phones.  Provide ____ cellular phones.  Ensure the cellular phone plan provides for unlimited mobile to mobile in-network usage, unlimited push-to-talk/ walkie-talkie usage and an anticipated monthly usage of 900 any-time minutes for each phone.  Ensure the phones are on the same plan.  Ensure the cellular phone plan has a home rate with no roaming charges within the state.  Ensure each cellular phone has the following features:

1.	Push to Talk / Walkie-Talkie capable

2.	Camera with 1 megapixel picture capability

3.	Battery life capable of 180 minutes of continuous use and 72 hours of standby use

4.	Equipped with a hands-free headset

5.	Base charger and car charger

d.	Computer System.  Provide a computer system meeting the following requirements:

2**************************************************************************************2

BDC12s-06 dated mar 30, 2012

___ computer configurations each meeting the following:

1.	Processor having a clock speed of ___ GHz or faster, ___ GB RAM, ___ MB Video RAM, ___ Gigabyte hard drive designated as drive C, one DVD (+/-) Writer Drive, one CD-R Recordable Drive.  Ensure the system is USB 2.0 compatible and has at least two front USB ports Include Keyboard, optical mouse and 2 piece desktop speakers.

2.	Wired Router with appropriate number of ports and cables and a print server.  Ensure there is at least one wired Ethernet switch.

3.	High-speed broad band connection and service with a minimum speed of ___ Megabits per second (mbps) with dynamic IP address for the duration of the project.

4.	19 inch or larger Flat Screen LCD monitor with tilt/swivel capabilities.

5.	___ Gigabyte or larger external drive with backup software for MS-Windows, and fifteen corresponding formatted data cartridges corresponding to the tape drive size.

6.	___ Flatbed USB version 2.0 or greater Color Scanner with automatic document feed.

7.	Uninterruptible power supply (UPS).

8.	Surge protector for the entire computer configuration to be used in conjunction with the UPS.

9.	Computer workstation, chair, printer stand, and/or table having both appropriate surface and chair height.

10.	One can of compressed air and screen cleaning solution every other month of the duration of the contract.

If more than one computer configuration is specified, provide one network interface card for the base computer configuration and hardwire connections between computer configurations as directed by the RE.

Also provide:

___ USB ___ GB Flash/Jump memory drives

___ CD-R ___ MB (or larger) recordable CD’s compatible with the CD drive and ___ recordable DVD’s.

___ CD/DVD Holder (each holds 50)

___ color laser printers and supplies as follows:

1.	Minimum of 192 Megabytes of expanded memory, printer cable, and legal size paper tray.

2.	One set of printer ink cartridges every other month for the duration of the construction project for each printer.

Software as follows:

1.	Microsoft Windows, latest version with future upgrades for the duration of the entire project.

2.	Microsoft Office Professional, latest version.

3.	Norton’s System Works for Windows, latest version, or compatible software package with future upgrades and latest virus patches.

4.	Anti-Virus software, latest version with monthly updates for the duration of the contract.

5.	Visio Professional Graphics Software for Windows, latest version

6.	Primavera Project Management, latest version

7.	Adobe Acrobat Professional, latest version, or compatible software for Scanner

2**************************************************************************************2

THE third PARAGRAPH IS CHANGED TO:

When the computer system is no longer required by the RE, the Department will remove and destroy the hard drive, and return the computer system to the Contractor.  The Department will retain other data storage media.

6.	Office Equipment.  Provide the following:

2**************************************************************************************2

BDC13s-01 dated MAR 01, 2013

Part (1) is changed to:

1.	A copier with automatic document feed, 15 pages per minute copy speed, variable reduce/enlarge capability, and letter, legal, and ledger size capabilities.  Erase the copier hard drive before removing the copier from the field office and provide the RE with a certification stating that the copier hard drive has been erased.

2**************************************************************************************2

2.	___ digital camera(s).  Ensure each digital camera has auto-focus, with rechargeable batteries and charger, __ MB memory card, USB Memory Card Reader compatible with camera and field office computer, 1.5 inch LCD monitor, ___ mega pixel resolution, __ X optical zoom lens, built in flash, image stabilization, computer connections, and a carrying case

3.	___ video camcorder(s).  Ensure each video camcorder is a mini DVD camcorder with ___ optical zoom, 2" LCD monitor, USB 2.0 compatible and includes USB 2.0 connections.

7.	Inspection Equipment.

- __ Calculators with trigonometric capability

- __ Date/ Received stamp and ink pad

- __ Electronic Smart level, 4 foot

- __ Electronic Smart level, 2 foot

- __ Carpenter rulers

- __ Steel tape, 100 feet

- __ Cloth tape, 100 feet

- __ Illuminated measuring wheel

- __ Plumb bob and cord

- __ Line level and cord

- __ Surface thermometer

- __ Concrete thermometer

- __ Digital infrared asphalt thermometer

- __ Direct Tension Indicator (DTI) Feeler Gage, 0.005 inch

- __ Sledge hammer, 8lb

- __ Self leveling laser level with range of 100 feet and an accuracy of ¼ inch per 100 feet

- __ Hard hats - orange, reflectorized hard hats according to ANSI Z89.1.

- __ Safety garments – orange, reflectorized, 360º high visibility safety garments according to ANSI/ISEA Class 3, Level 2 standards.  To be replaced yearly for the duration of the contract.

- __ Sets of rain gear with reflective sheeting

- __ Sets of hearing protection with a NRR rating of 22 dB

- __ Sets of eye protection according to ANSI Z87.1

- __ Sets of fall arrest equipment according to ANSII Z359.1 standards consisting of a full body harness, lanyard and anchor.

- __ Light meter - capable of measuring the level of luminance in foot-candles

- __ Lantern flashlight, 6V with monthly battery replacements

- __ Digital Psychrometer

- __ Chain Drag according to ASTM D4580-86

- __ Testing equipment and apparatus conforming to AASHTO T23, T119, T152

- __ Hard Bound Daily Diaries, 5-½” X 8” minimum with one day per page.  To be provided yearly for the duration of the contract.

- __ Legal size hanging folders

- __ Legal size manila file folders – three tab

1**************************************************************************************************************************1

155.03.03  Telephone Service

1**************************************************************************************************************************1

BDC11s-13 dated Feb 14, 2012

THE CONTENT OF THIS SUBSECTION is DELETED

1**************************************************************************************************************************1

155.04  Measurement and Payment

1**************************************************************************************************************************1

BDC11s-13 dated Feb 14, 2012

THE following ITEM is deletED:

Item	Pay Unit

TELEPHONE SERVICE	LUMP SUM

The third PARAGRAPH IS deleted.

1**************************************************************************************************************************1

Section 156 – Materials Field Laboratory and Curing facility

156.03  Procedure

1**************************************************************************************************************************1

2**************************************************************************************2

CONTACT the APPROPRIATE REGIONAL Materials engineer’s office.

to determine the need for materials field office and/or curing facility and the equipment needed (example: flex beam tester, nuclear gauge, or compression tester).

Region North

MS. jOaNNE gERBINO

Telephone: (973) 601-6675

*****OR*****

Region Central

Mr. JOSEPH MALONEY

Telephone: (732) 625-4227

*****OR*****

Region South

Mr. ALLEN KRICHEFF

Telephone: (856) 486-6611

156.03.01  Materials Field Laboratory

4.	Communication Equipment.

c.	Cell Phones.  Provide ____ cellular phones.  Ensure the cellular phone plan provides for unlimited mobile to mobile in-network usage, unlimited push-to-talk/ walkie-talkie usage and an anticipated monthly usage of 900 any-time minutes for each phone.  Ensure the phones are on the same plan.  Ensure the cellular phone plan has a home rate with no roaming charges within the state.  Ensure each cellular phone has the following features:

1.	Push to Talk / Walkie-Talkie capable

2.	Camera with 1 megapixel picture capability

3.	Battery life capable of 180 minutes of continuous use and 72 hours of standby use

4.	Equipped with a hands-free headset

5.	Base charger and car charger

d.	Computer System.  Provide a computer system meeting the following requirements:

3************************************************3

BDC12s-06 dated mar 30, 2012

___ computer configurations each meeting the following:

1.	Processor having a clock speed of ___ GHz or faster, ___ GB RAM, ___ MB Video RAM, ___ Gigabyte hard drive designated as drive C, one DVD (+/-) Writer Drive, one CD-R Recordable Drive.  Ensure the system is USB 2.0 compatible and has at least two front USB ports.

2.	Wireless Ethernet Hub Switch with appropriate number of ports and cables and a print server.

3.	High-speed broad band connection and service with a minimum speed of ___ Megabytes per second (mbps) with dynamic IP address for the duration of the project.

4.	19 inch or larger Flat Screen LCD monitor with tilt/swivel capabilities.

5.	___ Gigabyte or larger external drive with backup software for MS-Windows, and fifteen corresponding formatted data cartridges corresponding to the tape drive size.

6.	___ Flatbed USB version 2.0 Color Scanner with automatic document feed.

7.	Uninterruptible power supply (UPS).

8.	Surge protector for the entire computer configuration to be used in conjunction with the UPS.

9.	___ computer workstations, chair, printer stand, and/or table having both appropriate surface and chair height.

10.	One can of compressed air and screen cleaning solution every other month of the duration of the contract.

If more than one computer configuration is specified, provide one wireless network card for the base computer configuration and hardwire connections between computer configurations as directed by the RE.

Also provide:

___ USB ___ GB Flash/Jump memory drives

___ CD-R ___ MB (or larger) recordable CD’s compatible with the CD drive and ___ recordable DVD’s.

___ CD/DVD Holder (each holds 50)

___ color laser printers and supplies as follows:

1.	Minimum of 192 Megabytes of expanded memory, printer cable, and legal size paper tray.

2.	One set of printer ink cartridges every other month for the duration of the construction project for each printer.

3************************************************3

2**************************************************************************************2

THE third PARAGRAPH IS CHANGED TO:

When the computer system is no longer required by the ME, the Department will remove and destroy the hard drive, and return the computer system to the Contractor.  The Department will retain other data storage media.

6.	Office Equipment.  Provide the following:

3************************************************3

BDC13s-01 dated MAR 01, 2013

Part (1) is changed to:

1.	A copier with automatic document feed, 15 pages per minute copy speed, variable reduce/enlarge capability, and letter, legal, and ledger size capabilities.  Erase the copier hard drive before removing the copier from the field office and provide the RE with a certification stating that the copier hard drive has been erased.

3************************************************3

2**************************************************************************************2

BDC13S-13 dated Dec 18, 2013

THE FOLLOWING IS ADDED:

9.	Inspection Equipment.

- __ Hard hats - orange, reflectorized hard hats according to ANSI Z89.1.

- __ Safety garments – orange, reflectorized, 360º high visibility safety garments according to ANSI/ISEA Class 3, Level 2 standards.  To be replaced yearly for the duration of the contract.

- __ Sets of rain gear with reflective sheeting

- __ Sets of hearing protection with a NRR rating of 22 dB

- __ Sets of eye protection according to ANSI Z87.1

- __ Lantern flashlight, 6V with monthly battery replacements

2**************************************************************************************2

1**************************************************************************************************************************1

156.03.05  Nuclear Density Gauge

1**************************************************************************************************************************1

BDC10s-04 dated Apr 26, 2010

The last PARAGRAPH IS changed to:

Provide a nuclear density gauge for the exclusive use of the ME using one of the following methods:

1.	Purchase a nuclear density gauge under the Contractor’s New Jersey Department of Environmental Protection (NJDEP) License or the Contractors United States Nuclear Regulatory Commission (USNRC) license.

2.	Lease a nuclear density gauge from a New Jersey Department of Environmental Protection (NJDEP) or United States Nuclear Regulatory Commission (USNRC) licensed third party on the Department’s New Jersey Department of Environmental Protection (NJDEP) License.

The Contractor is barred from purchasing gauges on the Department’s New Jersey Department of Environmental Protection (NJDEP) license.  Perform calibration and servicing of the gauge, other than routine wipe tests, every 24 months.  The ME may direct additional calibrations, when necessary.  Supply a replacement gauge for the Department’s use during the calibration and servicing period.

1**************************************************************************************************************************1

Section 157 – Construction Layout and Monuments

157.03.01  Construction Layout

1**************************************************************************************************************************1

2**************************************************************************************2

BDC10S-05 dated May 18, 2010

THE seventh PARAGRAPH IS CHANGED TO:

Provide the Utilities with the layout needed to install relocated utility facilities and coordinate the Work.  Ensure that relocated facilities do not conflict with proposed construction, including High Voltage Proximity Act conflicts.

2**************************************************************************************2

2**************************************************************************************2

BDC10S-12 dated Dec 22, 2010

the following is added after the ninth paragraph:

For each bridge and sign structure within the Project Limits, provide the RE as-built measurements of the vertical under clearance at each lane line, shoulder line, curb line and edge of pavement line under a structure to the nearest inch.  For each bridge structure, provide vertical under clearance measurements at each fascia beam.

2**************************************************************************************2

1**************************************************************************************************************************1

157.04  Measurement and Payment

1**************************************************************************************************************************1

2**************************************************************************************2

BDC12s-13 dated sep 21, 2012

THE FOLLOWING ITEM’s pay unit IS revised to:

Item	Pay Unit

CONSTRUCTION LAYOUT	dollar

2**************************************************************************************2

2**************************************************************************************2

BDC11s-10 dated oct 25, 2011

THE second PARAGRAPH IS CHANGED TO:

The Department will adjust payment for construction layout based on the final contract amount and will calculate as follows:

Where: CL = Adjusted payment for Construction Layout. CLB = Bid price for Construction Layout. CO = Original Contract Price. CF = Final Contract Price. EF = Total of CLB and the final cost for Performance Bond and Payment Bond, Incentive/Disincentives for completion/interim completion, and claim settlements. EO = Total of CLB, and PERFORMANCE AND PAYMENT BOND.

2**************************************************************************************2

1**************************************************************************************************************************1

Section 158 – Soil Erosion and Sediment Control
and Water Quality Control

158.03.02  SESC Measures

1**************************************************************************************************************************1

2**************************************************************************************2

BDC11s-10 dated oct 25, 2011

8.	Inlet Filters.  Provide Type 1 and Type 2 inlet filters as follows:

a.	Type 1.

the entire text IS changed to:

For a new inlet structure without a casting, mold welded steel wire fabric around the inlet walls.  Extend the welded steel wire a minimum of 6 inches down each side of the structure.  Secure geotextile to the welded wire fabric.  Place No. 2 coarse aggregate against the inlet structure to hold the inlet filter in place.

For an inlet structure with a casting and exposed exterior walls, place geotextile under the casting and extend it a minimum of 6 inches below the top of the exposed walls.  Place No. 2 coarse aggregate around the drain hole opening.

For an existing inlet structure without exposed exterior walls, place geotextile under the grate and extend the geotextile for a minimum of 6 inches beyond the grate.

For an inlet with a curb piece and without exposed exterior walls, ensure that the opening in the curb piece has a height of 2 inches.  If the opening is greater than 2 inches, achieve the 2 inch opening size by wrapping the geotextile around an appropriately sized piece of lumber.  Place the lumber against the vertical opening.

2**************************************************************************************2

2**************************************************************************************2

19.	Oil-Only Emergency Spill Kit.

THE second SENTENCE OF THE first PARAGRAPH IS CHANGED TO:

Include Oil-only Emergency Spill Kit, Type 1 consisting of the following:

2**************************************************************************************2

2**************************************************************************************2

Provide other type Emergency Spill kit, if needed

sme contact – Environmental Solutions

2**************************************************************************************2

1**************************************************************************************************************************1

Section 159 – Traffic Control

1**************************************************************************************************************************1

provide specifications for temporary its or other requirements, if necessary.

sme contact – traffic operations centers

1**************************************************************************************************************************1

159.02.01  Materials

1**************************************************************************************************************************1

2**************************************************************************************2

BDC14s-11 dated May 22, 2015

The following is added to the list of materials references:

Box Beam for Construction Barrier Curb 	913.04

2**************************************************************************************2

2**************************************************************************************2

BDC12s-04 dated JUl 30, 2013

THE FOLLOWING is added:

Provide temporary crash cushions, inertial barrier systems as specified in 611.02.  Provide temporary compressive crash cushions as specified for compressive crash cushions in 611.02.

2**************************************************************************************2

1**************************************************************************************************************************1

159.02.02  Equipment

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

Include the following if the REMOTELY OPERATED PVMS OR PORTABLE TRAILER MOUNTED CCTV CAMERA ASSEMBLY are needed

sme CONTACT – TrAFFIC OPERATIONS

The following is added to the list of equipment references:

Portable Variable Message Sign w/Remote Communication…….………………...……………………1001.04

Portable Trailer Mounted CCTV Camera Assembly……………….……………………………………1001.05

1**************************************************************************************************************************1

159.03.02  Traffic Control Devices

1**************************************************************************************************************************1

2.	Construction Barrier Curb.

2**************************************************************************************2

BDC14s-11 dated may 22, 2015

the entire text is changed to:

Alternate A or B construction barrier curb may be used interchangeably in any location.   The Contractor may use construction barrier curb that is constructed using gray or white concrete. Do not place different colors of construction barrier curb in a continuous run. Do not use construction barrier curb having any of the following deficiencies:

1.	Exposed steel at the connector flangeway.

2.	Exposed reinforcement steel.

3.	Cracking through the cross section.

4.	An area of concrete missing larger than a 3-inch by 3-inch right triangle.

5.	Debris in the keyway.

6.	Non-functioning anchor bolt holes.

7.	Non-functioning anchor rod hole.

8.	Paint applied to the surface.

9.	Objects protruding from the surface.

10.	Previous repairs.

11.	Do not use damaged, kinked or bent connection key or box beam stiffener.

At least 30 days before delivering construction barrier curb to the Project Limit, provide the RE notice that the barrier curb is available for inspection.  The RE will inspect the barrier curb and approve individual pieces for delivery to the Project Limits.

Ensure that anchor pins do not project above the plane of the barrier curb. Install the Construction Barrier Curb stiffened with box beams as indicated in the contract documents.

Replace construction barrier curb that does not meet the specified requirements.  Do not patch or repair construction barrier curb.

Provide top and side mounted flexible delineators on the construction barrier curb.  For delineators located on the right side when facing in the direction of traffic, ensure that the retroreflective sheeting is white.  For delineators located on the left side when facing in the direction of traffic, ensure that the retroreflective sheeting is yellow.  Attach flexible delineators according to the manufacturer’s recommendations.

Starting at the beginning of the construction barrier curb section mount top delineators at 100-foot intervals on tangent sections, or curves of radii greater than 1,910 feet, and at 50-foot intervals on curves of radii of 1,910 feet or less.

Mount side delineators at the lead end of each barrier segment with the top of the delineator 3 inches from the top of the barrier.

2**************************************************************************************2

5.	Temporary Crash Cushion

2**************************************************************************************2

BDC12s-04 dated JUl 30, 2013

THE SECOND SENTENCE IS CHANGED TO:

Install temporary compressive crash cushions as specified for compressive crash cushions in 611.03.02.

2**************************************************************************************2

6.	Traffic Control Truck with Mounted Crash Cushions.

2**************************************************************************************2

BDC10s-08 dated des 29, 2010

THE last sentence is changed to:

Submit drawings to the RE detailing the manner of securing the ballast, signed and sealed by a Professional Engineer, certifying that it is capable of withstanding the impact forces for which the impact attenuator is rated.

2**************************************************************************************2

2**************************************************************************************2

BDC13S-04 dated JUN 10, 2013

THE FOLLOWING IS ADDED to the second paragraph:

1**************************************************************************************************************************1

BDC16s-03 dated Aug 24, 2016

8.	Portable Variable Message Sign with Remote Communication (PVMSRC).  Place the PVMSRC at the locations directed by the RE for the duration of the project.  Ensure that a designated representative familiar with the operation and programming of the unit is available on the Project for On-Site Configuration.  Only display messages on the PVMSRC authorized by the Department for the Project in accordance with the plans or as directed by the RE and make the signs available for use remotely from the Traffic Operation Center (TOC) specified in 105.07.01.B.  Program within 8 hours, any message requested by the RE to be displayed on the PVMS at a scheduled time and verify that the message is displayed correctly and notify the RE.  If the PVMSRC fails to function, repair the equipment within 48 hours of receiving notice from the Department that the PVMSRC is not functioning.

Integrate the PVMSRC for remote operation from TOC using Vanguard DMS software or the Department’s central DMS control software at the time of installation as directed by the RE.

Provide for one week of testing by the TOC for remotely operating the PVMSRC before the start of construction operations that require lane or shoulder closures, or other impacts to traffic.  At least 10 days before testing, submit to the RE for approval a plan for any work to be completed in the TOC.  Submit a request to the RE at least 4 days in advance to access the TOC for any work.

9.	Portable Trailer Mounted CCTV Camera Assembly (PTMCCA).

2**************************************************************************************2

If THE PTMCCA IS REQUESTED BY CONSTRUCTION MANAGEMENT, revise this and OTHER REQUIREMENTS WILL NEED TO BE INCLUDED.

SME CONTACT – MSE; traffic operations/CONSTRUCTION MANAGEMENT AS APPLICABLE

2**************************************************************************************2

Place the PTMCCA at the location directed by the RE.  Ensure that a designated representative familiar with the operation and programming of the unit is available on the Project for initial installation.  If the PTMCCA fails to function, repair the equipment within 48 hours of receiving notice from the Department that the PTMCCA is not functioning.

Provide a system that includes a robotic network camera remotely controllable, including Pan, Tilt and Zoom (PTZ).  Provide broadband internet service connection and On-Site Camera Configuration for remote operation and control of the camera via the Department’s existing Head-End Camera Control System, Genetec.  No other Head-End Camera Control System substitution is permitted.  A Management user system is also to be provided for remote system programming to the camera sites.  This includes a website that is to be provided and hosted by the vendor.  This website is to have secure authentication and is to show the current devices with their location, status, and display links for each device.  Provide continuous viewable image at a minimum of 320H x 240V resolution and 1 frame per sec (fps) through the website.  As directed by the Traffic Operation Center (TOC) specified in 105.07.01.B, establish password level designations, camera presets, and camera image displays.  Provide all incidental equipment and material required for successful remote operation and communications.

Provide for one week of testing by the TOC for remotely operating the PTMCCA before the start of construction operations that require lane or shoulder closures, or other impacts to traffic.

2**************************************************************************************2

DESIGNERS MUST CHECK WITH MSE’S MOBILITY MANAGEMENT WORK ZONE UNIT AND TRAFFIC OPERATIONS TO CONFIRM IF REAL TIME WORK ZONE TRAFFIC SYSTEM (RTWZTS) IS REQUIRED. ONCE CONFIRMED AND IF RTWZTS IS REQUESTED BY TRAFFIC OPERATIONS, THEN REQUEST THE SPECIFICATIONS FROM MSE AND INCLUDE HEREAFTER MODIFYING THE SPECIFICATIONS TO INCLUDE THE NUMBER OF PVMSRC REQUIRED WITH LOCATIONS AND ANY OTHER ADDITIONAL REQUIREMENTS SPECIFIC TO THE PROJECT. DEVELOP AND INCLUDE A REAL TIME MESSAGE TABLE LISTING THE DESIGNATED ROUTE, LOCATION OF EXISTING/PROPOSED SIGN AND THE TRAVEL TIME MESSAGE TO BE DISPLAYED.

SME CONTACT –MSE’S MOBILITY MANAGEMENT WORK ZONE UNIT, TRAFFIC OPERATIONS

10.	REAL TIME WORK ZONE TRAFFIC SYSTEM (RTWZTS)

2**************************************************************************************2

1**************************************************************************************************************************1

159.03.06  Temporary Traffic Stripes and Temporary Traffic Markings

1**************************************************************************************************************************1

BDC16s-02 dated sep 12, 2016

The subpart Heading and the entire text is changed to:

159.03.06  Traffic Stripes, Latex ,Traffic Markings Lines, Latex and Traffic Markings Symbols, Latex

Apply latex traffic stripes and latex markings when they are required for 14 days or less.  Apply epoxy traffic stripes and thermoplastic markings as specified in 610.03.01 and 610.03.02 when they are required for more than 14 days.  Apply latex traffic stripes and latex markings when the ambient and surface temperatures are at least 45 °F and rising and the surface temperature is no more than 140 °F. Apply the latex paint in a wet film thickness of 6 ± 1 mil. Apply glass beads to the wet paint in a uniform pattern and at the rate of 12 pounds per gallon of paint.

1**************************************************************************************************************************1

159.03.08  Traffic Direction

1**************************************************************************************************************************1

A.	Flagger.

2**************************************************************************************2

BDC08s-02 dated Feb 17, 2009

The last sentence is changed to:

Ensure that the flagger is equipped with a STOP/SLOW paddle and follows MUTCD flagging procedures.

2**************************************************************************************2

B.	Police.

2**************************************************************************************2

BDC13s-05 dated MAR 08, 2013

The fourth PARAGRAPH IS deleted.

2**************************************************************************************2

1**************************************************************************************************************************1

159.04  MEASUREMENT AND PAYMENT

1**************************************************************************************************************************1

2**************************************************************************************2

BDC10s-08 dated dec 29, 2010

THE FOLLOWING ITEMS ARE ADDED:

Item	Pay Unit

PORTABLE VARIABLE MESSAGE SIGN WITH REMOTE COMMUNICATION	UNIT

PORTABLE TRAILER MOUNTED CCTV CAMERA ASSEMBLY	UNIT

3************************************************3

BDC12s-04 dated JUl 30, 2013

THE FOLLOWING ITEMS ARE ADDED:

TEMPORARY crash cushion, compressive barrier, type___, width___	unit

TEMPORARY crash cushion, Low maintenance compressive barrier,

type___, width___	unit

3************************************************3

3************************************************3

BDC16s-02 dated sep 12, 2016

THE FOLLOWING ITEMS ARE ADDED:

TRAFFIC STRIPES, LATEX ___"	LINEAR FOOT

Traffic MARKINGs LINES, LATEX ___"	LINEAR FOOT

TRAFFIC MARKINGS SYMBOLS, LATEX	SQUARE FOOT

THE FOLLOWING ITEMs are Deleted:

Item	Pay Unit

Temporary TRAFFIC STRIPES, ___"	LINEAR FOOT

Temporary Traffic MARKINGs	SQUARE FOOT

3************************************************3

3************************************************3

BDC12s-04 dated JUl 30, 2013

THE FOLLOWING ITEM is Deleted:

TEMPORARY CRASH CUSHION, ___	UNIT

3************************************************3

3************************************************3

AFTER CHECKING WITH TRAFFIC OPERATIONS INCLUDE PAYMENT CRITERIA FOR PVMSRC AND PTMCCA.  NOTE THAT WHEN REAL TIME WORK ZONE SYSTEM (RTWZS) IS ALSO SPECIFIED IN A PROJECT INCLUDE SEPARATE SPECIFIC PAYMENT CRITERIA BASED ON PERFORMANCE OF RTWZS.

SME CONTACT – TRAFFIC OPERATIONS & Mobility and Systems Engineering (MSE)

3************************************************3

3************************************************3

BDC11s-10 dated oct 25, 2011

THE second PARAGRAPH IS CHANGED TO:

For traffic control devices measured by the linear foot or unit basis that are specified in 159.03.02, the Department will make payment for the maximum quantity in service at one time as required by the Contract.  For CONSTRUCTION SIGNS, the Department will make payment for the maximum quantity of specific sign types in service at one time as required by the Contract.  If a particular sign type has more than one unique text, each sign with a unique text will be considered to be a specific sign type.  The Department will make payment for 50 percent of the Contract bid price for traffic control devices specified in 159.03.02 that are measured on a linear foot, square foot or unit basis upon approved placement. The Department will prorate the balance of payment over the duration of the Contract.

3************************************************3

THE FOLLOWING IS ADDED

If after being notified by the Department that the PORTABLE VARIABLE MESSAGE SIGN WITH REMOTE COMMUNICATION or PORTABLE TRAILER MOUNTED CCTV CAMERA ASSEMBLY has failed to function and the equipment has not been restored to good working order within 48 hours, the Department will make payment reductions as follows:

For each occasion the equipment was not restored within 48 hours the Department will assess a liquidated damage of $250 for every 48 hours period the equipment is not functioning.

2**************************************************************************************2

2**************************************************************************************2

BDC16s-02 dated sep 12, 2016

The Department will not include payment for epoxy traffic stripes and thermoplastic traffic markings and symbols under TRAFFIC STRIPES LATEX, TRAFFIC MARKINGS LINES, LATEX and TRAFFIC MARKINGS SYMBOLS, LATEX.  The Department will make payment for epoxy traffic stripes and thermoplastic traffic markings under TRAFFIC STRIPES, TRAFFIC MARKINGS LINES, and TRAFFIC MARKINGS SYMBOLS as specified in 610.04.

2**************************************************************************************2

1**************************************************************************************************************************1

Section 160 – Price Adjustments

160.03.01  Fuel Price Adjustment

1**************************************************************************************************************************1

2**************************************************************************************2

BDC08s-02 dated Feb 17, 2009

throughout this subpart, TABLE 161.03.01-1 is CHANGED TO TABLE 160.03.01-1

THE third PARAGRAPH IS CHANGED TO:

If the as-built quantity of an Item listed in Table 160.03.01-1 differs from the sum of the quantities in the monthly Estimates, and the as-built quantity cannot be readily distributed among the months that the Item listed in Table 160.03.01-1 was constructed, then the Department will determine fuel price adjustment by distributing the difference in the same proportion as the Item’s monthly Estimate quantity is to the total of the Item’s monthly estimates.

3************************************************3

BDC11s-07 dated Jun 17, 2011

the 13 th and 15 th LINE IN THE TABLE 160.03.01-1 is changed to:

| SOIL AGGREGATE BASE COURSE, ___ " THICK | 1 Gallon per Cubic Yard |
| --- | --- |

| DENSE-GRADED AGGREGATE BASE COURSE, ___ " THICK | 1 Gallon per Cubic Yard |
| --- | --- |

3************************************************3

the 25 th LINE IN THE TABLE 160.03.01-1 is changed to:

| HOT MIX ASPHALT ___ ___ ___ BASE COURSE | 2.50 Gallons per Ton |
| --- | --- |

2**************************************************************************************2

2**************************************************************************************2

BDC09s-07 dated aug 13, 2009

THE FOLLOWING are ADDED to table 160.03.01-1

| Items | Fuel Usage Factor |
| --- | --- |
| NON-VEGETATIVE SURFACE, HOT MIX ASPHALT | 2.50 Gallons per Ton |
| COLOR-COATED NON-VEGETATIVE SURFACE, HOT MIX ASPHALT | 2.50 Gallons per Ton |

2**************************************************************************************2

1**************************************************************************************************************************1

160.03.02  Asphalt Price Adjustment

1**************************************************************************************************************************1

2**************************************************************************************2

BDC08s-02 dated Feb 17, 2009

note 1 of the Third PARAGRAPH IS CHANGED TO:

1.	The Department will determine the weight of asphalt binder for price adjustment by multiplying the percentage of new asphalt binder in the approved job mix formula by the weight of the item containing asphalt binder.  If a Hot Mix Asphalt item has a payment unit other than ton, the Department will apply an appropriate conversion factor to determine the number of tons used.

2**************************************************************************************2

2**************************************************************************************2

the fourth PARAGRAPH IS CHANGED TO:

For Tack Coat and Prime Coat, the Department will calculate asphalt price adjustments by the following formula:

A = B ( [(MA − BA)/BA] ( C ( M ( G

Where:

A = Asphalt Price Adjustment

B = Bid Price for Tack Coat/Prime Coat

MA = Monthly Asphalt Price Index

BA = Basic Asphalt Price Index

C = Petroleum Content of the Tack Coat and Prime Coat in Percent by Volume:

Use 100% for cutbacks and Tack Coat 64-22

60% for Polymer Modified Tack Coat

60% for RS or similar type emulsions

M = Percentage of Bid Price Applicable to Materials Only: Use 82%

G = Gallons of Tack Coat and Prime Coat Furnished and Applied

2**************************************************************************************2

1**************************************************************************************************************************1

160.04  Measurement and Payment

1**************************************************************************************************************************1

BDC12s-13 dated sep 21, 2012

THE FOLLOWING ITEMs’ pay units are revised to:

Item	Pay Unit

FUEL PRICE ADJUSTMENT	dollar

ASPHALT PRICE ADJUSTMENT	dollar

1**************************************************************************************************************************1

Division 200 – Earthwork

Section 201 – Clearing Site

201.03.01  Clearing Site

1**************************************************************************************************************************1

2**************************************************************************************2

BDC12s-12 dated Oct 12, 2012

B. Clearing and Grubbing.

THE FOLLOWING IS ADDED:

Dispose of material and debris as specified in 201.03.09.

2**************************************************************************************2

2**************************************************************************************2

BDC08s-02 dated Feb 17, 2009

If JCP&L related utility work is to be performed, add the following:

Remove trees and branches within 15 feet of the end of JCP&L pole cross arms.  If the resulting tree is rendered hazardous, then remove the entire tree according to SECTION 802.

2**************************************************************************************2

1**************************************************************************************************************************1

201.03.02  Clearing Site, Bridge and Clearing Site, Structure

the following is added to the first paragraph.

Only the following equipment is permitted for the work:

1.	Pneumatic or Electric Equivalent Hand Operated Hammers.

a.	When demolishing concrete not closer than 6 inches to structural members: hammers weighing no more than 90 lbs (exclusive of bit), equipped only with chisel point bits.

b.	When demolishing concrete within 6 inches of structural members: hammers weighing no more than 30 lbs (exclusive of bit).

2.	Saw Cutters.

a.	When cutting concrete within 6 inches of structural members:  concrete cutters and concrete saws.  While using water in the cutting operation, provide shielding beneath the cutting operation to prevent water leakage.  Continuously collect slurry and dispose of as specified in 201.03.09.  Ensure that the slurry does not enter the structure or highway drainage system.

3.	Hydraulic Breakers.  Ram-hoe type breakers, hydraulic breakers, and demolition shears may be used with the following restrictions:

a.	Submit required data to the RE for Department’s analysis of stresses induced to the girders.

b.	Delineate the centerline and limits of the top flange of girders before the equipment operation.

c.	Do not use equipment within 6 inches of the delineated flanges.

d.	Do not pull or twist the reinforcement steel.

4.	Hydraulic Splitters.  Hydraulic splitters.

5.	Other Equipment.  Obtain RE approval before use.

1**************************************************************************************************************************1

2**************************************************************************************2

include THE FOLLOWING FOR DECK AND/OR BEAM ENCASEMENT REMOVAL WHEn THE REMAINDER OF EXISTING SUPERSTRUCTURE IS TO REMAIN.

sme contact – Structural Engineering

the following is added:

The procedure is described below:

1.	Prestressed Concrete Stringers and Concrete Diaphragms.  Repair damage to prestressed concrete stringers and concrete diaphragms using nonshrink grout conforming to Subsection 903.08 before deck placement.

2.	Steel Stringers, Floorbeams, Cross Frames, and Diaphragms.

a.	Repair procedures to tensile components in conformance with ASTM A 6/A 6M and the following:

1	Repair gouges up to 1/8 inch by grinding flush in the direction of principal stress.

2	Repair gouges deeper than 1/8 inch by first grinding; then, depositing weld metal and grinding flush with the surface of the metal in the direction of principal stress.  Weld using low hydrogen electrodes conforming to current AWS Specifications A5.1 and A5.5.

3	Repair kinks and deformations by flame straightening or a combination of flame straightening and jacking.  Ensure flame straightening is performed by personnel having a minimum of three years of documented experience.  Submit the names of the personnel to the RE for review and approval prior to performing the work.

b.	Repair procedures to compression components for kinks and deformations as outlined in 2.a (3) above.  Where more than five percent of the cross-sectional area of the member is damaged, submit a repair procedure to the RE for review and approval.

Clean and paint exposed existing top flanges of beams with prime coat as specified in Subsection 554.03.

2**************************************************************************************2

2**************************************************************************************2

INCLUDE THE FOLLOWING IF grounding and bonding for ELECTRIFIED RAIL LINES is required

Bonding and Grounding for Electrified Railroad.  For the required materials, submit a list to the RE for approval 21 days before construction operation.  In the list, include:  material description, manufacturer and catalog number.  After obtaining the RE’s approval, submit the list to the railroad for review and approval.  Do not order the materials prior to obtaining the railroad’s approval.  Furnish and deliver the materials to the railroad.  Obtain a receipt for the materials from the railroad and provide a copy to the RE.

2**************************************************************************************2

2*************************************************************************************2

ENTER THE QUANTITIES BELOW AND ANY REVISIONS TO THE MATERIALS LISTED AFTER CONSULTATION WITH THE RAILROAD.

SME CONTACT – STRUCTURAL DESIGN AND project manager

| List of Materials |
| --- |
| Description | Quantity Required |
| U-bolt, ⅞-inch diameter by 4-inch, BS fastener | -------- |
| Strap, clevis, 1¼ by 2 inches stock, 12-inch connecting length, 1-inch diameter hole, ⅝-inch diameter bolt, ultimate strength 25 psi, Brewer Tilchener Corp.-3074 C | -------- |
| Dead end eye bolt, compression type steel, use DIE 6010SH, compression tool, 60A ALCOA 9190-332 | -------- |
| Jumper cable, compression type aluminum, use DIE 6020AH, compression tool 60A ALCOA 5120-781 | -------- |
| Terminal - Bundy AK2C39B1 to 336400 Cable (1) | -------- |
| Ground terminal - Bundy AK2C39B1 to 336400 Cable (2) | -------- |
| Terminal - solid barrier to 0.17 square inch cable Bundy KC28B1 | -------- |
| Compound, aluminum to copper connection (ALNOX) CANS | -------- |
| Termination, dead end strand clamp, ALCO 336 4 KCM | -------- |
| Clip, bronze, complete type BC, Ohio brass | -------- |
| Thimble-Bronx 336 4 KCM | -------- |
| U-bolt, 1¼-inch diameter by 1½-inch loop 336 4 KCM 11, 30/7 STR ACSR, ANACONDA insulated aluminum cable having a diameter of 0.17 square inches, ANACONDA | -------- |

2**************************************************************************************2

1**************************************************************************************************************************1

201.03.04  Removing Underground Storage Tanks

1**************************************************************************************************************************1

BDC10s-09 dated sep 10, 2010

The third paragraph, Subpart 2, last paragraph is changed to:

Before backfilling, remove and dispose of contaminated water not associated with ground water.  If directed, immediately backfill the excavated hole as required per N.J.A.C. 7:26E and obtain documentation for the quality of the fill.  In addition, provide certification stating that it is virgin material from a commercial or noncommercial source or decontaminated recycled soil.  Backfill the excavation as specified in 201.03.07.5 but use certified clean fill as noted above.

1**************************************************************************************************************************1

1**************************************************************************************************************************1

Complete and include following information, when removal of underground storage tank(s) are required

sme contact – Environmental Solutions

Remove following:

| Parcel No. | Tank Size | Contents | Tank Registration No. |
| --- | --- | --- | --- |

1**************************************************************************************************************************1

201.03.08  Asbestos Removal

1**************************************************************************************************************************1

include location and other requirements for the removal of Asbestos

sme CONTACT – Capital PROGRAM Systems Management

1**************************************************************************************************************************1

201.04  Measurement and Payment

THE FOLLOWING IS ADDED:

1**************************************************************************************************************************1

2**************************************************************************************2

complete and include amount using Engineer’s estimate

sme CONTACT – Construction Management

The Department will not make payment for the Item CLEARING SITE in excess of $_______________ until Completion.

2**************************************************************************************2

2**************************************************************************************2

INCLUDE PARTIAL PAYMENTS, IF REQUIRED for REMOVAL OF THE BRIDGE OR STRUCTURE SCHEDULED IN STAGES.

THE FOLLOWING EXAMPLE REPRESENTS A BRIDGE SCHEDULED TO BE REMOVED IN THREE STAGES.  THE SEQUENCE OF CONSTRUCTION REQUIRED REMOVAL OF 20 PERCENT OF THE BRIDGE IN STAGE I, 40 PERCENT IN STAGE II, AND 40 PERCENT IN STAGE III.  THE ENGINEER’S ESTIMATE FOR THE ITEM AMOUNT WAS $4,000,000.  THE PAYMENT SCHEDULE FOR “CLEARING SITE, BRIDGE (STRUCTURE NO.)” WILL BE AS FOLLOWS:

- for the item “clearing site bridge (structure no.)”, The department will not make IN EXCESS OF $4,000,000 UNTIL SUBSTANTIAL COMPLETION.

- the department will make payment of TWENTY PERCENT OF THE PRICE BID (OR $800,000, WHICHEVER IS LESS) UPON ACCEPTANCE OF STAGE I DEMOLITION.

- the department will make payment of FORTY PERCENT OF THE PRICE BID (OR $1,600,000, WHICHEVER IS LESS) UPON ACCEPTANCE OF STAGE II DEMOLITION.

- the department will make payment of FORTY PERCENT OF THE PRICE BID (OR $1,600,000, WHICHEVER IS LESS) UPON ACCEPTANCE OF STAGE III DEMOLITION.

3************************************************3

complete and include THE VALUE

sme CONTACT – Construction Management

The Department will not make payment for the Item CLEARING SITE, BRIDGE (___) in excess of $_______________ until Substantial Completion.

The Department will not make payment for the Item CLEARING SITE, STRUCTURE (___) in excess of $_______________ until Substantial Completion.

3************************************************3

2**************************************************************************************2

1**************************************************************************************************************************1

Section 202 – Excavation

202.02  Materials

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

the FIRST in the list IS CHANGED TO:

Coarse Aggregate (No. 57, or 67)	901.03

1**************************************************************************************************************************1

202.03.03  Excavating Unclassified Material

1**************************************************************************************************************************1

A.	Excavating.

2**************************************************************************************2

BDC12s-12 dated oct 12, 2012

THE first PARAGRAPH is CHANGED TO:

The Department, as the generator, is solely responsible for the designation of excavated material.  Unclassified excavation consists of excavation and management of material of whatever nature encountered, except for regulated material, pavement removal and acid producing soil.

2**************************************************************************************2

B.	Temporarily Storing.

2**************************************************************************************2

BDC16s-08 dated dec 16, 2016

THE FOLLOWING SENTENCE IS ADDED AFTER THE SECOND SENTENCE OF THE FIRST PARAGRAPH:

Do not commingle different types or classifications of material.

2**************************************************************************************2

1**************************************************************************************************************************1

202.03.04  Excavating Regulated Material

3.	Temporarily Storing.

THE first PARAGRAPH is CHANGED TO:

Temporarily store regulated or hazardous material in stockpiles within the Project Limits and as shown on the Plans.  Construct stockpiles on polyethylene sheeting.  Contain stockpiles with haybales or silt fence placed continuously at the perimeter of the stockpiles.  For hazardous material, if a stockpile area is not available within the Project Limits, sample and analyze materials in-situ for disposal.  Excavate and place the hazardous regulated material directly into trucks, and haul it directly to the approved disposal facility.

202.03.07  Reuse or Disposal of Excess Material

1**************************************************************************************************************************1

BDC14s-01 dated Feb 28, 2014

A.	Reuse.

The third Paragraph is Changed to:

Upon RE’s approval, reuse excavated soil to widen or flatten slopes of embankment, to fade embankments into cuts, or as approved at other locations.  Ensure that the excess material is not reused within a wetland, a transition area, a riparian zone, a flood hazard area or other regulated area without obtaining an appropriate NJDEP permit.

1**************************************************************************************************************************1

1**************************************************************************************************************************1

BDC14s-04 dated oct 31, 2014

B.	Disposal.

PARTS 1 AND 2 UNDER THE FIRST PARAGRAPH ARE CHANGED and part 3 is added:

1.	At least 10 days before disposing, submit the disposal procedure and location to the RE for approval. Do not dispose of excavation on property proposed to be or used for parks, playgrounds, and other recreational purposes; residential facilities; educational facilities; environmentally sensitive areas such as wetlands; historic sites; or within sight of a State highway during all seasons.

2.	Obtain the potential owner's notarized authorization of the acceptance of the excess material.  If the potential owner requires environmental material sampling, obtain RE’s approval at least 7 days before sampling for oversight only.  Approval of the sampling does not imply agreement with the sampling results and the Department reserves the right to sample the material for classification.  Provide the RE all testing results and documentation associated with the sampling.

3.	Load and transport excess material that the RE determines to be excess, unusable or unsuitable for the project according to Federal, State, and local law, rules and regulations.

1**************************************************************************************************************************1

Section 203 – Embankment

203.02.01  Materials

this subpart IS CHANGED TO:

Provide materials as specified:

Soil Aggregate (I-7, I-9, I-10, I-11, I-13, and I-14)	901.11

203.03.01  Constructing Embankment

1**************************************************************************************************************************1

BDC16s-10 dated jan 18, 2017

THE FOLLOWING IS ADDED TO THE FIRST PARAGRAPH:

The ME will determine the classification of the subgrade material specified in Table 203.03.02-1.  Compact the subgrade using the directed method as specified in 203.03.02.C for the classification of the subgrade material.

1**************************************************************************************************************************1

1**************************************************************************************************************************1

BDC12s-15 dated Feb 22, 2013

THE FOURTH PARAGRAPH IS CHANGED TO:

Before placing embankment or any other unbound aggregate material, such as subbase or dense graded aggregate, on existing pavement, break the pavement into pieces that are a maximum of 12 inches in all dimensions.

1**************************************************************************************************************************1

Division 300 – Subbase and Base Courses

SECTION 303 – ASPHALT-STABILIZED DRAINAGE COURSE

303.03.01  Asphalt-Stabilized Drainage Course

D.	Spreading and Grading

1**************************************************************************************************************************1

BDC11s-01 dated Mar 30, 2011

THE SECOND SENTENCE IS CHANGED TO:

Place asphalt-stabilized drainage course at a laydown temperature between 210 °F and 275 °F.

1**************************************************************************************************************************1

Division 400 – Pavements

Section 401 – Hot Mix Asphalt (HMA) Courses

401.02.01  Materials

1**************************************************************************************************************************1

BDC11s-01 dated Mar 30, 2011

Emulsified Asphalt under TACK COAT is revised to:

Emulsified Asphalt, Grade RS-1, CRS-1, SS-1, SS-1h, Grade CSS-1 or CSS-1h	902.01.03

1**************************************************************************************************************************1

1**************************************************************************************************************************1

BDC14s-07 dated Aug 29, 2014

The following is added to the materials list

Polymer Modified Tack Coat	902.01.04

1**************************************************************************************************************************1

401.02.02  Equipment

THE LAST PARAGRAPH is changed to:

When an MTV is used, install a paver hopper insert with a minimum capacity of 14 tons in the hopper of the HMA paver.

401.03.01  Preparing Existing Pavement

A.	Milling of HMA.

1**************************************************************************************************************************1

complete and include TIME INTERVAL FOR RESURFACING THE MILLED PAVEMENT BASED ON THE project STAGING. MAXIMUM TIME INTERVAL MAY VARY BUT SHALL NOT EXCEED 72 HOURS.

SME CONTACT – TRAFFIC OPERATIONS AND REGIONAL CONSTRUCTION Engineer

| Stage | Max. time interval allowed |
| --- | --- |

1**************************************************************************************************************************1

1**************************************************************************************************************************1

BDC11s-01 dated Mar 30, 2011

THE FOLLOWING IS ADDED AFTER THE fourth PARAGRAPH:

Sawcut at the limit of paving in driveways and at other limits requiring a neat edge between new and existing HMA.

1**************************************************************************************************************************1

D.	Repairing HMA Pavement.

1**************************************************************************************************************************1

BDC11s-01 dated Mar 30, 2011

the entire text is changed to:

If potholes are discovered, notify the RE immediately. The RE may immediately direct repairs of small areas.  The RE may require further evaluation of a large area to determine the need for additional milling and paving.

Sawcut existing HMA pavement to a maximum depth of 10 inches, or to the full depth of bound layers, whichever is less.  Sawcut lines parallel and perpendicular to the roadway baseline and 3 inches away, at the closest point, from the damaged area to be repaired.

Remove damaged and loose material to a depth of at least 3 and no more than 10 inches below the level of milling within the boundary of the sawcuts to form rectangular openings with vertical sides.  Shape and compact the underlying surface to produce a firm, level base.  Ensure that the remaining pavement is not damaged.

Apply polymerized joint adhesive or tack coat to the vertical surfaces of the openings.  Spread and grade HMA in the opening as directed by the RE.  Ensure that the temperature of the HMA when placed is at least 250 °F, and compact as specified in 401.03.03.F.  Compact areas not accessible to rollers with a flat face compactor.  Compact until the top of the patch is flush with the adjacent pavement surface.

Reuse removed material as specified in 202.03.07.A.

1**************************************************************************************************************************1

401.03.02  Tack Coat and Prime Coat

1**************************************************************************************************************************1

BDC14s-07 dated Aug 29, 2014

the entire text is changed to:

Clean the surface where the HMA is to be placed of foreign and loose material.  Immediately before beginning paving operations, ensure that the surface is dry.  Do not place tack coat or prime coat unless the weather restrictions, as specified in 401.03.03.B, are met.

Do not apply tack coat or prime coat to asphalt-stabilized drainage course.

For curbs, gutters, manholes, and other similar structures, do not apply tack coat or prime coat.  Clean the exposed surfaces of these structures and apply a uniform coating of polymerized joint adhesive to contact surfaces before paving.

In areas inaccessible to distributor spray bars, use hand spraying equipment for tack and prime coat.  Do not allow traffic on tack coated or prime coated surfaces.  Treat surfaces as follows:

1.	Tack Coat.  Uniformly spray tack coat when placing HMA on paved surfaces.  Apply tack coat only to areas to be paved in the same day.  Apply tack coat as specified in Table 401.03.02-1:

| Table 401.03.02-1 Tack Coat Application |
| --- |
| Material | Spraying Temp, °F | Gallons per Square Yard | Season |
| Cut-Back Asphalt: |  |  |  |
| RC-70 | 120 to 190 | 0.05 to 0.15 | Oct 15 to Apr 15 |
| Emulsified Asphalt: |  |  |  |
| RS-1 | 70 to 140 | 0.05 to 0.15 | All year |
| CRS-1 | 125 to 185 | 0.05 to 0.15 | All year |
| SS-1, SS-1h | 70 to 140 | 0.05 to 0.15 | All year |
| CSS-1, CSS-1h | 70 to 140 | 0.05 to 0.15 | All year |

Correct uncoated or lightly coated areas.  Blot areas showing an excess of tack coat with sand or other similar material.  Remove blotting material before paving.  Ensure that the material is not streaked or ribboned.

Before paving, allow tack coat to cure to a condition that is tacky to the touch.

2.	Tack Coat 64-22.  When precipitation has occurred within 24 hours before application, the RE will determine whether to allow the work to proceed, or to wait until the surface is completely dry.  Only apply tack coat that can be paved over in the same day.  Apply tack coat 64-22 at a rate of 0.06 to 0.14 gallons per square yard and at a spraying temperature of 325 °F.  Adjust the spraying temperature and application rate to produce a uniform coating, with no excess material.

Correct uncoated or lightly coated areas and remove excess tack coat from affected areas.  Ensure that the material is not streaked or ribboned.

3.	Polymer Modified Tack Coat.  Apply polymer modified tack coat with an ultra-thin paver at a temperature of 140 to 175 °F.  Continuously monitor rate of spray, ensuring a uniform application rate over entire width to be overlaid.  Apply at the rate of 0.20 ± 0.05 gallons per square yard.  Do not allow traffic, equipment, tools, or any other disturbance to the polymer modified tack coat before placing the ultra-thin friction course.

4.	Prime Coat.  Apply prime coat of cut-back asphalt on unpaved surfaces as follows:

| Table 401.03.02-2 Prime Coat Application |
| --- |
| Cut-Back Asphalt | Spraying Temp, °F | Gallons per Square Yard | Season |
| MC-30 | 85 to 150 | 0.1 to 0.5 | Oct 15 to Apr 15 |
| MC-70 | 120 to 190 | 0.1 to 0.5 | Oct 15 to Apr 15 |
| Emulsified Asphalt: |  |  |  |
| CSS-1 | 70 to 140 | 0.1 to 0.50 | All year |

Apply prime coat at least 12 hours before placement of the HMA and when the base courses are not saturated or frozen.  Unless the prime coat is under asphalt-stabilized drainage course, the RE may waive the application of prime coat if more than 5 inches of HMA is placed on the unbound aggregate course before the roadway is opened to traffic.  Take measures to prevent prime coat from entering into the drainage system or extending beyond the area to be paved.

1**************************************************************************************************************************1

401.03.03  HMA Courses

A.	Paving Plan.

1**************************************************************************************************************************1

BDC14s-07 dated Aug 29, 2014

The following is added at the end of the first paragraph:

15.	If applicable, the warm mix asphalt additive or process being used.

1**************************************************************************************************************************1

C.	Test Strip.

1**************************************************************************************************************************1

BDC14s-07 dated Aug 29, 2014

The following is added at the end of the first paragraph:

7.	Warm Mix Asphalt.  Note the warm mix asphalt additive or process, if used.

1**************************************************************************************************************************1

D.	Transportation and Delivery of HMA.

THE FIRST PARAGRAPH IS CHANGED TO:

Deliver HMA using HMA trucks in sufficient quantities and at such intervals to allow continuous placement of the material.  Do not allow trucks to leave the plant within 1 hour of sunset unless nighttime lighting is provided as specified in 108.06.  The RE will reject HMA if the HMA trucks do not meet the requirements specified in 1009.02.  The RE will suspend construction operations if the Contractor fails to maintain a continuous paving operation.  Before the truck leaves the plant, obtain a weigh ticket from a fully automatic scale.  Before unloading, submit for each truckload a legible weigh ticket that includes the following:

1.	Name and location of the HMA plant.

2.	Project title.

3.	Load time and date.

4.	Truck number.

5.	Mix designation.

6.	Plant lot number.

7.	Tare, gross, and net weight.

E.	Spreading and Grading.

1**************************************************************************************************************************1

2**************************************************************************************2

include the following if this condition is applicable

- THE LENGTH OF CONTINUOUS THROUGH TRAVEL LANE CONSTRUCTION IS less THAN 2,500 FEET.

THE THIRD PARAGRAPH IS CHANGED TO:

The use of an MTV is optional for the construction of intermediate and surface course in the traveled way.  If an MTV is used, ensure that the MTV independently delivers HMA from the HMA trucks to the HMA paver.  Operate the MTV to ensure that the axle loading does not damage structures, roadway, or other infrastructure.

2**************************************************************************************2

or

2**************************************************************************************2

include one of the following if the above condition is not applicable

THE THIRD PARAGRAPH IS CHANGED TO:

Use an MTV for the construction of intermediate and surface course in the traveled way.  Ensure that the MTV independently delivers HMA from the HMA trucks to the HMA paver.  Operate the MTV to ensure that the axle loading does not damage structures, roadway, or other infrastructure.

*******OR*******

Use an MTV for the construction of surface course in the traveled way.  Ensure that the MTV independently delivers HMA from the HMA trucks to the HMA paver.  Operate the MTV to ensure that the axle loading does not damage structures, roadway, or other infrastructure.

2**************************************************************************************2

2**************************************************************************************2

use 100% of the surface course joint length to estimate the quantity of Polymerized joint adhesive

2**************************************************************************************2

1**************************************************************************************************************************1

G.	Opening to Traffic.

1**************************************************************************************************************************1

BDC14s-07 dated Aug 29, 2014

the entire text is changed to:

Remove loose material from the traveled way, shoulder, and auxiliary lanes before opening to traffic.  Open HMA courses to traffic or construction equipment, including paving equipment, only after the surface temperatures meet the following requirements:

1.	When using PG 64-22, do not allow traffic or construction equipment on the HMA course until the surface temperature is less than 140 °F.

2.	When using PG 64E-22, do not allow traffic or construction equipment on the HMA course until the surface temperature is less than 170 °F.

3.	When using Warm Mix Asphalt, do not allow traffic or construction equipment on the HMA course until the surface temperature is less than 120 °F.

1**************************************************************************************************************************1

H.	Air Void Requirements.

1**************************************************************************************************************************1

BDC14s-07 dated Aug 29, 2014

2**************************************************************************************2

THE first PARAGRAPH is CHANGED TO:

Mainline lots are defined as the area covered by a day’s paving production of the same job mix formula for the traveled way and auxiliary lanes. The RE may combine daily production areas less than 1000 tons with previous or subsequent production areas. If a day’s production is greater than 4000 tons, the RE may divide the area of HMA placed into 2 lots with approximately equal areas.

2**************************************************************************************2

2**************************************************************************************2

BDC12s-15 dated Feb 22, 2013

THE FOLLOWING IS ADDED TO THE THIRD PARAGRAPH:

Inside shoulders less than 6 feet in width will not be included in other lots unless requested by the RE.

2**************************************************************************************2

2**************************************************************************************2

BDC11s-01 dated Mar 30, 2011

THE FOLLOWING IS ADDED AFTER THE THIRD PARAGAPH:

If areas of existing  shoulders are found to be insufficient to support the proposed HMA pavement and the required compaction cannot be achieved, notify the RE immediately.  The RE may either direct additional milling and paving to provide a suitable base to pave the proposed HMA or waive coring and air void requirements in such shoulder areas.

2**************************************************************************************2

2**************************************************************************************2

BDC15s-07 dated JUn 30, 2015

Subpart 5 & 7 are changed to:

5	Outlier Detection. If PD < 10, the ME will not screen for outliers. If PD ≥ 10, the ME will screen acceptance cores for outliers using a statistically valid procedure. The following procedure applies only for a sample size of 5 or 10.

    - The ME will arrange the core results in ascending order, in which X1 represents the smallest value and XN represents the largest value.

    - If XN is suspected of being an outlier, the ME will calculate:

| R = | XN - X (N-1) |
| --- | --- |
|  | XN - X1 |

    - If X1 is suspected of being an outlier, the ME will calculate:

| R = | X2 - X 1 |
| --- | --- |
|  | XN - X1 |

    - For N=5 if R > 0.642, the value is judged to be statistically significant and the core is excluded. For N = 10 if R > 0.412, the value is judged to be statistically significant and the core is excluded.

If an outlier is detected and no retest is warranted, the Contractor may replace that core by taking an additional core at the same offset and within 5 feet of the original station. If an outlier is detected and a retest is justified, take a replacement core for the outlier at the same time as the 5 additional retest cores are taken. If the outlier replacement core is not taken within 15 days, the ME will use the initial core results to determine PPA.

If an outlier is detected for N = 10, the Contractor may replace that core by taking an additional core at the same offset and within 5 feet of the original station. If the outlier replacement core is not taken within 15 days, the ME will use the initial core results to determine PPA.

- Removal and Replacement.  If the final lot PD ≥ 75 (based on the combined set of 10 cores or 5 cores if the Contractor does not take additional cores), remove and replace the lot and all overlying work. The replacement work is subject to the same requirements as the initial work.

For shoulder lots, instead of removal and replacement, the Department will assess the calculated PPA, and the Contractor shall perform a fog seal of the lot as specified in 422.03.01.

2**************************************************************************************2

1**************************************************************************************************************************1

J.	Ride Quality Requirements.

1**************************************************************************************************************************1

BDC12s-03 dated May 02, 2012

2**************************************************************************************2

INclude the following, IF PROJECT DOES not require the Ride Quality Requirements

sme CONTACT – send email to RQSpecSupport@dot.state.nj.us

The Department will not test the longitudinal profiles of the final riding surface for pay adjustment.

2**************************************************************************************2

thIS entire SUBPART is changed to:

When the Project exceeds one mile in continuous length, the Department will evaluate the final riding surface using the International Roughness Index (IRI) according to ASTM E 1926.  The final riding surface is defined as the last lift of the pavement structure where traffic will be allowed. The Department will use the measured IRI to compute the appropriate pay adjustment (PA).  The PA will be positive for superior quality work or negative for inferior quality work.

The Department will calculate the PA as specified in Table 401.03.03-7 and will base PA on lots of 0.01 mile length for each lane, ramp, and shoulder and 0.005 mile for each overlaid bridge structure.

1	Smoothness Measurement.  The Department will test the longitudinal profile of the final riding surface for ride quality with a Class 1 Inertial Profiling System according to AASHTO M 328 and NJDOT R-1.  If project conditions preclude the use of the Class 1 Inertial Profiling System, the Department will use a Class 1 walking profiler or lightweight profiler.

The IRI value reported for each lot is the average of 3 runs of each wheel path, unless otherwise directed by the Department.

2.	Quality Control Testing.  Perform control testing during lift placement to ensure compliance with the ride quality requirements specified in Table 401.03.03-7

3.	Preparation for IRI Testing.  Provide traffic control when the Department performs IRI testing.  Perform mechanical sweeping of the surface before IRI testing.  To facilitate auto triggering on laser profilers, place a single line of preformed traffic marking tape perpendicular to the roadway baseline 300 feet before the beginning and after the end of each lane, shoulder, and ramp to be tested or at the direction of the Department.  Submit the actual stationing for each traffic marking tape location to the RE.

4.	Quality Acceptance.  The Department will determine acceptance and provide PA based on the following:

a.	Pay Adjustment.  The pay equations in Table 401.03.03-7 express the PA in dollars per lot of 0.01 mile or 0.005 mile as shown in the table.  The number of lots for final pay adjustment will be reduced by the number of lots excluded for each segment shown in Table 401.03.03-7.  Lots excluded from final PA will be those with the highest recorded IRI numbers for respective roadway and bridge deck segments.  IRI numbers are in inches per mile.

2**************************************************************************************2

Use Ride Quality Requirement (RQR) software to develop PAY EQUATIONS of table 401.03.03-7 for this project.

Download LATEST VERSION OF software from -http://www.state.nj.us/transportation/eng/pavement/ridequality.shtm

sme CONTACT – send email to RQSpecSupport@dot.state.nj.us

Impediments include the following:

(i).	 Metal impediments, such as utility covers, manholes, catch basins and inlets, located in the lane and in shoulders within THE DISTANCE SPECIFIED IN RQR.  The exclusion length for metal impediments is SPECIFIED IN THE RQR.

(ii).	Transverse joints that separate the new pavement from an existing pavement, intersections, railroad crossings, and other features in the pavement deemed by the designer to be a potential impediment to achieving a smooth ride quality.  The exclusion length is the length of the feature plus LENGTH AS SPECIFIED IN RQR before and after each feature

(SAMPLE only)

| Table 401.03.03-7 Pay Equations for Ride Quality |
| --- |
|  | Excluded Lots | Pay Equation(s) |
| Route 00 from MP 6.3 to MP 7.9 | Lane 1 - 2 Lane 2 - 10 | PA on lots of 0.01 mile length |
|  |  | IRI < 28 | PA = $50 |
|  |  | 28 ≤ IRI < 48 | PA = $120 – ($2.50 × IRI) |
|  |  | 48 ≤ IRI ≤ 58 | PA = $0 |
|  |  | 58 < IRI ≤ 128 | PA = (IRI − 58) × (−$7.1429) |
|  |  | IRI > 128 | Remove & Replace |
| Route 00 Ramps and Shoulders | None | PA on lots of 0.01 mile length |
|  |  | IRI ≤ 120 | PA = $0 |
|  |  | 120 < IRI ≤ 170 | PA = (IRI-120) × (-$10.00) |
|  |  | IRI > 170 | Remove & Replace |
| Overlaid Bridge Decks on Route 00 Between MP 7.9 and MP 8.1 | None | PA on lots of 0.005 mile length |
|  |  | IRI ≤ 120 | PA = $0 |
|  |  | 120 < IRI ≤ 170 | PA = (IRI − 120) × (−$5.00) |
|  |  | IRI > 170 | Remove & Replace |

(III)	ADD MORE ROWS IN Table 401.03.03-7 FOR MULTIPLE SECTIONS AS REQUIRED. INCLUDE EXCLUSIONS FOR EACH LANE TO BE TESTED WITHIN THE PROJECT LIMITS. INCLUDE ATLEAST ONE EXCLUSION FOR EACH LANE, IF THERE IS NO IMPEDIMENT. THE LANE DESIGNATION SHALL BE MADE BY INCREASING NUMBERS FROM LEFT TO RIGHT IN THE DIRECTION OF TRAFFIC.WITH LEFT LANE BEING LANE 1.

(IV)	If the EXISTING IRI is already in bonus range of pay equations, then the specified target IRI range i.e. range with zero pay adjustment shall be adjusted such that the project’s IRI target range lower limits starts at the EXISTING IRI value.

Example:

Existing IRI = 100 inch/mile

Proposed target IRI range

110 ≤ IRI ≥ 120 	PA=0

Use:-

100 ≤ IRI ≥ 120 	PA=0

Modify pay equations accordingly.

| Table 401.03.03-7 Pay Equations for Ride Quality |
| --- |
|  | Excluded Lots | Pay Equation(s) |
| Route __ from MP __._ to MP __._ | Lane 1 - __ Lane 2 - __ | PA on lots of 0.01 mile length |
|  |  | IRI < __ | PA = $50 |
|  |  | __ ≤ IRI < __ | PA = $___.__ – ($2.50 × IRI) |
|  |  | __ ≤ IRI ≤ __ | PA = $0 |
|  |  | __ < IRI ≤ __ | PA = (IRI − __ ) x (−$7.1429) |
|  |  | IRI > __ | Remove & Replace |
| Route __ Ramps and Shoulders | None | PA on lots of 0.01 mile length |
|  |  | IRI ≤ 120 | PA = $0 |
|  |  | 120 < IRI ≤ 170 __ | PA = (IRI-120) x (-$10.00) |
|  |  | IRI > 170 | Remove & Replace |
| Overlaid Bridge Decks on Route __ Between MP __._ and MP __._ | None | PA on lots of 0.005 mile length |
|  |  | IRI ≤ 120 | PA = $0 |
|  |  | 120 < IRI ≤ 170 | PA = (IRI − 120) x (−$5.00) |
|  |  | IRI > 170 | Remove & Replace |

2**************************************************************************************2

b.	Removal and Replacement.  If the final IRI is greater than the Remove and Replace Value (RRV), remove and replace the lot.  Replacement work is subject to the same requirements as the initial work.

If less than 8 percent of paving lots exceeds the RRV, submit a plan for corrective action.  If the corrective action plan is not approved by the RE, remove and replace the designated lots.  If the corrective action plan is approved and the lots are reworked, the lots are subject to the requirements of subpart 401.03.03.J Ride Quality Requirements except that the lots are not eligible for positive PA. The RE may allow the lots to remain in place and apply the pay adjustment as computed in Table 401.03.03-7.

1**************************************************************************************************************************1

401.03.04  Sawcutting and Sealing of Joints in HMA Overlays

1**************************************************************************************************************************1

BDC12s-15 dated Feb 22, 2013

THE text of this subpart is deleted.

This subpart is INTENTIONALLY left blank

1**************************************************************************************************************************1

401.03.05  Core Samples

1**************************************************************************************************************************1

BDC11s-08 dated aug 26 2011

The last sentence of the 2nd paragraph is changed to the following:

Apply an even coating of tack coat to sides of the hole.  Place HMA in maximum lifts of 4 inches in the hole and compact each lift.  Ensure that the final surface  is 1/4 inch above the surrounding pavement surface.

1**************************************************************************************************************************1

401.04  Measurement and Payment

1**************************************************************************************************************************1

2**************************************************************************************2

BDC12s-15 dated Feb 22, 2013

THE FOLLOWING ITEM is deleted:

Item	Pay Unit

SAWING AND SEALING JOINTS IN HOT MIX ASPHALT OVERLAY	LINEAR FOOT

2**************************************************************************************2

2**************************************************************************************2

BDC14s-07 dated Aug 29, 2014

THE FOLLOWING ITEM is added:

Item	Pay Unit

POLYMER MODIFIED TACK COAT	GALLON

THE fourth PARAGRAPH is CHANGED TO:

The Department will measure TACK COAT, TACK COAT 64-22, PRIME COAT and  POLYMER MODIFIED TACK COAT by the volume delivered, converted to the number of gallons at 60 °F as calculated by the temperature-volume correction factors specified in 902.01.

2**************************************************************************************2

2**************************************************************************************2

THE FOLLOWING IS ADDED:

The Department will make a payment adjustment for HMA air void quality by the following formula:

Pay Adjustment = Q x  BP x PPA

Where:

BP = Bid Price

Q= Air Void Lot Quantity

PPA= air void PPA as specified in 401.03.03H.

The Department will make a payment adjustment for HMA thickness quality by the following formula:

Pay Adjustment = Q x  BP x PPA

Where:

BP = Bid Price

Q= Thickness Lot Quantity

PPA= thickness PPA as specified in 401.03.03I

The Department will make a payment adjustment for HMA ride quality, as specified in 401.03.03J.

2**************************************************************************************2

1**************************************************************************************************************************1

Section 402 – HMA Friction Course

402.01  Description

1**************************************************************************************************************************1

BDC11s-01 dated Mar 30 2011

the entire text is changed to:

This Section describes the requirements for constructing open-graded friction courses (OGFC), modified open-graded friction courses (MOGFC) and asphalt-rubber open-graded friction courses (AR-OGFC).

1**************************************************************************************************************************1

402.02.01  Materials

1**************************************************************************************************************************1

BDC11s-01 dated Mar 30, 2011

the following is added to list of materials

Asphalt-Rubber Open-Graded Friction Course	902.07

1**************************************************************************************************************************1

402.02.02  Equipment

1**************************************************************************************************************************1

BDC11s-01 dated Mar 30, 2011

the following is added to list of Equipment

Asphalt-Rubber Binder Blending Equipment	1009.03

1**************************************************************************************************************************1

402.03  Construction

1**************************************************************************************************************************1

BDC11s-01 dated Mar 30, 2011

THE FOLLOWING subpart is ADDED AFTER 402.03.01:

402.03.02  AR-OGFC

A.	Paving Plan.  At least 20 days before beginning placing the AR-OGFC, submit to the RE for approval a detailed plan of operation as specified in 401.03.03.A.

B.	Weather Limitations.  If within the 12 hours before paving, the National Weather Service locally forecasts a 50 percent chance or greater of precipitation during the scheduled placement, postpone the placement of AR-OGFC. Do not place AR-OGFC if it is precipitating and do not allow trucks to leave the plant when precipitation is imminent.  The Contractor may resume paving operations when the chance of precipitation is less than 50 percent and the surface is dry.

Do not pave if the surface temperature of the underlying pavement is below 50  F.

C.	Test Strip.  Construct a test strip as specified in 401.03.03.C.  The Department will not require quality control cores or nuclear density testing.

D.	Transportation and Delivery of AR-OGFC.  Transport and deliver AR-OGFC as specified in 401.03.03.D.

E.	Spreading and Grading.

2**************************************************************************************2

BDC12s-15 dated Feb 22, 2013

Apply tack coat 64-22 as specified in 401.03.02.  Place AR-OGFC at a laydown temperature between 275 °F and 330 °F maximum.  Spread and grade AR-OGFC as specified in 401.03.03.E, except do not apply polymerized joint adhesive or tack coat to longitudinal joints.

2**************************************************************************************2

F.	Compacting.  Immediately after spreading and strike-off, compact AR-OGFC with a minimum of 1 pass of a non-vibratory, 2-axle roller.  The RE may direct additional passes to eliminate roller marks.  The Contractor may use a vibratory roller if it is operated in static mode.

Orient the drive axles of the roller towards the paver during the compaction operation.  Operate rollers at a slow, uniform speed not exceeding 2-1/2 miles per hour.  If necessary to prevent adhesion of the AR-OGFC to the rollers, keep the wheels moistened with water mixed with small quantities of detergent or fabric softener.

Remove and replace AR-OGFC that becomes loose, broken, or otherwise defective or that shows an excess or deficiency of asphalt-rubber binder material.

When paving in echelon, keep the rollers for the first lane approximately 6 inches from the unconfined edge adjacent to the second paving operation.  After AR-OGFC from the second paver is placed against the uncompacted edge of the mat from the first paver, compact the AR-OGFC on both sides of the joint.

Prevent lateral or vertical displacement of the unconfined edge during the compaction operation.  Ensure that the edge of the drums of the rollers extends over the free edge of the mat by at least 6 inches.

When compacting the butt joint, while paving the adjacent lane, place the roller on the newly placed AR-OGFC and overlap the joint by approximately 6 inches.

G.	Curing.  Following compaction, spray 1 to 3 applications of lime water (a minimum of 50 pounds of pulverized limestone per 2,000 gallons of water) to prevent material pick-up.  Apply lime water in a manner that uniformly covers the entire surface of the paving pass. Prior to applying the lime water, do not allow traffic on the AR-OGFC, including the lime water applicator.

H.	Opening to Traffic.  Remove loose material from the traveled way, shoulder, and auxiliary lanes before opening to traffic. Before opening AR-OGFC to traffic or construction equipment, ensure that the lime water has been applied, the surface is tack free and the surface temperature is less than 140 °F.

I.	Ride Quality Requirements.  The Department will evaluate the AR-OGFC as specified in 401.03.03.J.

1**************************************************************************************************************************1

402.04  Measurement and Payment

THE FOLLOWING IS ADDED:

1**************************************************************************************************************************1

BDC11s-01 dated Mar 30, 2011

Item	Pay Unit

Asphalt-Rubber OPEN-GRADED FRICTION COURSE	TON

The Department will measure Asphalt-Rubber Open-Graded Friction Course by the ton as indicated on the certified weigh tickets, excluding unused material.

The Department will make payment for TACK COAT 64-22 as specified in 401.04.

1**************************************************************************************************************************1

The Department will make a payment adjustment for HMA thickness quality by the following formula:

Pay Adjustment = Q x  BP x PPA

Where:

BP = Bid Price

Q= Thickness Lot Quantity

PPA= thickness PPA as specified in 401.03.03I

The Department will make a payment adjustment for HMA ride quality, as specified in 401.03.03J.

Section 403 – Ultra-Thin Friction Course

403.02.02  Equipment

1**************************************************************************************************************************1

BDC14s-07 dated Aug 29, 2014

The following is added to the equipment list

Materials Transfer Vehicle (MTV)	1003.01

1**************************************************************************************************************************1

403.03.01 Ultra-Thin Friction Course

1**************************************************************************************************************************1

BDC14s-07 dated Aug 29, 2014

the entire text is changed to:

A.	Paving Plan.  At least 20 days before the start of placing the ultra-thin friction course, submit a detailed plan of operation to the RE for approval as specified in 401.03.03.A.

B.	Weather Limitations.  Do not place ultra-thin friction course if it is precipitating.  Do not allow trucks to leave the plant when precipitation is imminent.  The Contractor may resume operations when the precipitation has stopped and the surface is free of water.

Do not pave if the base temperature is below 50 °F.

C.	Test Strip.  Construct a test strip for the first 700 to 1200 square yards placed of ultra-thin friction course.  Operate spray paver without mix to determine tack coat application rate for the project. Ensure that the polymer modified tack coat has been placed as specified in 401.03.02.  Transport and deliver, spread and grade, and compact as specified in 403.03.02.D, 403.03.02.E, and 403.03.02.F, respectively, and according to the approved paving plan.  While constructing the test strip, record the following information and submit to the RE:

1.	Ambient Temperature.  Measure ambient temperature at the beginning and end of each day’s paving operation.

2.	Base Temperature.  Measure the surface temperature of the existing base before paving.

3. 	Polymer Modified Tack Coat.  Measure to verify the proper application of tack coat and the rate for compliance.

4.	HMA Temperature.  Measure the temperature of the ultra-thin HMA immediately after placement.

5.	Roller Pattern.  Provide details on the number of rollers, type, and number of passes used on the test strip.

6.	Quality Control Cores for Yield and Thickness.  Take 3 randomly selected quality control cores to test for compliance to the specified yield in 403.03.02.E.

Use drilling equipment with a water-cooled, diamond-tipped, masonry drill bit that shall produce 6-inch nominal diameter cores for the full depth of the pavement.  Remove the core from the pavement without damaging it.  After removing the core, remove all water from the hole.  Fill the hole with HMA or cold patching material, and compact the material so that it is 1/4 inch above the surrounding pavement surface.

Submit test strip results to the RE.  The RE will analyze the test strip results in conjunction with the ME’s results from the HMA plant to approve the test strip.  Do not proceed with production paving until receiving written permission from the RE.

If the test strip does not meet requirements, make adjustments and construct a second test strip.  If the second test strip does not meet requirements, suspend paving operations until written approval to proceed is received.

Before making adjustments to the paving operations, notify the RE in writing.

D.	Transportation and Delivery of HMA.  Transport and deliver HMA as specified in 401.03.03.D.

E.	Spreading and Grading.  Use of an MTV is required for the construction of ultra-thin friction course.  Ensure that the surface where the ultra-thin friction course is placed is clean of foreign and loose material.  Clean the surface of existing pavement using a self-propelled power broom equipped with a vacuum collection system before placing the ultra-thin friction course.  Ensure that the surface is dry when the paving operations are about to start.

Apply polymer modified tack as specified in 401.03.02.  Do not allow traffic, equipment, tools, or any other disturbance to the polymer modified tack coat before placing the ultra-thin friction course.

Ensure that the temperature of the ultra-thin friction course behind the screed is between 280 °F and 325 °F. Within 3 seconds of applying the polymer modified tack coat, place ultra-thin friction course at a rate of 65 to 95 pounds per square yard.

Construct longitudinal joints as specified in 401.03.03.E.1.  If constructing a cold longitudinal joint, construct a butt joint and do not use polymerized joint adhesive.  Construct transverse joints as specified in 401.03.03.E.2.

F.	Compacting.  Compact ultra-thin friction course as specified in 401.03.03.F.  Use a minimum of two 10-ton steel-wheel rollers.  If vibratory compaction causes aggregate breakdown or forces liquid asphalt binder to the surface, operate rollers in static mode only.

G.	Opening to Traffic.  Remove loose material from the traveled way before opening to traffic.  Do not allow construction equipment or traffic on the ultra-thin friction course until the mat cools to a temperature of less than 140 °F.

H.	Thickness Requirements.  When required for thickness determination, drill cores as specified in 401.03.05.  The Department will calculate total thickness as specified in 401.03.03.I.  The Department will not evaluate surface thickness.

I.	Ride Quality Requirements.  The Department will evaluate the surface course placed in the traveled way as specified in 401.03.03.J.

1**************************************************************************************************************************1

403.04  Measurement and Payment

The following is added:

1**************************************************************************************************************************1

BDC14s-07 dated Aug 29, 2014

The Department will make payment for POLYMER MODIFIED TACK COAT as specified in 401.04.

1**************************************************************************************************************************1

The Department will make a payment adjustment for HMA thickness quality, by the following formula:

Pay Adjustment = Q x  BP x PPA

Where:

BP = Bid Price

Q= Thickness Lot Quantity

PPA= thickness PPA as specified in 401.03.03I

The Department will make a payment adjustment for HMA ride quality, as specified in 401.03.03J.

Section 404 – Stone Matrix Asphalt (SMA)

404.03.01 SMA

H.	Air Void Requirements.

The entire part is changed to:

1**************************************************************************************************************************1

BDC15s-07 dated Jun 30, 2015

Drill cores as specified in 401.03.05.

Mainline lots are defined as the area covered by a day’s paving production of the same job mix formula for the traveled way and auxiliary lanes. The RE may combine daily production areas less than 1000 tons with previous or subsequent production areas. If a day’s production is greater than 4000 tons, the RE may divide the area of HMA placed into 2 lots with approximately equal areas.

Ramp pavement lots are defined as approximately 10,000 square yards of pavement in ramps.  The RE may combine ramps with less than the minimum area into a single lot.  If 2 or more ramps are included in a single lot, the RE will require additional cores to ensure that at least 1 core is taken from each ramp.

Other pavement lots are defined as approximately 10,000 square yards of pavement in shoulders and other undefined areas.

The ME will calculate the percent defective (PD) as the percentage of the lot outside the acceptable range of 1 percent air voids to 7 percent air voids.  The acceptable quality limit is 10 percent defective.  For lots in which PD < 10, the Department will award a positive pay adjustment.  For lots in which PD > 10, the Department will assess a negative pay adjustment.

The ME will determine air voids from 5 cores taken from each lot in random locations.  The ME will determine air voids of cores from the values for the maximum specific gravity of the mix and the bulk specific gravity of the core.  The ME will determine the maximum specific gravity of the mix according to NJDOT B-3 and AASHTO T 209, except that minimum sample size may be waived in order to use a 6-inch diameter core sample.  The ME will determine the bulk specific gravity of the compacted mixture by testing each core according to AASHTO T 166.

The ME will calculate pay adjustments based on the following:

1.	Sample Mean () and Standard Deviation (S) of the N Test Results (X1, X2,..., XN).

2.	Quality Index (Q).

3.	Percent Defective (PD).  Using NJDOT ST for the appropriate sample size, the Department will determine PDL and PDU associated with QL and QU, respectively.  PD = PDL + PDU

4.	Percent Pay Adjustment (PPA).  Calculate the PPA for traveled way and ramp lots as specified in Table 401.03.03-3.

| Table 404.03.01-1 PPA for Mainline Lots and Ramp Lots |
| --- |
|  | Quality | PPA |
| Surface | PD ( 10 | PPA = 4 − (0.4 PD) |
|  | 10 ( PD ( 30 | PPA = 1 − (0.1 PD) |
|  | PD ( 30 | PPA = 40 − (1.4 PD) |
| Intermediate and Base | PD ( 30 | PPA = 1 − (0.1 PD) |
|  | PD ( 30 | PPA = 40 − (1.4 PD) |

Calculate the PPA for other pavement lots as specified in Table 401.03.03-4.

| Table 404.03.01-2 PPA for Other Pavement Lots |
| --- |
|  | Quality | PPA |
| All Courses | PD ( 50 | PPA = 1 − (0.1 PD) |
|  | PD ( 50 | PPA = 92 − (1.92 PD) |

5.	Outlier Detection.  If PD < 10, the ME will not screen for outliers. If PD ≥ 10, the ME will screen all acceptance cores for outliers using a statistically valid procedure. The following procedure applies only for a sample size of 5 or 10.

1.	The ME will arrange the core results in ascending order, in which X1 represents the smallest value and XN represents the largest value.

2.	If XN is suspected of being an outlier, the ME will calculate:

| R = | XN - X (N-1) |
| --- | --- |
|  | XN - X1 |

3.	If X1 is suspected of being an outlier, the ME will calculate:

| R = | X2 - X 1 |
| --- | --- |
|  | XN - X1 |

4.	For N=5 if R > 0.642, the value is judged to be statistically significant and the core is excluded. For N = 10 if R > 0.412, the value is judged to be statistically significant and the core is excluded.

If an outlier is detected and no retest is warranted, the Contractor may replace that core by taking an additional core at the same offset and within 5 feet of the original station. If an outlier is detected and a retest is justified, take a replacement core for the outlier at the same time as the 5 additional retest cores are taken. If the outlier replacement core is not taken within 15 days, the ME will use the initial core results to determine PPA

If an outlier is detected for N = 10, the Contractor may replace that core by taking an additional core at the same offset and within 5 feet of the original station. If the outlier replacement core is not taken within 15 days, the ME will use the initial core results to determine PPA.

6.	Retest.  If the initial series of 5 cores produces a percent defective value of PD ( 30 for mainline or ramp lots, or PD ( 50 for other pavement lots, the Contractor may elect to take an additional set of 5 cores at random locations chosen by the ME.  Take the additional cores within 15 days of receipt of the initial core results.  If the additional cores are not taken within the 15 days, the ME will use the initial core results to determine the PPA.  If the additional cores are taken, the ME will recalculate the PPA using the combined results from the 10 cores.

7.	Removal and Replacement.  If the final lot PD ( 75 (based on the combined set of 10 cores or 5 cores if the Contractor does not take additional cores), remove and replace the lot and all overlying work.  The replacement work is subject to the same requirements as the initial work.

For shoulder lots, instead of removal and replacement, the Department will assess the calculated PPA, and the Contractor shall perform a fog seal of the lot as specified in 422.03.01.

1**************************************************************************************************************************1

404.04  Measurement and Payment

THE FOLLOWING IS ADDED:

The Department will make a payment adjustment for HMA air void quality by the following formula:

Pay Adjustment = Q x  BP x PPA

Where:

BP = Bid Price

Q= Air Void Lot Quantity

PPA= air void PPA as specified in 401.03.03H.

The Department will make a payment adjustment for HMA thickness quality by the following formula:

Pay Adjustment = Q x  BP x PPA

Where:

BP = Bid Price

Q= Thickness Lot Quantity

PPA= thickness PPA as specified in 401.03.03I

The Department will make a payment adjustment for HMA ride quality, as specified in 401.03.03J

Section 405 – Concrete Surface Course

405.03.02  Concrete Surface Course

I.	Thickness Requirements.

This part is changed to:

I.	Thickness Requirements.  The ME will divide the concrete pavement into lots of approximately 5000 square yards.  The ME will divide each lot into 5 equal sections.  The RE will direct the Contractor to drill 1 core, as specified in 405.03.03, from a randomly selected location within each section.  The ME will test these cores for thickness as specified in ASTM C 174.

The Department will determine conformance with thickness requirements as follows and will either assess the greater of the pay reduction for average core thickness or individual core thickness, or the Department will direct the Contractor to remove and replace the lot:

1.	Average Core Thickness.  If the average core thickness is greater than or equal to the specified core thickness, the Department will not apply a payment reduction.  If the average thickness is less than the specified thickness, but is greater than or equal to the specified thickness minus 1/2 inch, the Department will determine payment reduction by the following formula:

Payment Reduction = Q x BP x PPR Where: Q = Thickness Lot Quantity BP = Bid Price TS = Specified Thickness. TA = Average Thickness PPR = Percent Payment Reduction =

2.	Individual Core Thickness.  When more than 2 individual cores in the lot are less than the specified thickness minus 1/4 inch, the Department will determine the payment reduction using for the above noted formula and using a PPR = 2 percent.

3.	Remove and Replace.  If the average thickness is less than the specified thickness minus 1/2 inch, the RE will require that the lot be removed and replaced.

405.04  Measurement and Payment

THE FOLLOWING IS ADDED:

The Department will make a payment adjustment for Concrete Surface thickness quality, as specified in 405.03.02.

The Department will make a payment adjustment for HMA ride quality, as specified in 401.03.03J

1**************************************************************************************************************************1

BDC11s-01 dated Mar 30, 2011

THE Following SECTION IS ADDED to division 400:

Section 406 – High Performance Thin Overlay (HPTO)

406.01  Description

This Section describes the requirements for constructing high performance thin overlay (HPTO).

406.02  Materials

406.02.01  Materials

Provide materials as specified:

Tack Coat:

Emulsified Asphalt, Grade RS-1, SS-1, SS-1h, Grade CSS-1 or CSS-1h	902.01.03

HPTO	902.08

406.02.02  Equipment

Provide equipment as specified:

Materials Transfer Vehicle (MTV)	1003.01

HMA Paver	1003.03

Ultra-Thin Paver	1003.04

HMA Compactor	1003.05

HMA Plant	1009.01

HMA Trucks	1009.02

406.03  Construction

406.03.01  High Performance Thin Overlay (HPTO)

A.	Paving Plan.  At least 20 days before the start of placing the HPTO, submit a detailed plan of operation to the RE for approval as specified in 401.03.03.A.

B.	Weather Limitations.  If within the 3 hours before paving the National Weather Service locally forecasts a 50 percent chance or greater of precipitation during the scheduled placement, postpone the placement of HPTO.  Do not place HPTO if it is precipitating and do not allow trucks to leave the plant when precipitation is imminent.  The Contractor may resume paving operations when the chance of precipitation is less than 50 percent and the surface is dry.

Do not pave if the surface temperature of the underlying pavement is below 50 °F.

C.	Test Strip.  At least 14 days prior to production of the HPTO, construct a test strip as specified in 401.03.03.C except for the allowance to continue paving.  Submit test strip results to the RE.  The RE will analyze the test strip results in conjunction with the ME’s results from the HMA plant to approve the test strip.  Do not proceed with production paving until receiving written permission from the RE.

If paving HPTO only on a bridge deck, then the test strip is not required.

D.	Transportation and Delivery of HMA.  Transport and deliver HMA as specified in 401.03.03.D.

E.	Spreading and Grading.  Do not start paving of the HPTO until the RE has approved the underlying surface.  Apply tack coat as specified in 401.03.02.  Place HPTO at the laydown temperature recommended by the supplier of the asphalt binder or the supplier of the asphalt modifier without exceeding 330 ºF maximum discharge temperature.  Spread and grade HPTO as specified in 401.03.03.E.

F.	Compacting.  Compact as specified in 401.03.03.F.  If vibratory compaction causes aggregate breakdown, forces liquid asphalt to the surface or creates a surface with undesirable ride quality, then operate rollers in static mode only. If compacting HPTO on a bridge deck, then operate rollers in static mode only.

G.	Opening to Traffic.  Remove loose material from the traveled way before opening to traffic.  Do not allow construction equipment or traffic on the HPTO until the mat cools to a temperature of less than 140 °F.

H.	Air Void Requirements on Roadway.

2**************************************************************************************2

BDC15s-07 dated JUN 30, 2015

The entire part is changed to:

Drill cores as specified in 401.03.05. Mainline lots are defined as the area covered by a day’s paving production of the same job mix formula for the traveled way and auxiliary lanes.  The RE may combine daily production areas less than 500 tons with previous or subsequent production areas.  If a day’s production is greater than 2000 tons, the RE may divide the area of HMA placed into 2 lots with approximately equal areas.

Ramp pavement lots are defined as approximately 10,000 square yards of pavement in ramps.  The RE may combine ramps with less than the minimum area into a single lot.  If 2 or more ramps are included in a single lot, the RE will require additional cores to ensure that at least 1 core is taken from each ramp.

Other pavement lots are defined as approximately 10,000 square yards of pavement in shoulders and other undefined areas.

The ME will calculate the percent defective (PD) as the percentage of the lot outside the acceptable range of 1 percent air voids to 7 percent air voids.  The acceptable quality limit is 10 percent defective.  For lots in which PD<10, the Department will award a positive pay adjustment.  For lots in which PD > 10, the Department will assess a negative pay adjustment.

The ME will determine air voids from 5 cores taken from each lot in random locations.  The ME will determine air voids of cores from the values for the maximum specific gravity of the mix and the bulk specific gravity of the core.  The ME will determine the maximum specific gravity of the mix according to NJDOT B-3 and AASHTO T 209, except that minimum sample size may be waived in order to use a 6-inch diameter core sample.  The ME will determine the bulk specific gravity of the compacted mixture by testing each core according to AASHTO T 166.

The ME will calculate pay adjustments based on the following:

1.	Sample Mean () and Standard Deviation (S) of the N Test Results (X1, X2,..., XN).

2.	Quality Index (Q).

3.	Percent Defective (PD).  Using NJDOT ST for the appropriate sample size, the Department will determine PDL and PDU associated with QL and QU, respectively.  PD = PDL + PDU

4.	Percent Pay Adjustment (PPA).  Calculate the PPA for traveled way and ramp lots as specified in Table 401.03.03-3.

| Table 406.03.01-1 PPA for Mainline Lots and Ramp Lots |
| --- |
|  | Quality | PPA |
| Surface | PD ( 10 | PPA = 4 − (0.4 PD) |
|  | 10 ( PD ( 30 | PPA = 1 − (0.1 PD) |
|  | PD ( 30 | PPA = 40 − (1.4 PD) |
| Intermediate and Base | PD ( 30 | PPA = 1 − (0.1 PD) |
|  | PD ( 30 | PPA = 40 − (1.4 PD) |

Calculate the PPA for other pavement lots as specified in Table 401.03.03-4.

| Table 406.03.01-2 PPA for Other Pavement Lots |
| --- |
|  | Quality | PPA |
| All Courses | PD ( 50 | PPA = 1 − (0.1 PD) |
|  | PD ( 50 | PPA = 92 − (1.92 PD) |

5.	Outlier Detection.  If PD < 10, the ME will not screen for outliers. If PD ≥ 10, the ME will screen all acceptance cores for outliers using a statistically valid procedure. The following procedure applies only for a sample size of 5 or 10.

1.	The ME will arrange the core results in ascending order, in which X1 represents the smallest value and XN represents the largest value.

2.	If XN is suspected of being an outlier, the ME will calculate:

| R = | XN - X (N-1) |
| --- | --- |
|  | XN - X1 |

3.	If X1 is suspected of being an outlier, the ME will calculate:

| R = | X2 - X 1 |
| --- | --- |
|  | XN - X1 |

4.	For N = 5 if R > 0.642, the value is judged to be statistically significant and the core is excluded. For N = 10 if R > 0.412, the value is judged to be statistically significant and the core is excluded.

If an outlier is detected and no retest is warranted, the Contractor may replace that core by taking an additional core at the same offset and within 5 feet of the original station. If an outlier is detected and a retest is justified, take a replacement core for the outlier at the same time as the 5 additional retest cores are taken. If the outlier replacement core is not taken within 15 days, the ME will use the initial core results to determine PPA.

If an outlier is detected for N = 10, the Contractor may replace that core by taking an additional core at the same offset and within 5 feet of the original station. If the outlier replacement core is not taken within 15 days, the ME will use the initial core results to determine PPA.

6.	Retest.  If the initial series of 5 cores produces a percent defective value of PD ( 30 for mainline or ramp lots, or PD ( 50 for other pavement lots, the Contractor may elect to take an additional set of 5 cores at random locations chosen by the ME.  Take the additional cores within 15 days of receipt of the initial core results.  If the additional cores are not taken within the 15 days, the ME will use the initial core results to determine the PPA.  If the additional cores are taken, the ME will recalculate the PPA using the combined results from the 10 cores.

7.	Removal and Replacement.  If the final lot PD ( 75 (based on the combined set of 10 cores or 5 cores if the Contractor does not take additional cores), remove and replace the lot and all overlying work.  The replacement work is subject to the same requirements as the initial work.

For shoulder lots, instead of removal and replacement, the Department will assess the calculated PPA, and the Contractor shall perform a fog seal of the lot as specified in 422.03.01.

2**************************************************************************************2

I.	Air Void Requirements on Bridge Deck.  The RE may waive the coring of HPTO constructed on a bridge deck or may require that the Contractor to test bridge decks with the thin lift nuclear density gauge.  If required by RE, perform nuclear density gauge testing according to ASTM D 2950 at 5 random locations per bridge deck.  Use the maximum specific gravity determined at the HMA plant according to AASHTO T 209 to determine percent air voids.  If the average air voids for the bridge deck are 8 percent or greater, the RE will require a revised paving plan for any subsequent bridge deck placement of HPTO and may require the HPTO to be removed and replaced.

J.	Ride Quality Requirements.  The Department will evaluate the HPTO as specified in 401.03.03.J.

406.04  Measurement and Payment

The Department will measure and make payment for Items as follows:

Item	Pay Unit

high performance thin overlay	TON

The Department will measure high performance thin overlay by the ton as indicated on the certified weigh tickets, excluding unused material.

The Department will make payment for Tack Coat as specified in 401.04.

The Department will make payment for Core Samples, Hot Mix Asphalt as specified in 401.04.

1**************************************************************************************************************************1

THE FOLLOWING DIVISION IS ADDED:

1**************************************************************************************************************************1

BDC15s-01 dated mar 26, 2015

division 420 – Pavement preservation treatments

1**************************************************************************************************************************1

THE FOLLOWING Section IS ADDED:

1**************************************************************************************************************************1

BDC15s-01 dated mar 26, 2015

Section 421 – Micro surfacing and Slurry Seal

421.01  Description

This section describes the requirements for micropaving joints, micro surfacing and slurry seal.

421.02  Materials

421.02.01  Materials

Provide materials as specified:

Tack Coat:

Emulsified Asphalt, Grade SS-1, SS-1h, Grade CSS-1, CSS-1h	902.01.03

Micro Surfacing	902.09

Slurry Seal	902.10

421.02.02  Equipment

Provide equipment as specified:

Bituminous Material Distributor	1003.07

Pneumatic-Tired Compactor	1002.01

Mechanical Sweeper	1008.03

Micro Surfacing and Slurry Seal Paver	1012.01

Provide hand squeegees, shovels, and other equipment necessary to perform the work. Provide cleaning equipment such as power brooms, air compressors, water flushing equipment, and hand brooms adequate for surface preparation.

421.03  Construction

421.03.01 Micro Surfacing Rut Filling.

Fill ruts in the wheel paths and restore the designed profile of the pavement cross section as shown on the Plans and as directed by the RE.  Fill ruts which are 1/2” or less with a single full lane micro surfacing operation. Fill ruts which are greater than 1/2” in depth with a separate rut filling operation.  Fill ruts which are greater than 1 1/2” in depth with multiple applications utilizing a rut filling equipment.  Do not over fill rut areas.  Cure rut filling and level-up material for at least twenty-four (24) hours before additional material is placed.

421.03.02 Micropaving Joints.

Clean the joint, removing unsound patches and loose material. Use micro surfacing Type II as specified in 902.09 and rut filling equipment modified to provide a 2 feet wide application of material to fill in open longitudinal joints and rumble strips as shown on the plans and as directed by the RE.  For joint filling greater than 2” in depth perform multiple applications to even out settlement of the material after curing.  Avoid excess crowning and over filling of joints and rumble strips.  Cure each pass of material under traffic for at least twenty-four (24) hours before additional material is placed.

421.03.03 Micro Surfacing

- Micro Surfacing Plan.  At least 20 days before beginning placement of material, submit a detailed plan of operation to the RE for approval that includes the following:

- Paving contractor’s superintendent qualifications with a list of at least 5 successful projects, including project owner contact information.

- Size and description of crew.

- Number, type, model of equipment and material control/metering devices along with the current calibration documentation.

- Lighting plan for nighttime operations as specified in 108.06 for milling and paving.

- Method of locating, protecting and maintaining manholes, inlets, other utilities and RPM’s.

- Paving procedures for maintaining continuous operation as specified.

- Paving sequence.  Indicate that the surface is to be constructed for the full lane width as a single paving operation.

- Schedule, hours of operation, and production rates for the Project.

- Plant and stockpile locations for aggregate, emulsion, mineral filler and additives.

- Method of maintaining modified emulsion temperature during transportation.

- Method of constructing joints.

- Quality control plan outlining the material testing, number and frequency planned in order to ensure compliance.

- Mix design of the mixture, the AASHTO accredited laboratory used and the test results of the mixture.

Do not begin paving until the RE approves this plan.  Submit an adjusted plan before making adjustments to the paving operation.

- Weather Limitations.  Do not place material if the surface temperature of the underlying pavement is below 50 °F or if the National Weather Service is forecasting temperatures below 50 °F during installation or within 3 hours after installation.

Do not place material if the existing surface is wet. Do not place material if it is precipitating and when precipitation is imminent. If within the 3 hours of placement, the National Weather Service locally forecasts a 50 percent chance, or greater, of precipitation during the scheduled placement, then postpone the placement of material.    The Contractor may resume operations when the chance of precipitation is less than 50 percent, and the surface is dry.

- Test Strip.  Construct a test strip of at least 500 feet in length on the roadway before initial placement commences.  Ensure that the tack coat has been placed as specified in 401.03.02.  Ensure the test strip is performed during weather and sunlight conditions which represents project production placement of the material.  While constructing the test strip, record the following information and submit to the RE:

- Ambient Temperature. Measure the ambient temperature at the beginning and end of each day’s operation.

- Base Temperature.  Measure the surface temperature of the existing pavement at the beginning and end of each day’s operation.

- Weather Conditions.  Document the wind speed, weather conditions, time of day, and humidity at the time of placement.

- Tack Coat.  Measure to verify the proper application rate, coverage and temperature of tack coat for compliance.

- Material Quantities.  Measure to verify the proper proportions of emulsion, cement, aggregate, additives (if any) and temperature of the mixture during placement.  Measure to verify the proper application rate of the mixture for compliance.

- Roller Pattern.  Provide details on the number of rollers, type, and number of passes used on the test strip.

- Initial Set Time.  Record the initial time of placement.  Verify that the mixture has achieved initial set within 30 minutes of placement.

- Performance Under Traffic.  Verify that the surface shows no visual signs of distress when exposed to traffic after curing for 1 hour.

Submit test strip results to the RE.  The RE will analyze the test strip results in conjunction with the approved mix design to approve the test strip.  Do not proceed with production placement until receiving written permission from the RE.

If the test strip does not meet requirements, make adjustments and construct a second test strip.  If the second test strip does not meet requirements, suspend operations until written approval to proceed is received from the RE.

Before making adjustments to the operations, notify the RE in writing.  The RE may require a new test strip to verify the performance of the adjusted operations.

- Surface Preparation.  Ensure repairs are completed prior to beginning installation. Ensure rut filling and micropave joints have cured for at least 24 hours prior to applying material.

Ensure that manholes, inlets, utilities, curbs, RPM’s, structures, rumble strips, traffic striping and traffic markings to remain are protected by methods approved by the RE.  Do not proceed with placement until the RE approves the prepared surface.

Clean the surface of the pavement to remove all dust, debris, oil, and any other materials that may prevent bonding of the treatment to the existing surface. Ensure that the surface is clean and dry.

Apply tack coat prior to application of the treatment as specified in 401.03.02.

- Micro Surfacing Application.  Apply the mixture over the full lane width as specified in table 421.03.03-1.

| Table 421.03.03-1 Job Mix Types and Application |
| --- |
| Aggregate Type (See Table 902.09.03-1) | Location | Application Rate (lbs./yd2) |
| Type II | Surface Course | 16 – 22 |
|  | Intermediate Course | 10 – 20 |
| Type III | Rut filling | 20 – 40 (See ISSA1 A143) |
| 1. International Slurry Seal Association (ISSA) |

Operate equipment to prevent the loss of the mixture on super-elevated curves.  Spread the mixture to fill cracks and minor surface irregularities and leave a uniform high-skid resistant application of aggregate and asphalt on the surface.  Operate spreader box so a uniform consistency is achieved without causing skips, lumps or tears in the finished surface.

Carry a sufficient amount of material, at all times, in all parts of the spreader box, so complete coverage is obtained.  Water may be sprayed into spreader box to facilitate spreading without harming the mix.  No lumping, balling or unmixed aggregate is permitted in the finished surface.

Adjustments to the additive may be required for slow setting where hand spreading is needed.  Use squeegees and lutes to spread the mixture in areas inaccessible to the spreader box and areas requiring hand spreading.  When hand spreading, pour the mixture in a small windrow along one edge of the surface to be covered and then spread uniformly by a hand squeegee or lute.  Make a neat appearing seam where two passes join. Ensure transverse joints of micro surfacing are made straight, clean, and perpendicular to the direction of travel.  The maximum overlap of longitudinal lane line joints is 3 inches. Ensure micro surfacing longitudinal joints are parallel to, and not offset by more than 3 inches maximum from, the final traffic striping. Immediately remove excess material from ends of each run.

Do not leave streaks in the finished surface.  If streaking develops, stop the operation and submit a corrective action plan to the RE.  Do not resume operations until the RE approves the plan.

- Compaction.  Do not roll until the material has cured sufficiently to avoid damage by the roller.  Use a pneumatic-tired compactor as specified in 1002.01, except ensure the roller is equipped with a water-spray system.  Roll the material with a minimum of at least 2 passes of the pneumatic-tired compactor.  The RE may direct additional passes to eliminate roller marks or facilitate compaction of rut filled areas.

- Opening to Traffic.  Allow the material sufficient curing time before opening to traffic.  Remove loose material from the traveled way before opening to traffic. If the material becomes damaged replace the damaged area.

- Applying Striping and Traffic Markings.  Allow material to cure for at least 2 weeks before applying permanent traffic striping and traffic markings. Use temporary traffic striping and markings as directed by the RE until the material has cured.

- Surface Quality Requirements.  Ensure that there is no excess buildup, uncovered areas, or rough areas on the pavement surface including the longitudinal and transverse joints.  The RE will visually inspect the pavement for approval.  The RE may reject areas of pavement that are unsatisfactory based on visual inspection. Correct areas of the pavement that the RE rejects. Visual inspection by the RE is considered sufficient grounds for such rejection.

The RE may use a 10 foot straightedge to verify transverse profiles of finished surfaces.  Correct areas that have more than 1/4 inch deviation between any 2 contact points of the straightedge in a manner approved by the RE.  Following correction, retest the area to verify conformance with this requirement.

- Ride Quality Requirements.  The Department will evaluate the final surface placed in the traveled way as specified in 401.03.03.J.

421.03.04  Slurry Seal

- Slurry Seal Plan.  At least 20 days before beginning placement of slurry seal, submit a detailed plan of operation to the RE for approval as specified in 421.03.03.A

- Weather Limitations.  Place slurry seal in weather as specified in 421.03.03.B.

- Test Strip.  Construct a test strip as specified in 421.03.03.C.

- Surface Preparation.  Prior to starting slurry seal, prepare the existing surface as specified in 421.03.03.D.

- Slurry Seal Application.  Apply the slurry seal mixture as specified in 421.03.03.E, except that application rate should be as specified in table 421.03.04-1.

| Table 421.03.04-1 Job Mix Types and Application |
| --- |
| Aggregate Type (See Table 902.10.03-1) | Location | Application Rate (lbs./yd2) |
| Type I | Surface Course Intermediate Course | 10 - 14 |
| Type II | Surface Course Intermediate Course | 16 – 20 |
| 1. International Slurry Seal Association (ISSA) |

- Compaction.  Roll slurry seal as specified in 421.03.03.F.

- Opening to Traffic.  Open to traffic as specified in 421.03.03.G.

- Applying Striping and Traffic Markings.  Apply traffic striping and traffic markings as specified in 421.03.03.H.

- Surface Quality Requirements.  The Department will evaluate the surface quality of slurry seal as specified in 421.03.03.I.

- Ride Quality Requirements.  The Department will evaluate the final surface placed in the traveled way as specified in 401.03.03.J.

421.04  measurement and payment

The Department will measure and make payment for Items as follows:

Item	Pay Unit

Micro surfacing aggregate, type II 	Ton

Micro surfacing aggregate, type III	ton

Micro surfacing aggregate, type III Rut-filling	ton

Micro surfacing emulsion	gallon

Slurry Seal aggregate, type I 	Ton

Slurry Seal aggregate, type II 	Ton

Slurry Seal emulsion	gallon

Micropaving joints	Linear Foot

The Department will make payment for tack coat as specified in 401.04.

The Department will make payment for REMOVAL OF TRAFFIC STRIPES, REMOVAL OF TRAFFIC MARKINGS, TRAFFIC STRIPES, and TRAFFIC MARKINGS as specified in 610.04.

The Department will measure Micro surfacing emulsion and Slurry Seal emulsion by the volume delivered, converted to the number of gallons at 60 °F as calculated by the temperature-volume correction factors specified in 902.01, with the exception that micro surfacing emulsion required for Micropaving joints is included in the price per linear foot.

The Department will measure Micro surfacing aggregate type II, Micro surfacing aggregate type III, Micro surfacing aggregate type III rut-filling, SLURRY SEAL AGGREGATE TYPE I, and Slurry Seal aggregate type II by the ton as indicated on the certified weigh tickets, excluding unused material.

1**************************************************************************************************************************1

THE FOLLOWING Section IS ADDED:

1**************************************************************************************************************************1

BDC15s-01 dated mar 26, 2015

Section 422–Fog seal

422.01 DESCRIPTION

This section describes the requirements for furnishing and applying a fog seal surface treatment with a fine aggregate cover. This section also describes the requirements for applying a fog seal strip over centerline rumble strips (CLRS) and HMA longitudinal cold joints.

422.02 MATERIALS

422.02.01  Materials

Provide materials as specified:

Fine Aggregate for Fog Seal	901.07.02

1	Asphalt Emulsion.  For fog seal surface treatment, fog seal of centerline rumble strips and HMA longitudinal cold joint provide emulsified asphalt of grades SS-1, SS-1h, RS-1 or RS-2 in accordance with AASHTO M 140; or provide cationic emulsified asphalt of grades CSS-1, CSS-1h, CRS-1, or CRS-2 in accordance with AASHTO M 208; and ensure all emulsified asphalts are provided as specified in 902.01.03.

2	Polymerized Maltene Emulsion.  As an alternative for asphalt emulsion specified above for fog seal strip of centerline rumble strips and HMA longitudinal cold joints, provide JOINTBOND® emulsion. JOINTBOND® is proprietary to Pavement Technology, Inc. of Westlake, OH, telephone number (800)333-6309.  For new pavements, use JOINTBOND®.  For pavements that are more than 12 months old, use JOINTBOND® PM.

Slow setting emulsified asphalts may be diluted 1 part emulsion to 1 part water. All dilution must be done at the place of manufacture.

Other emulsified asphalt designed specifically for fog sealing may be used if approved by the Bureau of Materials. Determine the application rate by the amount of residual asphalt required as specified in 422.03.01.E.

422.02.02  Equipment

Provide equipment as specified:

Bituminous Material Distributor	1003.07

Mechanical Sweeper	1008.03

Mechanical Fine Aggregate Spreader	1012.02

422.03 CONSTRUCTION

422.03.01 Fog Seal Surface Treatment

- Fog Sealing Plan. At least 20 days before beginning placement of fog sealing, submit a detailed plan of operation to the RE for approval that includes the following:

- Fog sealing contractor’s superintendent’s qualifications with a list of at least 5 successful projects, including project owner contact information.

- Size and description of crew.

- Number, type, model of equipment and material control/metering devices along with the current calibration documentation.

- Fog seal material type, dilution amount, manufacturer, MSDS, handling and installation guidelines, weather limitations and Quality Control plan.

- Lighting plan for nighttime operations as specified in 108.06 for paving.

- Schedule, hours of operation, and production rates for the Project.

- Plant or storage locations for fog sealing emulsion, sand and additives.

- Method of maintaining fog-sealing emulsion temperature during transportation and operation.

- Quality control plan outlining the material testing, number and frequency planned in order to ensure compliance.

- Method of protecting manholes, valve boxes, drop inlets and other service entrances are protected from the fog sealing.

- Method of protecting RPMs from fog sealing

Do not begin fog sealing until the RE approves the plan.  Submit an adjusted fog sealing plan to the RE for approval before making adjustments to the fog sealing operation.

- Weather Limitations. If within the 3 hours of fog sealing, the National Weather Service locally forecasts a 40 percent chance or greater of precipitation during the scheduled placement, postpone the placement of fog seal.  Do not fog seal if it is precipitating or when precipitation is imminent.  The Contractor may resume fog sealing operations when the chance of precipitation is less than 40 percent, and the surface is dry.

Do not place fog sealing if the surface temperature of the underlying pavement is below 50 °F.

- Test Strip.  Construct a test strip of at least 100 feet in length on the roadway before initial placement commences.  Ensure the test strip is performed during weather and sunlight conditions which will represent project production placement of the fog sealing mixture.  While constructing the test strip, record the following information and submit to the RE:

- Ambient Temperature. Measure the ambient temperature at the beginning and end of the fog sealing operation.

- Base Temperature.  Measure the surface temperature of the existing pavement at the beginning and end of the fog sealing operation.

- Weather Conditions. Document the wind speed, weather conditions, time of day, and humidity at the time of placement.

- Emulsion Temperature.  Measure the temperature of the emulsion in the distributor truck.  Ensure that the emulsion is heated to the optimum application temperature as per the manufacturer prior to starting.

- Application Rate Verification.  With the RE present, check the application rate setting in the bituminous material distributor. With the RE present, verify the temperature of the fog sealing mixture during placement. With the RE present, verify application rate calibration using ASTM test method D2995 except that the tiles should be 3 feet by 3 feet in dimension.  After the emulsion has completely cured, weigh the tiles again to verify asphalt residual.

- Set Time. Record the initial time of placement. Notify the RE when the material has completely set and is ready to be opened to traffic.

- Performance Under Traffic.  Do not allow traffic on the fog seal until it has completely cured. Verify that the fog sealing shows no visual signs of distress when exposed to traffic.

Upon completion of the test strip, submit test strip documentation to the RE. The RE will review the test strip documentation and visually assess the coverage of the fog seal application. Do not proceed with production fog sealing until receiving approval from the RE.

Before making adjustments to the fog sealing operations, notify the RE in writing.  The RE may require a new test strip to verify the performance of the adjusted fog sealing operations.

- Surface Preparation. Ensure all repairs and rumble strips are completed prior to beginning fog seal installation. Clean the surface of existing pavement to remove all dust debris, oil and any other materials that may prevent bonding of the fog seal. Ensure that the surface is clean and dry.  Remove traffic stripes and traffic markings as specified in 610.03.08.

Ensure that manholes, inlets, utilities, curbs, RPM’s, structures, traffic striping, and traffic markings to remain are protected from the fog seal by methods approved by the RE.  Do not proceed with placement of the fog seal until the RE approves the prepared surface.

- Fog Sealing Application.  Ensure that the temperature of the emulsion prior to starting is at the application temperature recommended by the manufacturer but not exceeding 160 °F. Apply the fog seal uniformly at the rate determined during the test strip to provide a residual asphalt of between 0.06 to 0.10 gallons per square yard using a bituminous distributer.

Ensure that the fog seal material completely covers the pavement surface and is not streaked or ribboned. Ensure that the distribution is even with no uncoated areas or puddles of excess emulsion.  Correct uncoated or lightly coated areas by applying additional fog seal emulsion. Blot areas showing an excess of fog seal with sand approved by the RE. Remove excess sand and emulsion material. In areas inaccessible to distributor spray bars, use hand spraying equipment.

The RE may reject areas where fog seal has been applied that is uncoated, ribboned, streaked or has excess emulsion material and rendered unsatisfactory. Visual inspection by the RE is considered sufficient grounds for such rejection.

- Fine Aggregate Application.  Immediately after the fog seal has been applied, apply fine aggregate at a rate of 0.25 to 0.5 pounds per square yard. Ensure sand is applied uniformly over the area where fog seal has been applied. Remove excess material by sweeping prior to opening to traffic.

The RE may reject areas where fine aggregate has been applied that is not sufficiently covered or has excess fine aggregate material and rendered unsatisfactory. Visual inspection by the RE is considered sufficient grounds for such rejection.

- Opening to Traffic.  Allow the material sufficient curing time, as recommended by the manufacturer, before opening to traffic. Sweep to remove loose and excess aggregate by methods approved by and to the satisfaction of the RE before opening to traffic.

- Applying Striping and Traffic Markings.  Allow fog seal to cure for at least 2 weeks before applying permanent traffic striping and traffic markings. Use temporary traffic striping and markings as directed by the RE until the fog seal has cured.

- Surface Quality Requirements.  Ensure that there is no excess buildup, uncovered areas, or rough areas on the fog seal.  The RE will visually inspect the fog seal for approval.  The RE may reject areas of fog seal that are unsatisfactory based on visual inspection. Areas where fog seal has been applied that do not have sufficient aggregate cover or have excess aggregate material may be rendered unsatisfactory. Correct areas of the fog seal that the RE rejects. Visual inspection by the RE is considered sufficient grounds for such rejection.

422.03.02 Fog Seal Strip

- Fog Sealing Plan. At least 20 days before beginning placement of fog sealing, submit a detailed plan of operation to the RE for approval as specified in 422.03.01.A.

- Weather Limitations. Fog seal in weather as specified in 422.03.01.B.

- Test Strip.  Construct a test strip of at least 100 feet in length on the roadway before initial placement commences as specified in 422.03.01.C, except that the tiles as specified in 422.03.01.C.5 should be 2 feet by 2 feet in dimension.

- Surface Preparation.  Prepare the existing surface as specified in 422.03.01.D. When using polymerized maltene emulsion, the Contractor may leave the existing traffic stripes and traffic markings in place and may install new traffic stripes and markings as specified in 610.03 prior to fog seal.

- Fog Sealing Application.  Ensure that the temperature of the asphalt emulsion prior to starting is at the application temperature recommended by the manufacturer but not exceeding 160 °F. If using asphalt emulsion, apply the fog seal uniformly at the rate determined during the test strip to provide a residual asphalt of between 0.06 to 0.10 gallons per square yard using a bituminous distributer. If using polymerized maltene emulsion, apply according to manufacturer’s recommendations.

Apply fog seal in a 2 feet wide strip centered over the center line rumble strip or HMA longitudinal cold joint, ensuring complete coverage of the rumble strip or HMA longitudinal cold joint. Ensure that the fog seal material completely covers the pavement surface and is not streaked or ribboned. Ensure that the distribution is even with no uncoated areas or puddles of excess emulsion.  Correct uncoated or lightly coated areas by applying additional fog seal emulsion. Blot areas showing an excess of fog seal with sand approved by the RE. Remove excess sand and emulsion material. In areas inaccessible to distributor spray bars, use hand spraying equipment.

The RE may reject areas where fog seal has been applied that is uncoated, ribboned, streaked or has excess emulsion material and rendered unsatisfactory. Visual inspection by the RE is considered sufficient grounds for such rejection.

- Applying Striping and Traffic Markings.  If using asphalt emulsion, place striping as specified in 159.03.06 prior to opening to traffic. If permanent striping was not applied prior to fog sealing, allow fog seal to cure for at least 2 weeks before applying permanent traffic striping and traffic markings.

- Opening to Traffic.  Open to traffic as specified in 422.03.01.G.

- Surface Quality Requirements.  Ensure fog seal strip meets the requirements specified in 422.03.01.I.

422.04 MEASUREMENT and payment

The Department will measure and make payment for Items as follows:

Item	Pay Unit

fog seal SURFACE TREATMENT	gallon

fOG SEAL Strip	lINEAR FOOT

The Department will make payment for REMOVAL OF TRAFFIC STRIPES and REMOVAL OF TRAFFIC MARKINGS as specified in 610.04.

The Department will make payment for TRAFFIC STRIPES, ___” as specified in 610.04.

The Department will measure fog seal SURFACE TREATMENT by volume of residual asphalt by converting the quantity of emulsion to the number of gallons at 60 °F as calculated by the temperature-volume correction factors specified in 902.01 and then multiplying by the % residual asphalt in the emulsion from the certificate of compliance from the manufacturer.

1**************************************************************************************************************************1

Division 450 – Concrete Pavement Rehabilitation

Section 453 – Full Depth Concrete Pavement Repair

453.03.01  Full Depth Repair Using Concrete

A.	Preparation.

1**************************************************************************************************************************1

BDC14s-13 dated JAN 26, 2015

THE FOLLOWING IS ADDED as the first paragraph:

Arrange a meeting with the RE at the project site to establish the limits of repair.  Additional repairs, not delineated by the RE during the project site meeting with the Contractor, may be required if the need for them is established by the RE.

1**************************************************************************************************************************1

C.	Setting Forms, Joint Ties, and Dowels.

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

THE third SENTENCE OF THE seventh PARAGRAPH IS CHANGED TO:

Slowly withdraw the tube as the hole is filled.

1**************************************************************************************************************************1

453.03.02 Full Depth Repair Using HMA

A.	Preparation.

1**************************************************************************************************************************1

BDC14s-13 dated JAN 26, 2015

the entire text is changed to:

Arrange a meeting with the RE at the project site to establish the limits of repair.  Additional repairs, not delineated by the RE during the project site meeting with the Contractor, may be required if the need for them is established by the RE.

If milling and paving is also specified within the areas requiring full depth repair, then perform the repair work first and as a separate operation from the milling and paving.  Ensure that the top of the repaired concrete surface is flush with the existing unrepaired pavement.  The Contractor may request approval of the RE to perform the repair work, milling and paving as one operation.

Sawcut full depth at the limits of the repair. Remove existing concrete or composite pavement using the lift out method. Do not use in-place breaking to remove concrete. Ensure that spalling of the remaining concrete does not occur during the lifting. Reuse removed pavement as specified in 202.03.07.A. The Contractor may sawcut the slab and drill the lift out holes up to 5 days before the concrete removal. Only remove concrete that can be replaced during the workday. Repair any damage to remaining pavements.

After the existing concrete has been removed, the RE will examine underlying material to determine its condition. If water or excess moisture exists in the area, remove the underlying material to the depth specified by the RE. Place and compact coarse aggregate using the directed method as specified in 203.03.02.C. Grade the underlying surface so that the thickness of the repair matches the existing slab thickness.

1**************************************************************************************************************************1

B.	Weather Limitations.

1**************************************************************************************************************************1

BDC14s-13 dated JAN 26, 2015

The heading and the entire text is changed to:

B.	Placing Limitations. Comply with the limitations as specified in 453.03.01.B.

1**************************************************************************************************************************1

Division 500 – Bridges and Structures

Section 502 – Load Bearing Piles

502.03.03  Driving Piles

B.	Methods of Driving.

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

The following is added to the last paragraph:

4.	Cast-In-Place Piles.  Ensure that reinforcement steel is installed as specified in 504.03.01.  Place concrete as specified in 504.03.02.  Clean out open end piles to the elevation shown on Plans.  Weld closure plates for closed-end pipe piles as shown on Plans.

1**************************************************************************************************************************1

C.	Test Piles.

1.	Static Pile Load Test.

1**************************************************************************************************************************1

complete and include static test load to be applied

sme contact – geotechnical engineering

Apply a total of _____ tons of static test load to the piles.

1**************************************************************************************************************************1

2.	Dynamic Pile Load Tests.

1**************************************************************************************************************************1

Specify if restrike is required

sme contact – geotechnical engineering

1**************************************************************************************************************************1

Section 503 – Drilled Shaft Foundations

1**************************************************************************************************************************1

BDC15s-13 dated SEP 22, 2016

THE ENTIRE SECTION IS CHANGED TO:

Section 503 – Drilled Shaft Foundations

503.01  Description

This Section describes the requirements for installing and testing drilled shafts.

503.02  Materials

503.02.01  Materials

Provide materials as specified:

Concrete	903.03

Self Consolidating Concrete (SCC)	903.06.01

Grout.	903.08.02

Reinforcement Steel	905.01.01

Drilled Shaft Casing	906.03

Steel Tube......................................................................................................................................................906.08

Structural Steel Paint (Organic Zinc)	912.01.01

Water	919.08

Provide clay-mineral based slurry (processed attapulgite or bentonite) for mineral slurry.  Ensure that the mineral slurry has a mineral grain size that will remain in suspension and has sufficient viscosity and gel characteristics to transport excavated material to a suitable screening system.  Ensure that the percentage and specific gravity of the material used to make the mineral suspension is sufficient to maintain the stability of the excavation and to allow proper concrete placement.

Provide polymer slurry as recommended by the manufacturer.

Perform control tests on the mineral slurry in the presence of the RE to determine density, viscosity, and pH.  Adjust the slurry to meet the requirements shown in Table 503.02.01-1:

| Table 503.02.01-1 – Mineral Slurry3 |
| --- |
| Property | Range | Test |
| Density at time of slurry introduction | 64.3 – 69.11 lbs/ft3 | API 13B, Bentonite Slurry Section (Mud Balance) ASTM D 4380 |
| Density in hole at time of concreting | 64.3 – 75.01 lbs/ft3 | API 13B, Bentonite Slurry Section (Mud Balance) ASTM D 4380 |
| Viscosity at time of slurry introduction | 28 – 452 sec/quart | API 13B, Section 2 (Marsh Funnel and Cup) |
| Viscosity in hole at time of concreting | 28 – 452 sec/quart | API 13B, Section 2 (Marsh Funnel and Cup) |
| Sand content by volume | 4% max | API 13B, Section 4 (Sand Screen Set) ASTM D 4381 |
| pH at time of slurry introduction | 8 – 11 | API 13B, Section 6 (Paper Test Strips or Glass-Electrode pH Meter) |
| pH in hole at time of concreting | 8 – 11 | API 13B, Section 6 (Paper Test Strips or Glass-Electrode pH Meter) |
| 1. Increase by 2 lbs/ft3 in salt water. 2. Standard measurements are in seconds per quart. One sec/quart = 1.06 sec/liter. a. Perform tests when the slurry temperature is above 40 °F. b. Ensure that the sand content does not exceed 4 percent (by volume) at any point in the borehole as determined by the API sand content test when the slurry is introduced. 3. Perform tests to determine density, viscosity and pH value during the shaft excavation to establish a consistent working pattern. Perform a minimum of 4 sets of tests during the first 8 hours of slurry use. When the results show consistent behavior, the Contractor may decrease the testing frequency to 1 set per every 4 hours of slurry use. |

503.02.02  Equipment

Provide equipment as specified:

Concrete Batching Plant	1010.01

Concrete Trucks	1010.02

Provide Crosshole Sonic Logging (CSL) test equipment as per ASTM D6760.

503.03  Construction

503.03.01 Furnishing Drilled Shaft Equipment

Ensure that equipment does not introduce uncontrolled exhaust fumes into the surrounding areas, or other occupied areas adjacent to the work site.  Use crane and drilling equipment that is fitted with their own separate exhaust systems to adequately vent engine exhaust fumes to the atmosphere away from all confined work sites.

Ensure that equipment used for final bottom cleaning does not have a centralizing guide at the tip.

Use excavation and drilling equipment having adequate capacity, including power, torque, and down thrust to excavate a hole of both the maximum specified diameter and equal to the deepest shaft shown in the Plans, plus 15 feet or three times the shaft diameter, whichever is greater.

503.03.02  Demonstration Drilled Shaft

A.	Installation Plan.  No later than 30 days after the date of the Notice to Proceed, submit to the RE for approval an installation plan that includes the following:

1.	A summary of the Contractor’s or specialized drilled shaft subcontractor’s experience and qualifications.  The Contractor or subcontractor must have a minimum of 5 years experience in installation of drilled shaft foundations.  The Contractor performing the work described herein must have installed shafts of similar diameter, length, capacity and working environment to those shown on the Plans.

2.	The boring subcontractor and qualifications to perform the test boring at the demonstration shaft location and the boring at the production shafts when borings are required during the drilled shaft excavation.

3.	The Contractor or subcontractor to install the reinforcement cage into the drilled shaft.

4.	The Contractor or subcontractor to perform the placement of the drilled shaft concrete.

5.	A list containing the description, type, size, capacity and number of equipment to be used.

6.	Detail description of the overall construction operation sequence and the proposed sequence of shaft construction.

7.	Details of planned drilled shaft excavation methods including the proposed drilling methods.  Ensure the excavation method is suitable given the anticipated site.

8.	Details of the methods to ensure shaft stability during excavation and concrete placement.  Include a review of method suitability to the anticipated work site and subsurface conditions.  If casings are proposed or required, provide casing dimensions, detailed procedures for permanent casing installation, and procedures for temporary casing installation and removal.

9.	When slurry is specified or proposed, provide details of the methods for mixing, placing, circulating, and desanding the slurry.  Also include the method of monitoring and continuously maintaining the slurry level.  Provide the method of disposal.

10.	Details of methods to clean and maintain the shaft excavation, including removal of loose rock and sediment from the shaft bottom.

11.	Details of proposed methods to check shaft bottom cleanliness.

12.	Details of steel reinforcement lifting, splicing if necessary in a hanging position, insertion and securing, including support and centralization methods.

13.	Mix design of the concrete and documentation showing that the mix design meets the approved mix and strength requirements.

14.	The method used to fill or eliminate voids between the plan shaft diameter and excavated shaft diameter, or between the shaft casing and surrounding soil, if permanent casing is specified.

15.	Methods to determine drilled shaft dimensions and the deviation from vertical for the entire depth of the drilled shaft.  Details of casing removal when removal is required, including minimum concrete head in casing during removal.

16.	Procedures for control and removal of spoils on land, over water, or both.

17.	Details of concrete batching and/or delivery to the work site, and concrete placement, including proposed operational procedures for concrete pump or tremie.  Discuss the initial placement, raising tremie pipe(s) during placement, overfilling of the shaft concrete, the proposed method to accurately monitor the volume of concrete being placed at all times during the pour, and provisions to prepare the completed shaft top at its final shaft top elevation.

18.	The qualification records of the testing organization, consisting of the name, title, responsibilities and specific site experience with bi-directional projects.  The organization must provide proof of at least 10 successful bi-directional load tests and 3 successful lateral load tests.

19.	The qualification records of the testing organization to perform the CSL test, consisting of the name, title, responsibilities and specific site experience with CSL testing.

20.	Details of procedures, materials, and equipment for performing the bi-directional Load Test and the CSL.  Provide a certificate of calibration for the load cell from an approved testing laboratory.  Ensure that the calibration was performed for all ranges of proposed loading within the 2 months preceding the load tests.  Ensure that the certified accuracy of the load cell is within 1 percent of the true load.  Concrete core drilling equipment and procedures to retrieve the core specimens that may be required to determine the integrity of concrete placed in the drilled shaft.

The RE will schedule a review meeting between the Contractor, designer, and the Department (construction, project manager, geotechnical engineering) after reviewing the installation plan and at least 15 days before the start of work.

Within 30 days after receipt of the plan, the RE will notify the Contractor of additional information required and changes that may be necessary.

If the RE rejects the plan or a part of the plan, submit revisions to the RE for reevaluation.  The RE will approve or reject the resubmission within 10 days after receipt of proposed changes of their approval or rejection.

B.	Installation.  Perform a demonstration drilled shaft to verify the Contractor’s methods, techniques and equipment by successfully constructing a demonstration shaft.

Before demonstration shaft excavation, perform an exploratory test boring at the demonstration shaft location.  Extend the test boring(s) at least 10 feet or three times the shaft diameter whichever is greater below the tip elevation of the demonstration shaft.  Provide detailed information on the underlying bedrock if encountered.

Perform standard penetration test (SPT) and split-barrel sampling of soils in accordance with ASTM Standard D1586 and if rock is encountered, rock core drilling and sampling of rock for site investigation in accordance with ASTM Standard D2113.  Prepare the boring logs, place the rock samples in core boxes, mark, and pack them in accordance with ASTM Standard D5079.  Submit the results of the test borings, SPT tests, and photographs of each labeled core box to the Department prior to drilled shaft excavation.  If the drilled shafts are rock socketed or bearing on rock, the Department will require unconfined compression tests on a minimum of four samples in accordance with ASTM Standard D7012.  Submit the test results to the Department.  The Department will evaluate the rock mass strength and classify the rock using GSI and Hoek-Brown failure criterion based on AASHTO LRFD Bridge Design Specifications, 2014, Section 10.4.6.4, and determine the top of competent rock.

Install the demonstration shaft as shown on the Plans or as directed by the RE, but not less than a clear distance of three drilled shaft diameters from the closest production shaft.  Excavate the demonstration shaft to the depth of the deepest and maximum diameter of the production shaft as shown on the Plans.  Perform soil sampling and analyses of regulated material including solids from dewatered slurry as specified in 202.03.04.  Dispose of regulated material including solids from dewatered slurry as specified in 202.03.08.  Construct the demonstration shaft as specified in 503.03.07.  Include CSL as specified in 503.03.04.

Load tests and evaluation of the results must be completed and approved prior to installing the production drilled shafts.

Failure to demonstrate the adequacy of methods and equipment to the RE may require the installation of an additional demonstration shaft with appropriate alterations in equipment, methods by the Contractor, or both to eliminate unsatisfactory results.  An additional demonstration shaft and all testing required to demonstrate the adequacy of method or equipment will be at Contractor’s expense.

Cut-off the concreted demonstration shafts 2 feet below finished grade or 3 feet below the mudline if in water.  Restore disturbed areas at demonstration shaft holes to their original condition.

503.03.03  Load Test

If required, perform Axial and Lateral load tests according to ASTM D1143, D3966 or D7383.

A.	Bi-Directional Load Cell Installation.  Ensure that the installation and execution of the bi-directional load tests are supervised by a Professional Engineer and comply with the bi-directional load cell manufacturer recommendations, instructions and procedure manuals as approved by the Department.  Ensure that the bi-directional load cell, vibrating wire strain gauges, hydraulic supply, and other attachments are assembled according to the manufacturer’s recommendations.  Provide a reinforcement steel cage, as specified in 503.03.06.J, to attach the bi-directional load cell.  Excavate the shaft using the approved method at the location shown on the Plans.  After excavating the shaft, and obtaining approval from the RE, place a seating layer of concrete in the base of the drilled shaft.  While the seating concrete is still plastic, install the reinforcement steel cage with the bi-directional load cell in the test shaft so that the bi-directional load cell rests firmly in the concrete.  Build the bi-directional load cell into the steel reinforcing cage at a predetermined elevation approved by the Department.

After seating the bi-directional load cell assembly, place concrete in the drilled shaft as specified in 503.03.06.K.  The ME will take at least 6 concrete compression test cylinders from the concrete used in the shaft.  At least 1 day before the load test, the ME will test at least 1 of the cylinders.  The ME will test at least 2 cylinders on the day of the load test.  Do not perform the bi-directional load test until 7 days after placing the concrete and the concrete achieves the specified compressive strength.

B.	Load Testing and Reporting.  Do not perform Axial or Lateral Load testing until CSL test results have been approved.  Perform Axial Load test according to ASTM D 1143 unless otherwise specified in the Contract Documents.  If the test apparatus shows signs of negative effects due to the construction activities, immediately cease testing and do not resume until the conditions are favorable for testing.

Take direct movement indicator measurements of the following:

1.	Two Linear Variable Displacement Transducers (LVDT) vibrating wire displacement gauges, attach to each load cell to monitor the expansion and contraction of the load cell.

2.	Two Linear Variable Displacement Transducers (LVDT) gauges, mount on an independent reference beam and set on opposite sides of the top of the test shaft to monitor the axial shaft displacement.

3.	Vibrating wire strain gauges, placed in pairs on opposite sides of the reinforcement cage at elevations shown on the Plans.

Limit the deflection of the cage to a maximum of 2 feet between pick points while lifting the cage from the horizontal position to vertical.  Provide additional support, bracing, strong backs, etc. to maintain the deflection within the specified tolerance.

Apply loads in increments of 5 percent of the maximum test load as shown on the Plans.  The maximum test load is limited to the maximum axial resistance of the shaft above or below the cell or the maximum capacity of the cell or the maximum expansion of the bi-directional load cell, whichever comes first.

In addition to the requirements of ASTM D 1143, at each load increment, or decrement, take readings of the movement indicators at 1.0, 2.0, 4.0 & 8.0 minute intervals while holding the load constant.  Ensure that strain gauge readings are concurrent with shaft movement readings.  The RE may direct additional cycles of loading and unloading using similar procedures following the completion of the test cycle.

Ensure that dial gauges or LVDTs used to measure end bearing, side shear movement, and shaft compression have a minimum travel of 8 inches and are capable of being read to the nearest 0.0001 inch division.  The Contractor may alternately monitor end bearing movement using LVDTs capable of measuring the expansion of the bi-directional (6 inches).  Ensure that the reference beam has a minimum length equal to 6 times the drilled shaft diameter.  Monitor the reference beam for movement during load testing using a surveyor’s level.

Provide the performance results of each load test to the RE the day after performing the load tests.  Provide a final report of the load test results to the RE within 10 days of completing the test.

Ensure that the report includes, but is not limited to, the following:

1.	Test shaft identification and location

2.	Date(s) of testing

3.	Description of the test shaft details, instrumentation and test procedures

4.	Tables presenting all instrumentation data

5.	Plots of load versus displacement (up and down) for each load cell level and for each stage of the test

6.	Plots of load along the length of the drilled shaft determined from the strain gauge data for at least ten applied load increments

7.	Summary of unit side resistance along the drilled shaft and end bearing resistance

8.	Plots of creep displacement for each load increment

9.	Plot of equivalent top-of-shaft displacement for the test shaft, developed from the load test data

Within 20 days, the Department will notify the Contractor if revisions to the foundation lengths and installation procedures will be made based on the results of the load tests.  Do not begin construction of production drilled shafts without the Department’s approval.

C.	Post-Test Grouting Procedures.  Grout the interior of the bi-directional cell and annular space around the outside of the bi-directional cell according to the manufacturer’s recommendations.

The Contractor does not have to grout test shafts that will not be used as production shafts.

503.03.04  Crosshole Sonic Logging

Perform the Non-Destructive Integrity Crosshole Sonic Logging (CSL) testing on completed shafts including rock socket in accordance with ASTM D 6760 (Standard Test Method for Integrity Testing of Concrete Deep Foundations by Ultrasonic Crosshole Testing).

Begin CSL on demonstration and all production drilled shafts 72 hours after placing concrete in the shaft.  RE may specify a longer minimum time if concrete mix designs or other factors results in slower setting concrete.  Ensure that the testing is completed within 20 days after placing concrete.

The number of access tubes is provided in the drilled shaft detail in the contract Plans.

A.	Installation.  Ensure the tubes are 1.610 to 2.067 inch inside diameter schedule 40 steel pipe.  Ensure that the CSL tubes are watertight and have a round, regular, internal diameter free of defects or obstructions, including at tube joints, to allow the free, unobstructed passage of 1.3-inch diameter source and receiver probes.  Ensure the tubes are free from corrosion with clean internal and external faces to ensure passage of the probes and a good bond between concrete and the tubes.

Ensure that each pipe is fitted with a watertight shoe at the bottom and a removable cap at the top.  Attach the pipes securely to the interior of the reinforcement cage with a minimum cover of 4 inches or as shown in the contract Plans.  Install the tubes as near to parallel as possible.

Ensure that the tubes extend from 6 inches above the shaft bottoms to at least 3 feet above the shaft tops.  If the shaft top is sub-surface, extend the tubes at least 2 feet above the ground surface.  Ensure that joints required to achieve full-length tubes are watertight.

Ensure that the tubes are not damaged during reinforcement steel cage installation.  As the cage is being lowered into the shaft, monitor the tubes to ensure that they are vertical and parallel, and that connections are watertight.  After installing the reinforcement cage, immediately fill the tubes with potable water.  After the tubes are filled with water, cap or seal the tube tops.

Before placing concrete, plumb at least 1 tube per shaft and record the tube length.  Note the stickup of the tubes above the shaft tops.

Do not remove the seals or caps until the concrete in the shaft has set.  Remove the caps or plugs after installation and ensure not to apply excess torque, hammering, or other stresses that could break the bond between the tubes and the concrete.

Grout the access tube after the final acceptance of the drilled shaft.

B.	CSL Testing and Reporting.  Perform the CSL tests between all of the possible pairs of tubes in the drilled shaft concrete.  Perform the CSL tests with the source and receiver probes in the same horizontal plane, unless the RE directs that the defect is evaluated with the source and receiver probes in different horizontal plane.  Take CSL measurements at depth intervals of 2 inches or less, from the bottom of the tubes to the top of each shaft.  Pull the probes simultaneously, starting from the bottoms of the tubes, over a depth measuring device.  Remove slack from the cables before pulling to provide for accurate depth measurements of the CSL records.

Provide the RE the preliminary results of the testing on site prior to the CSL Consultant leaving the site.  Submit a detailed CSL test report and test data signed and sealed by a Professional Engineer to the RE within seven days, which includes recommendations as to the acceptability, unacceptability, soundness and further evaluation of the drilled shaft.

In addition to the report requirements in ASTM D 6760, the CSL report needs to include, but not be limited to, the following:

1.	Project Identification and Date of Testing.

2.	Description of the testing apparatus unit and probes.

3.	Name of the person responsible for the validity of the test report.

4.	A table and schematic showing shafts tested with accurate identification of CSL tube coordinates and their top elevation.

5.	Number of days between concrete placement and CSL testing.

6.	The Data Logs: Include XY plots of Velocity, First Arrival Time (FAT) and signal strength.  The signal strength needs to be expressed in units of decibels (dB).

7.	An evaluation of defect zones.

Evaluation of the CSL Tests will be based on the following table:

| Table 503.03.03-1 – Concrete Condition Rating Criteria |
| --- |
| Concrete condition Rating | Velocity reduction VR(%) | Signal distortion/Strength | Indicative conditions |
| Good (G) | 0 to 10 | none/normal energy reduction ≤ 6 dB | Acceptable quality concrete |
| Questionable (Q) | 10 to 20 | Minor/lower energy reduction 6.1 to 9 dB | Minor contamination, intrusion, and/or poor quality concrete |
| Poor/defect (P/D) | >20 | Severe/much lower energy reduction > 9 dB | contamination, intrusion, and/or poor quality concrete |
| No Signal (NS) | No Signal | None | Intrusion or severe defect: could also be caused by tube debonding |
| Water (W) | ≈ 60 | Severe/much lower energy reduction ≥12 dB | Water intrusion or water-filled gravel intrusion with few or no fines |

C.	Evaluation of the CSL Test Results.  The Department will evaluate the CSL test results and determine whether or not the drilled shaft construction is acceptable.  If the RE determines that the drilled shaft is acceptable, dewater and grout the CSL tubes.  Use the grout with the same strength or higher than the strength of the concrete used in the original drilled shaft.

If the tests indicate potential defects, the RE may direct the Contractor to perform additional tests for further evaluation.

D.	Further Evaluation.  Perform Tomography, Shaft Coring or other investigated methods as directed by the RE for further evaluation.  Submit a report signed and sealed by a Professional Engineer registered in the State of New Jersey providing the results of further evaluation and recommendations to accept or repair the shaft within 14 days.  The report must contain recommendations for modification of construction procedures to prevent defects for subsequent shaft installation.

E.	Corrective Measures.  If the Department determines that the drilled shaft is unacceptable, submit working drawings for approval of proposing corrective measures.  Do not begin corrective measures until the Department approves the working drawings.  Repair all detected defects as per working drawings and conduct post repair integrity testing using CSL tests and 2-D and 3-D Tomography tests.  Submit test results to RE within five days of tests completion for approval.  The Department will not pay for these additional tests or repairs or provide an increase in contract time.

Do not proceed with construction above a drilled shaft until the quality of the shaft, as represented by the core samples, is determined to be acceptable and the RE provides notification to continue construction.

503.03.05  Tomography

Use the same equipment and access tubes as the CSL method.  Submit the Tomography analysis results to RE for review.  Provide the two dimensional (2-D) horizontal and vertical slices and three dimensional (3-D) tomographs for the entire shaft between the respective tube pairs.  Present these images in color and coded to identify the variations in sonic velocity.  Include the complete discussion of the Tomography tests results in the report.

503.03.06  Shaft Coring

If the Department determines the drilled shafts are unacceptable based on CSL test results or CSL test results and tomographic analyses, or observed problems during drilled shaft construction, the RE will direct the Contractor to core the drilled shaft concrete to obtain samples in the area of the possible defects for further evaluation of accepting, repairing or replacing the drilled shaft.  The Department will determine the number, location and depth of cores required.  Ensure the concrete core samples are obtained in accordance with ASTM D2113.  Drill cores at a diameter between 2-4 inches.

Keep an accurate coring log, properly mark cores with the depth at each interval of core recovery, and place the cores in a crate.  Perform strength test on core samples that exhibit questionable concrete as determine by Department.

503.03.07 Constructing Drilled Shafts

A.	Installation Plan.  Submit an installation plan, as specified in 503.03.02.  Do not begin constructing drilled shafts until the RE approves the plan.

Once approval has been given to construct production shafts, do not change the personnel, methods, or equipment that were used to construct the approved demonstration shaft without written approval of the RE.

B.	Alignment and Tolerances.  For bridge foundations, ensure that the center axis of the poured shaft at the top of the drilled shaft or mudline, whichever is lower, is within the following tolerances:

Drilled Shaft Diameter	Tolerance

≤ 2’-0”	3”

> 2’-0” < 5’-0”	4”

≥ 5’-0”	6”

During construction, periodically, check the verticality of the excavation by holding a 4-feet level on the Kelly bar or other suitable method.  Ensure that the vertical alignment of a shaft excavation in soil does not vary from the alignment shown in the Plans by more than 1.5% of the shaft length.  Ensure that the vertical alignment of the shaft excavation in rock does not vary from the alignment shown in the Plans by more than 2.0% of the shaft length.

For bridge foundations, after placing all the concrete, ensure that the top of the reinforcing steel cage is no more than 6 inches above and no more than 3 inches below the plan position.

Recommended concrete cover to reinforcing steel:

Drilled Shaft Diameter	Minimum Concrete Cover

≤ 3’-0”	3”

> 3’-0” < 5’-0”	4”

≥ 5’-0”	6”

Ensure that the reinforcing cage is concentric with the shaft within a tolerance of 1 inch.

C.	Construction Sequence Limitations.  Excavate to the bottom of the footing elevation before beginning shaft construction.  When constructing drilled shafts and placing embankment, construct drilled shafts after the placement of embankment.  Repair disturbances caused by shaft installation to a subsequent drilled shaft area before beginning shaft construction.

Do not excavate a shaft if an adjacent shaft in the same substructure unit is open unless the RE’s written approval is obtained.  Do not perform blasting or vibrate to place casings until the concrete in adjacent shafts has reached 80 percent of the required 28-day compressive strength.  Once the excavation of a shaft has begun, do not stop the excavation until the excavation is completed.  If the excavation is stopped for more than 24 hours, maintain shaft stability as detailed in the installation plan.

D.	Excavation Log.  Maintain an excavation log during shaft excavation that includes at least the following:

1.	Name of the inspector, date, time and names of changes in the inspector.

2.	Identification number of each shaft.

3.	Location and surface elevation at each shaft.

4.	Description and approximate top and bottom elevation of each soil or rock material encountered during shaft excavation.

5.	Elevations at which seepage or groundwater flow are encountered, and remarks.

6.	The type and dimension of tools and equipment used for the excavation.

7.	Changes in the type of tools and equipment used for excavation.

8.	Type of drilling fluid used during the shaft excavation, if used.

9.	Problems that are encountered during the shaft excavation.

10.	Elevation changes in drilled shaft diameter.

11.	Method used for bottom of the shaft cleaning.

12.	Final bottom elevation of the shaft.

Ensure that discrepancies noted on the log by the RE are resolved by the end of each day.  Provide 2 copies of the final log to the RE within 24 hours after a shaft excavation is completed and approved.

Reuse excavated material as specified in 202.03.07.A.

E.	Excavating.  Use the appropriate method for constructing drilled shafts as follows:

1.	Dry Method.  Only use the dry method where the groundwater level and soil conditions allow construction of the drilled shaft in a relatively dry excavation, and where the sides and bottom of the shaft may be visually inspected by the RE before placement of reinforcement and concrete.  The dry method will consist of drilling the shaft excavation, removing all accumulated water and loose material from the excavation, placing the reinforcement cage, and concreting the shaft in less than 3 inches of water.

2.	Wet Method.  Construct drilled shafts using the wet method where dry excavation cannot be maintained.  The wet method will consist of using water or slurry, as specified in 503.03.07.G, to maintain stability of the drilled shaft perimeter while excavating to finished depth, placing the reinforcement cage, and concreting the shaft.  The Contractor may use the static or circulation process of the wet method.

When the material encountered cannot be drilled using conventional earth drilling tools and equipment, provide rock drilling equipment, including air tools, approved blasting materials, and other equipment as necessary to construct the shaft excavation to the size and depth required.  Obtain the RE’s approval before switching from earth to rock drilling tools and equipment.  Obtain the RE’s approval before blasting.

The Contractor may over ream with a grooving tool, overreaming bucket, or other RE approved equipment.  The RE will direct the thickness and extent of sidewall overreaming.

The Department will require sidewall overreaming between 1/2 and 3 inches when the sidewall of the hole has either softened due to excavation methods, swollen due to delays in concreting, or degraded because of slurry cake buildup.

Drilling tools lost in the excavation will not be considered as obstructions.  Immediately remove drilling tools that are lost in the excavation.

F.	Constructing Using Casings.  Construct drilled shafts using casings where shown on the Plans or where the dry or wet construction methods are inadequate to prevent caving or excessive deformation of the hole.  When downsizing of permanent casing is required, do not overlap more than 6 feet of casing.

When constructing drilled shafts in open water, extend the exterior casings from above the water elevation into the ground to protect the shaft concrete from water action during placement and curing of the concrete.  Install the casing to ensure a positive seal at the bottom of the casing so that no seepage of water or other materials occurs into or from the shaft excavation.

When casings are not shown on the Plans, but the Contractor believes that casings are necessary, submit details of the proposed casing method in the installation plan (including casing lengths and diameters) and the proposed procedures of casing installation to the RE for review.  If the Contractor does not determine the need for casings until after work on the shafts has begun, submit to the RE for review a revised installation plan proposing the casing installation method for review.

Ensure that casings are clean, round, straight, and free of weld breaks and holes that would allow passage of water or plastic concrete.  With RE approval, the Contractor may provide casings larger in diameter than shown on the Plans.

If splices are needed, make splices for steel casing by full penetration butt welding in the entire cross section as per AASHTO/AWS D1.1 and as shown on the contract Plans.

1.	Temporary Casings.  Casings are temporary unless shown as permanent casings on the Plans.  Telescoping, predrilling with slurry, and overreaming to beyond the outside diameter of the casing may be required to install casing.

Remove temporary casing before completing concrete placement in the drilled shaft.  Before withdrawing the casing, ensure that the level of plastic concrete in the casing is at least 5 feet above either the hydrostatic water level in the formation or the level of drilling fluid in the annular space behind the casing, whichever is higher.  As the casing is withdrawn, maintain an adequate level of concrete within the casing so that fluid trapped behind the casing is displaced upward and discharged at the ground surface without contaminating or displacing the shaft concrete.

If the Contractor removes a specified diameter or length of casing and substitutes a longer or larger diameter casing through caving soils, the Contractor shall stabilize the excavation using a slurry or backfill before the new casing is installed.

If temporary casings become bound or fouled during shaft construction and cannot be practically removed, the Department will designate the drilled shaft defective.  Submit working drawings for approval proposing corrective measures.

Do not begin corrective measures until the Department approves the working drawings.

2.	Removable Casing.  When the shaft extends above ground or through a body of water, the Contractor may use suitable, removable casing for the portion exposed above ground or through a body of water except when permanent casing is specified.  Strip removable casing from the shaft and ensure that the concrete is not damaged.

The Contractor may remove casings when the concrete has attained a strength of at least 2800 pounds per square inch as determined from 2 concrete cylinders field cured according to AASHTO T 23, provided that curing of the concrete is maintained, as specified in 504.03.02.F.  Do not expose the shaft concrete to salt water or moving water for 7 days.

3.	Permanent Casings.  When not shown on the Plans, the Contractor may use permanent casing if approved by the RE.  Ensure casings are continuous between the top and bottom elevations shown on the Plans.  After installation is complete, cut off the permanent casing at the specified elevation.

After installing the casings, repair damage to coated surfaces of the casings exposed to the air by applying an organic zinc prime coat from the same manufacturer as the shop-applied inorganic zinc prime coat.

G.	Constructing Using Slurries.  When using slurry to construct drilled shafts, the Contractor may use mineral or polymer slurries.  During construction, maintain the level of the slurry at a height sufficient to prevent caving of the shaft excavation.  Use a temporary surface casing in the upper soils.  Maintain the slurry level inside the shaft above the groundwater level during installation and cleaning out.  In the event of a sudden significant loss of slurry to the hole, cease the construction until either a method to stop slurry loss or an alternate construction procedure has been approved by the RE.

Pump slurry into holding tanks to ensure that no slurry spills or contaminates the site.  Provide physical or chemical treatment of the slurry according to the manufacturer’s recommendations.

During construction, maintain the level of mineral slurry in the shaft at least 4 feet above the highest expected piezometric pressure head that is along the depth of the shaft.  Maintain the level of polymer slurry at least 5 feet above the highest expected piezometric pressure head that is along the shaft.  If the selected slurry construction method fails, in the opinion of the RE, to produce the desired final results, cease this method and propose an alternate method to the RE for approval.

Ensure that a heavily contaminated slurry suspension, which could impair the free flow of concrete, has not accumulated in the bottom of the shaft.  Before placing concrete for shaft excavation, take slurry samples using a sampling tool approved by the RE.  Take slurry samples from the bottom of the shaft and at intervals not exceeding 10 feet up the slurry column in the shaft, until 2 consecutive samples produce acceptable values for density, viscosity, sand content, and pH at each sampling depth.

When slurry samples are unacceptable, take corrective actions.  Do not place concrete until the slurry is re-sampled and test results are approved.

If the slurry remains in the shaft for more than 12 hours or if caking develops, roughen or re-ream the shaft with appropriate new bottom cleaning and slurry testing before concreting.  Place concrete on the same day as the completion of the excavation of the drilled shaft to the bottom elevation.

Perform soil sampling and analyses of regulated material including solids from dewatered slurry as specified in 202.03.04.  Dispose of regulated material including solids from dewatered slurry as specified in 202.03.08

1.	Mineral Slurry.  During shaft excavation, premix mineral slurry with water and allow time for hydration according to the manufacturer’s recommendations.  Provide slurry tanks of adequate capacity for slurry circulation, storage, and treatment.  Do not substitute excavated slurry pits with slurry tanks without obtaining approval from the RE.  Do not mix the slurry in the shaft.

Monitor the properties of the pre-mixed slurry as it is introduced into the borehole and periodically thereafter, including a final check of a bottom sample before placing concrete to verify that the density and sand content are within the limits for the proper slurry displacement during concreting.  Use desanding equipment to control slurry sand content to less than 4 percent by volume at all points in the borehole at the time the slurry is introduced.

2.	Polymer Slurry.  Provide a slurry management plan to the RE that includes a set of the slurry manufacturer’s written recommendations and results of the following tests, as a minimum:

1.	Density Test (API 13B-1, Section 1).

2.	Viscosity Test (Marsh funnel and cup, API 13B-1), Section 2.2 or approved viscometer.

3.	pH Test (pH meter, pH paper).

4.	Sand Content Test (API sand content kit, API 13B-1, Section 5).

Also include the tests to be performed, the frequency of those tests, the test methods, and the maximum and minimum property requirements that must be met to ensure that the slurry meets its intended functions.  Ensure that test reports are signed, and provide them to the RE on completion of each drilled shaft.

H.	Rock Socketing.  If subsurface exploration is required, core drill and obtain samples of rock in accordance with ASTM Standard D2113.  Prepare the boring logs and place the rock samples in core boxes, mark and pack them in accordance with ASTM Standard D5079.  Submit the results of the test borings and photographs of each labeled core box to the Department prior to Drilled Shaft excavation.  Perform Unconfined Compressive Strength test on a minimum of four samples retrieved from each boring.  Submit the results of Unconfined Compression test results.  The Department will evaluate the Rock Mass Strength and classify the rock with GSI and Hoek-Brown failure criterion based on AASHTO LRFD Bridge Design Specifications, 2014.

If the top surface of the sound rock is found to be inclined across the width of the shaft, immediately notify the RE.

Prepare rock socket for concrete placement by roughening with drilling tools or by overreaming.  Rotate roughening tools against the rock socket area to remove accumulated slurry cake, to scale off loose rock fragments, and to roughen the finished rock socket surface.

I.	Excavation Cleaning and Verification.  Unless otherwise approved by the RE, ensure that at least 50 percent of the base of each shaft has less than 1/2 inch of sediment at the time of concrete placement.  Ensure that the maximum depth of sediment or debris on the base of the shaft does not exceed 1-1/2 inches.

In the presence of the RE, determine the cleanliness of the bottom of the shaft by the use of sounding, probe data, miniature drilled shaft inspection device (mini-SID), tape with weight, or other methods approved by the RE.  After final cleaning, determine the dimensions, depth, and alignment as directed by the RE.  For uncased drilled shafts, determine shaft dimensions, depth and alignment with a sonar caliper.  Inspect the bottom of each shaft including demonstration shaft before and after placing the rebar cage in the drilled shaft.  If the cleanliness of the excavation does not meet the requirements, remove the rebar cage and clean until the above requirements are satisfied.

J.	Constructing Reinforcement Steel Cages.  Completely assemble and place the reinforcement steel cage, consisting of longitudinal and transverse bars, ties, cage stiffeners, spacers, centralizers, and other necessary appurtenances as a unit shown on the Plans immediately after the excavation is inspected and approved and immediately prior to concrete placement.

Use concrete spacers or other approved noncorrosive spacing devices at sufficient vertical intervals, near the bottom, and at intervals not exceeding 10 feet up the shaft, to ensure concentric location of the cage within the shaft.  If the size of the spacers is not shown on the Plans, provide spacers that will create a minimum 3-inch annular space.  Ensure that flat or crescent shaped centralizers (“sleds”) are not used in an uncased shaft.

Provide reinforcing cage bottom support to ensure that the bottom of the cage is maintained at the specified distance above the base.  Use approved non corrosive devices such as cylindrical concrete feet, mortar or plastic chairs as the bottom supports.

K.	Concrete Placement. Place concrete according to the limitations specified in 504.03.02.C.  Place the concrete within 24 hours after completing all excavation, cleaning the shaft bottom, inspecting and finding it satisfactory.  Place concrete immediately after placing reinforcing steel cage and inspecting and finding it satisfactory.  Continuously, place the concrete from the bottom of the shaft excavation to the top elevation of the shaft.

L.	Time Limitations.  Ensure the concrete placement in the shaft is completed within 2 hours.

The RE may allow the concrete placement time to exceed 2 hours if the Contractor demonstrates that the slump of the concrete will be as specified in Table 903.03.06-2 during the entire time of concrete placement.

In cases when Self-Consolidated concrete is used, the RE may allow the concrete placement time to exceed 2 hours if the Contractor demonstrates that the slump flow of the Self Consolidated concrete will be as specified in Section 903.06.01B.

M.	Concrete Placement Methods.  Place the concrete using tremie pipe method or pump method from the bottom of the excavation.  Do not allow the concrete placement by free fall method.

Check the elevation of the top of the steel cage before, during, and after concrete placement.  If the final upward displacement of the rebar cage exceeds 6 inches or if the downward displacement exceeds 3 inches, the RE will reject the drilled shaft.  Correct the shaft to the satisfaction of the RE.  Do not construct additional shafts until the rebar cage support system is corrected.

1.	Tremie Method.  Ensure that tremie tubes are of sufficient length, weight, and diameter to discharge concrete at the shaft base elevation.  Ensure that the inside surface of the tremie is clean and smooth to minimize drag on the concrete flow during concrete placement.  Ensure that the outside surface of the tremie is smooth to avoid entanglement with the reinforcement cage.  Ensure that the tremie tube’s inside diameter is at least 6 times the maximum size of aggregate used in the concrete mix.  Do not use tremie tubes less than 10 inches in diameter.  Ensure that the tremie tube thickness is adequate to prevent crimping or sharp bends.  Do not use tremie tubes that have aluminum parts that will come in contact with concrete.  Ensure that tremie tubes are watertight to prevent inflow of slurry during concrete placement.

Do not begin placing concrete under the drilling fluid (water, slurry or other fluids) until the tremie is placed to the shaft base elevation.  In wet excavation and with a closed tremie, the Contractor may seal the bottom of the tremie pipe with a sacrificial cover plate.  In closed end tremie, ensure that the discharge end of tremie (valves or bottom cover plate) is within 6 to 12 inches of the bottom of the concrete placement when the concrete discharge begins.  For open tremie, the Contractor may use a traveling plug to act as a separator in between the drilling fluid and concrete in order to prevent mixing as the concrete travels down the tremie pipe.  Remove plugs from the excavation or construct them using a material that will not cause a defect in the shaft if not removed.  Ensure that the plug is not so compressible that it fails to perform its function as a separation within the tremie pipe under the anticipated hydrostatic pressure.  Construct the discharge end of the tremie to allow the free radial flow of concrete during placement operations.

Ensure that the tremie tube discharge end is immersed at least 10 feet in concrete at all times after starting the flow of concrete.  Use a weighted tape and a marked tremie pipe to monitor whether tremie is at least 10 feet in the concrete all the time.  However, excessive embedment of the tremie into the concrete can cause the reinforcing cage to start to lift along with the rising column of concrete.  Maintain a continuous flow of the concrete at a positive pressure differential to prevent water or slurry intrusion into the shaft concrete.  Maintain the continuous flow of concrete until the work is completed.

If the tremie tube discharge end is removed from the plastic concrete and discharges concrete above the rising concrete level, the RE will consider the drilled shaft defective.

2.	Pumped Method.  Concrete pumps and lines are used for concrete placement by either the wet or dry construction method.  Ensure that the pump lines in the shaft are typically a rigid steel pipe, have a minimum diameter of 4 inches and are constructed with watertight joints.  Ensure that the pump line is immersed at least 10 feet in concrete as with after starting the flow of concrete.

When lifting the pump line during concreting, temporarily reduce the line pressure until the discharge end has been repositioned at a higher level in the excavation.

If during the concrete pour the pump line discharge end is removed from the fluid concrete column and discharges concrete above the rising concrete level, consider the shaft defective.  In such case, remove the reinforcement cage and concrete, complete necessary sidewall removal directed by the RE, and replace the shaft.

When using a concrete pump to place concrete for the drilled shaft, provide a standby pump that is immediately available if there is a pump failure.

When using SCC to construct drilled shafts, only place SCC using the tremie method.

N.	Drilled Shaft top preparation during the completion of concrete placement.  Continue placing concrete until the waste concrete is pushed upward and ejected completely out of the top of the casing and wasted; or, place an additional 24 inches of concrete above the planned shaft top level and allow to cure in place for removal later.  Remove waste concrete at the top of the shaft to maintain a uniform appearance and to consider the top-most concrete placed in the shaft as waste concrete and either:

1.	Push upward and eject completely out of the top of the casing and waste as final concrete is placed.  Do not channel or bleed off waste concrete using notches, holes, or cuts in the casing top.  The Contractor may remove or pump out fresh concrete in the casing at a level above the Plan shaft top level after ejecting all waste concrete to the Plan top elevation while still plastic by methods and equipment approved by the Department or allow to cure in place for removal later.

2.	Pump upward to a level at least 2 feet clear distance above the Plan shaft top level and allow to cure in place to remove later.

Waste concrete is the top 24 inches of the initial concrete placed, plus the height of additional volume of waste concrete deposited in the shaft where concrete placement was halted and restarted, plus all additional amount necessary to produce full strength, non-segregated concrete at the Plan shaft top level.

Commence the final shaft top preparation only once the drilled shaft concrete obtains an average unconfined compression strength of at least 2500 psi, or, in lieu of concrete strength testing, after seven full days from completion of concrete placement.  Final top preparation consist of:

1.	Cutting off extra permanent casing above the top of casing Plan elevation

2.	Cutting off cured over-pour concrete to the Plan shaft top elevation by approved methods

3.	Verification by the RE that the exposed concrete consists of full strength concrete with typical, non-segregated mortar and aggregate distribution

4.	Approved non-destructive strength testing where required by the RE to verify that the concrete has obtained full design strength

O.	Approval.  Compare the computed theoretical volume of the excavation with the actual volume of concrete placed, and create a plot of depth versus volume.  Provide results to the RE.

After placing the concrete, ensure that the top elevation of the reinforcement steel cage is within −3 inches and +6 inches of the Contract Plan elevation.  Ensure that the top elevation of the completed drilled shaft is within −3 inches and +1 inch of the Contract Plan elevation.

The RE may reject drilled shafts because of damage; failure to advance through; mislocation, misalignment, or failure to install the drilled shaft to the proper bearing stratum; or results of CSL testing indicating defects.

If the CSL records indicate any anomolies, the RE may require further evaluation to confirm the location of the defect.  The RE may also require shaft coring, testing of core samples or excavation of the shaft to verify shaft conditions.  If a defect is confirmed, with further evaluation (Tomography, shaft coring, testing of core samples or excavation), the Department will not pay for costs including shaft coring, testing of core samples, remediation, or grouting.

If no defect is encountered, the Department will pay for all shaft coring, testing of core samples and excavation costs, including grouting all core holes.  The coring and grouting of core holes will be paid for at the Contract bid price per linear foot for coring of shafts including grouting core holes.

For each rejected drilled shaft, submit to the RE for approval a plan showing how to correct the problem and prevent its reoccurrence.  Repair, augment, or replace the drilled shaft.  To mitigate or remedy rejected drill shafts, the Contractor may be required to provide additional drilled shafts or supplement drilled shafts to meet specified requirements at no cost to the Department.  If the RE rejects a drilled shaft, the Contractor shall cease the construction of all other drilled shafts until the Contractor demonstrates the ability to construct an approved drilled shaft.

Within 10 days after completing the installation of all drilled shafts, and before removing the drilled shaft installation equipment from the Project Limits, provide the RE with a plan certified by a land surveyor registered in the State of New Jersey showing the as-installed location of drilled shafts.  The RE will analyze the total loads on individual drilled shafts based on the survey data.  If the load on each drilled shaft exceeds 10 percent of the specified load capacity, correct the drilled shaft as directed by the RE.  The corrections may include installation of additional drilled shafts.

Do not place substructure concrete on a drilled shaft until the concrete in the shaft reaches a minimum of 80 percent of the required 28-day compressive strength and until all CSL test results are approved and the CSL tubes have been dewatered and grouted.

503.03.08  Obstructions Removal

The RE will determine if an object is considered an obstruction.  Remove surface and subsurface obstructions at drilled shaft locations.  The Contractor may need to use special procedures and tools when the obstruction cannot be removed using conventional augers fitted with soil or rock teeth, drilling buckets or underreaming tools.  Special procedures and tools may include: chisels, boulder breakers, core barrels, air tools, hand excavation, temporary casing, and increasing the hole diameter.  Do not blast without obtaining written approval from the RE.

503.04  Measurement and Payment

The Department will measure and make payment for Items as follows:

Item	Pay Unit

FURNISHING DRILLED SHAFT EQUIPMENT	lump sum

Demonstration Drilled Shaft	Linear FOOT

LOAD TEST	unit

CROSSHOLE SONIC LOGGING	UNIT

Tomography	Unit

SHAFT CORING	linear FOOT

drilled shaft in soil ___" Diameter	linear Foot

drilled shaft in rock ___" Diameter	linear FOOT

OBSTRUCTION REMOVAL	linear FOOT

The Department will make payment for each load test completed and accepted.

The Department will not include payment for tomography under CROSSHOLE SONIC LOGGING.  If the RE directs Tomography, the Department will make payment for the number of 3-D evaluations performed and accepted under TOMOGRAPHY.

The Department will make payment under SHAFT CORING if the drilled core confirms that the shaft is acceptable.  The Department will not make payment for SHAFT CORING if the core confirms that there is a defect.

The Department will make payment for 60 percent of the lump sum price bid for furnishing drilled shaft equipment when the equipment necessary for drilling shafts is furnished and drilling of shafts has begun.  The Department will make payment for the remaining 40 percent when all shafts have been drilled and all shaft concrete has been placed to the top of the shafts.

The Department will not make payment for sampling and analysis for regulated waste under DEMONSTRATION DRILLED SHAFT, DRILLED SHAFT IN SOIL or DRILLED SHAFT IN ROCK.

The Department will make payment for sampling and analysis for regulated waste, including solids from dewatered slurry, under Soil Sampling and analyses, regulated as specified in 202.04.

The Department will not make payment for off-site transport and disposal and recycling of regulated waste or hazardous waste, including solids from dewatered slurry, under DEMONSTRATION DRILLED SHAFT, DRILLED SHAFT IN SOIL or DRILLED SHAFT IN ROCK.  The Department will make payment for off-site transport and disposal and recycling of regulated waste or hazardous waste, including solids from dewatered slurry, under Disposal of Regulated Material or Disposal of Regulated Material, Hazardous as specified in 202.04.

The Department will not include payment for removal of obstructions under DRILLED SHAFT IN SOIL.  If an obstruction is encountered, the Department will make payment for removal of the obstruction under OBSTRUCTION REMOVAL.

1**************************************************************************************************************************1

Section 504 – Structural Concrete

504.02.01  Materials

1**************************************************************************************************************************1

BDC15s-01 dated mar 26, 2015

the following material reference is changed to:

Grit for Epoxy Waterproofing	901.07.01

1**************************************************************************************************************************1

504.03.02  Constructing Concrete

1**************************************************************************************************************************1

D.	Placing and Consolidating Concrete.

2**************************************************************************************2

BDC15s-03 dated APR 22, 2015

THE first SENTENCE OF THE Fifth PARAGRAPH is deleted

2**************************************************************************************2

G.	Removal of Forms and Falsework.

2**************************************************************************************2

Complete and include the following if concrete strength required for the removal of forms and false work

sme contact – Structural Engineering

Do not remove forms and false work until the concrete obtains a compressive strength of ____ psi.

2**************************************************************************************2

1**************************************************************************************************************************1

Section 505 – Precast and Prestressed Structural Concrete

505.03.01  Prestressed Concrete Structures

1**************************************************************************************************************************1

BDC11s-03 dated Nov 15, 2011

C.	Erection Plan.

The first sentence is changed to:

Submit working drawings for certification regarding the plan of operations to the RE at least 30 days before the pre-erection meeting.

1**************************************************************************************************************************1

Section 506 – Structural Steel

506.03.01  Structural Steel

1**************************************************************************************************************************1

B.	Erection Plan.

2**************************************************************************************2

BDC11s-03 dated Nov 15, 2011

the entire text is changed to:

At least 30 days before the pre-erection meeting, submit working drawings for certification regarding the plan of operations to the RE.  Include, at a minimum, the following in the plan:

1.	Number and type of manpower and equipment.

2.	Shipping procedures.

3.	Lifting procedures.

4.	Beam erecting sequence, including method of setting bearings and diaphragms.

5.	Temporary bracing.

6.	Manufacturer’s recommendations.

7.	Procedures for employee safety.

8.	Traffic control and protection.

2**************************************************************************************2

E.	Installing High-Strength Steel Bolts.

2**************************************************************************************2

BDC11s-03 dated Nov 15, 2011

the entire text is changed to:

Check galvanized bolts and nuts to verify that a visible lubricant is on the threads.  Check black bolts and nuts to verify that they are oily to the touch.

Before beginning bolt installation, provide on the project site a Skidmore-Wilhelm calibrator or an acceptable equivalent tension measuring device.  Ensure that the manufacturer’s representative is present during the first full day of tensioning work to provide technical assistance.

Test assemblies as follows:

1.	For bolt assemblies that do not require Direct Tension Indicators (DTI’s), perform the rotational capacity test in accordance with 908.02.02.C, on 2 assemblies from each rotational-capacity lot.

2.	For bolt assemblies requiring DTI’s, install in accordance with the following, and perform the rotational-capacity test as specified in NJDOT S-3 on 3 assemblies from each rotational-capacity lot.

Ensure that the bolt, nut, and washer are from the same rotational-capacity lot.  If the DTI is used under the nut, place an additional washer between the nut and the protrusions on the DTI.  If recommended by the bolt manufacturer, the Contractor may use wax lubricant, beeswax, or a water wax emulsion to aid in installation.  Hold the bolt head stationary while tightening the nut.

Install bolts in all of the holes of the connection and tighten to a snug-tight condition to compact the joint.  Ensure that the number of spaces on DTIs in which a 0.005-inch feeler gauge is refused after snugging does not exceed the maximum snug-tight refusals as specified in Table 506.03.01-1.  If the number of refusals exceeds the maximum, remove the assembly, insert a new DTI, and resnug.

Tighten the assemblies successively from the most rigid part of the connection to the free edges by turning the nuts while holding the bolts stationary.  Tension the assemblies until the number of spaces in which the 0.005-inch thickness gauge is refused meets or exceeds the minimum final tension refusals specified in Table 506.03.01-1.

| Table 506.03.01-1 Criteria for DTI Spaces for A 325 Bolts |
| --- |
| Bolt Diameter, Inches | 1/2 | 5/8 | 3/4 | 7/8 | 1 | 1-1/8 | 1-1/4 | 1-3/8 |  | 1-1/2 |
| Number of Spaces on DTIs | 4 | 4 | 5 | 5 | 6 | 6 | 7 | 7 | 8 |
| Maximum Snug Tight Refusals1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 |
| Minimum Final Tension Refusals2 | 2 | 2 | 3 | 3 | 3 | 3 | 5 | 6 | 7 |
| 1. If the DTI is coated and under the nut, the maximum snug tight refusals is the number of spaces on the DTI minus one. 2. If the DTI is coated and under the nut, the minimum final tension refusals is the number of spaces on the DTI. |  |

If an assembly is tightened so that there are no visible gaps remaining in any of the spaces on the DTI, the assembly has been over-tightened.  Remove and replace over-tightened assemblies.

If assemblies do not meet the above rotational capacity requirements when tested at the work site, the Contractor may clean and relubricate the bolt assemblies in the rotational-capacity lot.  After cleaning and relubricating, retest the assemblies for compliance to the above rotational capacity requirements.

For painted steel, apply 3 coats of an organic paint system, supplied by the same manufacturer as the originally applied inorganic zinc system, to the field bolted connections.

2**************************************************************************************2

1**************************************************************************************************************************1

506.03.02  Bearings

C.	Installing Bearings.  Install bearings as follows:

1**************************************************************************************************************************1

BDC11s-03 dated Nov 15, 2011

1.	Anchor Bolts.

THE second SENTENCE OF THE FIRST PARAGRAPH IS CHANGED TO:

If using anchor bolt sleeves, ensure that they are circumferentially corrugated and are galvanized steel or plastic.

1**************************************************************************************************************************1

506.03.03 Shear Connectors

1**************************************************************************************************************************1

BDC12s-14 dated NOV 21, 2012

THE first PARAGRAPH is CHANGED TO:

Ensure that shear connectors conform to Section 7 of the ANSI/AWS D1.5 Bridge Welding Code.

1**************************************************************************************************************************1

506.03.06  Repair Galvanizing

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

THE last SENTENCE OF THE second PARAGRAPH IS CHANGED TO:

If painting is directed, treat the galvanized surface according to the manufacturer’s recommendations, then apply the epoxy intermediate and urethane finish coats only.

1**************************************************************************************************************************1

506.04  Measurement and Payment

1**************************************************************************************************************************1

BDC12s-14 dated NOV 21, 2012

THE FOLLOWING ITEM is deleted:

Item	Pay Unit

SHEAR CONNECTOR, GALVANIZED	UNIT

1**************************************************************************************************************************1

Section 507 – Concrete Bridge Deck and Approaches

1**************************************************************************************************************************1

BDC14s-05 dated Oct 28, 2015

This section is renamed to:

Section 507 – Concrete Bridge Deck, BRIDGE PARAPET and Approaches

1**************************************************************************************************************************1

507.02.01  Materials

1**************************************************************************************************************************1

BDC14s-05 dated Oct 28, 2015

the following is deleted from materials list:

4-Bar Open Steel Parapet	906.07

the following are added to materials list:

Steel Bar Bridge Railing	906.07

Anchor Bolts………………………………………………………………………………………...........….908.01.03

1**************************************************************************************************************************1

507.03.02  Constructing Bridge Decks

A.	Forms.  Construct forms as follows:

2.	Removable Forms.

1**************************************************************************************************************************1

BDC11s-03 dated Nov 15, 2011

This part is changed to:

Construct removable forms as specified in 504.03.02.B.  Do not use shoring to support stringers along the span length where the superstructure, under live load and impact loads, is designed for composite action.  Do not weld attachments required for placement of the removable forms to the beam.

1**************************************************************************************************************************1

L.	Saw Cut Grooved Surfacing.

1**************************************************************************************************************************1

BDC11s-03 dated Nov 15, 2011

The following is added to the first paragraph:

Do not saw cut until after the Department performs Acceptance Testing as specified in Subsection 507.03.02 N.

1**************************************************************************************************************************1

N.	Concrete Deck Surface Requirements

1.	Acceptance Testing.

1**************************************************************************************************************************1

BDC11s-03 dated Nov 15, 2011

The first paragraph is changed to:

Construct deck slabs so that less than 9 percent of the measured length of the lot exceeds 1/8 inch tolerance in 10 feet.  The ME will test the surface of concrete bridge deck slabs with a Class I Walking Profiler prior to the performance of saw cut grooved surfacing. The ME will calculate the percent defective using a rolling straight edge simulator analysis of the profiler data.

1**************************************************************************************************************************1

507.03.05  Concrete Parapet and Barrier Curb

1**************************************************************************************************************************1

BDC10s-09 dated sep 10, 2010

THE SECOND PARAGRAPH is CHANGED TO:

Cure using curing compound as specified 504.03.02.F.  If drilling is required for subsequent construction, allow the concrete to cure for a minimum of 14 days before drilling.

1**************************************************************************************************************************1

507.03.06  4-Bar Open Steel Parapet

1**************************************************************************************************************************1

BDC14s-05 dated Oct 28, 2015

subpart is renamed and changed to:

507.03.06  Steel Bar Bridge Railing

Ensure that the deck has cured for at least 14 days before placing concrete for steel bar bridge railing. Place concrete as specified in 504.03.02.D.  Install as shown on the Plans.  Construct anchor bolt system as specified in 509.03.01-1.

1**************************************************************************************************************************1

507.03.07  Concrete Bridge Approach

THE FOLLOWING IS ADDED:

Ensure the concrete conforms to the surface requirements as specified in 507.03.02 N, except each lot will be equal to the number of cubic yards of approach concrete placed in the lane.

507.04  Measurement and Payment

1**************************************************************************************************************************1

2**************************************************************************************2

BDC14s-05 dated Oct 28, 2015

THE FOLLOWING ITEM is deleted:

4-BAR OPEN STEEL Parapet	LINEAR FOOT

THE FOLLOWING ITEM is ADDed:

Steel ___Bar BRIDGE RAILING	LINEAR FOOT

2**************************************************************************************2

2**************************************************************************************2

BDC10s-01 dated Mar 29, 2010

THE second paragraph is changed to:

The Department will include payment for epoxy coated reinforcement steel for the bridge approach under the item CONCRETE BRIDGE APPROACH; for other concrete items, the Department will make payment for reinforcement steel under REINFORCEMENT STEEL, REINFORCEMENT STEEL, EPOXY-COATED, and REINFORCEMENT STEEL, GALVANIZED as specified in 504.04.

2**************************************************************************************2

2**************************************************************************************2

THE FOLLOWING IS ADDED:

The Department will make a payment adjustment for concrete surface requirement quality in deck slabs and approach, by the following formula:

Pay Adjustment = Q x  BP x PR

Where:

BP = Bid Price

Q= Surface Requirement Lot Quantity

PR= percent reduction as specified in Table 507.03.02-2

2**************************************************************************************2

1**************************************************************************************************************************1

Section 508 – Bridge Drainage

508.02  Materials

1**************************************************************************************************************************1

BDC09s-11 dated Jan 26, 2010

the following is added to list of materials:

Fiberglass Pipe	909.02.09

1**************************************************************************************************************************1

1**************************************************************************************************************************1

BDC09s-11 dated Jan 26, 2010

THE FOLLOWING subpart IS ADDED:

508.03.03  Fiberglass Pipe and Fittings

Ensure that pipe supports are located at spacings that do not exceed the pipe manufacturer’s recommendations.  Avoid supports that have point contact or narrow supporting areas.  Standard sling, clamp, and clevis hangers and shoe supports designed for use with steel pipe may be used. Ensure that the minimum strap width of all pipe hangers meets the pipe manufacturer’s recommendations. Ensure that straps have a minimum of 120 degrees of contact with the pipe.  On pipe supported on surface with less than 120 degrees of contact use a split fiberglass pipe protective sleeve bonded in place with adhesive.

Ensure that all connections of pipes and fittings shown on the plans to facilitate future removal for maintenance cleanout or flushing are made with a threaded, gasketed coupler or a bolted gasketed flange system.  Use only female – male threaded plugs for cleanouts.

1**************************************************************************************************************************1

508.04  Measurement and Payment

1**************************************************************************************************************************1

BDC09s-11 dated Jan 26, 2010

the following item is added:

Item	Pay Unit

___" FIBERGLASS PIPE	LINEAR FOOT

1**************************************************************************************************************************1

Section 509 – Bridge Railing and Fence

1**************************************************************************************************************************1

BDC14s-05 dated Oct 28, 2015

This section is renamed to:

Section 509 – Bridge COMBINATION Railing, MISCELLANEOUS RAILINGS and Fence

1**************************************************************************************************************************1

509.01  Description

1**************************************************************************************************************************1

BDC14s-05 dated Oct 28, 2015

THE ENTIRE subsection IS CHANGED TO:

This Section describes the requirements for constructing metal railing, fence, and guide rail on bridges. Metal railing includes metal railing components for combination traffic railing system, combination non-traffic railing system, non-traffic pedestrian or bicycle railing, ornamental railing and other railing not subject to vehicular impact.

1**************************************************************************************************************************1

509.03.01  Bridge Railing

1**************************************************************************************************************************1

2**************************************************************************************2

BDC14s-05 dated Oct 28, 2015

THE third paragraph is changed to without parts 1 & 2:

Ensure that the railing is fabricated to allow for minor adjustments in both horizontal and vertical directions.  Install 1 or 2-rail aluminum or steel railing on top of the concrete parapet as shown on the Plans. Install other types of metal railing on concrete sidewalk or deck as shown on the Plans.  Do not use expansion type anchor bolts.

2**************************************************************************************2

2**************************************************************************************2

BDC10s-09 dated sep 10, 2010

The third paragraph Subpart 2 is changed to:

2.	Adhesive Type.  Do not drill for installation until the concrete has cured for at least 14 days.  Install adhesive anchors according to the manufacturer’s recommendations.  When drilling, ensure that spalling does not occur and existing utilities are not damaged.  Repair damage to the existing concrete, utilities, and reinforcement steel as a result of drilling.  Clean and dry drill holes before and during installation of the adhesive anchors.

2**************************************************************************************2

1**************************************************************************************************************************1

509.03.02  Chain-Link Fence for Bridge

1**************************************************************************************************************************1

BDC11s-03 dated Nov 15, 2011

the entire subpart is changed to:

At least 30 days before beginning the work, submit working drawings for certification.  Indicate material specifications for adhesive, anchors, washers, and nuts on the working drawings.

Base the design embedment of the adhesive anchor bolts on a concrete compressive strength of 4000 pounds per square inch.  Ensure that the embedment depth of the adhesive anchors shown on the working drawings is sufficient to obtain the required pullout strength as required for the proof load testing as specified in 908.01.04.

Do not use expansion type anchor bolts.  Place anchors using one of the following:

1.	Cast-in-Place Type.  Set anchor bolts before placing concrete using a rigid template for each anchor assembly.  When placing concrete, ensure that bolts do not move and spacing is maintained between the rigid templates.  Ensure that the exposed threaded ends of the anchor bolts remain clean and protected from concrete.  Clean the anchor bolts before installing the specified hardware.

2.	Adhesive Type.  Do not drill for installation until the concrete has cured for at least 14 days.  Install adhesive anchors according to the manufacturer’s recommendations.  When drilling, ensure that spalling does not occur and existing utilities are not damaged.  Repair damage to the existing concrete, utilities, and reinforcement steel as a result of drilling.  Clean and dry drill holes before and during installation of the adhesive anchors.

Erect fencing as shown on the Plans.

1**************************************************************************************************************************1

509.04  MEASUREMENT AND PAYMENT

1**************************************************************************************************************************1

BDC12s-08 dated DEC 17, 2012

and

BDC14s-05 dated Oct 28, 2015

THE entire subsection is changed to:

The Department will measure and make payment for Items as follows:

Item	Pay Unit

bridge COMBINATION railing (___rail, aluminum)	Linear foot

bridge COMBINATION railing (___rail, steel)	Linear foot

chain-link fence, type I, zinc-coated steel, bridge, __'__" high	linear foot

chain-link fence, type II, Aluminum-coated steel, bridge, __'__" high	linear foot

chain-link fence, type III, Aluminum alloy, bridge, __'__" high	linear foot

chain-link fence, type IV, PVC-Coated steel, bridge, __'__" high	linear foot

chain-link fence, type I, zinc-coated steel, bridge, __'__" high, curved top	linear foot

chain-link fence, type II, Aluminum-coated steel, bridge, __'__" high, curved top	linear foot

chain-link fence, type III, Aluminum alloy, bridge, __'__" high, curved top	linear foot

chain-link fence, type IV, PVC-Coated steel, bridge, __'__" high, curved top	linear foot

1**************************************************************************************************************************1

Section 510 – Timber Structures

510.03.02  Sheeting and Wales

1**************************************************************************************************************************1

include the corrosion requirements for metal components, if NECESSARY

sme contact – Structural Engineering

1**************************************************************************************************************************1

510.04  Method of Measurement

This subsection Heading is changed to:

510.04  Measurement and Payment

Section 511 – Bulkhead, Fender, and Dolphin Systems

511.02.01  Materials

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

14 th on the list is changed to:

Fiberglass Reinforced Plastic Lumber (FRPL)	916.01

1**************************************************************************************************************************1

511.03.01 Bulkhead, Fender, and Dolphin Systems

C.	Coating Steel

1**************************************************************************************************************************1

BDC15s-06 dated jul 30, 2015

The second paragraph part 1 is changed to:

- Immediately after blast cleaning, apply 2 coats of coal tar epoxy paint at a maximum coverage rate of 125 square feet per gallon. Ensure that the total dry film thickness of the 2 coats is not less than 16 mils at any point. Apply the coating by brush, roller, or spray. The Contractor may thin the first coat with a maximum of 10 percent of solvent according to the coating manufacturer; however, the Contractor may not thin the second coat. Allow the first coat to thoroughly dry before applying the second coat. Allow the second coat to dry and harden before handling the steel.

1**************************************************************************************************************************1

Section 512 – Sign Support Structures

512.04  Measurement and Payment

1**************************************************************************************************************************1

BDC10s-08 dated dec 29, 2010

2**************************************************************************************2

INCLUDE THE FOLLOWING WHEN SUPPORT STRUCTURES FOR DYNAMIC MESSAGE SIGN (DMS) (other than ground mounted dms) ARE PROPOSED.

The following itemS ARE added:

Item	Pay Unit

Cantilever Sign Support, DMS Structure No. ____	Unit.

Butterfly Sign Support, DMS Structure No. ____	Unit.

2**************************************************************************************2

2**************************************************************************************2

INCLUDE THE FOLLOWING WHEN DRILLED SHAFT FOUNDATION IS proposED.

THE FOLLOWING IS ADDED:

The Department will make payment for drilled shaft foundations for sign supports under DRILLED SHAFT FOR SIGN STRUCTURE FOUNDATION as specified in 51X.04.

2**************************************************************************************2

1**************************************************************************************************************************1

Section 513 – Retaining Walls

513.02.01  Materials

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

The following is added:

For MSE Walls, use either Soil Aggregate, I-15 or Coarse Aggregate, No. 57. For Prefabricated Modular Retaining Walls and T-Wall, use either Soil Aggregate, I-9 or Coarse Aggregate, No. 57.

1**************************************************************************************************************************1

513.03.01  Proprietary Retaining Walls

F.	Backfilling.

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

the heading and first PARAGRAPH under subpart (1) are changed to:

1.	Soil Aggregate.

1**************************************************************************************************************************1

G.	Compacting.

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

the heading and first PARAGRAPH under subpart (1) are changed to:

1.	Soil Aggregate.  With the exception of the 5-foot zone directly behind the units, compact soil aggregate with large, smooth drum, vibratory rollers using the density control method as specified in 203.03.02.D.

1**************************************************************************************************************************1

513.04  Measurement and Payment

THE FOLLOWING IS ADDED AFTER THE FIRST PARAGRAPH:

The Department will make payment for reinforcement steel under REINFORCEMENT STEEL, and REINFORCEMENT STEEL, EPOXY-COATED as specified in 504.04 for reinforcement steel in cast-in-place retaining walls.

1**************************************************************************************************************************1

include the following upon ASSIGNING an APPROPRIATE SECTION/SUBSECTION/subpart NUMBERs if DRILLED SHAFT foundations FOR SIGN SUPPORT STRUCTURES is necessary

sme contact – Structural Engineering

The following section is added:

SECTION 51x - DRILLED SHAFT foundations FOR SIGN SUPPORT STRUCTURES

51x.01  DESCRIPTION

This work describes the requirements for installing drilled shafts for sign support structures.

51x.02  MATERIALS

51X.02.01  Materials

Provide materials as specified:

Concrete	903.03

Self Consolidating Concrete	903.06.01

Grout	903.08.02

Reinforcement Steel	905.01.01

Drilled Shaft Casing	906.03

Structural Steel Paint (Organic Zinc)	912.01.01

Water	919.08

Provide clay-mineral based slurry (processed attapulgite or bentonite) for mineral slurry.  Ensure that the mineral slurry has a mineral grain size that will remain in suspension and has sufficient viscosity and gel characteristics to transport excavated material to a suitable screening system.  Ensure that the percentage and specific gravity of the material used to make the mineral suspension is sufficient to maintain the stability of the excavation and to allow proper concrete placement.

Provide polymer slurry as recommended by the manufacturer.

51X.02.02  Equipment.

Provide equipment as specified:

Concrete Batching Plant	1010.01

Concrete Trucks	1010.02

Ensure that equipment does not introduce uncontrolled exhaust fumes into the surrounding areas, or other occupied areas adjacent to the work site.  Crane and drilling engine exhaust fumes will require their own separate exhaust systems adequately vented to the atmosphere away from any confined work sites.

Ensure that equipment used for final bottom cleaning does not have a centralizing guide at the tip.

Use excavation and drilling equipment having adequate capacity, including power, torque, and down thrust to excavate a hole of both the maximum specified diameter and to a depth of 20 percent beyond the depths shown on the plans when operated at rated capacity.

Provide Crosshole Sonic Logging (CSL) test equipment that includes the following components:

1.	A microprocessor-based CSL system for display of individual CSL records, analog-digital conversion and recording of CSL data, analysis of receiver responses, and printing of CSL logs.

2.	Ultrasonic source and receiver probes for 1.5-or 2-inch inner diameter pipe, as appropriate.

3.	An ultrasonic voltage pulser to excite the source with a synchronized triggering system to start the recording system.

4.	A depth measurement device to determine and record depths.

5.	Appropriate filter/amplification and cable systems for CSL testing.

51X.03  CONSTRUCTION

51X.03.01  Working Drawings and Calculations.

Submit six (6) copies of the following items to the RE for approval:

1.	A summary of the Contractor’s or his specialized drilled shaft Subcontractor's experience on projects of a similar nature and scope.  Select and obtain approval from the RE for the use of a specialty subcontractor.  Approval will be based on qualifications and previous experience on similar projects.

2.	List and size of proposed equipment including cranes, drills, augers, bailing buckets, final cleaning equipment, desanding equipment, slurry pumps, concrete pumps, temporary steel casing, slurry sampling and testing equipment.

3.	Details of equipment and procedures for drilled shaft installation, including drawings showing consecutive steps of drilled shaft installation and drawings with measurements showing that the proposed equipment can perform the specified work.  Identify in the drawings the areas that are planned to be used for staging the work.  Specify the proposed sequence of the drilled shaft installation including details of concrete placement and splicing and centering devices for reinforcement steel.

4.	Approval for the concrete mix design that is to be used for the work.

5.	Slurry details including proposed methods of mixing, placing and circulating.

6.	Details of shaft excavation methods.

7.	Details of proposed methods to clean the shaft after initial excavation.

8.	Procedures for control and removal of spoils.

9.	Details of shaft reinforcement steel, including methods to ensure centering, required cover, cage integrity during placement, placement procedures and cage support.

10.	Details of concrete placement including proposed operational procedures for concrete pump or tremie including initial placement, raising during placement, overfilling of the shaft concrete and provisions to prepare the completed shaft top at its final shaft top elevation.

51X.03.02  Shaft Drilling.

Perform the excavations required for the shafts through whatever materials are encountered, to the dimensions and elevations shown in the plans or otherwise required by these specifications.  Ensure that the equipment is capable of constructing shafts to a depth equal to the deepest shaft shown in the plans plus 15 feet or three times the shaft diameter, whichever is greater.

Provide, for all drilled shafts, an approved fixed template that is adequate to maintain the shaft position and alignment during all excavation and concreting operations.

Install a suitable temporary casing for the full depth of the drilled shaft.  Ensure that all drilled shafts meet construction tolerance criteria and are installed in accordance with the dimensions as shown on the plans, or as directed by the RE.

Ensure that the top center of each drilled shaft does not vary from the plan location by more than 3 inches.  At the top of the drilled shaft, ensure that reinforcement steel does not vary in plan distance from the plan shaft by more than 1 inch.  Ensure that the drilled shaft does not vary from the vertical by more than one percent of its length, as measured above ground and is not out of the required position at the top by more than 3 inches.

Protect any existing utility that is to remain within the drilled shaft installation work zone in accordance with the requirements of authorities having jurisdiction over same.  Repair or replace any construction-induced damage to the satisfaction of the governing authority.

Employ within the contract bid price, a licensed registered Land Surveyor, experienced in the type of work, who will establish lines and grades.  Assume responsibility for the correct location of drilled shafts and for keeping a record of drilled shafts that are installed.

Locate the drilled shaft locations and provide a stake out of the locations prior to the start of installation work.  Maintain all location stakes along with required elevation designations.

51X.03.03  Shaft Concrete.

Ensure that the handling, measuring, proportioning, mixing and placing of concrete conforms to these Specifications.  Place concrete only in the presence of the RE.

Place concrete by using concrete pumps or a tremie pipe from the bottom of the excavation upward so as to avoid segregation.  Do not inject air, water or slurry into the shaft concrete during placement.  Use a disposable foam or rubber plug in the concrete pump line or tremie pipe to separate the fresh concrete from the slurry at the start of concrete placement.  Insert the plug so that the first flow of concrete pushes the plug out of the pipe and prevents slurry mixing and contamination as the concrete placement commences.  Ensure that the concrete pump line or tremie consists of a tube constructed in sections that have flanged couplings fitted with gaskets.  Ensure the means of supporting the concrete pump line or tremie so as to permit free movement of the discharge end over the entire top of the concrete and to permit its being lowered rapidly when necessary to choke off or retard the flow.  If used, fill the tremie by a method that prevents washing of the concrete.  Submerge the discharge end completely in the concrete at all times after initiation of the concrete placement flow.  Ensure that the concrete line contains sufficient concrete to prevent any water entry.  Maintain the concrete level at the top of the drilled shaft until the concrete has set.

If concrete flow is halted and the concrete line’s discharge end is for any reason raised out of the shaft concrete, reinitiate the placement only after fully recharging the concrete line with fresh concrete by

1.	Inserting a foam or rubber plug or pig into the concrete line at the concrete hopper end,

2.	Placing the discharge end approximately 6 inches above the top of the shaft concrete,

3.	Recharging the pump or tremie line and depositing what will be classified as waste concrete on the top of the previously placed concrete,

4.	Discharging waste concrete until the line is fully recharged with fresh concrete and the pig is pushed completely through the line,

5.	Without halting the flow of fresh concrete plunging the discharge end of the concrete line into the shaft concrete to within 6 inches or less of the shaft bottom or to a level as directed by the RE,

6.	Continuing the concrete placement without further interruption, and

7.	Placing a final volume of additional concrete in the shaft that is no less than the volume of waste concrete placed to recharge the line in the process of resuming the concrete flow.

Apply this procedure without exception as necessary to avoid injecting any air, any water, any slurry, or any concrete that has flowed through a line filled with air, water, or slurry into the shaft concrete.

Do not initiate boring a new shaft hole that is within five drilled shaft diameters of a previously installed drilled shaft, until the concrete has been in place for a minimum of 2 days.

51X.03.04  Shaft Construction Timing.

Make every effort to plan, coordinate and carry out the work to minimize the time between the start of excavation and completion of shaft concrete placement.  In general, the time between shaft excavation and completion of concrete placement is expected to be eight (8) continuous hours or less.

For cases where two (2) or more continuous hours elapse between completion of excavation and commencement of concrete placement, remove any reinforcement steel already placed in the shaft, clean the shaft bottom, replace the reinforcement steel in the shaft and immediately commence the placement of the concrete.

51X.03.05  Shaft Reinforcement Steel.

Where shafts are extended at the direction of the RE to final authorized tip elevations that are lower than the estimated minimum tip elevations, extend no fewer than one-half of the vertical reinforcement steel (every other bar around the circumference) to the authorized tip elevation by lap splicing or mechanical splicing.  Firmly tie lap splices so as to support the full weight of the cage above the lap zone.  Add horizontal bands in the bottom extension zone at a vertical spacing that is no more than 6 inches center to center.

51X.03.06  Shaft Top Preparation.

If tremie concrete is used, consider the top-most concrete placed in the shaft to be waste concrete and either:

1.	Completely eject out of the top of the casing the wasted concrete or,

2.	Pump the waste upward to a level that is at least 2 feet clear distance above the plan shaft top level and allow it to cure in place for removal later.

Consider waste concrete to be the top 2 feet of initial concrete that is placed, plus

1.	The height of any additional volume of waste concrete deposited in the shaft where concrete placement was halted and restarted, plus

2.	Any additional amount necessary to produce full strength non-segregated concrete at the plan shaft top level.

Where the above waste concrete alternative 1 is selected, permit the waste concrete to evenly overflow the full top circumference of the casing.  Do not channel or bleed off by notches or holes cut in the casing top.  Any fresh concrete in the casing at a level above the plan shaft top level after ejecting all waste concrete may be dipped or pumped out to the plan top elevation while still plastic by methods and equipment approved by the RE, or be allowed to cure in place for removal later.

Final shaft top preparation may commence only after the drilled shaft concrete obtains its verification strength.  In lieu of concrete strength testing, the preparation may begin seven (7) full days after completion of concrete placement.  Final top preparation steps will consist of:

1.	Cutting off any extra casing above the top of casing elevation,

2.	Cutting off any cured over pour concrete to the plan shaft top elevation by approved methods,

3.	Dressing the final shaft top surface,

4.	Verification by the RE that the exposed concrete consists of full strength concrete with a typical, non-segregated mortar and aggregate distribution,

5.	Approved non-destructive strength testing by the Contractor where required by the RE to verify that concrete has attained its full design strength,

6.	Removal of additional concrete below the plan shaft top level as necessary to reach full-strength, non-segregated concrete, and

7.	Preparation of the shaft top key recess.

51X.03.7  Shaft Acceptance.

Provide a comparison of the computed volume of the excavation (theoretical) with the volume of concrete actually placed.  Plot depth versus volume chart.  Provide cooperation and whatever assistance necessary to accurately monitor the volume of concrete that is placed at all times during the pour.

Unaccepted drilled shafts are drilled shafts that are rejected by the RE because of damage, failure to advance through obstructions, mislocation, misalignment or failure to install the drilled shaft to the proper bearing stratum.  Submit a written plan of action to the RE for approval showing how to correct any problem and how to prevent a reoccurrence.  Repair the drilled shaft or replace it to the satisfaction of the RE.  To mitigate and/or to remedy unaccepted drilled shafts, the Contractor may be required to provide additional drilled shafts or supplement drilled shafts to meet specified requirements at no cost to the State.

When acceptably installed drilled shafts exceed specified tolerances, provide an accurate as-built survey.  If the load on any drilled shaft exceeds 10 percent of the specified load capacity, make as directed corrections.

51X.04  Measurement and Payment

The Department will measure and make payment as follows:

Item	Pay Unit

DRILLED SHAFT FOR SIGN STRUCTURE FOUNDATION	LINEAR FOOT

1**************************************************************************************************************************1

Division 550 – Structure Rehabilitation

Section 554 – Painting Existing Bridges

554.04  Measurement and Payment

1**************************************************************************************************************************1

BDC11s-03 dated Nov 15, 2011

THE second PARAGRAPH is CHANGED TO:

The Department will base payment for Testing, If and Where Directed on the actual cost as evidenced by paid receipts from the testing laboratory.

1**************************************************************************************************************************1

Division 600 – Miscellaneous Construction

Section 601 – Pipe

601.04  Measurement and Payment

1**************************************************************************************************************************1

BDC12s-11 dated SEP 28, 2012

THE FOLLOWING IS ADDED:

The Department will make payment for restoring the pavement structure for trenches in the traveled way and shoulder under various Items of the Contract.

1**************************************************************************************************************************1

Section 606 – Sidewalks, Driveways, and Islands

606.03.02  Concrete Sidewalks, Driveways, and Islands

1**************************************************************************************************************************1

F.	Placing Concrete.

2**************************************************************************************2

BDC15s-06 dated jul 30, 2015

THE entire part F. is changed to:

Obtain RE approval of forms and joint placement before placing concrete.  Place concrete according to the limitations specified in 504.03.02.C.  To place concrete between November 1 and March 15, submit to RE for approval a plan detailing the method of protecting the concrete from salt for at least 30 days after placing. Do not begin placing concrete until this plan is approved.  Place concrete across the formed area to minimize rehandling.  Ensure that concrete is not discharged into windrows or piles.  Continuously place concrete between transverse joints without the use of intermediate bulkheads.  To prevent bowing or misalignment of the transverse joints, place concrete simultaneously on both sides of transverse joints without disturbing the joints.  Consolidate the concrete by hand spading or using internal mechanical vibrators.  If a slab is not completed from transverse joint to transverse joint, remove the incomplete slab and replace.  Terminate each day’s placement at a transverse joint.  If concrete becomes segregated during placement, cease operations and correct handling operations.  Protect concrete as specified in 504.03.02.I.

2**************************************************************************************2

H.	Protection and Curing.

2**************************************************************************************2

BDC08s-02 dated Feb 17, 2009

THE last SENTENCE IS CHANGED TO:

Ensure vehicles and other loads are not placed on sidewalks, islands, and driveways until the concrete has attained compressive strength of 3000 pounds per square inch, as determined from 2 concrete cylinders field cured according to AASHTO T 23.

2**************************************************************************************2

1**************************************************************************************************************************1

Section 607 – Curb

607.03.01  Concrete Barrier Curb

D.	Placing Concrete.

1**************************************************************************************************************************1

dated Apr 16 2010

THE third SENTENCE OF THE FIRST PARAGRAPH IS CHANGED TO:

To place concrete between November 1 to March 15, submit to RE for approval a plan detailing the method of protecting the concrete from salt for at least 30 days after placing.

1**************************************************************************************************************************1

607.03.02  Concrete Vertical Curb and Concrete Sloping Curb

D.	Placing Concrete.

1**************************************************************************************************************************1

BDC11s-06 dated Jul 11, 2011

the entire text is changed to:

Place concrete for vertical curb and sloping curb as specified in 607.03.01.D, except that consolidation may be achieved by hand spading or internal mechanical vibrators.

1**************************************************************************************************************************1

607.03.04  Concrete Vertical Curb and Concrete Sloping Curb, Dowelled

D.	Placing Concrete.

1**************************************************************************************************************************1

BDC11s-06 dated Jul 11, 2011

the entire text is changed to:

Place concrete for vertical and sloping curb as specified in 607.03.02.D.

1**************************************************************************************************************************1

1**************************************************************************************************************************1

BDC10s-02 dated Oct 14, 2010

section 608 – non-vegetative surfaces

the entire section is changed to:

608.01  DESCRIPTION

This Section describes the requirements for constructing non-vegetative surfaces of HMA; color-coated HMA; porous HMA; broken stone, and polyester matting.

608.02  MATERIALS

608.02.01  Materials

1**************************************************************************************************************************1

dated May 25, 2011

Provide materials as specified:

Broken Stone, Coarse Aggregate No. 3………………………	…………………………………..901.03

HMA (9.5M64)……………………………………………………	……………………………...902.02

Asphalt-Stabilized Drainage Course………………………………	………………..…………….902.06

Non-Vegetative Surface Coating………………………………	……………………………...912.02.04

Herbicide………………………………………………………	………………………………917.11.03

Polyester Matting………………………….…………………	……………………………….…..919.15

Provide Non-Vegetative Surface, Porous HMA conforming to the requirements of Asphalt-Stabilized Drainage Course.

1**************************************************************************************************************************1

608.02.02  Equipment

Provide equipment as specified:

HMA Compactor………………………………………………	………………………………..1003.05

Vibratory Drum Compactor…………………………………	…………………………………..1003.06

HMA Plant………………………………………………………	………………………………1009.01

HMA Trucks……………………………………………………	…………………………….....1009.02

608.03  CONSTRUCTION

608.03.01  Non-Vegetative Surface, HMA

Excavate as specified in 202.03.03.  Shape and compact the underlying material to produce a firm, even surface.  Obtain RE approval before finishing excavation.  If the RE determines that the bottom of the excavation is unstable, undercut, backfill, and compact as directed by the RE.

Construct the non-vegetative surface, HMA before installing guide rail.  Obtain RE approval for alternate methods of construction.

Deliver HMA as specified in 401.03.03.D.  Construct non-vegetative surfaces 4 inches thick.  Place and compact the material to produce a surface free of roller marks and ridges.  Spread and grade the HMA as specified in 401.03.03.E.  Ensure that the finished surface is smooth, even, and graded to drain away from the guide rail.  Compact HMA as specified in 401.03.03.F.  Spread, rake, and lute areas not accessible to pavers and rollers with hand tools and compact with dynamic compactors.

Repair non-vegetative surface damaged by guide rail installation with HMA.  Use hand tampers around posts and other obstacles where mechanical compactors are not accessible.

608.03.02  Color-Coated Non-Vegetative Surface, HMA

Construct color-coated non-vegetative surfaces as specified in 608.03.01.

Uniformly apply the final color at the rate of 0.3 to 0.5 gallons per square yard by spraying, brushing, or squeegeeing over the HMA surface course.  Ensure that the surface is clean and dry at the time of application.  Reapply the coating to any missed spots or areas to obtain a uniform coating.

Avoid spilling the color coating on adjacent surfaces.  If the color coating spills, immediately clean it with water before the coating dries.  If the coating dries, repair as directed by the RE.

The RE will not allow traffic on the color-coated surface until it is dry.

608.03.03  Non-Vegetative Surface, Broken Stone

Ensure that areas to receive non-vegetative surface, Broken Stone, are free from vegetation.  Vegetation removal may require manual removal, herbicide treatment as specified in 608.03.06 or both.

Apply a pre-emergent herbicide to the area before placement of broken stone.  Spread broken stone, aggregate size No. 3, in a uniform layer, to prescribed thickness.

608.03.04  Non-Vegetative Surface, Porous HMA

Ensure that areas to receive non-vegetative surface, Porous HMA, are free from vegetation.  Vegetation removal may require manual removal, herbicide treatment as specified in 608.03.06 or both.  Excavate as specified in 202.03.03.  Shape and compact the underlying material to produce a firm, even surface.  Obtain RE approval before finishing excavation.  If the RE determines that the bottom of the excavation is unstable, undercut, backfill, and compact as directed by the RE.

Construct the non-vegetative surface, porous HMA before installing guide rail.  Obtain RE approval for alternate methods of construction.

Construct porous HMA surface course to prescribed thickness according to the requirements of Section 303 except for the application of prime coat.  Repair non-vegetative surface damaged by guide rail installation with porous HMA.  Use hand tampers around posts and other obstacles where mechanical compactors are not accessible.

608.03.05  Non-Vegetative Surface, Polyester Matting

Install polyester matting according to the manufacturer’s requirements by manufacturer certified workers.

Ten days before installation, submit to the RE a list of manufacturer certified workers and one copy of the “engineering package” including demonstration compact discs and samples of product components; such as foot prints, finished seams, etc.  The manufacturer may elect to train the workers and Department inspectors on a test section on the worksite.

Ensure that the surface areas to receive the matting are smooth, firm, stable and free of rocks, clods, foliage, roots or other material which might prevent the matting from lying in direct contact with the ground surface, free of wrinkles or bulges.  Existing non-vegetative surface or HMA that is in the same location as proposed polyester matting may be left in place as long as its surface area is properly prepared as previously stated.  Mow grass as low as possible prior to installation of matting.  Install the matting immediately following installation of guide rail posts and prior to installation of the guide rail hardware by lifting the matting above the posts and allowing it to drop to the ground with the posts passing through prefabricated openings.

Stake the matting along its edges in accordance with the manufacturer’s recommendations.

Seal matting openings with a separate prefabricated piece of matting that will provide a snug fit around the post and completely cover the opening.  Ensure that seams are sealed.

Ensure that the matting surface is vegetation-free from installation until final acceptance.  Vegetation removal may require herbicide treatment, mechanical removal, or both, as specified in 608.03.06.

608.03.06  Post-Emergent Weed Control of Non-Vegetative Surfaces

1**************************************************************************************************************************1

dated May 25, 2011

Manually remove or spray vegetation growing on the non-vegetative surface with a post-emergent non-selective herbicide treatment for total control of vegetation on the non-vegetative surface area, as directed by the RE.  Select post-emergent herbicides for control of targeted vegetation based on the manufacturer’s recommendations and product label.  Begin the work associated with vegetation removal as early as the conditions permit.  Herbicides must be applied by, or under the direct supervision of, a Certified Commercial Pesticide Applicator, according to the manufacturer’s recommendations.  Restore areas where herbicide has been applied and not intended to its prior existing condition at no cost to the State.  Do not apply herbicide in the rain or when wet weather is expected within 24 hours.  Do not apply herbicide after rain until approved by the RE.

The RE will notify the ME after Acceptance for inclusion of the non-vegetative surface in its herbicide spraying program including the date that the herbicide was last applied on the project section.

1**************************************************************************************************************************1

608.04  MEASUREMENT AND PAYMENT

The Department will measure and make payment for Items as follows:

Item	Pay Unit

NON-VEGETATIVE SURFACE, HOT MIX ASPHALT	SQUARE YARD

COLOR-COATED NON-VEGETATIVE SURFACE, HOT MIX ASPHALT	SQUARE YARD

NON-VEGETATIVE SURFACE, BROKEN STONE,___THICK	SQUARE YARD

NON-VEGETATIVE SURFACE, POROUS HOT MIX ASPHALT,___THICK	SQUARE YARD

non-vegetative surface, polyester matting	square yard

When the RE directs undercutting of unstable material in the excavation area, the Department will make payment, as specified in 104.03.03, for the additional excavation.  The Department will also make payment, as specified in 104.03.03, for the additional bedding if there is not an excess of excavated material available for use as bedding.

1**************************************************************************************************************************1

Section 609 – Beam Guide Rail

609.03.01  Beam Guide Rail

1**************************************************************************************************************************1

BDC09s-08 dated DEC 07, 2009

THE seventh paragraph is changed to:

Install flexible delineators with white retroreflective sheeting on the right side of the direction of traffic.  Install flexible delineators with yellow retroreflective sheeting on the left side of the direction of traffic.  Mount flexible delineators on the blockout of beam guide rail using either a “U” channel base on the I-beam blockout or a flat base attached to a wood, polymer, or other solid top blockout.  Attach the base to the blockout using an adhesive recommended by the manufacturer of the base and panel.

1**************************************************************************************************************************1

609.03.03  Terminals and Anchorages

1**************************************************************************************************************************1

BDC10s-10 dated Nov 16, 2010

THE FOLLOWING IS ADDED:

Excavate cut slope as specified in 202.03.03 within the limits of the buried guide rail terminal.  Drive beam guide rail posts for buried guide rail terminal to the required position. Ensure that posts are driven plumb, properly spaced, and to the line and grade shown.  Attach the beam guide rail element to the spacer at every post.  Attach the beam guide rail element and plate to the terminal posts.  Align the top edge of the beam guide rail element in a straight line.  Where a vertical transition is required, ensure that the top edge of the beam guide rail element forms the chords of a smooth vertical curve.  Backfill with excavated material as specified in 203.03.02C.

1**************************************************************************************************************************1

609.04  Measurement and Payment

1**************************************************************************************************************************1

BDC10s-10 dated Nov 16, 2010

THE FOLLOWING ITEM IS ADDED

Item	Pay Unit

bURIED Guide rail terminal	UNIT

1**************************************************************************************************************************1

Section 610 – Traffic Stripes, Traffic Markings, and Rumble Strips

610.02.01  Materials

1**************************************************************************************************************************1

dated Sep 18, 2013

the following materials are renamed to:

Traffic Stripes	912.03.01

Traffic Markings	912.03.02

1**************************************************************************************************************************1

610.03.01  Long-Life Traffic Stripes

1**************************************************************************************************************************1

BDC13s-08 dated Aug 19, 2013

The subpart Heading and the entire text is changed to:

610.03.01 Traffic Stripes

A.	Striping Plan.  At least 20 days before beginning the work, submit to the RE for approval a striping plan that includes:

1.	Schedule of operations for applying traffic stripes.

2.	Number and type of equipment.

3.	Manufacturer’s recommendations for use of the materials, including, but not limited to, mixing ratios and application temperatures.

4.	Details on the means and methods for surface preparation

5.	Details on the means and methods for premarking

6.	Details on the proposed test strip such as location, length etc

B.	Surface Preparation.  Immediately before striping the pavement surface, clean the surface of dirt, oil, grease, and foreign material, including curing compound on new concrete.  Clean the surface 2 inches beyond the perimeter of the stripes to be placed.

C.	Striping Test Strip.  Before beginning striping operations, construct 1 or more striping test strips to demonstrate the Contractor’s ability to meet the requirements specified in 610.03.01.D.  For each striping test strip, apply striping to approximately 500 linear feet of pavement with the same striping procedure that will be used for the Project.  Construct a test strip for each applicator unit and epoxy resin material used.  Provide the RE with 50 test cards made of heavy stock paper measuring 8 inches by 2 inches, and two wet film thickness gauges.  Construct additional test strips when major equipment repairs or adjustments are made or when the traffic stripes are determined to be defective.  Construct additional test strips when traffic striping operations are performed on multiple, non-continuous occasions.  Perform additional test strips as requested by the RE. When the test strip is in compliance, as determined by the RE, proceed with striping operations.  Each test strip may remain in place and become part of the finished stripes subject to the requirements of 610.03.01.E.

D.	Applying Striping.  Mix epoxy resin with an automatic proportioning and mixing machine, and hot-spray the compound at a temperature of between 100 and 130 °F onto dry surfaces.  Apply the compound with a wet film thickness of 20 ± 1 mil.  Apply the material during dry weather conditions when the ambient temperature is a minimum of 45 °F and the surface temperature is a minimum of 50 °F.  Adjust operations as required for the prevailing ambient and surface conditions to achieve a no-track drying time of 30 minutes or less.

Immediately after, or in conjunction with, the compound application, uniformly apply 12 pounds of large glass beads per gallon of epoxy resin to the compound.  After applying the large glass beads, uniformly apply 12 pounds of small glass beads per gallon of epoxy resin to the compound.

Remove all compound that has been tracked or spilled outside of the intended placement areas.

E.	Performance.  Ensure that the traffic stripes, show no fading, lifting, cracking, chipping for any reason including but not limited to traffic wear, maintenance activities including snow plowing, until Acceptance.  Ensure that 60 days after application, traffic stripes have a minimum retroreflectance value of:

375 millicandelas per square meter per lux for white traffic stripe

250 millicandelas per square meter per lux for yellow traffic stripe

F.	Defective work.

2**************************************************************************************2

BDC16s-07 dated dec 21, 2016

THE FIRST SENTENCE IN THE FOURTH PARAGRAPH is CHANGED TO:

Replace traffic stripes that are determined by the RE before Acceptance to be defective or that are damaged during construction.  Remove defective stripes as specified in 610.03.08.

Replace an entire 10-foot skip line if the RE determines the stripe to have a deficiency.

If the RE determines, based upon calculated and measured yields, that the striping has a wet film thickness of less than 19 mils, restripe the entire length with 20 mils of new compound.

Provide the RE with a Reflectometer that meets a 30 meter geometry as specified in ASTM E 1710, capable of measuring wet and dry conditions as specified in ASTM E 2176 and ASTM E 2177, and that has been certified by the manufacturer as being calibrated within the last two years.  The RE will test the retroreflectance of traffic stripes.  Replace traffic stripes that do not meet the retroreflectance values indicated in 610.03.01.E.  Replace the entire length of striping where improper curing or discoloration has occurred.  Discoloration is localized areas or patches of brown or grayish colored compound.  Where improper curing or discoloration occurs intermittently in intervals of 100 feet or less throughout the striping length, replace the entire length of striping from the beginning of the first occurrence until the end of the last occurrence, plus 5 feet on each end.

Replace the entire length of striping that has failed to bond to the pavement, or has chipped or cracked.  Where more than 25 spots of chipping, cracking, or poor bonding have occurred within 1000 linear feet of striping, replace the entire 1000 foot length of striping as indicated in 610.03.01.E.

2**************************************************************************************2

G.	Opening to Traffic.  Complete each application of all types of traffic stripes and allow to thoroughly dry before opening to traffic.  At a minimum, delineate center lines on undivided roadways and broken lines between lanes before the traveled way is opened.  The RE will determine when the traveled way can be opened to traffic.

1**************************************************************************************************************************1

610.03.02  Thermoplastic Traffic Markings

1**************************************************************************************************************************1

BDC13s-08 dated Aug 19, 2013 and BDC16S-02 dated Sep 12, 2016

The subpart Heading and the entire text is changed to:

610.03.02  Traffic Markings Lines, Traffic Markings Symbols and Traffic Markings Route Symbols

A.	Marking Plan.  At least 20 days before beginning the work, submit to the RE for approval a marking plan that includes:

1.	Schedule of operations for applying traffic markings,

2.	Number and type of equipment,

3.	Manufacturer’s recommendations for use of the materials, including mixing ratios and application temperatures.

4.	Details on the means and methods for surface preparation

5.	Details on the means and methods for premarking

B.	Surface Preparation.  Immediately before marking the pavement surface, clean the surface of dirt, oil, grease, and foreign material, including curing compound on new concrete.  Clean the surface 2 inches beyond the perimeter of the marking to be placed.

C.	Applying Traffic Markings.  Place preformed thermoplastic or hot extruded thermoplastic traffic markings on thoroughly dry surfaces and during dry weather conditions.  Apply using equipment and procedures that produce markings of the specified color, width, and thickness with well-defined edges, uniform retroreflectivity, and proper bonding to the pavement.  Apply the thermoplastic material as follows:

1.	Preformed Thermoplastic.  Melt the preformed thermoplastic tape to bond the traffic markings permanently in position according to the manufacturer’s recommendations.

Meet the minimum initial retroreflectance value, as specified in 610.03.01.D for thermoplastic tape, by applying additional glass beads to the hot-wet material in a uniform pattern as necessary.

2.	Extruded Thermoplastic.  Uniformly heat the thermoplastic material.  When the ambient and surface temperatures are at least 50 °F, apply the melted material at a temperature of between 400 and 425 °F.  Extrude the thermoplastic traffic markings on the HMA or concrete pavement ensuring a thickness of 90 ( 1 mils.

Immediately after, or in conjunction with the thermoplastic extrusion, uniformly apply glass beads to the wet material at a minimum rate of 10 pounds per 100 square feet of markings.  Apply glass beads by mechanical means only.

D.	Performance.  Ensure that the traffic markings show no fading, lifting, cracking, chipping for any reason including but not limited to traffic wear, maintenance activities including snow plowing, until Acceptance.  Ensure that 60 days after application, traffic markings have a minimum retroreflectance value of:

375 millicandelas per square meter per lux for white traffic markings

250 millicandelas per square meter per lux for yellow traffic markings

E.	Defective work.

2**************************************************************************************2

BDC16s-07 dated dec 21, 2016

THE FIRST SENTENCE IN THE FOURTH PARAGRAPH IS CHANGED TO:

Replace thermoplastic traffic markings that are determined by the RE before Acceptance to be defective or that are damaged during construction.  Remove defective markings as specified in 610.03.08.

Replace the entire area of thermoplastic traffic markings determined to be less than the required thickness, to have incorrect color or width, to have failed to bond to the pavement, or to have chipped or cracked.  The minimum replacement area is an individual word or symbol, or for longitudinal lines the entire length from where the deficiency first occurs to where it no longer exists.

The RE will determine initial retroreflectance as follows:

Provide the RE with a Reflectometer that meets a 30 meter geometry as specified in ASTM E 1710, capable of measuring wet and dry conditions as specified in ASTM E 2176 and ASTM E 2177, and that has been certified by the manufacturer as being calibrated within the last two years.  The RE will test the retroreflectance of traffic markings.  Replace traffic markings that do not meet the retroreflectance values indicated in 610.03.02.D.

2**************************************************************************************2

F.	Opening to Traffic.  Complete each application of thermoplastic traffic markings and allow to thoroughly dry before opening to traffic.  The RE will determine when the traveled way can be opened to traffic.

1**************************************************************************************************************************1

610.03.04  Removal of RPMs

1**************************************************************************************************************************1

BDC11s-06 dated Jul 11, 2011

the entire text is changed to:

Remove RPMs as directed by the RE.  Dispose of RPMs as specified in 201.03.09.  If directed by the RE, fill the hole with HMA patch as specified in 159.03.07 except sawcutting is not required.

1**************************************************************************************************************************1

610.03.06  Ground Mounted Flexible Delineators

1**************************************************************************************************************************1

BDC09s-08 dated DEC 07, 2009

THE FIRST paragraph is changed to:

Use white retroreflective sheeting for delineators located on the right side when facing in the direction of traffic.  Use yellow retroreflective sheeting for delineators located on the left side when facing in the direction of traffic.

1**************************************************************************************************************************1

610.03.07  Rumble Strip

1**************************************************************************************************************************1

BDC15s-11 dated Nov 13, 2015

THE ENTIRE subpart IS CHANGED TO:

At least 20 days before constructing rumble strips, submit a plan for cutting rumble strips and debris collection/removal to the RE for approval.

Construct rumble strips on newly constructed pavement after it has cooled sufficiently to allow the cutting to be done cleanly without causing damage to the adjacent pavement.

Clean the area where rumble strips are to be constructed.  Construct rumble strips by cutting indentations into the pavement perpendicular to the traveled way without disturbing the surrounding pavement. Collect cuttings and reuse or dispose of as specified in 202.03.07.

Ensure that the centerline rumble strips are constructed before placing TRAFFIC STRIPES.  After cutting centerline rumble strips and collecting the debris, apply Fog Seal over the centerline rumble strip as specified in 422.03.02.

Do not construct rumble strips 200 feet linear feet before and after the approximate midpoint of Weigh-in-Motion (WIM) systems in the roadway as listed in the Special Provisions.

2**************************************************************************************2

List locations of the approximate midpoint of Weigh-in-Motion (WIM) systems based on the database information provided in http://www.state.nj.us/transportation/refdata/roadway/pdf/wim_sites.pdf

SME CONTACT – Bureau of Transportation Data and Safety

| Route | Weigh-in-Motion (WIM) Systems Midpoint Station |
| --- | --- |

2**************************************************************************************2

1**************************************************************************************************************************1

610.04  Measurement and Payment

1**************************************************************************************************************************1

2**************************************************************************************2

BDC08s-02 dated Feb 17, 2009

THE FOLLOWING ITEMs are DELETED:

Item	Pay Unit

RPM, BI-DIRECTIONAL, WHITE LEns	UNIT

2**************************************************************************************2

2**************************************************************************************2

BDC16s-02 dated sep 12, 2016

THE FOLLOWING ITEMs are Deleted:

TRAFFIC STRIPES, LONG-LIFE, EPOXY RESIN ___"	LINEAR FOOT

TRAFFIC MARKINGS, THERMOPLASTIC	SQUARE FOOT

THE FOLLOWING ITEMS ARE ADDED:

Item	Pay Unit

TRAFFIC STRIPES, ___"	LINEAR FOOT

Traffic Markings Lines, ___"	LINEAR FOOT

TRAFFIC MARKINGS Symbols	SQUARE FOOT

Traffic markings route symbols	SQUARE FOOT

2**************************************************************************************2

2**************************************************************************************2

BDC16s-02 dated sep 12, 2016

THE second PARAGRAPH IS CHANGED TO:

The Department will measure TRAFFIC STRIPES and TRAFFIC MARKINGS LINES by the linear foot for each specified width of stripe.  The Department will not measure gaps in striping.

2**************************************************************************************2

2**************************************************************************************2

BDC15s-02 dated Mar 30, 2015

The following is added at the end of the Subsection:

The Department will measure rumble strip by the linear foot measured in the longitudinal direction of the rumble strip without deducting the interval spacing between rumble strips and the gaps for RPM placement and make payment under the Item RUMBLE STRIP.

The Department will not include payment for traffic stripes in RUMBLE STRIP.  The Department will make payment for traffic stripes placed in conjunction with constructing a centerline rumble strip under TRAFFIC STRIPES as specified in 610.04.

The Department will not include payment for fog seal in RUMBLE STRIP.  The Department will measure and make payment for FOG SEAL STRIP as specified in 422.04.

2**************************************************************************************2

2**************************************************************************************2

BDC15s-11 dated Nov 23, 2015

The Department will not measure the gaps such as WIM locations in the Rumble Strip.

2**************************************************************************************2

1**************************************************************************************************************************1

Section 611 – Crash Cushions

611.01  DESCRIPTION

1**************************************************************************************************************************1

BDC12s-04 dated JUl 30, 2013

THE FIRST SENTENCE IS CHANGE TO:

This section describes the requirements for providing and constructing inertial barrier systems and compressive crash cushions.

1**************************************************************************************************************************1

611.02  Materials

1**************************************************************************************************************************1

2**************************************************************************************2

BDC11s-06 dated Jul 11, 2011

THE second PARAGRAPH IS CHANGED TO:

Ensure that the sand has a dry density of 90 to 100 pounds per cubic foot and a 3 percent maximum allowable moisture content.  The RE may require the Contractor to test the moisture content of the sand according to AASHTO T 255 and to submit certified test results.

2**************************************************************************************2

2**************************************************************************************2

BDC12s-04 dated JUl 30, 2013

THE THIRD PARAGRAPH IS CHANGED TO:

Provide an inertial barrier system listed on the QPL.  Provide a compressive crash cushion as shown on the Plans.

The list of the manufacturers / suppliers is as follows:

QuadGuard	Energy Absorption Systems, Inc.

QuadGuard Elite	Energy Absorption Systems, Inc.

QuadGuard Cz	Energy Absorption Systems, Inc.

REACT 350	Energy Absorption Systems, Inc.

REACT 350 WZ	Energy Absorption Systems, Inc.

SCI	SCI Products Inc.

TAU II	Barrier Systems Inc.

TRACC	Trinity Highway Products

2**************************************************************************************2

1**************************************************************************************************************************1

611.03.02  Crash Cushion

1**************************************************************************************************************************1

BDC12s-04 dated JUl 30, 2013

THE TITLE OF THE SUBSECTION IS CHANGED TO:

611.03.02  Compressive Crash Cushion

THE SECOND SENTENCE IS CHANGED TO:

Install compressive crash cushions including foundations, backup supports and transitions according to the manufacturer’s recommendations and as shown on the Plans.

1**************************************************************************************************************************1

611.04  MEASUREMENT AND PAYMENT

1**************************************************************************************************************************1

BDC12s-04 dated JUl 30, 2013

THE FOLLOWING ITEM is Deleted:

Item	Pay Unit

CRASH CUSHION, ___	UNIT

THE FOLLOWING ITEMS ARE ADDED:

Item	Pay Unit

crash cushion, compressive barrier, type___, Width___	unit

crash cushion, Low maintenance compressive barrier, type___, width___	unit

1**************************************************************************************************************************1

section 612 – signs

612.02	materials

1**************************************************************************************************************************1

BDC09s-01 dated apr 09, 2010

The following is deleted from the Materials list.

Non-Breakaway Sign Supports	911.02.03

the second paragraph is deleted.

1**************************************************************************************************************************1

612.03.02  Type GA Breakaway and Non-Breakaway Support Guide Signs

1**************************************************************************************************************************1

BDC09s-01 dated apr 09, 2010

The subpart Heading is changed to:

612.03.02  Type GA Breakaway Support Guide Signs

1**************************************************************************************************************************1

612.03.02  Type GA Breakaway Support Guide Signs

1**************************************************************************************************************************1

BDC09s-01 dated apr 09, 2010

C.	Constructing Pedestals

The Subpart is changed to:

Place reinforcement steel as specified in 504.03.01 before placing the concrete.  Ensure that concrete placement complies with the limitations as specified in 504.03.02.C.  Place concrete as specified in 504.03.02.D.  Cure concrete as specified in 504.03.02.F.

D.	Erecting Posts

The Subpart is changed to:

Erect posts as specified in 512.03.01.G.

the following is added:

F.	Constructing Anchor, Hinge, Bracket and Coupling Assemblies..At least 10 days before beginning the work, submit the manufacturer’s installation guide and installer’s certification to the RE.

Ensure that the installer is certified by the manufacturer.

Ensure that the manufacturer’s representative is present during the foundation pour and the installation of the first sign.  Install anchor, hinge, bracket and coupling assemblies according to the manufacturer’s recommendations.  The RE may require the system manufacturer’s representative to be present at all times during the installation to provide on-site technical support.

1**************************************************************************************************************************1

612.04	measurement and payment

1**************************************************************************************************************************1

BDC09s-01 dated apr 09, 2010

The following Item is deleted:

Item	Pay Unit

GUIDE SIGN, TYPE GA, NON-BREAKAWAY SUPPORTS	SQUARE foot

1**************************************************************************************************************************1

1**************************************************************************************************************************1

include specifications upon ASSIGNING an APPROPRIATE SECTION/SUBSECTION/subpart NUMBERs if noise barriers are required

sme contact – Structural Engineering and Landscape Architecture

The following section is added:

Section 61x – noise barriers

1**************************************************************************************************************************1

1**************************************************************************************************************************1

include specifications upon ASSIGNING an APPROPRIATE SECTION/SUBSECTION/subpart NUMBERs if Architectural Treatments are required

sme contact – Structural Engineering and Landscape Architecture

The following section is added:

Section 61X – Architectural Treatments

1**************************************************************************************************************************1

1**************************************************************************************************************************1

include specifications upon ASSIGNING an APPROPRIATE SECTION/SUBSECTION/subpart NUMBERs if RUBBLE walls are required

sme contact – Structural Engineering and Landscape Architecture

The following section is added:

Section 61x – RUBBLE walls

1**************************************************************************************************************************1

Division 650 – Utilities

Section 651 – Water

1**************************************************************************************************************************1

651.02  Materials

include additional materials requirements as needed

sme contact – utilities

1**************************************************************************************************************************1

1**************************************************************************************************************************1

651.03.02  Water Pipe, Bridge

include OTHER CONSTRUCTION REQUIREMENTS AS NEEDED.

sme contact – utilities

1**************************************************************************************************************************1

651.04  Measurement and payment

1**************************************************************************************************************************1

BDC11s-12 dated Dec 12, 2011

the last PARAGRAPH IS deletED.

1**************************************************************************************************************************1

Section 652 – Sanitary Sewers

1**************************************************************************************************************************1

652.02  Materials

include additional materials requirements as needed

sme contact – utilities

1**************************************************************************************************************************1

652.03.01  Sewer Pipe

F.	Thrust Blocks.

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

The third sentence is changed to:

Ensure that thrust blocks do not come in contact with other utilities or structures without the approval of the RE.

1**************************************************************************************************************************1

G.	Sewer Pipe Testing.

1.	Gravity Main Sewer Testing.

1**************************************************************************************************************************1

include leakage testing list

sme contact – utilities

1**************************************************************************************************************************1

652.03.02  Sanitary Sewer Pipe, Bridge

1**************************************************************************************************************************1

INCLUDE Specification

sme contact – utilities

1**************************************************************************************************************************1

652.04 Measurement and Payment

1**************************************************************************************************************************1

BDC11s-12 dated Dec 12, 2011

the last PARAGRAPH IS deletED.

1**************************************************************************************************************************1

Section 653 – Gas

653.03.01  Gas Main

A.	Prequalification.

1**************************************************************************************************************************1

INCLUDE list of pre-qualified subcontractors

sme contact – utilities

List of pre-qualified subcontractors is as follows:

1**************************************************************************************************************************1

C.	Handling and Storing.

1**************************************************************************************************************************1

INCLUDE utility location for pickup and return

1**************************************************************************************************************************1

J.	Air-Pressure Test.

1**************************************************************************************************************************1

INCLUDE pressures and durations for test

1**************************************************************************************************************************1

653.04 Measurement and Payment

1**************************************************************************************************************************1

BDC11s-12 dated Dec 12, 2011

the last PARAGRAPH IS deletED.

1**************************************************************************************************************************1

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

include the following upon ASSIGNING an APPROPRIATE SECTION/SUBSECTION/subpart NUMBERs if JCP&L related utility work is to be performed

ensure that the work package has been received from jcp&l; provide an electronic file (PDF format) of the construction order detail & construction order compatible unit summary only to the project manager for it to be posted on bid express as mentioned in QIA no: 046 dated Aug 01, 2007

The following section is added:

Section 65x – JCP&L Facility

65x.01  Description

This Section describes the requirements for installing, relocating and removing Jersey Central Power and Light (JCP&L) electric utility facilities including conduits, manholes, transformer vaults, handholes, and appurtenances and also includes the requirements for transferring electric services.

65x.02  Materials

Except for the materials noted below, JCP&L will supply all materials necessary for the work at no cost to the Contractor.  Provide JCP&L written notice 30 days in advance of when materials will be required.  Ensure the electric subcontractor takes delivery of the materials from JCP&L’s storage facility within two weeks of the notice from JCP&L indicating that the material is available. Materials may be located at more than one JCP&L storage facility.  If the electric subcontractor fails to take delivery, the material may not be available, and the electric subcontractor may be required to provide an additional request for materials.  The Contractor is responsible for compensating the Department for any additional handling costs incurred by JCP&L resulting from the failure to take delivery within the time required.

The electric subcontractor is responsible for loading the material, delivering it to the job site, and all subsequent handling and delivery within the jobsite.  Store and protect all materials received from JCP&L. Return and deliver all excess materials furnished by JCP&L to JCP&L’s storage facility.  Obtain a receipt for all material received from JCP&L, maintain a documented inventory of materials used and obtain a receipt for all material returned to JCP&L.

Provide materials as specified:

Tack Coat 64-22: PG 64-22	902.01.01

Concrete	903.03

Curing Materials	903.10

Controlled Low Strength Material (CLSM)	903.09

Hot Mix Asphalt (HMA)	902.02

Sealer, Hot-Poured	914.02

Polymerized Joint Adhesive	914.03

65x.03  Construction

65X.03.01  Electric

A.	Prequalification.

1**************************************************************************************************************************1

dated Jan 15, 2014

the entire text is changed to:

Only a prequalified electric subcontractor, approved by JCP&L, may construct and relocate JCP&L electric facilities.  The following is a list of electric subcontractors that have been previously approved by JCP&L.  This list is provided as information only, and is not an endorsement by the Department of any subcontractor.  The Contractor is responsible for soliciting from a subcontractor that will be approved by JCP&L when preparing its Bid.  Work restricted to the electric subcontractor does not preclude the Contractor from performing the work of layout, traffic control, sawcutting, pavement removal, temporary or final pavement restoration, and landscape restoration associated with the work of installing or relocating JCP&L electrical facilities.

APPROVED ELECTRICAL SUBCONTRACTOR

| DX (Distribution) & TX (Transmission) OVERHEAD |
| --- |
| Hawkeye, LLC | Tri-M Corp |
| 100 Marcus Blvd | PO Box 69 |
| Hauppague, NY 11788 | 204 Gale Lane |
| Tel: 631-447-3100 | Kennett Square, PA 19348 |
| Fax: 631-776-1847 | Tel: 610-444-1001 ext 200 |
| Att: Rick Reed – Mgr-Operations | Fax: 484-731-0209 |
| email: rreed@hawkeyellc.com | Attn: Katie Bleiler |
|  | email: kbleiler@energtest.com |
| Henkels & McCoy, Inc |  |
| 985 Jolly Road | Richardson & Wayland |
| Blue Bell, PA 19422 | PO Box 12648 |
| Tel: 215-283-7707 | Roanoke, VA 24027 |
| Fax: 215-283-7573 | Tel: 540-344-3244 |
| Att: Alan L. Lippy - Director, Power Operations East | Attn: Andy Euclide |
| email: alippy@henkels.com | email: aeuclide@rwec.com |
| JBL Electric Inc. | SREC Resources |
| 3001 South Clinton Avenue | PO Box 7250 |
| South Plainfield, NJ 07080 | Sussex, NJ 07461 |
| Tel: 800-525-4628 | Attn: Chris Reese |
| Att: Jerry Reid | Tel: 973-875-5101 x123 |
| email: jreid@jblelectric.com | FAX: 973-875-2394 |
| Cell 973-900-2871 | email: creese@sussexrec.com |
| MYR (Harlan & The L.E. Myers Company) | J Wm Foley |
| 1416 Trindle Road 3-A | 340 Chestnut Avenue |
| Carlisle, PA 17013-9718 | West Berlin, NJ 08091 |
| Tel: 717-243-4600 | Attn: Bob Dougherty |
| Fax: 717-243-3633 | Tel: 856-768-8800 |
| Att: Jon Arganbright | FAX: 856-768-8884 |
| email: jarganbright@myrgroup.com | email: rdougherty@jwmfoley.com |
| M.J. Electric, Inc. | Riggs Distler & Co., Inc |
| 1047 Shoemaker Avenue | 4 Esterbrook Lane, Cherry Hill, NJ 08003 |
| PO Box 310 | POC: Scott Zemaitatis |
| Shoemaker, PA 19555-310 | Office: 856-433-6007 |
| Tel: 610-562-7570 x 4802 | Fax: 856-433-6035 |
| Fax: 610-562-1375 | Cell: 609-254-3858 |
| Att: Mike Troutman | email: scottzemaitatis@riggsdistler.com |
| email: mtroutman@mjelectric.com |  |
|  | Demeter Electric |
| Asplundh | 896 Bushkill Center Rd |
| 161 Second Street | Nazareth, PA 18064 |
| Wilkes Barre, PA 18702 | POC: Rich Demeter |
| Tel: 570-947-1101 | Office: 610-759-4513 |
| Fax: 570-822-0770 | Fax: 610-759-5799 |
| Attn: Vincent Stanbro | Cell: 484-634-0265 |
| email: v.stanbro@asplundh.com | email: demeterelectric@verizon.net, |
| DX & TX -UG (Underground) (CIVIL & ELECTRICAL) |
| Henkels & McCoy, Inc. |  |
| 985 Jolly Road |  |
| Blue Bell, PA 19422 |  |
| Tel: 215-283-7707 |  |
| Fax: 215-283-7573 |  |
| Att: Alan L. Lippy - Director, Power Operations East |  |
| email: alippy@henkels.com |  |
| JBL Electric Inc. |  |
| 250 Lackawanna Ave |  |
| West Paterson, NJ 07424 |  |
| Tel: 973-774-4218 |  |
| Attn: Jim Leary – President |  |
| email: jleary@jblelectric.com |  |
| Cell 908-310-7726 |  |
| SREC Resources |  |
| PO Box 7250 |  |
| Sussex, NJ 07461 |  |
| Attn: Chris Reese |  |
| Tel: 973-875-5101 x123 |  |
| FAX: 973-875-2394 |  |
| email: creese@sussexrec.com |  |
| J Wm Foley |  |
| 340 Chestnut Avenue |  |
| West Berlin, NJ 08091 |  |
| Attn: Bob Dougherty |  |
| Tel: 856-768-8800 |  |
| FAX: 856-768-8884 |  |
| email: rdougherty@jwmfoley.com |  |
| DX & TX-UG (CIVIL ONLY – NON ELECTRICAL) |
| Union Paving & Construction |  |
| 1140 Globe Ave |  |
| Mountainside, NJ 07092 |  |
| Tel: 908-232-0738 |  |
| Fax: 908-232-4100 |  |
| Attn: Scott Woodfield - CFO |  |
| email: swoodfield@unionpaving.com |  |
| J. Fletcher Creamer & Son, Inc |  |
| 1701 E. Linden Avenue |  |
| Linden, NJ 07036 |  |
| Tel: 908-925-3200 |  |
| Fax: 908-925-3350 |  |
| Att: Ted Paliwoda |  |
| email: tpaliwoda@jfcson.com |  |
| W&B |  |
| 75 South Gold Drive |  |
| Hamilton, NJ 08691 |  |
| Tel: 609-584-1100 |  |
| Attn: C. Waters – Principal |  |
| email: cwaters@watersandbugbee.com |  |
| George Harms Construction Co, Inc |  |
| PO Box 817 |  |
| Farmingdale, NJ 07727 |  |
| Tel: 732-938-4004 |  |
| Fax: 732-938-2782 |  |
| Attn: James Duffe – Vice President Project Management |  |
| email: jduffe@ghcci.com |  |
| J Wm Foley |  |
| 340 Chestnut Avenue |  |
| West Berlin, NJ 08091 |  |
| Attn: Bob Dougherty |  |
| Tel: 856-768-8800 |  |
| FAX: 856-768-8884 |  |
| email: rdougherty@jwmfoley.com |  |
| HC Constructors |  |
| PO Box 855 |  |
| Whitehorse Station, NJ 08889 |  |
| Tel: 908-534-3833 |  |
| FAX: 908-534-3851 |  |
| Attn: Harry Chowansky - VP |  |
| email:hchowansky@hcconstructors.com |  |
| DIRECTIONAL BORING |
| J. Fletcher Creamer & Son, Inc. |  |
| 1701 E. Linden Avenue |  |
| Linden, NJ 07036 |  |
| Tel: 908-925-3200 |  |
| Fax: 908-925-3350 |  |
| Att: Ted Paliwoda |  |
| email: tpaliwoda@jfcson.com |  |
| W&B |  |
| 75 South Gold Drive |  |
| Hamilton, NJ 08691 |  |
| Tel: 609-584-1100 |  |
| Attn: C. Waters – Principal |  |
| email: cwaters@watersandbugbee.com |  |
| EM Utility Contractors LLC |  |
| 2425 South Front Street |  |
| Allentown PA 18103 |  |
| Attn: Michael Marino |  |
| Office :4842275774 |  |
| Fax: 7326266685 |  |
| Cell: 6105739352 |  |
| email: mmarino@emutilitycontractors.com |  |
| Delaware Valley Utility Contractors, Inc. |  |
| Michael Zeller |  |
| General Manager |  |
| 225 Warren Street |  |
| Reading, PA 19601 |  |
| Office: 610-372-7390 EXT. 232 |  |
| Fax: 610-822-0665 |  |
| Cell: 484-332-7982 |  |
| email: mzeller@esreading.com |  |
| Kline Construction Company |  |
| 240 Waveland Avenue, Galloway NJ 08025 |  |
| Poc: Pete Deirocini |  |
| Office # 856-728-7773 |  |
| Fax# 867-728-4868 |  |
| Cell# 609-703-8335 |  |
| Email: pete@klineconstruction.net |  |
| GENERAL CONTRACTORS |
| Henkels & McCoy, Inc. |  |
| 985 Jolly Road |  |
| Blue Bell, PA 19422 |  |
| Tel: 215-283-7707 |  |
| Fax: 215-283-7573 |  |
| Att: Alan L. Lippy - Director, Power Operations East |  |
| email: alippy@henkels.com |  |
| JBL Electric Inc. |  |
| 3001 South Clinton Avenue |  |
| South Plainfield, NJ 07080 |  |
| Tel: 800-525-4628 |  |
| Att: Jerry Reid |  |
| email: jreid@jblelectric.com |  |
| Cell 973-900-2871 |  |
| George Harms Construction Co, Inc |  |
| PO Box 817 |  |
| Farmingdale, NJ 07727 |  |
| Tel: 732-938-4004 x2006 |  |
| Fax: 732-938-2782 |  |
| Attn: James Duffe – Vice President Project Management |  |
| email: jduffe@ghcci.com |  |
| Union Paving & Construction |  |
| 1140 Globe Ave |  |
| Mountainside, NJ 07092 |  |
| Tel: 908-232-0738 |  |
| Fax: 908-232-4100 |  |
| Attn: Scott Woodfield - CFO |  |
| email: swoodfield@unionpaving.com |  |

1**************************************************************************************************************************1

B.	Indemnification.  The Contractor agrees to indemnify and hold harmless JCP&L, its officers, employees and agents from liability and claims related to the work described under Section 654.  This requirement does not establish JCP&L as a third party beneficiary; the provisions specified in Section 107.10 are unaltered.

C.	Scheduling of Work and Interruption to Utilities.  Provide the RE and the designated JCP&L representative with a detailed schedule of when the electric utility work will be performed.  Indicate in the schedule for each activity the following information: the work locations; the number of crews; and whether the work will be performed during a day shift or night shift, or on weekends.  Coordinate all electric utility work with the JCP&L representative, and notify the RE and the JCP&L representative at least two weeks prior to starting electric utility work.  Do not interrupt existing electric service until approved by the JCP&L representative.

Weather conditions may prevent connections to existing systems between June 1 and September 30.  Do not perform work which will require electric transmission service interruptions from June 1 through September 30 without the approval of JCP&L.  JCP&L may extend this period based on weather conditions and system demand.  Notify JCP&L at least one month in advance of commencing conductor work.

If service transfers are required, coordinate service transfers with the JCP&L representative.  Notify the property owner and all tenants affected by service interruptions or transfers prior to making the service transfer.  Minimize disruption to normal operations of existing facilities and minimize any interruption of electric service to JCP&L customers.  Protect existing facilities during construction and installation of the service transfer.

D.	Quality Control and Quality Assurance.  Provide access to the work for the JCP&L representative at all times.  Perform all electric utility work in a manner acceptable to the JCP&L representative.  Perform all electric utility work in accordance with JCP&L standards and details.

E.	Safety.  Perform work in accordance with applicable OSHA regulations, N.J.S.A. 34:6-47.1 et seq. “High Voltage Proximity Act”, and JCP&L safety standards.

F.	Abandonment and Removal.  Prior to beginning work, review the condition of all existing electric utility facilities noted to be removed with the JCP&L representative.  If the JCP&L representative designates the material to be salvaged, remove the material and deliver it to a JCP&L storage facility.  Remove and dispose of all other electrical utility material designated for removal.

G.	Excavation.  When excavation is required in areas having existing pavement and sidewalk, sawcut to the full depth of the existing pavement and sidewalk.  Excavate trenches for conduit, manholes and vaults and appurtenances.  Provide vertical sides for excavations within the traveled way, shoulder, sidewalk areas, and where existing facilities require protection.  Remove unstable material at the bottom of the excavation and backfill with granular material.  Do not excavate trenches more than 300 feet in advance of installing conduit unless approved by the RE.  Provide and maintain trench crossings where necessary to maintain access.  Do not leave trenches open overnight unless protected by temporary fencing or steel plates.  Remove and dispose of excess or unsuitable material as specified in 202.03.07.

H.	Backfill.  Backfill with suitable material in lifts not exceeding 6 inches thick, loose measurement.  If the backfill is predominantly granular material, compact the backfill material with a vibratory plate compactor.  For material that is not predominately granular, compact the backfill material with a vibratory rammer compactor.  If it is not possible to compact the backfill material, the Contractor may backfill with CLSM with the approval of the JCP&L representative.  If using CLSM, install as specified in 601.03.01.F.

I.	Restoration.  Restore areas disturbed in the performance of electrical utility relocations to its original condition.  In areas that are disturbed for which the plans provide final grading, pavement or landscaping, provide temporary restoration to the satisfaction of the RE.  If open-cut trenching across a road is required, restore the pavement with in-kind construction.

J.	Field Testing.  Perform a high-potential test (also known as a dielectric voltage withstand test) on all cables and splices prior to energizing.  Testing must be performed by a person who is qualified to operate the test equipment, and is familiar with the cable system.  Ensure that the cables are disconnected from non-cable systems equipment, and that adequate physical clearances are maintained between all cable ends, energized cables, and electrical grounds and all other equipment during the test.  Prior to performing the test, verify that all taps or laterals in the circuit are cleared. In the event hot poured compound filled splices and terminations are involved, do not perform testing until they have cooled to ambient temperature.  Set the relays in the high voltage direct current test equipment to operate between 5 and 25 milliamperes leakage.  The shape of the leakage curve under constant voltage is more important than the absolute leakage current of a “go or no go” withstand test result.  The field test voltage is related to the final factory applied dc potentials using a factor of 80 percent.

Ensure the high potential test is performed in the presence of the JCP&L representative. Apply a direct current field test voltage according to the following table:

| Field Test Values |
| --- |
| Rated Voltage | dc Hi-Pot Test | dc Hi-Pot Test |
| Phase to | (15 Minutes) |
| Phase | Wall - mils | Kv | Wall - mils | kV |
| 5000 | 90 | 25 | 115 | 35 |
| 8000 | 115 | 35 | 140 | 45 |
| 15000 | 175 | 55 | 220 | 65 |
| 25000 | 260 | 80 | 320 | 95 |
| 28000 | 280 | 85 | 345 | 100 |
| 35000 | 345 | 100 | 420 | 125 |
| 46000 | 445 | 130 | 580 | 170 |
| 69000 | 650 | 195 | 650 | 195 |
| Note: If the leakage current quickly stabilizes, the duration may be reduced to 10 minutes. |

After the voltage has been applied and the test level reached, record the leakage current at one-minute intervals.  If the leakage current decreases or stays steady after it has leveled off, the cable is considered satisfactory.  If the leakage current starts to increase, excluding momentary spurts due to supply-circuit disturbances, extend the test to see if the rising trend continues.  At the conclusion of the test, discharge the circuit through the test set and voltmeter circuit.  After the potential drops below 95% of the test value, ground the cable and discharge the circuit. Leave the grounds on all conductors for a minimum of four times as long as the test voltage was applied.

Remove and replace cables that fail to meet the requirements of the direct current field test.  The Contractor is responsible for reimbursing the Department for any additional material costs incurred by the Department resulting from the failure to meet the requirements of the direct current field test.

K.	Energizing Lines.  Energize lines with the guidance of the JCP&L representative.  Prior to energizing lines, submit a request to JCP&L.  Switching orders may only originate from JCP&L employees.  Submit a request for permission to energize transmission lines 10 days in advance of when the work will be performed.  Request permission to energize distribution lines in a manner that will permit the JCP&L representative to submit a request to JCP&L’s Dispatch Office by noon the previous business day.

L.	As-builts.  Upon completion of the work, submit to JCP&L as-built drawings in accordance with JCP&L standards.  Prints of construction drawings, marked to show the final location, are acceptable.  Provide a copy of the as-built drawings to the RE.

65x.04  Measurement and Payment

The Department will measure and make payment for Items as follows:

Item	Pay Unit

ELECTRICAL UTILITY RELOCATION, JCP&L	LUMP SUM

1**************************************************************************************************************************1

Division 700 – Electrical

Section 701 – General Items

701.03.01  Existing Systems

1**************************************************************************************************************************1

2**************************************************************************************2

BDC13S-04 dated JUN 10, 2013

The Fifth paragraph is changed to:

If removal of existing above ground electrical material is required, deliver salvaged materials to the nearest Department electrical maintenance yard and unload the salvaged materials as directed. Dispose of salvaged materials rejected by the Department from the Project Limits as specified in 201.03.09.

2**************************************************************************************2

2**************************************************************************************2

BDC10s-08 dated dec 29, 2010

3************************************************3

if there are any its materials to be salvaged, provide the location to deliver and unload salvaged its materials

SME CONTACT –

traffic operations and/or mse

Deliver and unload salvaged ITS materials to:

Mobility Management North (MMN)- ITS Maintenance

670 River Drive

Elmwood Park, NJ 07407-1347

Telephone: 732-697-7360

Mobility Management South (MMS) – ITS Maintenance

One Executive Suite Route 70 West

Cherry Hill, NJ  08002-4106

Telephone: 856-486-6615

3************************************************3

3************************************************3

inCLUDE THE FOLLOWING WHEN EXISTING CONDUIT SYSTEMS ARE PROPOSED TO BE USED for PULLING electrical CONDUCTORS OR FIBER OPTIC CABLES.

SME CONTACT – traffic engineering

and/or

Bureau of Mobility and Systems Engineering (MSE)

THE FOLLOWING IS ADDED:

If new cable or wire is designated to be installed into existing conduit systems, clean and swab the conduit system prior to installing the cable or wire.  After cleaning, test each conduit by pulling through a metal ball with a diameter at least 85 percent of the nominal inside diameter of the conduit to ensure the conduit is free of any obstruction or foreign material.  If the ball fails to pass through the conduit, repair or replace the defective conduit as directed by the RE.  Restore disturbed areas to original condition.

3************************************************3

2**************************************************************************************2

1**************************************************************************************************************************1

701.03.02  Rigid Metallic Conduit (Earth)

B.	Installation.

1**************************************************************************************************************************1

BDC16s-03 dated Aug 24, 2016

the FOLLOWING IS ADDED:

In rigid metallic conduit used exclusively for fiber optic cable, install a tracer wire continuously for the entire run of conduit, including through the junction boxes, mounting it on the wall.  Splice the tracer wire only in the junction box.  Seal the ends of rigid metallic conduit carrying the tracer wire.  If wire or cable is not scheduled to be installed within 6 months of conduit installation, cap and seal the other conduits leaving the true tape inside.  Install warning tape in the trench above the conduit.

1**************************************************************************************************************************1

701.03.03  Rigid Metallic Conduit (Roadway)

the FOLLOWING IS ADDED:

1**************************************************************************************************************************1

BDC16s-03 dated Aug 24, 2016

Ensure that jacking or drilling and receiving pits are not within 2 feet from the edge of the pavement.

In rigid metallic conduit used exclusively for fiber optic cable, install a tracer wire continuously for the entire run of conduit, including through the junction boxes, mounting it on the wall.  Splice the tracer wire only in the junction box.  Seal the ends of rigid metallic conduit carrying the tracer wire.  If wire or cable is not scheduled to be installed within 6 months of conduit installation, cap and seal the other conduits leaving the true tape inside.  Install warning tape in the trench above the conduit.

1**************************************************************************************************************************1

701.03.05  Rigid Nonmetallic Conduit

B.	Installation.

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

the last paragraph is changed to:

Install true tape marked in 1-foot increments for the length of the rigid non-metallic conduit.  Install a tracer wire continuously for the entire run of conduit, including through the junction boxes, mounting it on the wall.  Splice the tracer wire only in the junction box.  Seal the ends of rigid nonmetallic conduit carrying the tracer wire.  If wire or cable is not scheduled to be installed within 6 months of conduit installation, cap and seal the other conduits leaving the true tape inside.  Install warning tape in the trench above the conduit.

1**************************************************************************************************************************1

701.03.06  Flexible Metallic Conduit

the entire Subsection text is changed to:

1**************************************************************************************************************************1

BDC16s-03 dated Aug 24, 2016

Install liquidtight flexible metallic conduit according to NEC requirements. Cut liquidtight flexible metallic conduit according to manufacturer’s recommendations. Ensure that conduit used for fiber optic cables meets the minimum bend and radius requirements as specified in the Contract and according to the fiber optic cable manufacturer.  Utilize NEMA-4X weather-tight hubs for conduit connections to ITS and electrical enclosures.

1**************************************************************************************************************************1

701.03.07  Flexible Nonmetallic Conduit

B.	Installation.

1**************************************************************************************************************************1

2**************************************************************************************2

BDC16s-03 dated Aug 24, 2016

the second paragraph is deleted.

the third paragraph is changed to:

Construct flexible nonmetallic conduit runs so that there are no joints or splices in the conduit between adjacent junction boxes.  Ensure flexible nonmetallic conduit runs are terminated in the junction boxes according to manufacturer’s recommendations.

2**************************************************************************************2

2**************************************************************************************2

BDC10s-08 dated dec 29, 2010

the last paragraph is changed to:

Install true tape marked in 1-foot increments for the length of the flexible non-metallic conduit.  Install a tracer wire continuously for the entire run of conduit, including through the junction boxes, mounting it on the wall.  Splice the tracer wire only in the junction box.  Seal the ends of flexible nonmetallic conduit carrying the tracer wire.  If wire or cable is not scheduled to be installed within 6 months of conduit installation, cap and seal the other conduits leaving the true tape inside.  Install warning tape in the trench above the conduit.

2**************************************************************************************2

1**************************************************************************************************************************1

701.03.15  Cable and Wire

A.	Installing.

1**************************************************************************************************************************1

BDC13S-04 dated JUN 10, 2013

The following is added

Test the existing tracer wire in the conduit for continuity.  If there is no existing tracer wire in any of the conduits in the same trench, then install a continuous tracer wire between the adjacent junction boxes without any splice when installing the cable and wire as directed by the RE.

1**************************************************************************************************************************1

C.	Connection and Coordination with Utility Services.

1**************************************************************************************************************************1

BDC16s-03 dated Aug 24, 2016

2**************************************************************************************2

for its facilities design, confirm on the requirements for interim communication and power connections, and connections to njta network. Also, for establishment of ip addresses, interim and permanent.

SME CONTACT – MSE

2**************************************************************************************2

2**************************************************************************************2

INCLUDE THE FOLLOWING WHEN ITS FACILITIES ARE PROPOSED THAT REQUIRES ANY NEW UTILITY SERVICES.

SME CONTACT – MSE

THE FOLLOWING IS ADDED:

Obtain and provide for utility services required for testing and operation of ITS systems until interim acceptance of each system or device.  Utility Services may be governed by differing Authorities Having Jurisdiction (AHJ).  Along with Utility Requirements, comply with all AHJ requirements.  Upon successful completion of level C testing and acceptance of any device, provide the RE with a letter requesting transfer of utility services providing the latest copy of the utility bill from each utility company.  Such transfers are to be effective beginning the next monthly billing cycle after completion of successful ITS system testing as specified in Section 704 and interim acceptance of the device or as directed by the RE.

Once new utility services have been energized or activated and the utility company has de-energized and unhooked the old service connection; remove existing pole risers and service heads, cut back one foot below grade, and plug the conduits.

Service Requests

| Device Site No. | Primary Route | Final MP | Direction | Location | Township | County | Utility Territory | Job No. | Utility Contact Person | Utility Pole No. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

2**************************************************************************************2

1**************************************************************************************************************************1

701.04  Measurement and Payment

1**************************************************************************************************************************1

BDC16s-03 dated Aug 24, 2016

THE FOLLOWING IS ADDED:

The Department will not include payment for restoring disturbed areas in the various Items of this Section.  The Department will pay for restoring disturbed areas (pavement, curb, sidewalk, driveway or island) as specified in 104.03.03.

The Department will not include payment when the RE directs the installation of a new conduit or a repair to the defective conduit in the various Items of this Section.  The Department will pay for the installation, when directed by the RE, of a new conduit or a repair to the defective conduit as specified in 104.03.03

The Department will not include payment when the RE directs the installation of a tracer wire in existing conduit in the various Items of this Section.  The Department will pay for the installation, when directed by the RE, of a tracer wire in existing conduit as specified in 104.03.03.

1**************************************************************************************************************************1

Section 702 – Traffic Signals

702.03  Construction

The following is added:

After placing a new, temporary or interim traffic signal system into operation, inspect the traffic signal system every 2 months.  Fill out a Contractor Maintenance Traffic Signal Inspection Report (Form EL-16C) when the traffic signal system becomes operational, when the traffic signal system is modified, and at every 2-month inspection.

Maintain as-built drawings of each signal modification.  Place copies of the as-built drawings for each traffic signal system modification, Forms EL-16C, and Forms EL-11C in a plastic pocket mounted inside the cabinet door of each controller cabinet.  Also provide a copy of all forms and as-built drawings to the RE.

If a new, temporary or interim traffic signal system fails or becomes damaged, repair and restore the traffic signal system to normal operation.  Begin repair of the traffic signal system within 2 hours of receiving notice of damage or malfunction from the Department, State police, or local authorities.  Ensure that workers assigned to such repair work continuously until the traffic signal resumes normal signal operation.

For each response to a system failure or damage, fill out a Contractor Maintenance Emergency Call Record (Form EL-11C) and place it in a plastic pocket mounted inside the cabinet door of each controller cabinet.

If the Contractor fails to respond to a failure or damage notification and begin work within 2 hours of notification, or does not continue to work until the traffic signal system resumes normal operation, the Department, in the interest of safety, will respond with its own forces to restore normal operation.  If the Department mobilizes its forces to effect repairs, the Contractor agrees to pay the Department a sum of $3000 for costs of mobilizing its forces and equipment.  In addition, the Contractor must pay the Department the actual cost of material used for the repair and pay the actual costs of police traffic protection.

702.03.11  Temporary and Interim Traffic Signal Systems

the first THROUGH FIFTH PARAGRAPHs are deletED:

Section 703 – highway lighting

703.03  Construction

The following is added:

Maintain up-to-date as-built drawings of the highway lighting system and temporary highway lighting system.  Place copies of the as-built drawings in a plastic pocket mounted inside the meter cabinet, and provide a copy to the RE

If the highway lighting system or temporary highway lighting system fails or becomes damaged, repair and restore the system to normal operation.  Begin repair of the signal system within 2 hours of receiving notice of damage or malfunction from the Department, State police, or local authorities.  Ensure workers assigned to such repair work continuously until the lighting system is restored to normal operation.

For each response to a system failure or damage, fill out a Contractor Maintenance Emergency Call Record (Form EL-11C) and place it in a plastic pocket mounted inside the cabinet door of each controller cabinet.

If the Contractor fails to respond to a failure or damage notification and begin work within 2 hours of notification, or does not continue to work until the lighting system is restored to normal operation, the Department, in the interest of safety, will respond with its own forces to restore normal operation.  If the Department mobilizes its forces to effect repairs, the Contractor agrees to pay the Department a sum of $3000 for costs of mobilizing its forces and equipment.  In addition, the Contractor must pay the Department the actual cost of material used for the repair and pay the actual costs of police traffic protection.

703.03.07  Temporary Highway Lighting System

1**************************************************************************************************************************1

2**************************************************************************************2

Determine whether or not the Contractor must design the Temporary lighting system at a given location and include the following

SME CONTACT – traffic signal and safety engineering

The Contractor must design the Temporary lighting system at ___________________________

2**************************************************************************************2

2**************************************************************************************2

provide the locations to deliver and unload salvaged materials

SME CONTACT – traffic signal and safety engineering

Deliver and unload salvaged materials to:

2**************************************************************************************2

2**************************************************************************************2

the sixth PARAGRAPH is deletED:

the EIGHTH THROUGH tenth PARAGRAPHs are deletED:

2**************************************************************************************2

1**************************************************************************************************************************1

Section 704 – Intelligent Transportation Systems (ITS)

1**************************************************************************************************************************1

Prior to final design submission confirm with the respective traffic operations center if any of the proposed its systems have to be completed early in the project THAT ARE REQUIRED TO BE available to use for traffic mitigation during construction.  include respective interim completion dates in subsection 108.10 and confirm with Mobility and Systems Engineering (MSE) on the requirements for interim communication and power connections.

if project includes connection to njta network, including direct fiber or wireless, confirm with Mobility and Systems Engineering (MSE) on coordination requirements with njta.

SME CONTACTS – TRAFFIC OPERATIONS & MSE

1**************************************************************************************************************************1

1**************************************************************************************************************************1

BDC16s-03 dated Aug 24, 2016

the entire section text is changed to:

704.01  Description

This Section describes the requirements for providing, installing, configuring, calibrating, testing and placing into operation Advanced Traveler Information Systems (ATIS) and Advanced Traffic Management Systems (ATMS).

704.02  Materials

704.02.01  Materials

2**************************************************************************************2

MOST COMMON ITS MATERIAL SPECifICATIONS ARE AVAILABLE ON THE DEPARTMENT’S WEBSITE AND A QPL of pre-qualified materials is posted, DOWNLOAD THE REQUIRED SPECIFICATIONS FROM THE DEPARTMENT’S WEBSITE AND LIST THEM HERE IN THE TABLE REFERRING TO THE APPROPRIATE SUB SECTION OF SECTION 918 AND INCLUDE THE SPECIFICATIONS IN THAT SECTION

2**************************************************************************************2

Provide materials as specified in:

Coarse Aggregate (No. 57)	901.03

Concrete	903.03

Grout	903.08.02.A

Precast Concrete	904.01

Reinforcement Steel	905.01

Anchor Bolts	908.01.03

Miscellaneous Hardware	908

Coal Tar Epoxy Paint	912.01.03

Guide Rail, Fence, and Railing	913

Landscaping Materials	917

Conduit and Fittings	918.01

Cable and Wire	918.02

Loop Detector Lead	918.02.01

Loop Wire	918.02.02

Bonding and Grounding Materials	918.03

Resin Splicing Kits	918.05

Electrical Tape	918.06

Cable Racks	918.07

Cabinets	918.09

Panel Boards and Circuit Breakers	918.10

Standards	918.12

Follow the accepted standards of ANSI, NEMA, UL, NEC, ITE, and ASTM for materials not specified in the Contract.

For fittings and mounting hardware not specified, follow the manufacturer’s recommendations.

Provide materials as specified in the Contract and in the New Jersey Electrical Materials Specifications that are available on the Department’s website.  A listing of pre-qualified materials is also available on the QPL.

Submit the system working drawings in a complete package for approval.  The complete package of the system working drawings includes but is not limited to the ITS System Block Diagrams, Fiber Assignment Diagrams, and Rack/Cabinet Equipment Layout Diagrams; Certified Structural Details & Calculations.  All components must be approved in the system working drawings before use on the Contract.  List the ITS and EE approval numbers of each component in the equipment list on the system block diagram when a pre-approved product from the QPL is proposed to be used.  For all components that are proposed without a pre-approved number, submit eight copies of catalog cut sheets along with the working drawings.  Submit all structural components that are not listed on QPL separately for structural review and approval with the required certification and include a copy of all approvals when submitting the system working drawings to meet the complete package requirement.  For materials furnished and installed, provide a minimum 2-year warranty from the date of Completion against any imperfections in workmanship, components and materials.  Submit a warranty certificate to the RE from each material manufacturer, with the Department named as holder of the certificate.

704.02.02  Equipment

Provide equipment as specified in:

Traffic Control Equipment	1001

Vibrator	1005.04

Pavement Saw	1008.04

Hot-Air Lance	1008.06

Concrete Batching Plant	1010.01

Concrete Trucks	1010.02

704.03  Construction

704.03.01  General System (GS)

A.	Components.  A GS consists of the specified Items needed to modify an existing system or construct a proposed system.  The system includes, but is not limited to, electronic and electrical devices, cabinets, wiring, programming, configuration, communication and electric service connections, service charges, utility software, grounding, and surge protection

B.	Installation.  Before beginning the work and during the work, comply with the requirements of 701.03.01.  The allowable time frame for existing system shutdown will begin at 10 P.M. daily and continue through to 4 A.M. on weekdays, 5 A.M. on Saturdays, and 6 A.M. on Sunday mornings unless otherwise noted in the Special Provisions.  The Department will recover the cost of damages for exceeding the allowable time frames as specified in 107.16.  When installing a new system or modifying an existing system, ensure the respective manufacturer’s certified field representative of ITS components and related equipment is on site to commission the equipment into operation.  Restore the operation of the overall system to its original condition, the conditions specified in the Contract, or as directed by the RE.

When leased services are specified to be used, provide advance notice to Internet Service Providers to verify current status of service requests for all required ISP services.  Perform necessary coordination required to re-establish and revise any service requests that may have expired due to time constraints, or due to a change in the system requirements.

2**************************************************************************************2

cONTACT TRAFFIC OPERATIONS TO CONFIRM THE EXISTING SYSTEM SHUTDOWN TIME. REVISE AS DIRECTED and insert here

SME CONTACT – traffic operations AND MSE

2**************************************************************************************2

2**************************************************************************************2

Provide the cost of damages for exceeding the allowable time frames

SME CONTACT – MSE

2**************************************************************************************2

1.	Junction Box ITS.

a.	Installation.  Excavate as specified in 202.03.02.  Install junction boxes only in areas where the slope is not less than 22H:1V.  Place junction boxes on 10 inches of coarse aggregate No. 57.  With each junction box, provide six (6) coiling brackets, inserts and fasteners, and a ground rod and clamp.  Backfill and compact using the directed method as specified in 203.03.02.C.  Restore disturbed areas to the original conditions, the conditions specified in the Contract, or as directed by the RE.

2**************************************************************************************2

IF REMOVAL OR RELOCATION OF ITS JUNCTION BOX IS NOT FEASIBLE IN A PROJECT THAT REQUIRES TRAFFIC TO BE SHIFTED IN THE AREA OVER THIS JUNCTION BOX DURING ANY STAGE OF CONSTRUCTION THEN IT MUST BE PROTECTED DURING CONSTRUCTION AND MUST INCLUDE DETAILS FOR PROTECTING THE ITS JUNCTION BOX.

SME CONTACT – MSe

2**************************************************************************************2

b.	Relocation.  Submit plans showing the proposed method of relocation of junction box including provisions for maintaining network operation and/or cut-over during the process to the RE for approval.  Remove existing ITS junction box by excavating around the junction box, cutting back conduits, pulling the cable slack equally to adjacent junction boxes and notching the portion of junction box below the conduits sufficient to slide the fiber optic cable.  After removal of the junction box, re-couple the conduit(s), and terminate them using approved conduit repair kits and backfill with approved material and compact using the directed method as specified in 203.03.02.C.  Install the Junction Box after approval by the RE.  Ensure that the cut conduit ends are terminated at the entrance of the junction box wall using a manufacturer recommended kit depending upon the type of conduits.  Ensure that the fiber optic cable is pulled back from the adjacent junction boxes in equal length to maintain the required slack for immediate and future splicing.  Ensure that a ground rod and clamp are installed.

2.	Communication Cable.  Install communication cable from the utility pole or manhole to the controller.  Provide and install the material necessary to provide a complete installation, including a weather-tight terminal block enclosure on the utility pole as required by the Utility, cable ties, cable tags, labels, clamps, jumpers, and connectors.  Ensure that there are no splices in the section of cable between the terminal block and the devices.

Provide the standard allowable slack for cable and wire, as specified in 701.03.15.A, within the in-ground rectangular junction boxes.  Provide 3 feet of slack with an appropriate connector in the cabinet for connection to devices and utility service.  Provide 10 feet of slack to allow for the Utility to make their connections in the manholes or on utility poles.

3.	Foundation ITS.  Construct the foundation as specified in 701.03.12.

4.	Controller ITS.  At least 30 days before beginning the work, submit working drawings for approval that include a block wiring diagram illustrating the interconnections of the system components from the field location to the designated control center.  Identify each component by manufacturer and model number.

Securely bolt the controller, equipped with communications and electronic devices for a fully functional and operational system, to the foundation in a vertical position using stainless steel hardware.

5.	Communication Hub.  At least 30 days before beginning the work, submit working drawings for approval that include a block wiring diagram illustrating the interconnections of the system components from the field location to the designated communication hub or control center or both.  Identify each component by manufacturer and model number.  Procure technicians that are certified by the existing operating system providers to integrate the ITS devices into existing operating systems.  Coordinate with NJ Office of Information Technology (NJOIT) through the RE to establish Firewall/Network/IP addresses as required.  Ensure that a fully functional and operational system is provided.

6.	Control Center System.  At least 30 days before beginning the work, submit working drawings for approval that include a block wiring diagram illustrating the interconnections of the system components from the field location to the designated communication hub or control center or both.  Identify each component by manufacturer and model number.  Procure technicians that are certified by the existing operating system providers to integrate the ITS devices into existing operating systems.  Coordinate with NJOIT through the RE to establish Firewall/Network/IP addresses as required.  Ensure that a fully functional and operational system is provided.

2**************************************************************************************2

include the work to be performed at eACH control center (toc, HUB OR ANY BUILDING/CABINET WITH A NETWORK NODE) clearly and remove the portion of the work that is not applicable to any particular project as the bid price for this item will be based on the work involved at the designated control center. THE DESIGNERS MUST INCLUDE SYSTEM BLOCK DIAGRAMS AND FIBER ASSIGNMENT DIAGRAMS IN THE SET OF CONSTRUCTION PLANS. THE CONTRACTOR WILL USE THESE AS WORKING DRAWINGS BY ADDING A LIST OF EQUIPMENT AND NETWORK IP ADDRESSES.

SME CONTACT – MSE

2**************************************************************************************2

Ensure the ITS System Network working drawing is submitted in a format acceptable to the Department. Sample ITS Working Drawings are available at:

http://www.state.nj.us/transportation/eng/elec/ITS/pdf/sampledrawings.pdf

Ensure the working drawing contains the following information:

1	Affected network nodes are shown in nodal format with Latitude/Longitude.

2.	Each node shows equipment type and the proposed communication links between them.

3.	Distances between Ethernet switches and calculated dB loss between them.

4.	A Communication Network Assignment Table specifying Equipment Location (Node, Site ID, Lat/Long, Plan sheet reference, Route, Mile Post), Equipment Information (Item No., Description, Function, VLAN No., Subnet Mask, and IP Address).

Supply and install equipment, software, software revisions, firmware, miscellaneous wiring and cabling, at the specified Control Centers to ensure the remote operation and control of all ITS field devices from the Traffic Operation Centers.  Comply with building installation requirements, restrictions, access, and security requirements in the performance of work.  The material and work required for the integration of the various ITS installations into the various existing operating systems or subsystems used by the Department includes, but is not limited to, the following:

a.	At least 5 (five) business days in advance of requiring access to the designated Control Center, submit a Facility Daily Access Request Form available on Department’s ITS website.

b.	Ensure complete functionality with field devices.  Coordinate with the Department for access, rack space, and LAN connections to Client Workstations, respectively.

c.	Ensure CCTV encoders are compatible with approved camera system especially for PTZ and focus control and CCTV Controller Software.

d.	Ensure CCTV Controller Software is updated by integrating new cameras installed and ensure video and control is available to all necessary Traffic Operations personnel.

e.	Ensure DMS signs are integrated and remotely operable by the DMS Controller Software.

f.	Ensure TTS Devices are integrated and operational in accordance with Contract requirements.  Develop the required travel time routes and the appropriate travel time sign messages as directed by the Department.

g.	Ensure CTSS components are fully integrated and all the necessary functionality is demonstrated in the designated CTSS Controller Software.

h.	Secure and provide all necessary Network configurations and assignments as directed by the Department.

i.	Provide and install other electronic equipment that may become necessary as a result of network protocol translation, electrical signal transmission degradation or communications media translation (fiber optic, coax, DSL interface, network interface, etc.)

j.	Provide for software support to integrate new ITS devices into new and existing platforms for workstations and servers utilized by DOT operators. This includes work required from each of the software suppliers for workstations located remotely from the Traffic Operation Centers.  The Department will provide information regarding the respective system, on particulars for authorized remote users.

k.	Provide for the installation of network assignments for field devices as well as enabling the network and device management protocols as directed by the Department.

l.	Ensure that network support requests through the RE to the Department are made at least 60 days prior to the installation of all devices to be included in the network.

m.	For RWIS, integrate weather station(s) into the appropriate password protected website as directed by the Department.

n.	For WIMS, integrate the system for live data retrieval by the designated staff with password protected website as directed by the Department.

7.	Meter Cabinet ITS.  Install cabinets, meters, control and distribution systems, including the grounding of all materials, and internal wire and wiring.  Install the metering systems as required by the Utility.

2**************************************************************************************2

This includes a fnmc reserved for electrical service conductors that may require separate junction boxes at short intervals. coordinate with MSE before PROCEEDING WITH THE DESIGN plans to determine what is exactly required. If a fiber glass sleeve is required, specify it and include with bridge structure attachments and expansion fittings as per manufacturer requirements. When Fiberglass conduit is not proposed across an existing structure, built-in sleeves within the parapet can be utilized if empty and available.

ITS CONDUIT TYPE A INCLUDES THREE (3) fnmc. IF THE PROJECT SPECIFIC CONSTRUCTION REQUIREMENTS NEED DIFFERENT SIZE CONDUITS, modify THE STANDARD detail TO incorporate the proposed changes AND includE IT IN THE SET OF PLANS reflecting the correct size and type of conduits. ALSO, REVISE THE SPECIFICATIONS BELOW TO LIST ANY CHANGES NEEDED TO MATCH THE TYPE OF CONDUITS OTHER THAN FNMC.

SME CONTACT – MSE

2**************************************************************************************2

8.	ITS Conduits.  Install Flexible Nonmetallic Conduits as specified in 701.03.07 with the following exceptions:

a.	Do not install mechanical joints on conduit runs between junction boxes.

b.	Obtain RE approval for fusion joints that may be permitted under special circumstances on conduit runs between junction boxes.

c.	Provide an as-built list indicating the location of all joints to the RE.

d.	Install a continuous tracer wire without any splice in the conduits and from junction box to a termination point in the field cabinet.

e.	Ensure that conduits and ducts entering a junction box, foundation, cabinet, hub, or building are terminated based on manufacturer’s recommendation and are rodent proofed and sealed around cables, or plugged if conduit is built for future use.

f.	Ensure that the ITS Conduits facilitate the various means of cable and wire installations including but not limited to pulling, jetting, and blowing of fiber optic cable and electrical wires.

g.	Install conduits simultaneously with proposed curb work and prior to constructing resurfacing courses.

h.	Install true tape marked in 1-foot increments for the length of the ITS Conduit.

i.	Install warning tape in the trench above the conduit.

j.	Restore disturbed areas to the original conditions, the conditions specified in the Contract, or as directed by the RE.

9.	Fiber Cross-Connect Cabinet.  Submit working drawings for approval that include a block wiring diagram illustrating the interconnection of the system components within the cabinet.  Identify each component by manufacturer and model number.  Install a Fiber Cross Connect Cabinet on Foundation ITS Type A with concrete pads on front and back of the cabinet.  Ensure all fiber optic cables entering this cabinet are terminated into individual patch panels.  Provide and install jumpers between multiple patch panels as required to complete the fiber network continuity.

10.	ITS Integration.  Procure the services of a Systems Integrator to ensure ITS systems and individual components are integrated as shown on the plans and in the specifications.  Submit proof of the integrator’s qualifications demonstrating 3 years of experience on similar ITS construction projects and on similar magnitude to the RE for review and approval.  Provide certifications and credentials demonstrating the integrator is certified as a Professional and authorized by Cisco® to provide the services required for the network devices.  Ensure that all ITS network drawings are prepared and certified by the Systems Integrator.

C.	Testing.  Perform wiring and cable testing, as specified in 701.03.15.D, before performing other testing.  Complete the device and system testing as indicated on the Department provided forms and instructions.  Provide trained personnel to test the system and subsystems.  This includes providing manufacturer certified representatives to ensure complete functionality of said systems and subsystems.  The period of testing under this section and in the various testing forms available from the Department's website are in terms of working days.  The test will be extended if there are state holidays during the designated testing period.  When a device fails during any phase of the testing period, the testing period will be rescheduled to progress again starting from day one of that phase after the problem is addressed for the testing time period specified.

1.	Device Testing.  Before beginning system testing, complete individual device testing as follows:

a.	Level A.  Demonstrate that the individual devices at each work site are fully operational.

b.	Level B.  Demonstrate that each device is fully operational from the designated control center to the work site with the original equipment manufacturer software.  The Department will operate and monitor the device for a minimum of 7 working days to observe its functionality.

c.	Level C.  Demonstrate that each device is fully operational from the designated control center to the device work site after integration into the designated control center software management systems.  Conduct a test to verify that the device and communications meet the specified requirements of the Contract.  After the Contractor’s verification test, the Department will conduct a 14-day observational and functional test period.  Provide support as needed during this testing, including adjustments to or replacements of the equipment and materials installed, modified, or otherwise disturbed until the full 14-day observation period is completed without failure as determined by the Department.

Upon successful completion of level C testing of a device, the Department will accept the device on an interim basis and will pick up the cost of associated utility services for that device from the next billing cycle as specified in 701.03.15.

2.	Project Testing.  After completion of device testing, verify the operation of the individual devices from all locations interconnected and functioning as a complete and integrated system by exercising control with the central control software of Level C.  In the presence of the RE, ensure that the manufacturer’s authorized technician is present to assist with installation, configuration, and testing of system hardware and software.

After the Contractor’s verification test, the Department will conduct a 14-day observational and functional test period of all systems on the Project.  Provide support including adjustments to or replacements of equipment and materials until the 14-day observation and functional test period is completed.

In the event of a failure as determined by the RE, the RE will suspend the observation and functional test period until corrective action is completed.  After the corrective action is completed, the RE will resume the observation and functional test period.

D.	Maintenance.  Perform maintenance as follows:

1.	Regular Maintenance.  Perform regular maintenance and repairs as specified in 108.09 after interim acceptance of a device or project testing or both until acceptance of the project and as follows:

1.	Troubleshoot malfunctioning equipment within 48 hours of failure notification by the RE.

2.	If the Contractor cannot complete the repairs in the time specified by the RE, the Department may repair the equipment and recover the cost as specified in 107.16.  The Department will assess liquidated damages at a minimum of $1000 per hour for each hour after the specified time until the completion of the repair.

3.	Record the work performed and submit the record to the RE.  Include an explanation of the exact repairs made and identification of parts replaced by part number and circuit number.

If the Contractor fails to respond to a failure or damage notification and begin work within 2 hours of notification, the Department may respond with its own forces to restore normal operation.  If the Contractor begins the work but does not finish the work within a reasonable time period as determined by the RE, the Department will also respond with its own forces to restore normal operation.  If the Department mobilizes its forces to perform repairs, the Contractor agrees to pay the Department’s cost of performing the work including the cost of material and labor used for the repair and the actual costs for police traffic protection and maintenance and protection of traffic.

2.	Operational Maintenance.  If an Item has completed system device testing before Substantial Completion, perform operational maintenance in 6 month intervals as follows:

1.	Exercise the equipment functionality, including uploads, downloads, fans, lights, and sensors.

2.	Replace filters, clean lenses, and check communications.

3.	Run diagnostics.

4.	Record all work and submit it to the RE.

E.	Final Documentation.  Submit 2 sets of the complete schematics and maintenance manuals of the equipment for each type of device provided.  Include a complete sub-component parts list with each maintenance manual.  Place one complete set of manuals of each device in the respective controller cabinet installed in the field, and provide a set to the RE.  Also, send an electronic set to the RE.  Provide documentation listed under this section at or prior to Substantial Completion of the project.

Submit as-built documentation showing the function and detail of each individual fiber and termination connection installed.  Submit as-built drawings for each subsystem, including wiring and set up configurations, and software versions.

Provide drawings and diagrams in the Department’s CADD format in accordance with the file structure and standards of the Department.  Provide reports in MS Word format.

At a minimum, also include the following documentation:

1.	Controller equipment layout and wiring.

2.	System wiring diagram that illustrates the connections and cross-connections between equipment components from the field device through to the designated control center equipment and rack profiles.  Include work site and designated control center set up configurations and firmware versions installed.

3.	Licensed copies of the software needed for complete operation and testing of the system.  Include software necessary to read the electronic files of the test results and documentation and needed to program and configure devices for any software not covered by an existing Department license.  Ensure software is compatible with the Department’s current operating software.

4.	Controller communication protocol and System Development Kit.

5.	As-Built (GPS) Inventory Report on forms provided by the Department and in the required format.

6.	The original signature certification from an independent laboratory that the devices have been tested and comply with the NTCIP protocol requirements of this Contract.

7.	2 CD-R copies of the final documentation and 2 paper copies.  Compile and organize the test results in 3-ring binders.

8.	Troubleshooting guidelines that identify symptoms, rank their possible causes in order of highest probability, and recommend remedial actions and the required testing equipment.

9.	Installation, operation, configuration, programming, maintenance, data, and schematic manuals.

10.	Certification of successful deployment of ITS components from the respective equipment manufacturers with complete details of any repair work performed under warranty.

11.	Commissioning reports.

12.	Warranty certificates.

F.	Equipment Training.  Provide, for use by the Department, equipment necessary for proper instruction, demonstration, and testing of the system materials.  Submit software used for testing to the Department for use in equipment maintenance.  The software will become the property of the Department.

Provide training for installation, control, testing, and maintenance of the systems for ten (10) Department personnel.  Schedule the training with the designated control center personnel to avoid interruption of daily Department operations.  If necessary, conduct the training over several sessions or in multiple groups.

G.	Warranty.  In addition to the provisions set forth in 108.21, procure a service agreement for parts and labor to cover the period between the commissioning of the device by the manufacturer and Completion.  Document the repairs made, by the manufacturer or its designated representative, to the device prior to Completion.  Include an explanation of the exact repairs made and identification of parts replaced by part number and circuit number.  Provide the necessary equipment for safe access to the installed device along with traffic control promptly upon request by the manufacturer to perform the repairs under the service agreement during this period.  Provide the Department with a complete record of the repairs made to each device as part of the Final Documentation.  Ensure that a minimum two-year warranty certificate by the manufacturer is provided and transferred to the Department with documentation as set forth in 704.02.01 for any repairs to be performed by the manufacturer after the date of Completion.  Ensure that the start and end dates of the warranty are clearly stated on the certificate.  Ensure the warranty includes shipping costs, a statement for the repair or replacement of all failed components or both to be performed by a factory authorized depot repair facility located in the United States, and that the components are returned to the Department within two weeks of the date of receipt at the repair depot.  Ensure that unlimited technical support from the manufacturer or authorized dealer is provided within 4 hours of the time a call is made by the Department.

H.	Networking Requirements.  Provide ITS network devices as directed by both the Department and the State Office of Information Technology (OIT) to ensure the efficient operation, security and diagnostic capability of the ITS network being installed or modified.  Provide trained personnel with the proper credentials (specifically with a Cisco Certified Network Professional certification) to properly interface and configure the ITS network to the State’s network and to also interface with OIT and the Department’s IT staff.  Ensure the Cisco Certified Network Professional (CCNP) has at least three 3 years of experience on similar ITS networks with similar in size, complexity, and scope of this contract.  Provide credentials of the CCNP to the Department for approval.  Obtain a Virtual Private Network (VPN) into the Department’s network to set up and monitor the network under construction by CCNP.  This includes, but is not limited to the following:

1.	Providing necessary Layer 3 configurations

2.	Obtaining and installing network assignments

3.	Security provisions

4.	Multiple Virtual Local Area Network’s (VLAN’s) for IP switches, routers and ITS devices as directed

6.	Enabling Rapid Spanning Tree protocols

7.	Internet Group Management Protocol (IGMP)

8.	Setting up VPNs, White lists, and Black lists

9.	NATting, multicasting,

10.	Configuring routers for broadband services

11.	Other settings as deemed necessary by the Department

12.	Other hardware configurations that are required at the behest of the Department and OIT

Ensure the correct Fiber Optic Transceiver is utilized for each switch and the correct transceiver power is used based on distance and dB loss

Ensure all Internetwork Operating System (IOS) and protocols for the network devices are compatible across the network.

Ensure that the default IP addresses and passwords set from the manufacturer are changed for all electronic devices where applicable and forward that information to the RE for each device.  This includes but is not limited to ITS devices, IP switches, routers, modems and wireless equipment.

Provide an Ethernet Networking Block Diagram along with an Excel spreadsheet that includes the networking devices and the descriptions of device type, Network Assignment, and corresponding switch port and other requirements as it pertains to Ethernet networking.

I.	IT Requirements.  At least three (3) months prior to systems roll-out supply the RE with the software systems installation CD/DVDs, End User License Agreement (EULA) & other applicable licenses, instructions and configurations/settings that are required.  Turn over the licenses indicating NJDOT as being the licensee at the time of acceptance.

Provide the above information in an acceptable way for NJDOT’s Division of Information Technology’s Security and Services personnel to perform the Server-side and Client-side installation, support and troubleshoot of the application without the need of a third-party.  Refer to 704.03.01.F Equipment Training for the required training.

Failure to comply with this time-constraint will result in delayed Substantial and Final Completion.  The Department reserves the right to seek Liquidated Damages, as specified in 108.20 of the Special Provisions, for each day delayed for Substantial and Final Completion.

704.03.02  Camera Surveillance System (CSS)

A.	Components.  CSS consists of the specified components in order to provide a complete system capable of processing video and control data to and from the designated control center.  The system also includes but is not limited to wiring, communication and power connections, network equipment, encoder/decoder, service charges, software, grounding, and surge protection.

B.	Installation.  Before beginning the work and during the work, comply with the requirements of 701.03.01.  The allowable time frame for existing system shutdown and cost of damages for exceeding the allowable time frames will be as specified in 704.03.01.B.  If directed by the RE, provide a bucket truck with safety equipment that can reach the height of the camera.  Operate the bucket truck for the Department to use to determine the camera’s final location and orientation, and for testing

Construct components as follows:

1.	Foundation CSS.  Construct the foundation as specified in 701.03.12.

Ensure that the anchor bolts are placed after verifying the orientation of the camera lowering system to minimize the obstruction of desired camera view by the Camera Standard.

2.	Camera Standard.  Bolt the standard securely to the foundation, and erect the standard with sufficient rake to assume a vertical position after all attachments and appurtenances are in place.  Install a ground wire that extends to the ground rod from the standard.

At least 30 days before beginning construction, submit working drawings for approval that include structural calculations meeting the specified criteria.  Ensure the calculations are signed and sealed by a Professional Engineer.

3.	Camera.  Mount the camera housing and camera according to the manufacturer’s recommendation.  Ensure that the camera’s field of view is unobstructed.  Perform tree trimming and site clearing to provide an unobstructed field of view as directed by the RE.  Set up “On Screen Display” to indicate the quadrant views with directional titles (e.g. NB view, EB view, SB view, WB view) displayed in the bottom right corner of the screen for each camera.  Leave the display blank for any quadrant not representing any highway view.  For a camera with multiple highway views, include route and directional title (e.g. Rt 1 NB view).  Also, establish a pan and tilt zones system and set up 4 presets for quick pan-tilt-zoom views prior to level B testing.  At least 6 days prior to Level C testing, submit a request to the RE for the Department to integrate each camera into the designated control center CSS control software management system in use at the time of construction.

Ensure the camera is equipped with video and control cables that have weatherproof connectors and strain relief.  Ensure cables are factory assembled and tested according to the camera manufacturer’s recommendations.  Make all wire and cable camera connections to the camera controller.

Apply a polymer spray recommended by the camera manufacturer to enhance rainwater sheeting and runoff on the dome and positional housing.

4.	Controller, Camera.  Submit working drawings for approval that include a block wiring diagram illustrating the interconnections of the required CSS components for successful transmission of video from the field location to the designated control center and the remote operation from TOC using central CSS software.  Identify each component by manufacturer and model number.

Mount the camera controller cabinet to a foundation as specified in 704.03.01.B.4.  Ensure that the conduit entry points are properly closed off with duct sealing compound.  Install the controller according to the manufacturer’s recommendations.  Provide and install all required components.

C.	Testing.  Perform testing as specified in 704.03.01.C.

D.	Maintenance.  Perform maintenance as specified in 704.03.01.D.

E.	Final Documentation.  Provide the documentation specified in 704.03.01.E.

F.	Equipment Training.  Provide training as specified in 704.03.01.F and in the Special Provisions.

2**************************************************************************************2

provide recommendation prior to final design submission for any special training, and/or if more than 10 personnel require the training.

SME CONTACT – MSE

2**************************************************************************************2

G.	Warranty.  Perform repairs under warranty and provide documentation as specified in 704.03.01.G.

H.	Networking Requirements.  Comply with the networking requirements and perform work as specified in 704.03.01.H.

I.	IT Requirements.  Comply with the IT requirements and perform work as specified in 704.03.01.I and in the Contract documents.

704.03.03  Fiber Optic Cable

A.	Components.  When installing fiber optic cable, provide a complete communications path between 2 or more ITS devices.  Installing fiber optic cable includes, but is not limited to, providing and installing conduit, junction boxes, cables, splicing, communication and power connections, service charges, terminations, software, and grounding.

At least 30 days before beginning work, submit to the RE for approval a fiber optic installation plan that lists the following items and includes a brief narrative on each:

1.	Cable layout with splice locations and linear distances between splice points.

2.	Fiber specific connection assignments to devices.

3.	Catalog cut of the cable lubricant.

4.	The manufacturer's minimum allowable cable and fiber strand bending radii.

5.	Pulley wheel sizes.

6.	Manufacturer's maximum outer jacket pulling tensions and monitoring device.

7.	If using an air pressure system, list the blowing pressures applied to each cable size and conduit type.

8.	Provide certifications from the fiber optic splice unit, OTDR, and power meter equipment manufacturer that verify the qualifications of each individual employed to perform the work.

B.	Installation.  Before beginning the work and during the work, comply with the requirements of 701.03.01.  The allowable time frame for existing system shutdown and cost of damages for exceeding the allowable time frames will be as specified in 704.03.01.B.

Provide and install the material necessary for a complete, functional installation including cables, cable ties, jumpers, cable identification tags, pigtails, breakout kits, connectors, patch panels, splices, splice enclosures, testing, end caps, consumables, attenuators, and related documentation.  Ensure that cable tags follow the industry standard CLEI GR-485-CORE format and nomenclature for communications and electronic components.

After the connections are completed, provide the minimum amount of slack for each cable that enters a junction box or termination enclosure as specified in Table 701.03.15-1.  Provide additional slack as required to meet the proposed installation as follows:

1.	For an ITS Junction Box provide a total of sixty (60) feet of slack (30 feet from each entry point.)

2.	For a Hub provide 10 feet of slack

3.	For a Cabinet provide 3 feet of slack

Attach cable tags to cables at junction boxes that contain multiple cables and at all cabinets.  Secure them with nylon cable ties.

For armored cables, install a ground rod, ground and bond all armor casings at any existing or proposed junction box at which electrical power conductors are also present.

Before installing the tracer wire, obtain RE approval of the installation locations of the tracer wire.  Install a continuous tracer wire in the conduit.  Do not splice tracer wire in the conduit.  Provide 10 feet of slack in each junction box.  If approved by the RE, the Contractor may splice the tracer wire in the junction box.  If more than one conduit is installed in a single trench, the Contractor may install the tracer wire in only one conduit.  When installing fiber optic cable in existing conduits, install a tracer wire as specified in 701.03.15.A.  Perform testing of existing tracer wires for continuity and perform splicing as required in junction boxes to ensure access to the tracer wire from cabinet to cabinet.

Ensure that splices are fusion splices.  Install splices only in ITS junction boxes or ITS cabinets.  Use splice enclosures for splices made in junction boxes.  For mid-span termination cable entry, cut only those individual fiber bundle/strands needed (ring cut) for connection to the devices.  For those fibers designated for trunk line communications, do not cut the fibers or install cables that require splices at lengths less than 2500 feet.

Splice a manufacturer recommended fiber optic breakout kit with connectors to each end of the strands for a cable that terminates at a device cabinet.  Label each strand using machine-printed, laminated, self-adhesive labels.  Fully document the connections and individual splices in the as-built drawings.

C.	Testing.  Perform wiring and cable testing as specified in 701.03.15.D before performing any other testing.  The Department will provide forms detailing the testing requirements for the following tests:

1.	Level 1.  Test each splice with the fusion splicing unit at the time the splice is made.  Record each splice decibel value electronically with the splicing machine at 1310 nanometers.  Provide 2 paper copies and 1 electronic copy of the results immediately to the RE for review and approval.  Clearly identify each fiber on the report.  Ensure that the maximum splice loss does not exceed 0.05 decibels.  If the 0.05-decibel value cannot be reached in 3 attempts, the RE may employ a third party vendor to redo the work.  The Department will recover the cost as specified in 107.16.  Provide the RE with certification from the equipment manufacturer that the splice machine was calibrated within 3 months of its use on the Contract.  Recalibrate the splice machine at 6-month intervals from the initial calibration by the manufacturer.

2.	Level 2.  Perform the following Level 2 tests:

a.	OTDR.  Test each individual fiber after completion of splicing and connections.  Perform the testing at 1310 and 1550 nanometers in both directions.  Ensure that the maximum decibel loss for any single event is not greater than 0.3 decibels at 1310 nanometers; however, ensure that the OTDR machine threshold is set to record events greater than or equal in absolute value to 0.05 decibels along the positive and negative axes.  Events revealed by the OTDR machine bi-directional trace average to exceed 0.3 decibels are cause for the rejection of the cable.  If directed, remove and replace the cable.

Ensure that the net result of the bi-directional trace average at 1310 nanometers across a splice event is not greater than 0.15 decibels.  Redo splices revealed by the OTDR machine to be greater than 0.15 decibels up to 2 additional times in order to achieve 0.15 decibels or less.  If the 0.15-decibels value cannot be reached in 3 attempts, the RE may employ a third party vendor to redo the work.  The Department will recover the cost as specified in 107.16.

Ensure that reflectance at each connector is better than (−55) decibels.  Ensure the fiber loss across each fiber segment is not greater than 0.4 decibels per kilometer when tested at 1310 nanometers.

Also test, and include in the report, the dark fiber segments that are not being utilized by the signal transmission equipment.  Provide connectors as necessary to test unterminated fibers.

Provide 2 paper copies and 1 electronic copy of the results immediately to the RE for review and approval.  Clearly identify each fiber on the report.  Provide the RE with certification from the equipment manufacturer that the OTDR was calibrated within 3 months of its use on the Contract.  Recalibrate the OTDR at 6-month intervals.

b.	Power Meter.  Measure and record fiber segment optical budgets including each end connector, according to the meter manufacturer instructions.  Compile the test results in a binder and submit 2 copies with the final documentation.  Perform power meter tests at 1310 nanometers and 1550 nanometers in both directions after completion of cable and connector splicing.  Ensure that the maximum connector loss tested at 1310 nanometers is 0.8 decibels with the average of all connectors in the tested fiber segment being 0.5 decibels.

Provide 2 paper copies and 1 electronic copy of the results immediately to the RE for review and approval.  Clearly identify each fiber on the report and the work site location of the end points.  Provide the RE with a certification from the equipment manufacturer that the power meters were calibrated within 3 months of their use on the Contract.  Recalibrate at 6-month intervals.

After completion of Level 1 and 2 tests, perform network communication system testing and demonstrate that the communication system is fully operational to meet the material specifications and project requirements.  Complete the testing as specified on the Department provided forms and instructions.

D.	Maintenance.  Perform maintenance as specified in 704.03.01.D.

E.	Final Documentation.  Provide the following:

1.	Individual splice connection as-built drawings in the format specified by the Department.

2.	Splice machine, OTDR, and power meter readings with manufacturer’s software disks to read the test results.  Include power meter test results for each individual fiber section showing the optical budget between the termination point connectors.  Include all unused fibers.  Include OTDR electronic trace files and computer software so that the user can set any threshold values desired for all parameters and can view all ranges of events.

3.	Cable identification key sheet.

4.	Spreadsheets that identify the file names of the same fiber shot in both directions.  Identify the individual common events and calculate the true event loss by averaging the point value of the fiber traces from each direction.  Include this calculation in the spreadsheet tables.  Supply 2 CD-R copies of the final documentation and 2 paper copies.  Compile and organize the test results in 3-ring binders.

5.	Licensed copies of splice and test equipment software.  Ensure that the software is compatible with Windows XP operating system.

6.	Communications system equipment fiber optic interconnections, including patch panel cross connections.

7.	Inventory Report on the form provided by the Department.

F.	Equipment Training.  Provide training as specified in 704.03.01.F and in the Special Provisions.

2**************************************************************************************2

provide recommendation prior to final design submission for any special training, and/or if more than 10 personnel require the training.

SME CONTACT – MSE

2**************************************************************************************2

704.03.04  Controlled Traffic Signal System (CTSS)

A.	Components.  CTSS consists of the Items needed to provide a complete system that is capable of controlling a series of interconnected signalized intersections and processing control data to and from the designated control center.  The system also includes, but is not limited to, electronic and electrical devices, network equipment, servers, cabinet, wiring, programming, configuration, communication and electric service, service charges, connections, software, grounding, and surge protection.

B.	Installation.  Before beginning the work and during the work, comply with the requirements of 701.03.01.  The allowable time frame for existing system shutdown and cost of damages for exceeding the allowable time frames will be as specified in 704.03.01.B.  Prior to beginning any work, coordinate with Traffic Operations and NJOIT to confirm the system architecture and placement of the specified servers.

Construct components as follows:

1.	Controller, CTSS.  Submit working drawings for approval that include a block wiring diagram that illustrates the interconnections of the CTSS components from the field location to the designated control center.  Identify each component by manufacturer and model number.

Construct as specified in 702.03.01 and configure the CTSS software.

Configuration of the CTSS software includes the following at a minimum:

a.	Setup of intersection parameters, coordination parameters, system parameters, and graphics including all GIS shape files and aerials

b.	Configuration of control operations and coordination

c.	Development of intersection operational databases

d.	Configuring and programming local traffic controllers

e.	Inputting the timing plans into the CTSS software and traffic controller software to be utilized as a fallback backup for intersections that are not running in the adaptive mode

f.	Integration of the CTSS server, workstations and local traffic controllers with the communication network

g.	Integration of the Image Detection units and System Detection units with traffic controller.

h.	Configuration and calibration of Image Detection units

i.	Configuration and calibration of System Detection units

j.	Integration of the Image Detection server and Image Detection units with the communication network

k.	Configuration of Image Detection System

l.	Integration of the System Detection server and System Detection units with the communication network

m.	Configuration of System Detection System

2.	CTSS Controller Unit.  Submit working drawings that include a block wiring diagram that illustrates the interconnections of the CTSS components from the field location to the designated control center.  Identify each component by manufacturer and model number.

Provide and install a traffic controller unit, NEMA “D” panel and harness to maintain compatibility in the existing traffic signal controller cabinet.  Perform: the required wiring; CTSS software configuration, programming and testing; and remove the existing controller unit from the traffic signal control cabinet.  Provide and install traffic signal controller module hardware and software necessary to satisfy the communications and manufacturer requirements of the requested type of CTSS.  Clean dust, dirt, and debris from the inside of the cabinet and replace air filters and light fixtures.  Employ a manufacturer’s certified representative to program and configure the controllers with the timing plan directive parameters.  Place the intersection into cabinet flash during installation of the CTSS controller unit.

Configure the CTSS software as specified in 704.03.04.B.1.  Controller, CTSS.

3.	Controller, CTSS Turn On.  Controller CTSS Turn On consists of supplying a technician authorized by the controller manufacturer at the work site when each controller is placed into flash mode and into final operation.  Provide the RE a letter at least 48 hours in advance of the work, from the controller manufacturer, stating the technician is authorized and qualified to perform the work.  Ensure that the technician is available at all times during flash mode testing.  Ensure that traffic signals complete a successful flash period for 3 consecutive days as part of the required testing.   The Department will allow the signal to be on flash mode between 11:00 pm and 4:00 am.  Program the Department’s existing signal timing directives as a fallback for when the system is not running in adaptive operation.

4.	System Detector, Type Radar.  At least 30 days before beginning construction, submit working drawings for approval that include structural calculations for the pole-mounted System Detector equipment.  Ensure the calculations are signed and sealed by a NJ-licensed Professional Engineer.  Submit a block wiring diagram and cabinet layout diagram for integration of the System Detectors in the applicable traffic signal cabinet back panels, the existing Department Traffic Management System, and the CTSS.  Identify each component by manufacturer and model number.  Provide and install a local disconnect switch and grounding components in accordance with NEC requirements.  Ensure that the work conforms to the NEC and does not violate the High Voltage Proximity Act.

Mount the radar detectors as displayed on the Plans.  Provide and install the required components at the System Detector locations and in the CTSS controller cabinets, including but not limited to communications components, firmware, contact closures, and applicable network components.

Provide and install pole-mounted cabinet enclosures and hardware required to house equipment at System Detector locations.  Provide and install material, equipment, and wiring required to control and power the equipment.

Obtain and provide software licensing required to successfully interface and integrate the radar detectors with NJDOT’s head-end traffic data storage server, existing Traffic Management System, and CTSS.  Provide for the transmission of detector-collected data to the NJDOT storage server.  Coordinate with NJOIT and the Department to determine and verify data port assignments in the field and at the server to automatically transmit the archived data to an FTP server.

C.	Testing.  Perform testing as specified in 704.03.01.C and in accordance with the Verification Plan and Department Testing and Certification Procedures using the forms found at the following link:

http://www.state.nj.us/transportation/eng/elec/ITS/testing.shtm

After the Contractor’s verification testing of the Adaptive CTSS is completed in accordance the Verification Plan and the Department’s CTSS Testing and Certification forms, the Department will conduct an observational and functional “burn-in” test period of the systems on the Project which may last up to 6 months.  During this period the Department will validate the CTSS in accordance with the Validation Plan with the contractor providing assistance and support where necessary.

Also, before delivery to the Project Limits, perform a 168-hour burn in test period for the assembled, programmed and configured CTSS controller and CTSS controller unit following the requirements of 702.03.01 for continuous operation without failure.

D.	Maintenance.  Perform maintenance as specified in 704.03.01.D.

E.	Final Documentation.  Provide the documentation specified in 704.03.01.E and the following:

1.	For CTSS controller, provide a detailed drawing of the controller back panel and subpanel wiring and equipment layout.  For CTSS controller unit, provide the detailed “D” harness wiring drawing and the connections to the back panel.

2.	Original signature certification of the CTSS controller and CTSS controller unit to verify that the equipment has been programmed, configured, wired, functions, and operates as specified in the Contract.

3.	For Image Detectors and System Detectors, provide configuration and calibration parameters for each detector.

4.	Provide documents and information related to installation of CTSS devices, servers and workstations communicating on the NJDOT network as required by OIT and IT.

F.	Equipment Training.  Provide training as specified in 704.03.01.F and in the Special Provisions.

2**************************************************************************************2

provide recommendation prior to final design submission for any special training, and/or if more than 10 personnel require the training.

SME CONTACT – AAM UNIT OF MSE

2**************************************************************************************2

G.	Warranty.  Perform repairs under warranty and provide documentation as specified in 704.03.01.G.

2**************************************************************************************2

cONTACT mse’s aam unit for any specific warranty requirements and modify the above TO meet their requirements and insert here

SME CONTACT – AAM (Advanced ARTERIAL Management) of MSE

2**************************************************************************************2

H.	Networking Requirements.  Comply with the networking requirements and perform work as specified in 704.03.01.H and in the Special Provisions.

2**************************************************************************************2

provide additional networking requirements

SME CONTACT – NJOIT

2**************************************************************************************2

I.	IT Requirements.  Comply with the IT requirements and perform work as specified in 704.03.01.I and in the Special Provisions.

2**************************************************************************************2

provide additional IT requirements

SME CONTACT – njOIT

2**************************************************************************************2

704.03.05  Travel Time Systems (TTS)

A.	Components.  A TTS consists of the specified components needed to provide a complete system that is capable of measuring traffic speed, time, and volume, can process data to and from the designated control center and is integrated into the central control system for the purpose of determining and reporting travel time information.  The system also includes, but is not limited to, the electronic and electrical equipment, wiring, central system database configurations, communication and electric service connections, service charges, software, grounding, and surge protection.

B.	Installation.  Before beginning the work and during the work, comply with the requirements of 701.03.01.  The allowable time frame for existing system shutdown and cost of damages for exceeding the allowable time frames will be as specified in 704.03.01.B.

Construct components as follows:

1.	Foundation, TTS.  Construct the foundation as specified in 701.03.12.

2	Detector Standard.  Bolt the standard securely to the foundation, and erect the standard with sufficient rake to assume a vertical position after the attachments and appurtenances are in place.  Install a ground wire that extends to the ground rod from the standard.

3	Controller, TTS.  Submit working drawings for approval that include a block wiring diagram that illustrates the interconnections of the TTS components from the field location to the designated control center.  Identify each component by manufacturer and model number.

Securely bolt the controller cabinet to the foundation in a vertical position using stainless steel hardware.  Seal the underground conduit entrance to the controller with a sealing compound.

4	TTS Detector.  Submit working drawings for approval that include a block wiring diagram that illustrates the interconnections of the TTS components from the field location to the designated control center.  Identify each component by manufacturer and model number.

Install the detector according to the manufacturer’s recommendations.

Mark wire and cable detector connections to the controller.

C.	Testing.  Perform testing as specified in 704.03.01.C.  Ensure that the system demonstrates accurate posting of travel times during AM, Midday, and PM peaks in accordance with TTS test forms and specified requirements.

D.	Maintenance.  Perform maintenance as specified in 704.03.01.D.

E.	Final Documentation.  Provide the documentation specified in 704.03.01.E, including configuration data and parameters with channel assignments per traveled lane.

F.	Equipment Training.  Provide training as specified in 704.03.01.F and in the Special Provisions.

2**************************************************************************************2

provide recommendation prior to final design submission for any special training, and/or if more than 10 personnel require the training.

SME CONTACT – MSE

2**************************************************************************************2

G.	Warranty.  Perform repairs under warranty and provide documentation as specified in 704.03.01.G.

H.	Networking Requirements.  Comply with the networking requirements and perform work as specified in 704.03.01.H and in the Contract documents.

I.	IT Requirements.  Comply with the IT requirements and perform work as specified in 704.03.01.I and in the Contract documents.

704.03.06  Road Weather Information System (RWIS)

A.	Components.  A RWIS consists of the specified components needed to provide a complete system that is capable of processing sensor and control data to and from the designated control center for wind speed and direction, gusts, precipitation, visibility, humidity, pavement surface, and subsurface temperature.  The system also includes, but is not limited to, the electronic and electrical equipment, cabinet, wiring, configuration, communication and power connections, service charges, software, grounding, and surge protection.

B.	Installation.  Before beginning the work and during the work, comply with the requirements of 701.03.01.  The allowable time frame for existing system shutdown and cost of damages for exceeding the allowable time frames will be as specified in 704.03.01B.

Construct components as follows:

1.	Weather Station.  Construct the foundation as specified in 701.03.12.

Submit working drawings for approval that include a block wiring diagram that illustrates the interconnections of the RWIS components from the field location to the designated control center.  Identify each component by manufacturer and model number.

Install RWIS devices and materials, including cabinet enclosure, camera, electric power devices, remote microprocessor controlled unit, software, back panel, main power disconnect, surge suppression, communication modems, atmospheric sensors, road, subsurface and bridge sensors, sensor leads, grounding, and wires and incidental material.  Aim the camera for proper functioning of the system.  Follow the manufacturer’s recommended installation, calibration, and configuration instructions.

Install sensors embedded in the pavement according to the manufacturer’s recommendations.  Sawcut the pavement, pressure wash, and dry the sawcut before installing the sensors.  Install each cable from the sensor in a separate individual sawcut to the conduit at the curb leading to the nearest junction box.  Install bridge sensors according to the manufacturer’s recommendations.

Do not splice cables and sensor leads.

If not connected into the fiber optic network, obtain and provide communications with a utility service provider from the field microprocessor to the existing Department RWIS designated control center.

2.	Weather Station, Roadway Devices.  Install sensors embedded in the pavement and on bridges according to the manufacturer’s requirements for connections into existing weather stations.  Sawcut the pavement, pressure wash, and dry the sawcut before installing the sensors.

Install each cable from the sensor in a separate individual sawcut to the conduit at the curb leading to the nearest junction box.  Do not splice cables and sensor leads.

C.	Testing.  Perform testing as specified in 704.03.01.C.

D.	Maintenance.  Perform maintenance as specified in 704.03.01.D.

E.	Final Documentation.  Provide the documentation specified in 704.03.01.E and the following:

1.	Configuration data and parameters, port and channel assignments for each traveled lane.

2.	Calibration coefficient data for each sensor.

F.	Equipment Training.  Provide training as specified in 704.03.01.F and in the Special Provisions.

2**************************************************************************************2

provide recommendation prior to final design submission for any special training, and/or if more than 10 personnel require the training.

SME CONTACT – bureau of permits, electrical maintenance & claims

2**************************************************************************************2

G.	Warranty.  Perform repairs under warranty and provide documentation as specified in 704.03.01.G.

H.	Networking Requirements.  Comply with the networking requirements and perform work as specified in 704.03.01.H and in the Contract documents.

I.	IT Requirements.  Comply with the IT requirements and perform work as specified in 704.03.01.I and in the Contract documents.

704.03.07  Dynamic Message System (DMS)

A.	Components.  DMS consists of the specified components needed to provide a complete system that is capable of processing control data to and from the designated control center.  The system also includes, but is not limited to, wiring, communication and power connections, networking equipment, service charges, software, grounding, and surge protection.

2**************************************************************************************2

complete and include the following WHEN dms signs are included in the project.

also, include THE APPROPRIATE notes and INFORMATION FOR EACH DMS PROPOSED IN THE CONTRACT.

SME CONTACT – MOBILITY & SYSTEMS ENGINEERING

The following are the Model numbers for the various DMS to be provided and installed in this project:

| Location | Communication Type | DMS Type | Manufacturer/Model No. |
| --- | --- | --- | --- |

Ensure that the designated Model numbers for the various DMS signs are provided as specified in the Contract documents.

Ensure that Controller, DMS is purchased with pre-installed controller, pre-wired with the equipment listed below along with specialized communications cables (minimum 120ʹ Fiber Optic Cable with Connectors for each sign).

As part of the specified model numbers, ensure the DMS manufacturer supplies the cabinet and controller for each DMS sign with pre-installed uninterruptable power supply (UPS), a media converter and a TCP/IP wireless modem conforming to the wireless provider requirements.  Provide other equipment not listed here but required for the remote operation of the DMS.

2**************************************************************************************2

Ensure that the installation of DMS is coordinated with the power service company in such a manner that the DMS sign is powered up within two weeks of installation.  If this is not achieved, provide a generator on site for electrical power along with needed maintenance of the generator and refueling until the electrical service by the power company is installed.

When the final communication using fiber or other leased ISP services is delayed by more than two weeks upon initial installation of DMS sign, activate the wireless service for temporary or interim use until final communications service is installed so the TOC can use the DMS during this delay beyond two weeks.

For DMS sign that will be communicating over fiber optic communication media, provide and install an Ethernet Switch Type B and a fiber optic cable patch panel with interconnecting cables for each DMS controller.

For DMS sign that will be communicating over leased ISP services, provide and install a Router as specified in the Special Provisions and in the Contract Documents.

B.	Installation.  Before beginning the work and during the work, comply with the requirements of 701.03.01.  The allowable time frame for existing system shutdown and cost of damages for exceeding the allowable time frames will be as specified in 704.03.01.B.

2**************************************************************************************2

Construct the DMS sign mounting structure and foundation as specified in Division 500.

DMS STRUCTURE REQUIRES THE CONTRACTOR TO follow DIVISION 500 specifications FOR STRUCTURAL DETAILS AND other REQUIREMENTS.INCLUDING FOUNDATION

SME CONTACT –STRUCTURES

2**************************************************************************************2

Construct components as follows:

1.	DMS Sign.  At least 30 days before beginning construction, submit working drawings for approval that include sign mounting and lifting calculations.  Ensure the calculations are signed and sealed by a Professional Engineer.  Mount the sign on the standard or structure and install the controller according to the manufacturer’s recommendations.  Securely bolt the controller to the foundation in a vertical position using stainless steel hardware.  Seal the underground conduit entrance to the controller with a sealing compound.  Install cables and wire connections between the sign and controller according to the manufacturer’s recommendations.  Ensure that the conduit entry points are properly closed off with duct sealing compound.  Provide sign manufacturer technician for commissioning the sign and coordinate with the sign manufacturer by providing access and support during commissioning and for any warranty work covered by the DMS manufacturer.

2**************************************************************************************2

THIS ITEM IS FOR DMS SIGNS OF VARIOUS types and SIZES WHEN PROPOSED TO BE PROVIDED AND INSTALLED BY THE CONTRACTOR. INCLUDE THE MAKE AND MODEL NUMBER OF DMS SIGN in section 918 AND in the table in section 704.03.07.a. also, include it IN THE ITS PLANS. CONTACT MSE FOR FURTHER DETAILS. WHEN THIS ITEM IS USED IN A PROJECT, “CONTROLLER DMS” AND “FOUNDATION ITS TYPE D” OR “FOUNDATION ITS TYPE D-MC” AS APPLICABLE WILL BE REQUIRED FOR CONTROLLER/METER CABINET MOUNTING.

SME CONTACT – mSe

2**************************************************************************************2

Ensure control cables are factory assembled and tested according to the sign manufacturer’s recommendations.  Make wire and cable connections to the DMS sign controller according to the sign manufacturer’s recommendations.

Perform tree trimming and site clearing to provide an unobstructed field of view up to 1000 feet from the sign as directed by the RE.

2.	Controller, DMS.

2**************************************************************************************2

thIS ITEM is required when installing new dms signs and must be purchased from the dms sign manufacturer. PROVIDE THE MODEL NUMBER OF the dms SIGNS to the manufacturer for which controller dms are required. ADDITIONAL PAY ITEMS LIKE “FOUNDATION ITS TYPE D” OR “FOUNDATION ITS TYPE D-MC” FOR MOUNTING CONTROLLER/METER CABINETS AS APPLICABLE WILL BE REQUIRED.

sme CONTACT – MSE

2**************************************************************************************2

At least 30 days before beginning construction, submit working drawings for approval that include a block wiring diagram that illustrates the interconnections of the DMS components from the field location to the designated control center.  Identify each component by manufacturer and model number.

Securely bolt the controller to the foundation in a vertical position using stainless steel hardware.  Seal the underground conduit entrance to the controller with a sealing compound.

Install cables and wire connections between the sign and controller according to the manufacturer’s recommendations.  Ensure that the conduit entry points are properly closed off with duct sealing compound.

C.	Testing.  Perform testing as specified in 704.03.01.C.

For DMS, perform both Level B and Level C Testing after integration into the Central DMS control software system.

D.	Maintenance.  Perform maintenance as specified in 704.03.01.D.

E.	Final Documentation.  Provide the documentation specified in 704.03.01.E.

F.	Equipment Training.  Provide training as specified in 704.03.01.F and in the Special Provisions.

2**************************************************************************************2

provide recommendation prior to final design submission for any special training, and/or if more than 10 personnel require the training.

SME CONTACT – MSE

2**************************************************************************************2

G.	Warranty.  Perform repairs under warranty and provide documentation as specified in 704.03.01.G.

H.	Networking Requirements.  Comply with the networking requirements and perform work as specified in 704.03.01.H and in the Contract documents.

I.	IT Requirements.  Comply with the IT requirements and perform work as specified in 704.03.01.I and in the Contract documents.

704.03.08  Weigh in Motion System (WIMS)

A.	Components.  A WIMS consists of the specified components needed to provide a complete system that is capable of processing pavement sensor and control data to and from the control center in Trenton.  The WIMS is composed of electronic and electrical equipment, pavement sensors, cables, wiring, control cabinet, site processor, remote communication modems, operating software, and software used to process and generate reports on the collected raw vehicle record files.  The system also includes, but is not limited to, wiring, cabinet, foundation, communication and power connections, service charges, software, grounding, and surge protection.

B.	Installation.  Before beginning the work and during the work, comply with the requirements of 701.03.01.  The allowable time frame for existing system shutdown will begin at 10 P.M. daily and continues through to 4 A.M. on weekdays, 5 A.M. on Saturdays, and 6 A.M. on Sunday mornings unless otherwise noted in the Special Provisions and the cost of damages for exceeding the allowable time frames is specified in the Special Provisions.  The Department will recover the cost as specified in 107.16.

2**************************************************************************************2

cONTACT TRAFFIC OPERATIONS TO CONFIRM THE EXISTING SYSTEM SHUTDOWN TIME. REVISE AS DIRECTED and insert here

SME CONTACT – TRANSPORTATION DATA AND SAFETY

Provide the cost of damages for exceeding the allowable time frames

SME CONTACT – TRANSPORTATION DATA AND SAFETY

2**************************************************************************************2

If not connected into the fiber optic network, obtain and provide communications with a Utility service provider from the field microprocessor to the Department WIMS control center in Trenton.

Make operational electronic and electrical components to monitor volume, speed, length, gap, headway, vehicle type classification by axle configuration, and axle weights.  The roadway sensors are composed of inductive loop detectors, loop leads, weight sensors, and temperature sensor.  The WIMS electronics are installed at each work site with electrical power and communications for remote station programming, monitoring and failure diagnosis, and data retrieval.

Construct components as follows:

1.	Controller, WIMS.  Construct the foundation as specified in 701.03.12.

At least 30 days before beginning construction, submit working drawings for approval that include a block wiring diagram that illustrates the interconnections of the WIMS components from the field location to the control center in Trenton.  Identify each component by manufacturer and model number.

Securely bolt the controller cabinet to the foundation in a vertical position using stainless steel hardware.  Seal the underground conduit entrance to the controller with a sealing compound.

2.	WIM Roadway Devices.  Install the devices according to the manufacturer’s requirements.  Pressure wash and dry the sawcut as recommended by the manufacturer.  Ensure that sensors, loop detector wires, and cables are installed in separate conduit per type of device and that conduit is waterproofed and sealed.  Ensure that the temperature sensor is installed in a schedule 80 PVC conduit in the shoulder of the roadway.  Maintain at least 3 feet of space between the sawcut loops and the sensors.  After completion of the HMA, re-establish the location of each loop edge to facilitate and mark for cutting of the slot for the axle weight sensor.  Ensure that the lengths of weight sensors do not exceed the width of the lanes.  Do not splice cables.  Grind the top of the encapsulation material flushed with the road.

Ensure that the piezoelectric sensors are installed perpendicular to the flow of traffic and are without twists or curls.  Position shorter sensors (6 feet length) to one side in a wheel path, not in the center of the lane; position longer sensors in the center of the lane.  Cut a slot for the sensor that is 8 inches longer than the sensor.  Do not mix or place the epoxy until the RE has approved the cleaning operations.

C.	Testing.  Perform testing as specified in 704.03.01.C, except do not perform Level B as specified in 704.03.01.C.1.b.  Also perform the testing as follows:

Use an LCR Meter to measure the capacitance, resistance, and dissipation factor of each sensor.  When the lane is opened to traffic, perform a functional test on the sensor using an oscilloscope.

Provide a 5-axle tractor-trailer combination (3-axle tractor and 2-axle semi-trailer) and driver for calibration of the WIM system.  Weigh the calibration truck on a certified, multi-draft public scale.  Also weigh the steering axle, drive tandem axles, and trailer tandem axles.  Record and provide the weight data to the RE at the start of the test.  Include the total gross weight of the combination.  Ensure that the truck has an air-ride suspension and is in good mechanical condition.  Ensure that the trailer is a dry van type and loaded with a non-shifting load so that the gross weight of the tractor-trailer combination is between 75,000 and 80,000 pounds.  Ensure that the axle-loads do not exceed New Jersey Title 39 limits, and do not violate the Federal Bridge Formula.

Drive the truck over each lane a minimum of 5 times and record the axle and gross weights as determined by the WIM system by each sensor for each pass.  Use the average values among the 5 passes to calculate a calibration factor for each sensor.  Perform this test twice.

After the calibration, ensure that the average values recorded by the WIM system are within 10 percent of each axle weight (average axle weight of each axle group) and within 5 percent of the gross weight of the combination of the weights recorded at the public scale.

If the system cannot be properly calibrated after 3 attempts, the RE may employ a third party vendor to redo the work. The Department will recover the cost as specified in 107.16.

D.	Maintenance.  Perform maintenance as specified in 704.03.01.D.

E.	Final Documentation.  Provide the documentation specified in 704.03.01.E and the following:

1.	Configuration data and parameters, port and channel assignments for each traveled lane.

2.	Calibration coefficient data for each sensor.

F.	Equipment Training.  Provide training as specified in 704.03.01.F and in the Special Provisions.

2**************************************************************************************2

provide recommendation prior to final design submission for any special training, and/or if more than 10 personnel require the training.

SME CONTACT – TRANSPORTATION data AND SAFETY

2**************************************************************************************2

G.	Warranty.  Perform repairs under warranty and provide documentation as specified in 704.03.01.G.

H.	Networking Requirements.  Comply with the networking requirements and perform work as specified in 704.03.01.H and in the Contract documents.

I.	IT Requirements.  Comply with the IT requirements and perform work as specified in 704.03.01.I and in the Contract documents.

704.03.09  Traffic Volume System (TVS)

A.	Components.  A TVS consists of the specified components needed to provide a complete system that is capable of processing traffic control data to and from the control center in Trenton including pavement loop and vehicle detectors, electronic devices to measure and record vehicle volume, speed, length, gap, and headway in each lane connected to the respective monitoring devices in a cabinet.  The system also includes wiring, cabinet, foundation, communication and power connections, service charges, software, grounding, and surge protection.

B.	Installation.  Before beginning the work and during the work, comply with the requirements of 701.03.01.  The allowable time frame for existing system shutdown will begin at 10 P.M. daily and continues through to 4 A.M. on weekdays, 5 A.M. on Saturdays, and 6 A.M. on Sunday mornings unless otherwise noted in the Special Provisions and the cost of damages for exceeding the allowable time frames is specified in the Special Provisions.  The Department will recover the cost as specified in 107.16.

2**************************************************************************************2

complete and include the following.

INsert THE existing system shutdown time frames, including days of the week, specific dates, and/or hours of the day(s).

SME CONTACT – traNSPORTATION DATA AND SAFETY

The Department will allow existing TVS system shutdowns from _____.

Provide the cost of damages for exceeding the allowable time frames

SME CONTACT – traNSPORTATION DATA AND SAFETY

2**************************************************************************************2

If not connected into the fiber optic network, obtain and provide communications with a Utility service provider from the field microprocessor to the Department TVS control center in Trenton.

Construct components as follows:

1.	Controller, TVS.  Construct the foundation as specified in 701.03.12.

Submit working drawings for approval that include a block wiring diagram that illustrates the interconnections of the TVS components from the field location to the control center in Trenton.  Identify each component by manufacturer and model number.

Make operational electronic and electrical components to monitor volume, speed, length, gap, and headway.  Ensure the roadway sensors are composed of inductive loops and loop leads.  Ensure the TVS electronics are installed at each work site with electrical power and communications for remote station programming, monitoring and failure diagnosis, and data retrieval.

Securely bolt the controller cabinet to the foundation in a vertical position using stainless steel hardware.  Seal the underground conduit entrance to the controller with a sealing compound.

2.	TVS Roadway Devices.  Sawcut the pavement.  Pressure wash then dry the sawcut according to the manufacturer’s recommendations.  Ensure that sensors, loop detector wires, and cables are installed in separate conduit per type of device and that the conduit is waterproofed and sealed.  Maintain at least 3 feet of space between the sawcut loops and the sensors.  Do not splice cables.  Grind the top of the encapsulation material flush with the road.

C.	Testing.  Perform testing as specified in 704.03.01.C, except do not perform Level B as specified in 704.03.01.C.1.b.  Also perform the testing as follows:

Use an LCR Meter to measure the capacitance, resistance, and dissipation factor of each sensor.  When the lane is opened to traffic, perform a functional test on the sensor using an oscilloscope.

Measure the ratio of loop inductance to lead inductance and ensure it is within the requirements of the sensor manufacturer.

D.	Maintenance.  Perform maintenance as specified in 704.03.01.D.

E.	Final Documentation.  Provide the documentation specified in 704.03.01.E and the following:

1.	Configuration data and parameters, port and channel assignments.

2.	Calibration data for each sensor.

F.	Equipment Training.  Provide training as specified in 704.03.01.F and in the Special Provisions.

2**************************************************************************************2

provide recommendation prior to final design submission for any special training, and/or if more than 10 personnel require the training.

SME CONTACT – TRANSPORTATION data AND SAFETY

2**************************************************************************************2

G.	Warranty.  Perform repairs under warranty and provide documentation as specified in 704.03.01.G.

H.	Networking Requirements.  Comply with the networking requirements and perform work as specified in 704.03.01.H and in the Contract documents.

I.	IT Requirements.  Comply with the IT requirements and perform work as specified in 704.03.01.I and in the Contract documents.

704.03.10  Variable Speed Limit System (VSLS)

A.	Components.  A VSLS consists of the specified components needed to provide a complete system that is capable of processing traffic speed data to and from the control center, including electronic devices to measure and record vehicle speed in each lane connected to the respective monitoring devices in a cabinet.  The system also includes wiring, cabinet, foundation, communication and power connections, service charges, software, grounding, and surge protection.

Ensure that the designated Model numbers for the various VSLS signs are provided as specified in the Special Provisions and the Contract Plans.

Procure VSLS auxiliary control panel with the speed limit sign from the VSLS manufacturer.  Install VSLS auxiliary control panel inside VSLS, Controller.  Provide Ethernet cables from VSLS sign to controller, VSLS (length as required per contract plans).  Provide other equipment not listed here but required for the remote operation of the VSLS.

B.	Installation.  Before beginning the work and during the work, comply with the requirements of 701.03.01.  The allowable time frame for existing system shutdown and cost of damages for exceeding the allowable time frames will be as specified in 704.03.01.B.

Construct components as follows:

1.	VSLS Sign.  Submit working drawings for approval that include a block wiring diagram that illustrates the interconnections of the VSLS components from the field location to the control center.  Identify each component by manufacturer and model number.  Mount the sign on the VSLS sign support structure as specified in the contract documents and install the controller according to the manufacturer’s recommendations.  Construct the foundation for Controller VSLS as specified in 701.03.12 and as per contract documents.  Securely bolt the controller to the foundation in a vertical position using stainless steel hardware.  Seal the underground conduit entrance to the controller with a sealing compound.  Install cables and wire connections between the sign and controller according to the manufacturer’s recommendations.  Ensure that the conduit entry points are properly closed off with duct sealing compound.  Provide a manufacturer technician for commissioning the VSLS and coordinate with the manufacturer by providing access and support during commissioning and for warranty work covered by the VSLS manufacturer under their service agreement with the contractor.

Make operational electronic and electrical components of VSLS to display the desirable speed limit based on field conditions collected by roadway sensors and as per specific information provided by NJDOT during designated times of the day and based on other criteria specified in the contract documents.  Ensure that the VSLS signs are installed at the designated locations with power and communications for remote operation of programming, monitoring, failure diagnosis, and data retrieval.

2.	Controller, VSLS.

2**************************************************************************************2

thIS ITEM is required when installing new VSLs signs and must be purchased from the VSLS sign manufacturer. PROVIDE THE MODEL NUMBER OF the VSLs SIGNS to the manufacturer for which controller VSLs ARE required. ADDITIONAL PAY ITEMS FOR MOUNTING CONTROLLER/METER CABINETS AS APPLICABLE WILL BE REQUIRED.

sme CONTACT – MSE & TRAFFIC OPERATIONS

2**************************************************************************************2

At least 30 days before beginning construction, submit working drawings for approval that include a block wiring diagram that illustrates the interconnections of the VSLS components from the field location to the designated control center.  Identify each component by manufacturer and model number.

Securely bolt the controller to the foundation in a vertical position using stainless steel hardware.  Seal the underground conduit entrance to the controller with a sealing compound.

Install cables and wire connections between the sign and controller according to the manufacturer’s recommendations.  Ensure that the conduit entry points are properly closed off with duct sealing compound.

C.	Testing.  Perform testing as specified in 704.03.01.C and in the Special Provisions.

D.	Maintenance.  Perform maintenance as specified in 704.03.01.D.

E.	Final Documentation.  Provide the documentation specified in 704.03.01.E.

F.	Equipment Training.  Provide training as specified in 704.03.01.F and in the Special Provisions.

G.	Warranty.  Perform repairs under warranty and provide documentation as specified in 704.03.01.G.

H.	Networking Requirements.  Comply with the networking requirements and perform work as specified in 704.03.01.H and in the contract documents.

I.	IT Requirements.  Comply with the IT requirements and perform work as specified in 704.03.01.I and in the Contract document.

704.04  Measurement and Payment

2**************************************************************************************2

obtain the latest revised standard detail SHEETS that are available from NJDOT Mobility and Systems Engineering (MSE) for inclusion in the contract plans until they are issued via bdc

SME CONTACT – MSE

2**************************************************************************************2

The Department will measure and make payment for Items as follows:

Item	Pay Unit

Junction Box ITS TYPE ___	UNIT

JUNCTION BOX ITS, RELOCATION	UNIT

Communication Cable	lineAR foot

Foundation ITS TYPE ___	unit

Controller, ITS 	unit

Communication Hub	unit

Control Center System, location ___	LUMP SUM

METER CABINET ITS	UNIT

ITS CONDUITS, TYPE _____	LINEAR FOOT

FIBER CROSS CONNECT CABINET	UNIT

FOUNDATION CSS	UNIT

CAMERA STANDARD type ___	UNIT

CAMERA	UNIT

CONTROLLER, CAMERA	UNIT

Fiber Optic Cable TYPE ___	lineAR foot

CONTROLLER, Ctss	unit

ctss CONTROLLER unit	unit

CONTROLLER, Ctss turn on	unit

SYSTEM DETECTOR, TYPE ___	UNIT

FOUNDATION TTS type ___	UNIT

detector standard	unit

CONTROLLER, tts	unit

tts Detectors Type _____	UNIT

Weather Station	UNIT

Weather station Roadway Devices ____ LANES	UNIT

DMS Sign	unit

CONTROLLER DMS	UNIT

CONTROLLER, WIM	UNIT

WiM Roadway Devices ____ LANES	UNIT

Controller, Tvs	UNIT

Tvs Roadway Devices ____ LANES	UNIT

VSLS sign	unit

CONTROLLER, VSLS	UNIT

The Department will consider ITS CONDUITS, TYPE ____ as a single conduit comprised of multiple individual conduits as shown in details along with a tracer wire and will be measured as one pay unit.

The Department will make payment for each item, except for FIBER OPTIC CABLE, TYPE___, standards, junction boxes, and foundations, as follows:

| Work Completed | Payment |
| --- | --- |
| Installing the Item | 60% of Total Contract Price |
| Successful completion of Level A testing | 10% of Total Contract Price |
| Successful completion of Level B testing | 10% of Total Contract Price |
| Successful completion of Level C testing | 10% of Total Contract Price |
| Successful completion of Project testing | 10% of Total Contract Price |

If a level of testing is not required, the Department will include the percentage specified for that level of payment in the Installing the Item percentage.

The Department will make payment for FIBER OPTIC CABLE, TYPE___, as follows:

| Work Completed | Payment |
| --- | --- |
| Installing the fiber optic cable | 80% of Total Contract Price |
| Successful completion of Level 1 testing | 10% of Total Contract Price |
| Successful completion of Level 2 testing | 10% of Total Contract Price |

1**************************************************************************************************************************1

Division 800 – Landscaping

Section 811 – Planting

811.03.01  Planting

E.	Excavation for Plant Pits and Beds.

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

THE last SENTENCE OF THE second PARAGRAPH IS CHANGED TO:

Obtain RE approval before reusing topsoil from the excavated pits.

1**************************************************************************************************************************1

I.	Watering.

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

THE first PARAGRAPH IS CHANGED TO:

Water plants with sufficient frequency and quantity to ensure that the soil surrounding the root system remains moist but not saturated.

1**************************************************************************************************************************1

811.03.02  Plant Establishment Period

1**************************************************************************************************************************1

2**************************************************************************************2

complete and include THE FOLLOWING

sme contact – landscape architecture

THE third and fourth paragraphs are changed to:

The Department will reinspect the plants annually for _____ years, beginning approximately 1 year after the start of the plant establishment period.  If the Department determines that plants need to be replaced after each inspection, replant plants as specified in 811.03.01 within 3 weeks of notification.  If replacing outside of the optimal planting season as specified in Table 811.03.01-1, only use containerized or balled and burlapped plants that are certified as being dug dormant.

2**************************************************************************************2

2.	Maintenance Bond.

2**************************************************************************************2

complete and include the bond amount (a percentage of planting value)

sme contact – landscape architecture

Provide a bond to the Department in the amount of $_____________.

2**************************************************************************************2

1**************************************************************************************************************************1

Division 900 – Materials

Section 901 – Aggregates

the entire subsection is changed to:

1**************************************************************************************************************************1

BDC15s-01 dated mar 26, 2015

901.07  Grit

901.07.01  Grit for Epoxy Waterproofing.  Use grit for spreading over the epoxy waterproofing that is a subangular, natural, 98 percent silica sand.  Ensure that 90 percent of the total sample by weight falls between the No. 4 and No. 30 sieves, with 0 percent passing the No. 30 sieve.

901.07.02 Fine Aggregate for Fog Seal.  Use fine aggregate for spreading over fog seal that conforms to 901.05.02 and the gradation requirements in Table 901.07.02-1:

| Table 901.07.02-1 Gradation Requirements for Fine Aggregate used on Fog Seal |
| --- |
| Sieve Size | Percent Passing |
| No. 8 | 100 |
| No. 16 | 90 - 100 |
| No. 50 | 70- 100 |
| No. 200 | 0 - 2 |

1**************************************************************************************************************************1

901.11  Soil Aggregate

1.	Composition of Soil Aggregate.

1**************************************************************************************************************************1

BDC10s-03 dated Mar 17, 2010

The following is added to the last paragraph:

For Designation I-14, the Contractor may use up to 30 percent steel slag by weight of the coarse aggregate portion of the soil aggregate.  Obtain steel slag from a source listed on the QPL as specified in 901.01.  Use steel slag that was produced as a co-product of the steel making process.  Ensure that the steel slag consists of tough, durable pieces that are uniform in density and quality.  Stockpile steel slag as specified in 901.02.  Ensure steel slag for blending with I-14 Soil Aggregate does not exceed 0.50 percent expansion from hydration when tested according to ASTM D 4792.

1**************************************************************************************************************************1

Section 902 – Asphalt

902.01.01  Asphalt Binder

1**************************************************************************************************************************1

BDC14s-07 dated Aug 29, 2014

THE second PARAGRAPH is CHANGED TO:

When specified, use PG 64E-22 asphalt binder that is a storage-stable and conforms to AASHTO MP 19 (AASHTO M 332), including compliance with the elastic response requirement in Appendix 1.

1**************************************************************************************************************************1

1**************************************************************************************************************************1

BDC14s-07 dated Aug 29, 2014

THE FOLLOWING Subpart is ADDed:

902.01.05  Warm Mix Asphalt (WMA) Additives and Processes

Use a WMA additive or process that is listed on the Northeast Asphalt User/Producer Group (NEAUPG) Qualified WMA Technologies List which can be found at the following website:  http://www.neaupg.uconn.edu/

If an approved HMA mix design is used, a separate mix design with WMA additives or processes is not required.

Submit information on the WMA additive or process with the Paving Plan required in 401.03.03.A.  For controlled foaming systems, also submit the operating parameters of the system including accuracy of the meter, operating range, and temperature of the binder.  Provide the target and operating tolerances for the percent water injection and temperatures for the binder.  Provide a method for validating this with changing production rates.

Ensure that a technical representative of the manufacturer is on-site or available for consultation for the first day or night of production.

1**************************************************************************************************************************1

902.02.01  Mix Designations

1**************************************************************************************************************************1

BDC14s-07 dated Aug 29, 2014

the entire subpart is changed to:

The requirements for specific HMA mixtures are identified by the abbreviated fields in the Item description as defined as follows:

HOT MIX ASPHALT 12.5ME SURFACE COURSE

1.	“HOT MIX ASPHALT”  “Hot Mix Asphalt” is located in the first field in the Item description for the purpose of identifying the mixture requirements.

2.	“12.5”  The second field in the Item description designates the nominal maximum size aggregate (in millimeters) for the job mix formula (sizes are 4.75, 9.5, 12.5, 19, 25, and 37.5 mm).

3.	“M”  The third field in the Item description designates the design compaction level for the job mix formula based on traffic forecasts as listed in Table 902.02.03-2 (levels are L=low and M=medium).

4.	“E”  The fourth field in the Item description designates the high temperature designation of the performance-graded binder. Options are “64” for PG 64-22 and “E” for PG 64E-22.

5.	“SURFACE COURSE”  The last field in the Item description designates the intended use and location within the pavement structure (options are surface, intermediate, or base course).

1**************************************************************************************************************************1

902.02.02 Composition of Mixtures

1**************************************************************************************************************************1

BDC14s-07 dated Aug 29, 2014

the entire subpart is changed to:

Provide materials as specified:

Aggregates for Hot Mix Asphalt	901.05

Asphalt Binder	902.01.01

Warm Mix Additives and Processes (optional)	902.01.05

If a WMA additive is pre-blended in the asphalt binder, ensure that the asphalt binder meets the requirements of the specified grade after the addition of the WMA additive.  If a WMA additive is added at the HMA plant, ensure that the addition of the additive will not negatively impact the grade of asphalt binder.  Follow the manufacturer’s recommendations for percentage of WMA additive needed.

Mix HMA in a plant that is listed on the QPL and conforms to the requirements for HMA Plants as specified in 1009.01.

Composition of the mixture for HMA surface course is coarse aggregate, fine aggregate, and asphalt binder, and may also include mineral filler, WMA additive, and up to 15 percent Reclaimed Asphalt Pavement (RAP).  For controlled asphalt foaming system WMA, the Department may require an anti-stripping additive. Ensure that the finished mix does not contain more than a total of 1 percent by weight contamination from Crushed Recycled Container Glass (CRCG).

The composition of the mixture for HMA base or intermediate course is coarse aggregate, fine aggregate, and asphalt binder, and may also include mineral filler, WMA additive and up to 35 percent of recycled materials.  For controlled asphalt foaming system WMA, the Department may require an anti-stripping additive.  The 35 percent of recycled materials may consist of a combination of RAP, CRCG, Ground Bituminous Shingle Material (GBSM), and RPCSA, with the following individual limits:

| Table 902.02.02-1 Use of Recycled Materials in HMA Base or Intermediate Course |
| --- |
| Recycled Material | Maximum Percentage |
| RAP | 25 |
| CRCG | 10 |
| GBSM | 5 |
| RPCSA | 20 |

Combine the aggregates to ensure that the resulting mixture meets the grading requirements specified in Table 902.02.03-1.  In determining the percentage of aggregates of the various sizes necessary to meet gradation requirements, exclude the asphalt binder.

Ensure that the combined coarse aggregate, when tested according to ASTM D 4791, has less than 10 percent flat and elongated pieces retained on the No. 4 sieve and larger.  Measure aggregate using the ratio of 5:1, comparing the length (longest dimension) to the thickness (smallest dimension) of the aggregate particles.

Ensure that the combined fine aggregate in the mixture conforms to the requirements specified in Table 902.02.02-2. Ensure that the material passing the No. 40 sieve is non-plastic when tested according to AASHTO T 90.

| Table 902.02.02-2 Additional Fine Aggregate Requirements for HMA |
| --- |
| Tests | Test Method | Minimum Percent |
| Uncompacted Void Content of Fine Aggregate Sand Equivalent | AASHTO T 304, Method A AASHTO T 176 | 45 45 |

1**************************************************************************************************************************1

902.02.03  Mix Design

1**************************************************************************************************************************1

BDC14s-07 dated Aug 29, 2014

TABLES 902.02.03-2, AND 902.02.03-3 ARE CHANGED TO:

| Table 902.02.03-2 Gyratory Compaction Effort for HMA Mixtures |
| --- |
| Compaction Level | ESALs1 (millions) | Ndes | Nmax |
| L | ( 0.3 | 50 | 75 |
| M | ≥ 0.3 | 75 | 115 |
| 1. Design ESALs (Equivalent (80kN) Single-Axle Loads) refer to the anticipated traffic level expected on the design lane over a 20-year period. |

| Table 902.02.03-3 HMA Requirements for Design |
| --- |
| Compaction Levels | Required Density (% of Theoretical Max. Specific Gravity) | Voids in Mineral Aggregate (VMA), % (minimum) | Voids Filled With Asphalt (VFA)1 % | Dust-to-Binder Ratio |
|  |  | Nominal Max. Aggregate Size, mm |  |  |
|  | @Ndes2 | @Nmax | 37.5 | 25.0 | 19.0 | 12.5 | 9.5 | 4.75 |  |  |
| L | 96.0 | ≤ 98.0 | 11.0 | 12.0 | 13.0 | 14.0 | 15.0 | 16.0 | 70 - 80 | 0.6 - 1.2 |
| M | 96.0 | ≤ 98.0 | 11.0 | 12.0 | 13.0 | 14.0 | 15.0 | 16.0 | 65 - 78 | 0.6 - 1.2 |
| 1. For 37.5-mm nominal maximum size mixtures, the specified lower limit of the VFA is 64 percent for all design traffic levels. 2. As determined from the values for the maximum specific gravity of the mix and the bulk specific gravity of the compacted mixture. Maximum specific gravity of the mix is determined according to AASHTO T 209. Bulk specific gravity of the compacted mixture is determined according to AASHTO T 166. For verification, specimens must be between 95.0 and 97.0 percent of maximum specific gravity at Ndes. |

THE fourth paragraph is changed to:

At the ME’s request, test the mix design to ensure that it meets a minimum tensile strength ratio of 80 percent, when tested according to AASHTO T 283. The ME will require tensile strength ratio testing for new aggregate sources and for aggregates or mixes suspected of stripping susceptibility.

1**************************************************************************************************************************1

902.02.04  Sampling and Testing

1**************************************************************************************************************************1

BDC14s-07 dated Aug 29, 2014

the entire text is changed to:

A.	General Acceptance Requirements.  The RE or ME may reject and require disposal of any batch or shipment that is rendered unfit for its intended use due to contamination, segregation, improper temperature, lumps of cold material, or incomplete coating of the aggregate.  For other than improper temperature, visual inspection of the material by the RE or ME is considered sufficient grounds for such rejection.

For PG 64-22, ensure that the temperature of the mixture at discharge from the plant or surge and storage bins is at least 290 °F when the ambient temperature is less than 50 °F or is at least 275 °F when the ambient temperature is greater than or equal to 50 °F.  For PG 64E-22, ensure that the temperature of the mixture at discharge from the plant or surge and storage bins is at least 10 °F above the manufacturer’s recommended laydown temperature.  For mixes produced using a WMA additive or process, ensure that the temperature of the mixture at discharge from the plant or surge and storage bins is at least 10 °F above the WMA manufacturer’s recommended laydown temperature.

Do not allow the mixture temperature to exceed 330 °F at discharge from the plant.

Combine and mix the aggregates and asphalt binder to ensure that at least 95 percent of the coarse aggregate particles are entirely coated with asphalt binder as determined according to AASHTO T 195.  If the ME determines that there is an on-going problem with coating, the ME may obtain random samples from 5 trucks and will determine the adequacy of the mixing on the average of particle counts made on these 5 test portions.  If the requirement for 95 percent coating is not met on each sample, modify plant operations, as necessary, to obtain the required degree of coating.

If used, ensure that the equipment for controlled asphalt foaming system is running according to the manufacturer’s recommendations.  Ensure that the metering of water to foam the asphalt is controlled to produce a uniform mixture.

B.	Sampling.  The ME will take a random sample from each 700 tons of production for volumetric acceptance testing and to verify composition.  The ME will perform sampling according to AASHTO T 168, NJDOT B-2, or ASTM D 3665.

C.	Quality Control Testing.  The HMA producer shall provide a quality control (QC) technician who is certified by the Society of Asphalt Technologists of New Jersey as an Asphalt Technologist, Level 2.  The QC technician may substitute equivalent technician certification by the Mid-Atlantic Region Technician Certification Program (MARTCP).  Ensure that the QC technician is present during periods of mix production for the sole purpose of quality control testing and to assist the ME.  The ME will not perform the quality control testing or other routine test functions in the absence of, or instead of, the QC technician.

The QC technician shall perform sampling and testing according to the approved quality control plan, to keep the mix within the limits specified for the mix being produced.  The QC technician may use acceptance test results or perform additional testing as necessary to control the mix.

To determine the composition, perform ignition oven testing according to AASHTO T 308 and aggregate gradation according to AASHTO T 30.

For each acceptance test, perform maximum specific gravity testing according to AASHTO T 209 on a test portion of the sample taken by the ME.  Sample and test coarse aggregate, fine aggregate, mineral filler, and RAP according to the approved quality control plan for the plant.

When using RAP, ensure that the supplier has in operation an ongoing daily quality control program to evaluate the RAP. As a minimum, this program shall consist of the following:

1.	An evaluation performed to ensure that the material conforms to 901.05.04 and compares favorably with the design submittal.

2.	An evaluation of the RAP material performed using a solvent or an ignition oven to qualitatively evaluate the aggregate components to determine conformance to 901.05.

3.	Quality control reports as directed by the ME.

D.	Acceptance Testing and Requirements.  The ME will determine volumetric properties at Ndes for acceptance from samples taken, compacted, and tested at the HMA plant.  The ME will compact HMA to the number of design gyrations (Ndes) specified in Table 902.02.03-2, using equipment according to AASHTO T 312.  The ME will determine bulk specific gravity of the compacted sample according to AASHTO T 166.  The ME will use the most current QC maximum specific gravity test result in calculating the volumetric properties of the HMA.

The ME will determine the dust-to-binder ratio from the composition results as tested by the QC technician.

Ensure that the HMA mixture conforms to the requirements specified in Table 902.02.04-1, and to the gradation requirements in Table 902.02.03-1.  If 2 samples in 5 consecutive samples fail to conform to the gradation or volumetric requirements, immediately initiate corrective action.

The ME will test a minimum of 1 sample per 3500 tons for moisture, basing moisture determinations on the weight loss of an approximately 1600-gram sample of mixture heated for 1 hour in an oven at 280 ± 5°F.  Ensure that the moisture content of the mixture at discharge from the plant does not exceed 1.0 percent.

| Table 902.02.04-1 Hot Mix Asphalt Requirements for Control |
| --- |
| Compaction Levels | Required Density (% of Theoretical Max. Specific Gravity) | Voids in Mineral Aggregate (VMA), % (minimum) | Dust-to-Binder Ratio |
|  |  | Nominal Max. Aggregate Size, mm |  |
|  | @Ndes1 | 37.5 | 25.0 | 19.0 | 12.5 | 9.5 | 4.75 |  |
| L, M | 95.0 – 97.0 | 11.0 | 12.0 | 13.0 | 14.0 | 15.0 | 16.0 | 0.6 - 1.3 |
| 1. As determined from the values for the maximum specific gravity of the mix and the bulk specific gravity of the compacted mixture. Maximum specific gravity of the mix is determined according to AASHTO T 209. Bulk specific gravity of the compacted mixture is determined according to AASHTO T 166. |

1**************************************************************************************************************************1

902.03.01  Composition of Mixtures

1**************************************************************************************************************************1

BDC14s-07 dated Aug 29, 2014

the entire text is changed to:

Mix OGFC and MOGFC in a plant that is listed on the QPL and conforms to the requirements for HMA plants as specified in 1009.01.

Composition of mixture for OGFC and MOGFC is coarse aggregate, fine aggregate and asphalt binder and may include a WMA additive. Ensure that the mixture conforms to the following requirements:

1.	Use aggregate for OGFC and MOGFC that conforms to 901.05, except, for coarse aggregate, use broken stone of gneiss, granite, quartzite, or trap rock. Do not use RAP, CRCG, GBSM, or RPCSA.

2.	Use asphalt binder for OGFC and MOGFC that is PG 64E-22 as specified in 902.01.01.

3.	If used, ensure that WMA additives or processes conform to 902.01.05.  If a WMA additive is pre-blended in the asphalt binder, ensure that the asphalt binder meets the requirements of the specified grade after the addition of the WMA additive.  If a WMA additive is added at the HMA plant, ensure that the addition of the additive will not negatively impact the grade of asphalt binder.  Follow the manufacturer’s recommendations for percentage of WMA additive needed. For controlled asphalt foaming system WMA, the Department may require an anti-stripping additive.

4.	For MOGFC, add a stabilizing additive consisting of mineral fiber or cellulose fiber to the mix.  Use a stabilizing additive that conforms to the requirements for stabilizing additives in AASHTO M 325.  Use only 1 type per mix design. If using mineral fibers, use a dosage rate of 0.4 percent by weight of total mix.  If using cellulose fibers, use a dosage rate of 0.3 percent by weight of total mix.  The dosage rate may be increased, as necessary, to prevent draindown as measured by the visual draindown determination of asphalt content in NJDOT B-8.  Accurately control proportioning the fibers into the mixture within ±10 percent of the required weight, and use equipment that ensures uniform dispersion of the fibers.  Store fibers in a dry location with a storage temperature not to exceed 120 °F.  The supplier of the cellulose or mineral fibers shall provide a certification of compliance, as specified in 106.07, that the material supplied conforms to AASHTO M 325.  Ensure that a technical representative from the additive supplier is at the work site for the first full day of construction for technical assistance.

1**************************************************************************************************************************1

902.03.02  Mix Design

1**************************************************************************************************************************1

BDC11s-01 dated Mar 30, 2011

THE FOURTH PARAGRAGH IS CHANGED TO:

The ME will test 2 specimens to verify that the final JMF produces a mixture that has a minimum void content as specified in Table 902.03.03-1.  The ME will determine percent air voids according to AASHTO T 209, and either NJDOT B-6 or AASHTO T 331.

1**************************************************************************************************************************1

902.03.03  Sampling and Testing

1**************************************************************************************************************************1

BDC11s-01 dated Mar 30, 2011

THE FOLLOWING IS ADDED TO THE FIRST PARAGRAPH:

Ensure that the mix meets the requirements as specified in 902.02.04.A, otherwise the RE or ME will reject the material.

2**************************************************************************************2

BDC11s-08 dated aug 26 2011

THE second PARAGRAPH IS CHANGED TO:

During production, the ME will take one random acceptance sample from each 700 tons of production to verify composition.  Conduct air voids and draindown tests as directed by the ME.

2**************************************************************************************2

THE FOURTH PARAGRAPH IS CHANGED TO:

The ME will perform sampling according to NJDOT B-2 or ASTM D 3665, and will perform testing for composition according to AASHTO T 308 or NJDOT B-5.  Perform testing for air voids according to AASHTO T 209 and either NJDOT B-6 or AASHTO T 331. Perform testing for draindown according to NJDOT B-7 or NJDOT B-8.

1**************************************************************************************************************************1

902.04.01  Composition of Mixture

1**************************************************************************************************************************1

BDC14s-07 dated Aug 29, 2014

the entire Subsection text is changed to:

Mix ultra-thin HMA in a plant listed on the QPL conforming to the requirements for HMA plants specified in 1009.01.

Use ultra-thin HMA that consists of coarse aggregate, fine aggregate, and polymer modified asphalt binder and that may contain mineral filler and a WMA additive.  Do not add RAP, CRCG, GBSM, or RPCSA.  Combine the material in such proportions that the total aggregate and asphalt binder conform to the composition percentages specified in Table 902.04.02-1.

To produce the ultra-thin HMA, use aggregates and asphalt binder that conforms to the following:

1.	For asphalt binder, use PG 64E-22 conforming to the requirements of 902.01.01.

2.	If used, ensure that WMA additives or processes conform to 902.01.05.  If a WMA additive is pre-blended in the asphalt binder, ensure that the asphalt binder meets the requirements of the specified grade after the addition of the WMA additive.  If a WMA additive is added at the HMA plant, ensure that the addition of the additive will not negatively impact the grade of asphalt binder.  Follow the manufacturer’s recommendations for percentage of WMA additive needed. For controlled asphalt foaming system WMA, the Department may require an anti-stripping additive.

3.	For fine aggregate, use 100 percent stone sand conforming to 901.05.02.  Ensure that the combined gradation with coarse aggregate conforms to Table 902.04.02-1.

4.	Use coarse aggregate that conforms to 901.05.01 and Table 902.04.01-1.  Permissible geologic classifications for coarse aggregate are argillite, gneiss, granite, quartzite, or trap rock.  Ensure that the combined gradation with fine aggregate conforms to Table 902.04.02-1.

|  | Table 902.04.01-1 Coarse Aggregate Properties |
| --- | --- |
| Tests | Test Method | Minimum Percent | Maximum Percent |
| Percentage of wear, Los Angeles Abrasion Test | AASHTO T 96 | - | 25 |
| Flakiness Index | BS1 812, part 105.1 | - | 20 |
| Clay Lumps and Friable Particles | ASTM C 142 | - | 2 |
| Asphalt Affinity* | ASTM D 3625 | 95 | - |
| 1. British Standard Test Method |  |  |  |

5.	Use mineral filler, if necessary, that conforms to 901.05.03.

1**************************************************************************************************************************1

902.04.02  Mix Design

1**************************************************************************************************************************1

BDC14s-07 dated Aug 29, 2014

the entire Subsection text is changed to:

For the mix design of the ultra-thin HMA, submit lab qualifications and references to the ME for approval prior to beginning work.  Ensure that a technical representative from the lab which will perform the mix design is present during production to make adjustments as needed for mix compliance.

At least 30 days before the initial production date, submit the mix design to the ME for approval on forms supplied by the Department, including JMF for the ultra-thin HMA performed by an AASHTO accredited lab with at least five successfully completed ultra-thin HMA friction course projects greater than 5,000 tons each.  Include a statement naming the source of each component and a report with the results for the criteria specified in Table 902.04.01-1 and 902.04.02-1.

If the source of any component material changes, submit a new JMF and obtain ME approval before using the new material.  When unsatisfactory results or other conditions make it necessary, the ME may require a new JMF.

Design the ultra-thin HMA so that it has a draindown of less than 0.1 percent when tested according to AASHTO T 305.

When tested for moisture sensitivity according to AASHTO T 283, ensure that the ultra-thin HMA has a tensile strength ratio of at least 80 percent.  Prepare specimens according to AASHTO T 312, and test according to T 283 except for the following:

1.	Before compaction, condition the mixture for 2 hours according to AASHTO R 30, Section 7.1.

2.	Compact specimens with 75 gyrations.

3.	Extrude specimens as soon as possible without damaging.

4.	Use AASHTO T 269 to determine void content.

5.	Record the void content of the specimens.

6.	If less than 55 percent saturation is achieved, repeat the procedure, unless the difference in tensile strength between duplicate specimens is greater than 25 pounds per square inch.

7.	If visual stripping is detected, modify or readjust the mix.

Size, uniformly grade, and combine aggregate fractions in proportions so that the grading of total aggregate and asphalt binder in the JMF conform to the composition by mass percentages specified in Table 902.04.02-1.

| Table 902.04.02-1 JMF Requirements for Ultra-Thin Friction Course |
| --- |
| Sieve Size | Total % Passing By Mass | Production Control Tolerances from JMF |
| 1/2" | 100 | (6.0 |
| 3/8" | 75-100 | (5.5 |
| ¼” | 30-45 | ±5.5 |
| No. 4 | 24-37 | (5.5 |
| No. 8 | 21-26 | (4.5 |
| No. 16 | 15-23 | (4.0 |
| No. 30 | 11-16 | (4.0 |
| No. 50 | 8-14 | (4.0 |
| No. 100 | 5-10 | (3.0 |
| No. 200 | 5.0-7.0 | (2.0 |
| Asphalt % | 4.9-6.0 | Ignition Oven ±0.40 |

During the construction of the test strip, take samples to confirm that the plant mixed material meets the requirements of the mix design.  The ME will not grant final approval of the mix design until a successful verification of the plant produced mix and construction test strip.

1**************************************************************************************************************************1

902.04.03  Sampling and Testing

1**************************************************************************************************************************1

BDC14s-07 dated Aug 29, 2014

the entire Subsection text is changed to:

Ensure that the mix meets the requirements as specified in 902.02.04.A, otherwise the RE or ME will reject the material.  Maintain the temperature of the mix between 300 °F and 330 °F.  Perform and meet requirements for quality control testing as specified in 902.02.04.C.

Ensure that a technical representative from the lab which designed the mix is present during production to make adjustments as needed for mix compliance.  During production, the ME will take one random acceptance sample from each 700 tons of production to verify composition. Conduct draindown tests as directed by the ME.

If the composition testing results are outside of the production control tolerances specified in Table 902.04.02-1 for an acceptance sample, determine if a plant adjustment is needed and immediately run a quality control sample.  If the quality control sample is also outside of the control tolerances in Table 902.04.02-1, immediately take corrective action to bring the mix into compliance.  Take additional quality control samples after the corrective action to ensure that the mix is within the production control tolerances.  If 2 consecutive acceptance samples are outside the tolerances specified in Table 902.04.02-1, immediately stop production.  Obtain ME approval of a plant correction plan before resuming production.  Upon restarting production, do not transport mixture to the Project Limits before the results of a QC sample from the mixture indicate that the mixture meets JMF tolerances.  The ME will reject mixture produced at initial restarting that does not meet tolerances.

The ME will perform sampling according to NJDOT B-2 or ASTM D 3665, and will perform testing for composition according to AASHTO T 308.  Perform testing for draindown according to NJDOT B-7 or NJDOT B-8.

1**************************************************************************************************************************1

902.05.01  Composition of Mixture

1**************************************************************************************************************************1

BDC14s-07 dated Aug 29, 2014

the entire text is changed to:

Mix SMA in a plant that is listed on the QPL and conforms to the requirements for HMA plants as specified in 1009.01.

The composition of the SMA mixture is coarse aggregate, fine aggregate, mineral filler, mineral fibers or cellulose fibers, and polymer modified asphalt binder and may include a WMA additive.

Use asphalt binder for SMA that is PG 64E-22 as specified in 902.01.01.

For coarse aggregate in SMA, use crushed stone conforming to 901.05.01 and Table 902.05.01-1.  Use at least 2 stockpiles of crushed stone with differing gradations to allow adjustments to meet the JMF.

| Table 902.05.01-1 Coarse Aggregate Properties for SMA |
| --- |
| Tests | Test Method | Maximum Percent |
| Percentage of wear, Los Angeles Abrasion Test | AASHTO T 96 | 30 |
| Flat and Elongated, 5 to 1 (Material Retained on the No. 4 Sieve) | ASTM D 4791 | 5 |
| Flat and Elongated, 3 to 1 (Material Retained on the No. 4 Sieve) | ASTM D 4791 | 20 |

For fine aggregate, use 100 percent stone sand conforming to 901.05.02.  Ensure that the combined fine aggregate in the mixture conforms to the requirements in Table 902.02.02-2.

For mineral filler, use rock dust or crushed limestone conforming to AASHTO M 17.  Ensure that the mineral filler has a plasticity index of less than 4 percent when tested according to AASHTO T 90.

Do not add RAP, CRCG, GBSM, or RPCSA to the mixture.

Add stabilizing fibers consisting of mineral fiber or cellulose fiber conforming to AASHTO M 325. Use only one type per mix design.  If using mineral fibers, use between 0.4 and 0.6 percent by weight of total mix.  If using cellulose fibers, use between 0.3 and 0.4 percent by weight of total mix.  Provide control to accurately proportion the fibers into the mixture within ±10 percent of the required weight, and use equipment that ensures uniform dispersion of the fibers.  If using pre-packaged bags of fibers added to the pugmill during the dry mix cycle, follow the manufacturer’s recommendations for the dry and wet mixing time.  Store fibers in a dry location with a storage temperature not to exceed 120 °F.  The supplier of the cellulose or mineral fibers shall provide a certification of compliance, as specified in 106.07, for the fibers.  Ensure that a technical representative from the fiber supplier is at the HMA plant for the first full day of production for technical assistance.

If used, ensure that WMA additives or processes conform to 902.01.05.  If a WMA additive is pre-blended in the asphalt binder, ensure that the asphalt binder meets the requirements of the specified grade after the addition of the WMA additive.  If a WMA additive is added at the HMA plant, ensure that the addition of the additive will not negatively impact the grade of asphalt binder.  Follow the manufacturer’s recommendations for percentage of WMA additive needed. For controlled asphalt foaming system WMA, the Department may require an anti-stripping additive.

1**************************************************************************************************************************1

902.05.02  Mix Design

1**************************************************************************************************************************1

BDC14s-07 dated Aug 29, 2014

the entire text is changed to:

Design the SMA to meet the requirements in Table 902.05.02-1 and Table 902.05.02-2. Prepare the JMF according to AASHTO R 46.  Determine the JMF at 4 percent air voids and 75 gyrations of the Superpave gyratory compactor.

| Table 902.05.02-1 SMA Specification Band (% passing) nominal-maximum aggregate size |
| --- |
| Production Control Tolerances1 | Sieve Size | 19 mm % Passing | 12.5 mm % Passing | 9.5 mm % Passing |
| 0% | 1" | 100 | 100 | 100 |
| (5% | 3/4" | 90-100 | 100 | 100 |
| (5% | 1/2" | 50-88 | 90-100 | 100 |
| (5% | 3/8" | 25-60 | 50-80 | 70-95 |
| (4% | No. 4 | 20-28 | 20-35 | 30-50 |
| (4% | No. 8 | 16-24 | 16-24 | 20-30 |
| (4% | No. 16 | – | – | 0-21 |
| (3% | No. 30 | – | – | 0-18 |
| (3% | No. 50 | – | – | 0-15 |
| (2% | No. 200 | 8.0-11.0 | 8.0-11.0 | 8.0-12.0 |
|  | Coarse Aggregate Fraction | Portion Retained on No. 4 Sieve | Portion retained on No. 4 Sieve | Portion retained on No. 8 Sieve |
|  | Minimum Lift Thickness | 2 inches | 1-1/2 inch | 1 inch |
| 1. Production tolerances may fall outside of the wide band gradation limits. |

| Table 902.05.02-2 SMA Mixtures Volumetrics For Design and Plant Production |
| --- |
| Property | Production Control Tolerances | Requirement |
| Air Voids | (1% | 4.0% |
| Voids in Mineral Aggregate (VMA) | – | 17.0% minimum |
| VCAmix | – | Less than VCAdry |
| Draindown @ production temperature | – | 0.30% maximum |
| Asphalt Binder Content (AASHTO T 308) | (0.40% | 6% minimum |
| Tensile Strength Ratio (AASHTO T 283) | – | 80% minimum |

1**************************************************************************************************************************1

902.05.03  Sampling and Testing

1**************************************************************************************************************************1

BDC14s-07 dated Aug 29, 2014

the entire text is changed to:

Perform quality control testing as specified in 902.02.04.C.  Ensure that the mix meets the requirements as specified in 902.02.04.A, otherwise the RE or ME will reject the material.

During production at the plant, the ME will take a sample from each 700 tons of production to verify composition and air voids.  Conduct draindown, VCAmix, VCAdry, and VMA testing as directed by the ME.  Perform tests according to AASHTO R 46.

If the testing results are outside of the production control tolerances specified in Table 902.05.02-1 and Table 902.05.02-2 for an acceptance sample, determine if a plant adjustment is needed and immediately run a quality control sample.  If the quality control sample is also outside of the control tolerances in Table 902.05.02-1, immediately take corrective action to bring the mix into compliance.  Take additional quality control samples after completing the corrective action to ensure that the mix is within tolerances.  If 2 consecutive acceptance samples are outside the tolerances specified in Table 902.05.02-1 and Table 902.05.02-2, immediately stop production.  Obtain ME approval of a plant correction plan before resuming production.  Upon restarting production, do not transport mixture to the Project Limits before the results of a QC sample from the mixture indicate that the mixture meets JMF tolerances.  The ME will reject mixture produced at initial restarting that does not meet tolerances.

The ME will perform sampling according to NJDOT B-2 or ASTM D 3665, and will perform testing for composition according to AASHTO T 308.  The ME will determine bulk specific gravity of the compacted sample according to AASHTO T 166 or AASHTO T 331.  The ME will use the most current QC maximum specific gravity test result, obtained according to AASHTO T 209, in calculating the volumetric properties of the SMA. Perform testing for draindown according to AASHTO T 305.

1**************************************************************************************************************************1

902.06.01  Composition

1**************************************************************************************************************************1

BDC14s-07 dated Aug 29, 2014

the entire text is changed to:

Mix ASDC in a plant that is listed on the QPL and conforms to the requirements specified in 1009.01.

The mixture shall consist of asphalt binder and aggregate and may contain a WMA additive.  Use asphalt binder that is PG 64-22 as specified in 902.01.01.  Use aggregate that conforms to 901.05.01 or 901.05.02 and the gradation requirements specified in Table 902.06.01-1.

If used, ensure that WMA additives or processes conform to 902.01.05.  If a WMA additive is pre-blended in the asphalt binder, ensure that the asphalt binder meets the requirements of the specified grade after the addition of the WMA additive.  If a WMA additive is added at the HMA plant, ensure that the addition of the additive will not negatively impact the grade of asphalt binder.  Follow the manufacturer’s recommendations for percentage of WMA additive needed.  For controlled asphalt foaming system WMA, the Department may require an anti-stripping additive.

| Table 902.06.01-1 Gradation Requirements and Tolerances for ASDC |
| --- |
| Production Tolerance (Variation From JMF) | Sieve Size | JMF (Percent Passing) |
| ±0.0 | 1" | 100 |
| ±6.0 | 3/4" | 95 - 100 |
| ±5.5 | 1/2" | 85 - 100 |
| ±5.5 | 3/8" | 60 - 90 |
| ±5.5 | No. 4 | 15 - 25 |
| ±4.5 | No. 8 | 2 - 10 |
| ±2.0 | No. 200 | 2 - 5 |

Design the mixture to have an asphalt binder content of 3 ± 1/2 percent by weight of dry aggregate.

1**************************************************************************************************************************1

902.06.03  Sampling and Testing

1**************************************************************************************************************************1

BDC14s-07 dated Aug 29, 2014

the entire text is changed to:

Perform quality control testing as specified in 902.02.04.C.  Ensure that the mix meets the requirements as specified in 902.02.04.A, except that the temperature of the mix at discharge is required to be between 230 °F and 275 °F, otherwise the RE or ME will reject the material.  For mixes produced using a WMA additive or process, ensure that the temperature of the mixture at discharge from the plant or surge and storage bins is at least 10 °F above the WMA manufacturer’s recommended laydown temperature.

During production, the ME will take one random acceptance sample from each 700 tons of production to verify composition.  Conduct draindown tests as directed by the ME.

If the composition testing results are outside of the production control tolerances specified in Table 902.06.01-1 for an acceptance sample, determine if a plant adjustment is needed and immediately run a quality control sample.  If the quality control sample is also outside of the control tolerances specified in Table 902.06.01-1, immediately take corrective action to bring the mix into compliance.  Take additional quality control samples after the corrective action to ensure that the mix is within tolerances.  If 2 consecutive acceptance samples are outside the tolerances specified in Table 902.06.01-1, immediately stop production.  Obtain ME approval of a plant correction plan before resuming production.  Upon restarting production, do not transport mixture to the Project before the results of a QC sample from the mixture indicate that the mixture meets JMF tolerances.  The ME will reject mixture produced at initial restarting that does not meet tolerances.

The ME will perform sampling according to NJDOT B-2 or ASTM D-3665 and will perform testing for composition according to AASHTO T 308.  If directed by the ME, perform testing for draindown according to AASHTO T 305.

1**************************************************************************************************************************1

1**************************************************************************************************************************1

BDC14s-07 dated Aug 29, 2014

THE FOLLOWING SUBsections ARE ADDED

902.07  Asphalt-Rubber Open-Graded Friction Course (AR-OGFC)

902.07.01  Composition of Mixture

Mix AR-OGFC in a plant listed on the QPL and conforming to the requirements for HMA plants specified in 1009.01.  Ensure the HMA plant is equipped with asphalt-rubber binder blending equipment as specified in 1009.03.

Composition of mixture for AR-OGFC is coarse aggregate, fine aggregate and asphalt-rubber binder.  Ensure that the mixture conforms to the following requirements:

1.	Use aggregates that conform to 901.05.  Use fine aggregate that is 100 percent stone sand and conforms to Table 902.02.02-2.

2.	Do not use RAP, CRCG, GBSM, or RPCSA.

3.	Use asphalt-rubber binder that conforms to 902.07.02.

902.07.02  Asphalt-Rubber Binder

A.	Materials.  Use the following materials:

1.	Ground Crumb Rubber.  Ensure that the ground crumb rubber has a specific gravity of 1.15 ± 0.05, is free of wire or other contaminating materials, and contains not more than 0.5 percent fabric.  Use crumb rubber that is ambient ground and conforms to the gradation requirements specified in Table 902.07.02-1.  Ensure that the moisture content is less than 0.75 percent.  The Contractor may add up to four percent calcium carbonate by weight of the granulated rubber, to prevent the particles from sticking together.

| Table 902.07.02-1 Ground Crumb Rubber Gradation |
| --- |
| Sieve Size | Percent Passing1, 2 |
| No. 8 | 100 |
| No. 16 | 65 – 100 |
| No. 30 | 20 – 100 |
| No. 50 | 0 – 45 |
| No. 200 | 0 – 5 |
| 1. Perform gradation according to AASHTO T 27 using a minimum 50 gram sample. 2. Ensure that the gradation is performed as specified in NJDOT B-11. |

Submit to the ME a certification of compliance, as specified in 106.07, for the ground crumb rubber.  In addition, ensure that the certificates confirm that the rubber is a crumb rubber, derived from processing whole scrap tires or shredded tire materials; and the tires from which the crumb rubber is produced are taken from automobiles, trucks, or other equipment owned and operated in the United States.  Include with the certifications verifications that the processing did not produce, as a waste product, casings, or other round tire material that can hold water when stored or disposed of above ground.

2.	Asphalt Binder.

- Use asphalt binder that conforms to AASHTO M 320, Table 1; PG 64-22, PG 58-28 or an approved blend of both grades.  The asphalt binder producer is required to provide the asphalt binder quality control plan annually to the ME for approval.  Ensure that the quality control plan conforms to AASHTO R 26. Submit to the ME a certification of compliance, as specified in 106.07, for the asphalt binder.  The ME will perform quality assurance sampling and testing of each asphalt binder lot as defined in the approved quality control plan.

- Use one or more of the following types of warm mix asphalt (WMA) additives or processes:

1. Organic additives such as a paraffin wax or a low molecular weight esterified wax.

2. Chemical additive that acts as a surfactant or dispersing agent.

Do not use controlled asphalt foaming systems or any other steam injection processes or steam introducing additives.  WMA is a method of producing asphalt pavement at a mixing and compaction temperatures at least 30 ºF lower than Hot Mix Asphalt (HMA) by using one or more of the types of WMA additives listed above.  Submit information on the WMA additive or process with the Paving Plan required in 402.03.02.A.  Include in the submission, the name and description of the additive or process, the manufacturer’s recommendations for usage of the additive or process, recommendations for mixing and compaction temperatures, and details on at least one project on which the additive was successfully used in the United States on a crumb rubber modified asphalt mixture.  In the details of a project, include tonnage, type of mix, dosage, mixing and compaction temperatures, available test results, and contact information for project.  If a WMA additive is pre-blended in the asphalt binder, ensure that the asphalt binder meets the requirements of the specified grade after the addition of the WMA additive.  If a WMA additive is added at the HMA plant, ensure that the addition of the additive will not negatively impact the grade of asphalt binder.  The ME will evaluate the impacts to performance grade of the asphalt binder based upon certification from manufacturer in conjunction with laboratory data indicating the effects of the additive on the asphalt binder properties.  Follow the manufacturer’s recommendations for the dosage of WMA additive needed and approved blending method(s).

Ensure that a technical representative of the WMA additive manufacturer is on-site or available for consultation during the production and placement of the AR-OGFC with the warm mix additive.

B.	Mixing.  Using the asphalt-rubber binder blending equipment in 1009.03, produce the asphalt-rubber binder to contain at least 17 percent ground rubber by the weight of total asphalt binder (asphalt + crumb rubber).  Ensure that the temperature of the asphalt cement is between 350 and 400 °F at the time of addition of the ground rubber.  Ensure that there are no agglomerations of rubber particles in excess of two inches in the least dimension in the mixing chamber.

Document that the proportions are accurate and that the rubber has been uniformly incorporated into the mixture.  Report as directed by the ME.  Ensure that the crumb rubber and asphalt-cement are thoroughly mixed before beginning the one-hour reaction period.  Rubber floating on the surface or agglomerations of rubber particles is evidence of insufficient mixing.  Maintain the temperature of the asphalt-rubber binder immediately after mixing between 325 and 375 °F.  Maintain the temperature of the asphalt-rubber binder for at least one hour before using.

C.	Properties.  Prepare asphalt-rubber binder using the “wet process.”  Physical properties are required to comply with the requirements of ASTM D 6114, Type II, except for the properties specified in Table 902.07.02-2.

| Table 902.07.02-2 Asphalt-Rubber Binder Properties |
| --- |
| Property | Test Procedure | Requirement |
| Resilience: 77 °F; %, minimum Rotational Viscosity1 350 °F; cP | ASTM D 5329 NJDOT B-12 | 25 2000 – 4000 |
| 1. The viscotester used must be correlated to a Rion (formerly Haake) Model VT-04 viscotester using the No. 1 Rotor. The Rion viscotester rotor, while in the off position, is required to be completely immersed in the binder at a temperature from 350 ± 3 °F for a minimum heat equilibrium period of 60 seconds, and the average viscosity determined from three separate constant readings (( 500 cP) taken within a 30 second time frame with the viscotester level during testing and turned off between readings. Continuous rotation of the rotor may cause thinning of the material immediately in contact with the rotor, resulting in erroneous results. |

D.	Handling and Testing.  Once the asphalt-rubber binder has been mixed, thoroughly agitate during periods of use to prevent settling of the rubber particles.  During production, maintain asphalt-rubber binder between 325 and 375 °F. Ensure that asphalt-rubber binder is not held at 325 °F or higher for more than 16 hours.  Allow asphalt-rubber binder held for more than 16 hours to cool.  To reuse, gradually reheat to between 325 and 375 °F.  Do not cool and reheat more than one time.  Do not store asphalt-rubber binder above 250 °F for more than four days.

For each load or batch of asphalt-rubber binder, provide the RE with the following:

1.	The source, grade, amount, and temperature of the asphalt cement before the addition of rubber.

2.	The source and amount of rubber and the rubber content expressed as percent by the weight of the asphalt cement.

3.	Times and dates of the rubber additions and resultant viscosity test.

4.	A record of the temperature, with time and date reference for each load or batch.  The record begins at the time of the addition of rubber and continue until the load or batch is completely used.  Take readings and record every temperature change in excess of 20 °F, and as needed to document other events that are significant to batch use and quality.

902.07.03  Mix Design

Submit binder and mix designs including JMF for each mixture performed by an AASHTO accredited lab with at least five successfully completed asphalt-rubber open-graded friction course projects greater than 5,000 tons each.  Include a statement naming the source of each component and a report with the results for the criteria specified in Table 902.07.03-1.  Include a report detailing the rotational viscosity of the asphalt-rubber binder at 60, 90, 135, 240, and 1440 minutes.  Submit lab qualifications and references to the ME for approval prior to beginning work.

Design the mix to meet the criteria in Table 902.07.03-1.

| Table 902.07.03-1 JMF Master Ranges and Mixture Requirements AR-OGFC |
| --- |
|  | Mixture Designations (% Passing1) |
| Sieve Sizes | AR-OGFC |
| 1/2" | 100 |
| 3/8" | 90 – 100 |
| No. 4 | 20 – 40 |
| No. 8 | 5 – 10 |
| No. 200 | 0 – 3.0 |
| Minimum asphalt-rubber binder, %2 | 8.4 |
| Minimum % Air Voids, design | 15 |
| 1. Aggregate percent passing to be determined based on dry aggregate weight. 2. Asphalt-rubber binder content to be determined based on total weight of mix. |

Determine and verify the JMF according to NJDOT B-8.  Ensure that the JMF is within the master range specified in Table 902.07.03-1.

Prepare compacted test specimens for submittal to the ME at least 30 days before the initial production date.  Prepare these specimens from material mixed according to the final JMF, using 50 gyrations of the Superpave gyratory compactor according to AASHTO T 312.

The ME will test 2 specimens to verify stone-on-stone contact according to NJDOT B-8 and that the final JMF produces a mixture that has a minimum void content as specified in Table 902.07.03-1.  The ME will determine percent air voids according to AASHTO T 209 and AASHTO T 331.

The ME will test 2 test specimens for abrasion and impact resistance using a modified L.A.  Abrasion Test according to NJDOT B-8.  The maximum allowable loss as calculated by this method is 30 percent.

Do not modify, which includes changing the asphalt cement supplier, the JMF unless the ME approves the modification.

902.07.04  Sampling and Testing

A.	General Acceptance Requirements.  General Acceptance Requirements.  The RE or ME may reject and require disposal of any batch or shipment that is rendered unfit for its intended use due to contamination, segregation, improper temperature, lumps of cold material, or incomplete coating of the aggregate.  For other than improper temperature, visual inspection of the material by the RE or ME is considered sufficient grounds for such rejection.

For AR-OGFC with WMA additive, ensure that the temperature of the mixture at discharge from the plant or surge and storage bins meets the WMA additive manufacturer’s recommendations.  Do not allow the mixture temperature to exceed 300 °F at discharge from the plant.  For mixes produced using a WMA additive or process, ensure that the temperature of the mixture at discharge from the plant or surge and storage bins is at least 10 °F above the WMA manufacturer’s recommended laydown temperature.

Combine and mix the aggregates and asphalt-rubber binder to ensure that at least 95 percent of the coarse aggregate particles are entirely coated with asphalt-rubber binder as determined according to AASHTO T 195.  If the ME determines that there is an on-going problem with coating, the ME may obtain random samples from 5 trucks and will determine the adequacy of the mixing on the average of particle counts made on these 5 test portions.  If the requirement for 95 percent coating is not met on each sample, modify plant operations, as necessary, to obtain the required degree of coating.

B.	Quality Control Testing.  The HMA producer is required to provide a quality control (QC) technician who is certified by the Society of Asphalt Technologists of New Jersey as an Asphalt Technologist, Level 2.  The QC technician may substitute equivalent technician certification by the Mid-Atlantic Region Technician Certification Program (MARTCP).  Ensure that the QC technician is present during periods of mix production for the sole purpose of quality control testing and to assist the ME.  The ME will not perform the quality control testing or other routine test functions in the absence of, or instead of, the QC technician.

The QC technician is required to perform sampling and testing according to the approved quality control plan, to keep the mix within the limits specified for the mix being produced.  The QC technician may use acceptance test results or perform additional testing as necessary to control the mix.

For each acceptance test, perform maximum specific gravity testing according to AASHTO T 209 on a test portion of the sample taken by the ME.  Sample and test coarse aggregate, fine aggregate and mineral filler according to the approved quality control plan for the plant.

C.	Acceptance Testing.  During production, the ME will take one random acceptance sample from each 700 tons of production to verify composition.  The ME will perform sampling according to NJDOT B-2 or ASTM D 3665, and will perform testing for composition according to AASHTO T 308.  Perform testing for air voids according to T 209 and either B-6 or T 331. Perform testing for draindown according to NJDOT B-8.

Conduct air voids and draindown tests as directed by the ME.

If the composition testing results are outside of the production control tolerances specified in Table 902.07.04-1 for an acceptance sample, determine if a plant adjustment is needed and immediately run a quality control sample.  If the quality control sample is also outside of the control tolerances in Table 902.07.04-1, immediately take corrective action to bring the mix into compliance.  Take additional quality control samples after the corrective action to ensure that the mix is within the production control tolerances.  If two consecutive acceptance samples are outside the tolerances specified in Table 902.07.04-1, immediately stop production.  Obtain ME approval of a plant correction plan before resuming production.  Upon restarting production, do not transport mixture to the Project Limits before the results of a QC sample from the mixture indicate that the mixture meets JMF tolerances.  The ME will reject mixture produced at initial restarting that does not meet tolerances.

| Table 902.07.04-1 Production Control Tolerances for AR-OGFC Mixtures |
| --- |
| Sieve Sizes | Production Control Tolerances from JMF1 |
| 1/2" | (6.0 |
| 3/8" | (5.5 |
| No. 4 | (5.5 |
| No. 8 | (4.5 |
| No. 200 | (2.0 |
| Asphalt-rubber binder, % (AASHTO T 308) | (0.40 |
| Minimum % Air Voids | 1.0% less than design requirement |
| 1. Production tolerances may fall outside of the wide band gradation limits in Table 902.07.03-1. |

902.08 HIGH PERFORMANCE THIN OVERLAY (HPTO)

902.08.01 Composition of Mixture

Mix HPTO in a plant that is listed on the QPL and conforms to the requirements for HMA Plants as specified in 1009.01.  The composition of the mixture for HPTO is coarse aggregate, fine aggregate, and asphalt binder, and may also include mineral filler and a WMA additive.  Do not use Reclaimed Asphalt Pavement (RAP), Ground Bituminous Shingle Material, Remediated Petroleum Contaminated Soil Aggregate, or Crushed Recycled Container Glass (CRCG).  Use asphalt binder and aggregates that meet the following requirements:

1.	For the asphalt binder, use PG 64E-22 as specified in 902.01.01.

2.	If used, ensure that WMA additives or processes conform to 902.01.05.  If a WMA additive is pre-blended in the asphalt binder, ensure that the asphalt binder meets the requirements of the specified grade after the addition of the WMA additive.  If a WMA additive is added at the HMA plant, ensure that the addition of the additive will not negatively impact the grade of asphalt binder.  Follow the manufacturer’s recommendations for percentage of WMA additive needed.  For controlled asphalt foaming system WMA, the Department may require an anti-stripping additive.

3.	Use coarse aggregate that is argillite, gneiss, granite, quartzite, or trap rock and conforms to 901.05.01.

4.	For fine aggregate, use 100 percent stone sand conforming to 901.05.02 and having an uncompacted void content of at least 45 percent when tested according to AASHTO T 304, Method A.  In addition, the minimum sand equivalent is 45 percent when tested according to AASHTO T 176.

5.	If necessary, use mineral filler as specified in 901.05.03.

902.08.02 Mix Design

At least 45 days before initial production, submit a job mix formula for the HPTO on forms supplied by the Department.  Include a statement naming the source of each component and a report showing the results meet the criteria specified in Tables 902.08.03-1 and 902.08.03-2.

For the job mix formula for the HPTO mixture, establish the percentage of dry weight of aggregate passing each required sieve size and an optimum percentage of asphalt binder based upon the weight of the total mix.  Determine the optimum percentage of asphalt binder according to AASHTO R 35 and M 323 with an Ndes of 50 gyrations.  Before maximum specific gravity testing or compaction of specimens, condition the mix for 2 hours according to the requirements for conditioning for volumetric mix design in AASHTO R 30, Section 7.1.  If the absorption of the combined aggregate is more than 1.5 percent according to AASHTO T 84 and T 85, condition the mix for 4 hours according to AASHTO R 30, Section 7.2 prior to compaction of specimens (AASHTO T 312) and determination of maximum specific gravity (AASHTO T 209).  Ensure that the job mix formula is within the master range specified in, Table 902.08.03-1.

Ensure that the job mix formula provides a mixture that meets a minimum tensile strength ratio (TSR) of 85 percent when prepared according to AASTHO T 312 and tested according to AASHTO T 283 with the following exceptions:

1.	Before compaction, condition the mixture for 2 hours according to AASHTO R 30 Section 7.1.

2.	Compact specimens with 40 gyrations.

3.	Extrude specimens as soon as possible without damaging.

4.	Use AASHTO T 269 to determine void content.

5.	Record the void content of the specimens.

6.	If less than 55 percent saturation is achieved, the procedure does not need to be repeated, unless the difference in tensile strength between duplicate specimens is greater than 25 pounds per square inch.

7.	If visual stripping is detected, modify or readjust the mix.

For each mix design, submit three gyratory specimens and one loose sample corresponding to the composition of the job mix formula, including the design asphalt content.  The ME will use these samples for verification of the properties of the job mix formula.  Compact the specimens to the design number of gyrations (Ndes).  To be acceptable all three gyratory specimens must comply with the gradation and asphalt content requirements in Table 902.08.03-1 and with the control requirements in Table 902.08.03-2.  The ME reserves the right to be present at the time of molding the gyratory specimens.

In addition, submit 6 gyratory specimens and a 5 gallon bucket of loose mix to the ME.  Compact the additional gyratory specimens according to AASHTO T 312.  Ensure that the 6 gyratory specimens are 77 millimeters high and have an air void content of 5.0 ± 0.5 percent.  The ME will use the additional samples for performance testing of the HPTO mix.  The ME will test the specimens using an Asphalt Pavement Analyzer according to AASHTO T 340 at 64 °C, 100 pounds per square inch hose pressure, and 100 pound wheel load.  The ME will approve the job mix formula if the average rut depth for the 6 specimens in the asphalt pavement analyzer testing is not more than 4 millimeters in 8,000 loading cycles.  If the job mix formula does not meet the APA criteria, redesign the HPTO mix.

If unsatisfactory results for any specified characteristic of the work make it necessary, establish a new job mix formula for approval.  In such instances, if corrective action is not taken, the ME may require an appropriate adjustment.

If a change in sources is made or a change in the properties of materials occurs, the ME will require that a new job mix formula be established and approved before production can continue.

902.08.03  Sampling and Testing

A.	General Acceptance Requirements.  The RE or ME may reject and require disposal of any batch or shipment that is rendered unfit for its intended use due to contamination, segregation, improper temperature, lumps of cold material, or incomplete coating of the aggregate.  For other than improper temperature, visual inspection of the material by the RE or ME is considered sufficient grounds for such rejection.

Ensure that the temperature of the HPTO at discharge from the plant or surge and storage bins is maintained between 300 and 330 °F.  For mixes produced using a WMA additive or process, ensure that the temperature of the mixture at discharge from the plant or surge and storage bins is at least 10 °F above the WMA manufacturer’s recommended laydown temperature.

Combine and mix the aggregates and asphalt binder to ensure that at least 95 percent of the coarse aggregate particles are entirely coated with asphalt binder as determined according to AASHTO T 195.  If the ME determines that there is an on-going problem with coating, the ME may obtain random samples from 5 trucks and will determine the adequacy of the mixing on the average of particle counts made on these 5 test portions.  If the requirement for 95 percent coating is not met on each sample, modify plant operations, as necessary, to obtain the required degree of coating.

B.	Sampling.  The ME will take a sample of HPTO for volumetric acceptance testing from each 700 tons of a mix.  The ME will perform sampling according to AASHTO T 168, NJDOT B-2, or ASTM D 3665.

C.	Quality Control Testing.  The HMA producer is required to provide a quality control (QC) technician who is certified by the Society of Asphalt Technologists of New Jersey as an Asphalt Technologist, Level 2.  The QC technician may substitute equivalent technician certification by the Mid-Atlantic Region Technician Certification Program (MARTCP).  Ensure that the QC technician is present during periods of mix production for the sole purpose of quality control testing and to assist the ME.  The ME will not perform the quality control testing or other routine test functions in the absence of, or instead of, the QC technician.

The QC technician is required to perform sampling and testing according to the approved quality control plan, to keep the mix within the limits specified for the HPTO mix being produced.  The QC technician may use acceptance test results or perform additional testing as necessary to control the mix.

To determine the composition, perform ignition oven testing according to AASHTO T 308.  For each acceptance test, perform maximum specific gravity testing according to AASHTO T 209 on a test portion of the sample taken by the ME.  Sample and test coarse aggregate, fine aggregate, mineral filler, and RAP according to the approved quality control plan for the plant.

D.	Acceptance Testing and Requirements.  The ME will determine volumetric properties at Ndes for acceptance from samples taken, compacted, and tested at the HMA plant.  The ME will compact HPTO to 50 gyrations, using equipment according to AASHTO T 312.  The ME will determine bulk specific gravity of the compacted sample according to AASHTO T 166.  The ME will use the most current QC maximum specific gravity test result in calculating the volumetric properties of the HPTO.

The ME will determine the dust-to-binder ratio from the composition results as tested by the QC technician.

Ensure that the HMA mixture conforms to the requirements specified in Table 902.08.03-2, and to the gradation requirements in Table 902.08.03-1.  If 2 samples in 5 consecutive samples fail to conform to the gradation or volumetric requirements, immediately initiate corrective action.

The ME will test a minimum of 1 sample per 3500 tons for moisture, basing moisture determinations on the weight loss of an approximately 1600-gram sample of mixture heated for 1 hour in an oven at 280 ± 5 °F.  Ensure that the moisture content of the mixture at discharge from the plant does not exceed 1.0 percent.

E.	Performance Testing.  Provide 6 gyratory specimens and a 5 gallon bucket of loose mix to the ME.  Compact the additional gyratory specimens according to AASHTO T 312.  Ensure that the 6 gyratory specimens are 77 millimeters high and have an air void content of 5.0 ± 0.5 percent.  The first sample is required to be taken in the first 1500 tons of production.  Thereafter, random samples every 10,000 tons is required to be sampled.  The ME will use the samples for performance testing of the HPTO mix.  The ME will test the specimens using an Asphalt Pavement Analyzer according to AASHTO T 340 at 64 °C, 100 pounds per square inch hose pressure, and 100 pounds wheel load.  If the HPTO mix exceeds the APA criteria of 5 mm in 8000 loading cycles, the ME may stop production until corrective action is taken.  If the HPTO mix exceeds the APA criteria of 12 mm in 8000 loading cycles, the RE may require removal and replacement of the HPTO.

| Table 902.08.03-1 HPTO Grading of Total Aggregate |
| --- |
| Sieve Size | Percent Passing by Mass |
| 3/8” | 100 |
| #4 | 65-85 |
| #8 | 33-55 |
| #16 | 20-35 |
| #30 | 15-30 |
| #50 | 10-20 |
| #100 | 5-15 |
| #200 | 5.0-8.0 |
| Minimum Percent Asphalt by Mass of Total Mix | 7 |

| Table 902.08.03-2 Volumetric Requirements for Design and Control of HPTO |
| --- |
|  | Required Density | Voids in Mineral Aggregate | Dust to Binder Ratio | Draindown AASHTO T 305 |
|  | (% of Max. Sp. Gr.) |  |  |  |
|  | Ndes (50 gyrations) | Nmax ( 100 gyrations) | (VMA) |  |  |
| Design Requirements | 96.5 | ≤ 99.0 | ≥ 18.0 % | 0.6 - 1.2 | ≤ 0.1 % |
| Control Requirements | 95.5 - 97.5 | ≤ 99.0 | ≥ 18.0 % | 0.6 – 1.3 | ≤ 0.1 % |

1**************************************************************************************************************************1

THE FOLLOWING SUBsections ARE ADDED

1**************************************************************************************************************************1

BDC15s-01 dated mar 26, 2015

902.09  Micro surfacing

902.09.01  Composition of the Mixture

Ensure that the micro surfacing mixture components conform to the following:

- Micro Surfacing Emulsion. Use polymer modified emulsified asphalt.  Ensure that the emulsified asphalt and emulsified asphalt residue is a quick set polymer modified asphalt emulsion conforming to the requirements of AASHTO M 208 for a CQS-1h emulsion and the following:

  - Use a minimum of 3 percent polymer material, by weight of asphalt.

  - Ensure that the polymer material is milled or blended into the asphalt prior to the emulsification process by an emulsion manufacturer approved by the ME.

  - Ensure that the polymer modifier and any additives enable the micro surfacing material to receive normal traffic within one hour without causing damage to the surface.  The cement mixing test is waived for this emulsion.  .

  - Ensure that the emulsified asphalt and the emulsified asphalt residue meet all of the quality test criteria in section 4.1.2 of the International Slurry Surfacing Association (ISSA) “Recommended Performance Guideline for Micro Surfacing”; A 143

- Aggregate.  Use only manufactured stone sand and crushed stone that conform to 901.05. Ensure that the fine aggregate has a Sand Equivalent value of 65 percent minimum when tested according to AASHTO T 176.

- Mineral Filler.  Use mineral filler that conforms to ASTM D 242 and is free of lumps.

- Water.  Use water that conforms to 919.08.

- Other Additives.  The Contractor may use other additives to provide control of the break/set time in the field.  Ensure that the type of additive is specified in the mix design.

902.09.02  Mix Design of Micro Surfacing Mixture

- Mix Design Requirements.  Ensure that an AASHTO accredited lab, with at least five successfully completed micro surfacing projects greater than 5,000 square yards each, performs the mix design.  Submit the mix design and certified test results of the micro surfacing mixture for approval in accordance with the provisions of ASTM D 6372, Standard Practice for Design, Testing, and Construction of Micro Surfacing and the following:

- Ensure that the aggregate used in the job mix formula is from the same source and representative of the material proposed for use on the project.

- Ensure that the compatibility of the aggregate, micro surfacing emulsion, water, mineral filler, and other additives is evaluated in the mix design. Perform the mix design using materials consistent with those supplied by the contractor for the project. Ensure the micro surfacing mix conforms to the requirements as specified in Table 902.09.02-1.

| 902.09.02-1 Micro Surfacing Mixture Requirements |
| --- |
| Tests | ISSA Test Method | Specification |
| Mix Time @ 77 °F Mix Time @ 100 °F | TB 113 | Controllable to 120 seconds minimum Controllable to 35 seconds minimum |
| Wet Cohesion @ 30 minutes minimum (set) @ 60 minutes minimum (traffic) | TB 139 | 12 kg-cm minimum 20 kg-cm or near spin minimum |
| Wet Stripping | TB 114 | 90 % minimum |
| Wet-Track Abrasion Loss One-hour soak Six-day soak | TB 100 | 50 g/ft2 (538 g/m2) maximum 75 g/ft2 (807 g/m2) maximum |
| Lateral Displacement | TB 147 | 5% maximum |
| Specific Gravity after 1,000 cycles of 125 pounds (56.71 kg) | TB 147 | 2.10 maximum |
| Excess Asphalt by LWT Sand Adhesion | TB 109 | 50 g/ft2 (538 g/m2) maximum |
| Classification Compatibility | TB 144 | 11 grade points minimum (AAA, BAA) |

- Ensure proportioning of the mix design is within the limits in Table 902.09.02-2:

| Table 902.09.02-2 Mix Design Proportion Requirements |
| --- |
| Component Materials | Limits |
| Residual asphalt | 5.5 to 11.5% by dry weight of aggregates |
| Mineral filler | 0.0 to 3% by dry weight of aggregates |
| Polymer-based modifier | min. of 3% polymer solids based on bitumen weight content |
| Additives | as needed |
| Water | as required to ensure proper mix consistency |

- Ensure that the proportions of aggregate and mineral filler are provided and within the limits of Table 902.09.03-1.

- Mix Design Report.  Submit the final mix design in the following format:

  - Source of each individual material.

  - Aggregate:

    - Gradation

    - Sand Equivalent

    - Abrasion Resistance

    - Soundness

  - Field Simulation Tests:

    - Wet Stripping Test

    - Wet Track Abrasion Loss

    - Classification Compatibility

    - Trial Mix Time @ 77 °F and 100 °F

  - Interpretation of Results and the Determination of a Job Mix Formula (JMF):

    - Percentage of Mineral Filler (minimum and maximum)

    - Percentage of Water, including aggregate moisture (minimum and maximum)

    - Percentage of Mix Set Additive (if required)

    - Percentage of Modified Emulsion

    - Residual Content of Modified Emulsion

    - Percentage of Residual Asphalt

    - Combined Aggregate Gradation (JMF)

  - Signature and date

902.09.03  Sampling and Testing

The ME will perform sampling and testing of the aggregate at least 10 days prior to the start of work.  The ME will sample aggregate from stockpiles designated and constructed for each mixture type on the project.  The ME will sample the aggregate according to AASHTO T 2 and test according to AASHTO T 11 and T 27 using the following sampling frequency:

- When the project quantity for the specified mixture type is less than 500 tons, designate the entire quantity as one lot and divide into three equal sublots for sampling.  Obtain one sample from each sublot and submit to the ME for testing. The ME will randomly select only one of the three samples and test for compliance with Table 902.09.03-1.  If the sample tested meets the specification, the entire lot is acceptable for use on the project.  If the sample fails, the ME will test the remaining two samples. If the two samples both meet specification, the entire lot is acceptable for use on the project.  If either of the two additional samples fails to meet the specification, the entire lot is rejected.

- When the project quantity for the specified mixture type is 500 tons or greater, divide the aggregate into equal lots at the discretion of the ME, but in no case is the lot size to exceed 1,000 tons.  Divide each lot into three equal sublots and obtain one sample for each sublot. The ME will randomly select only one of the three samples and test for compliance with Table 902.09.03-1.  If the sample tested meets the specification, the entire lot is acceptable for use on the project.  If the sample fails, the ME will test the remaining two samples. If the two samples both meet specification, the entire lot is acceptable for use on the project.  If either of the two additional samples fails to meet the specification, the entire lot is rejected.

Take precautions to ensure that approved stockpiles of aggregate do not become contaminated at the jobsite.  Screen oversize aggregate or foreign materials from the aggregate prior to delivery to the mixer.

During the micro surfacing application, in the presence of the inspector, sample the mixture twice daily or as directed from the pug mill discharge chute.  Use a rectangular non-absorptive container, such as a loaf pan, of sufficient size to obtain a sample from the entire cross section of the mixture being discharged.  Ensure that an AASHTO accredited lab, with at least five successfully completed micro surfacing projects greater than 5,000 square yards each, analyzes the mix for binder content and compliance with specifications.  Submit certified results to the ME.  The ME may perform independent testing.

Ensure that the asphalt content is within ± 0.40 of the JMF.  If the asphalt content is outside of the allowable tolerance, recalibrate or adjust the mixing machine.  The RE may stop the micro surfacing operation if two or more samples fail to conform to the tolerance.  Take corrective action or re-design the micro surfacing mixture.  Resume operations only after RE has approved the corrective action.

Use aggregate, including mineral filler, which conforms to the gradation in Table 902.09.03-1.

| Table 902.09.03-1 Gradation Requirements for Aggregate and Mineral Filler |
| --- |
| Sieve Size | Type II Percent Passing | Type III Percent Passing | Stockpile Tolerances from JMF |
| 3/8” | 100 | 100 | - |
| No. 4 | 90-100 | 70-90 | ±5% |
| No. 8 | 65-90 | 45-70 | ±5% |
| No. 16 | 45-70 | 28-50 | ±5% |
| No. 30 | 30-50 | 19-34 | ±5% |
| No. 50 | 18-30 | 12-25 | ±4% |
| No. 100 | 10-21 | 7-18 | ±3% |
| No. 200 | 5-15 | 5-15 | ±2% |

902.10  Slurry seal

902.10.01  Composition of the Mixture

Ensure that the slurry seal mixture components conform to the following:

- Slurry Seal Emulsion. Use polymer modified emulsified asphalt.  Ensure that the emulsified asphalt and emulsified asphalt residue is a quick set polymer modified asphalt emulsion conforming to the requirements of AASHTO M 208 for a CQS-1h emulsion and the following:

  - Use a minimum of 3 percent polymer material, by weight of asphalt.

  - Ensure that the polymer material is milled or blended into the asphalt prior to the emulsification process by an emulsion manufacturer approved by the ME.

  - Ensure that the polymer modifier and any additives enable the slurry seal material to receive normal traffic within one hour without causing damage to the surface.

  - Ensure that the emulsified asphalt and the emulsified asphalt residue material conform to the requirements in table 902.10.01-1.

| 902.10.01-1 Emulsified Asphalt and Residue Requirements |
| --- |
| Tests | Test Method | Specification |
| Tests on Emulsified Asphalt |
| Storage Stability, 24 hours, percent | AASHTO T 59 | 1 % maximum |
| Residue by Distillation1, percent | AASHTO T 59 | 62 % minimum |
| Tests on Asphalt Residue |
| Softening Point by Ring and Ball | AASHTO T 53 | 135 °F minimum |
| 1. Test temperature held at 350 °F for 20 minutes. |

- Aggregate.  Use only manufactured stone sand and crushed stone that conform to 901.05. Ensure that the fine aggregate has a Sand Equivalent value of 45 percent minimum when tested according to AASHTO T 176.

- Mineral Filler.  Use mineral filler that conforms to ASTM D 242 and is free of lumps.

- Water.  Use water that conforms to 919.08.

- Other Additives.  The Contractor may use other additives to provide control of the break/set time in the field.  Ensure that the type of additive is specified in the mix design.

902.10.02  Mix Design of Slurry Seal Mixture

A	Mix Design Requirements.  Ensure that an AASHTO accredited lab, with at least five successfully completed slurry seal projects greater than 5,000 square yards each, performs the mix design.  Submit the mix design and certified test results of the slurry seal mixture for approval in accordance with the provisions of ASTM D 3910, Standard Practice for Design, Testing, and Construction of Slurry Seal and the following:

1.	Ensure that the aggregate used in the job mix formula is from the same source and representative of the material proposed for use on the project.

2.	Ensure that the compatibility of the aggregate, slurry seal emulsion, water, mineral filler, and other additives is evaluated in the mix design. Perform the mix design using materials consistent with those supplied by the contractor for the project. Ensure the slurry seal mix conforms to the requirements as specified in Table 902.10.02-1.

| 902.10.02-1 Slurry Seal Mixture Requirements |
| --- |
| Tests | ISSA Test Method | Specification |
| Mix Time @ 77 °F Mix Time @ 100 °F | TB 113 | Controllable to 120 seconds minimum Controllable to 35 seconds minimum |
| Slurry Seal Consistency | TB 106 | 0.79 to 1.18 inches |
| Wet Cohesion @ 30 minutes minimum (set) @ 60 minutes minimum (traffic) | TB 139 | 12 kg-cm minimum 20 kg-cm or near spin minimum |
| Wet Stripping | TB 114 | 90 % minimum |
| Wet-Track Abrasion Loss One-hour soak Six-day soak | TB 100 | 50 g/ft2 (538 g/m2) maximum 75 g/ft2 (807 g/m2) maximum |
| Lateral Displacement | TB 147 | 5% maximum |
| Specific Gravity after 1,000 cycles of 125 pounds (56.71 kg) | TB 147 | 2.10 maximum |
| Excess Asphalt by LWT Sand Adhesion | TB 109 | 50 g/ft2 (538 g/m2) maximum |
| Classification Compatibility | TB 144 | 11 grade points minimum (AAA, BAA) |

3.	Ensure proportioning of the mix design is within the limits in Table 902.10.02-2:

| Table 902.10.02-2 Mix Design Proportion Requirements |
| --- |
| Component Materials | Limits |
| Residual asphalt | 7.5 to 13.5% by dry weight of aggregates |
| Mineral filler | 0.0 to 3% by dry weight of aggregates |
| Polymer-based modifier | min. of 3% polymer solids based on bitumen weight content |
| Additives | as needed |
| Water | as required to ensure proper mix consistency |

4.	Ensure that the proportions of aggregate and mineral filler are provided and within the limits of Table 902.10.03-1.

B	Mix Design Report.  Submit the final mix design in the following format:

1.	Source of each individual material.

2.	Aggregate:

a.	Gradation

b.	Sand Equivalent

c.	Abrasion Resistance

d.	Soundness

3.	Field Simulation Tests:

a.	Wet Stripping Test

b.	Wet Track Abrasion Loss

c.	Classification Compatibility

d.	Trial Mix Time @ 77 °F and 100 °F

4.	Interpretation of Results and the Determination of a Job Mix Formula (JMF):

    - Percentage of Mineral Filler (minimum and maximum)

    - Percentage of Water, including aggregate moisture (minimum and maximum)

    - Percentage of Mix Set Additive (if required)

    - Percentage of Modified Emulsion

    - Residual Content of Modified Emulsion

    - Percentage of Residual Asphalt

    - Combined Aggregate Gradation (JMF)

5.	Signature and date

902.10.03  Sampling and Testing

The ME will perform sampling and testing of the aggregate at least 10 days prior to the start of work.  The ME will sample aggregate from stockpiles designated and constructed for each mixture type on the project.  The ME will sample the aggregate according to AASHTO T 2 and test according to AASHTO T 11 and T 27 using the following sampling frequency:

- When the project quantity for the specified mixture type is less than 500 tons, designate the entire quantity as one lot and divide into three equal sublots for sampling.  Obtain one sample from each sublot and submit to the ME for testing. The ME will randomly select only one of the three samples and test for compliance with Table 902.10.03-1.  If the sample tested meets the specification, the entire lot is acceptable for use on the project.  If the sample fails, the ME will test the remaining two samples. If the two samples both meet specification, the entire lot is acceptable for use on the project. If either of the two additional samples fails to meet the specification, the entire lot is rejected.

- When the project quantity for the specified mixture type is 500 tons or greater, divide the aggregate into equal lots at the discretion of the ME, but in no case is the lot size to exceed 1,000 tons. Divide each lot into three equal sublots and obtain one sample for each sublot. The ME will randomly select only one of the three samples and test for compliance with Table 902.10.03-1.  If the sample tested meets the specification, the entire lot is acceptable for use on the project.  If the sample fails, the ME will test the remaining two samples. If the two samples both meet specification, the entire lot is acceptable for use on the project.  If either of the two additional samples fails to meet the specification, the entire lot is rejected.

Take precautions to ensure that approved stockpiles of aggregate do not become contaminated at the jobsite.  Screen oversize aggregate or foreign materials from the aggregate prior to delivery to the mixer.

During the slurry seal application, in the presence of the inspector, sample the mixture twice daily or as directed from the pug mill discharge chute.  Use a rectangular non-absorptive container, such as a loaf pan, of sufficient size to obtain a sample from the entire cross section of the mixture being discharged.  Ensure that an AASHTO accredited lab, with at least five successfully completed slurry seal projects greater than 5,000 square yards each, analyzes the mix for binder content and compliance with specifications.  Submit certified results to the ME.  To ensure mix compliance, the ME may perform independent testing.

Ensure that the asphalt content is within ± 0.40% of the JMF.  If the asphalt content is outside of the allowable tolerance, recalibrate or adjust the mixing machine.  The RE may stop the slurry seal operation if two or more samples fail to conform to the tolerance.  Take corrective action or re-design the slurry seal mixture.  Resume operations only after RE has approved the corrective action.

Use aggregate, including mineral filler, which conforms to the gradation in Table 902.10.03-1.

| Table 902.10.03-1 Gradation Requirements for Aggregate and Mineral Filler |
| --- |
| Sieve Size | Type I Percent Passing | Type II Percent Passing | Type III Percent Passing | Stockpile Tolerances from JMF |
| 3/8” | 100 | 100 | 100 | - |
| No. 4 | 100 | 90-100 | 70-90 | ±5% |
| No. 8 | 90-100 | 65-90 | 45-70 | ±5% |
| No. 16 | 65-90 | 45-70 | 28-50 | ±5% |
| No. 30 | 40-65 | 30-50 | 19-34 | ±5% |
| No. 50 | 25-42 | 18-30 | 12-25 | ±4% |
| No. 100 | 15-30 | 10-21 | 7-18 | ±3% |
| No. 200 | 10-20 | 5-15 | 5-15 | ±2% |

1**************************************************************************************************************************1

Section 903 – Concrete

903.02.04 Viscosity Modifying Admixture

1**************************************************************************************************************************1

BDC15s-06 dated jul 30, 2015

The first sentence is changed to:

Use a viscosity modifying admixture that is listed on the QPL and that, when evaluated according to the test methods and mix design proportions in AASHTO M 194, conforms to the following physical requirements:

1**************************************************************************************************************************1

903.03.05  Control and Acceptance Testing Requirements

E.	Acceptance Testing for Strength for Pay-Adjustment Items.

1**************************************************************************************************************************1

2**************************************************************************************2

INCLUDE ONLY THE following ITEMS, as APPLICABLE, for pay adjustment

(do not include any variance such as: concrete bridge deck, hpc)

Concrete Items which are subject to pay adjustment and the base prices are as follows:

| ITEMS | DESCRIPTION | UNIT | BASE PRICE |
| --- | --- | --- | --- |
| 507021P | CONCRETE BRIDGE DECK | CY | $500.00 |
| 507036P | CONCRETE BRIDGE PARAPET | LF | $305.00 |
| 505039P | PRESTRESSED CONCRETE SLAB BEAM, (TYPE SII-36), 36" X 15" | LF | $125.00 |
| 505042P | PRESTRESSED CONCRETE SLAB BEAM, (TYPE SIII-36), 36" X 18" | LF | $130.00 |
| 505015P | PRESTRESSED CONCRETE BOX BEAM, (TYPE BI-36), 36" X 27" | LF | $170.00 |
| 505045P | PRESTRESSED CONCRETE SLAB BEAM, (TYPE SIV-36), 36" X 21" | LF | $160.00 |
| 505018P | PRESTRESSED CONCRETE BOX BEAM, (TYPE BII-36), 36" X 33" | LF | $170.00 |
| 505021P | PRESTRESSED CONCRETE BOX BEAM, (TYPE BIII-36), 36" X 39" | LF | $175.00 |
| 505024P | PRESTRESSED CONCRETE BOX BEAM, (TYPE BIV-36), 36" X 42" | LF | $185.00 |
| 505003P | PRETENSIONED PRESTRESSED CONCRETE BEAM, 45" | LF | $155.00 |
| 505006P | PRETENSIONED PRESTRESSED CONCRETE BEAM, 54" | LF | $155.00 |
| 505048P | PRESTRESSED CONCRETE SLAB BEAM, (TYPE SII-48), 48" X 15" | LF | $160.00 |
| 505051P | PRESTRESSED CONCRETE SLAB BEAM, (TYPE SIII-48), 48" X 18" | LF | $135.00 |
| 505009P | PRETENSIONED PRESTRESSED CONCRETE BEAM, 63" | LF | $185.00 |
| 505027P | PRESTRESSED CONCRETE BOX BEAM, (TYPE BI-48), 48" X 27" | LF | $215.00 |
| 505054P | PRESTRESSED CONCRETE SLAB BEAM, (TYPE SIV-48), 48" X 21" | LF | $215.00 |
| 505030P | PRESTRESSED CONCRETE BOX BEAM, (TYPE BII-48), 48" X 33" | LF | $185.00 |
| 505033P | PRESTRESSED CONCRETE BOX BEAM, (TYPE BIII-48), 48" X 39" | LF | $220.00 |
| 505036P | PRESTRESSED CONCRETE BOX BEAM, (TYPE BIV-48), 48" X 42" | LF | $230.00 |
| 505012P | PRETENSIONED PRESTRESSED CONCRETE BEAM, 72" | LF | $200.00 |
| 502045M | CAST-IN-PLACE CONCRETE PILE, DRIVEN, 12" DIAMETER | LF | $50.00 |
| 502090M | PRECAST CONCRETE PILE, DRIVEN, 12" X 12" | LF | $90.00 |
| 502132M | PRESTRESSED CONCRETE PILE, DRIVEN, 12" X 12" | LF | $50.00 |
| 502135M | PRESTRESSED CONCRETE PILE, DRIVEN, 14" X 14" | LF | $50.00 |
| 502138M | PRESTRESSED CONCRETE PILE, DRIVEN, 16" X 16" | LF | $50.00 |
| 502141M | PRESTRESSED CONCRETE PILE, DRIVEN, 18" X 18" | LF | $50.00 |
| 502144M | PRESTRESSED CONCRETE PILE, DRIVEN, 20" X 20" | LF | $75.00 |
| 502147M | PRESTRESSED CONCRETE PILE, DRIVEN, 22" X 22" | LF | $75.00 |
| 502150M | PRESTRESSED CONCRETE PILE, DRIVEN, 24" X 24" | LF | $75.00 |
| 502151M | PRESTRESSED CONCRETE PILE, DRIVEN, 30" X 30" | LF | $75.00 |
| 502156M | PRESTRESSED CONCRETE PILE, DRIVEN, 54" DIAMETER | LF | $200.00 |

2**************************************************************************************2

2**************************************************************************************2

BDC13s-06 dated Apr 19, 2013

4.	Compute Percent Pay Adjustment (PPA).

the fifth paragraph is changed to:

If the Department elects not to core, the Contractor may accept the PPA calculated by Equation 1 or 2, as appropriate, or, when approved by the Department, the Contractor may take cores as specified in Table 903.03.06-4.  Take the cores within 90 days from the date of concrete placement.  The Department will not award a positive pay adjustment based on core samples taken more than 90 days from the date of concrete placement.  If electing to core, perform the coring as directed by the ME, and provide the cores to the ME for testing.

2**************************************************************************************2

1**************************************************************************************************************************1

F.	Acceptance Testing for Strength for Non-Pay-Adjustment Items.

1**************************************************************************************************************************1

BDC13s-06 dated Apr 19, 2013

the fifth paragraph is changed to:

If cores are taken, the Department will use the core results to determine the final disposition of the lot.  If, based on the core results, the lot is determined to be at a quality level of PD < 75, the Department will compute the pay-adjustment as specified in 903.03.05.E.  The Department will not award positive pay adjustment for non-pay-adjustment Items.  If the lot is confirmed to be at a quality level of PD ≥ 75, the ME will reject the lot and the RE may do one of the following:

1.	Require the Contractor to remove and replace the defective lot

2.	Allow the Contractor to leave the defective lot in place and receive a PPA computed by Equation 2.

3.	Allow the Contractor to submit a plan, for approval, for corrective action.

1**************************************************************************************************************************1

903.03.06  Tables

Table 903.03.06-2  Requirements for Structural Concrete Items

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

the seventh LINE under Cast-in-Place Items IS changed to:

| Table 903.03.06-2 Requirements for Structural Concrete Items |
| --- |
|  | Concrete Class | Slump1 (inches) | Percent Air Entrainment for Coarse Aggregate1 |
|  |  |  | No. 57 & No. 67 | No. 8 |
| Decks, Sidewalks, Curbs, Parapets, Concrete Patch | A | 3 ± 1 | 6.0 ± 1.5 | 7.0 ± 1.5 |

1**************************************************************************************************************************1

903.05.04 Control and Acceptance Testing Requirements

1**************************************************************************************************************************1

BDC11s-08 dated aug 26 2011

The superscript reference No. 4 under table 903.05.04-1 is changed to:

4.	For chloride permeability testing, the ME will mold 4 additional cylinders, taking 2 cylinders each from 2 randomly selected delivery trucks for testing at 56-days.

THE fourth PARAGRAPH IS CHANGED TO:

If, upon testing at 56 days, 1 or more individual test results exceed 2000 coulombs, the RE may:

- Require that the Contractor remove and replace the defective lot, or

- Allow the Contractor to submit a corrective action plan for approval.

1**************************************************************************************************************************1

903.06.02  SCC For Precast Concrete

THE entire part B. is changed to:

1**************************************************************************************************************************1

BDC15s-06 dated jul 30, 2015

B.	Mix Design and Verification.  Design the mix, as specified in 903.03.02 or 903.05.02, to conform to the strength, water-cement ratio, and air content requirements for the specified class of concrete for the item that is being cast. In addition, ensure that the SCC conforms to the requirements specified in Table 903.06.02-1.

| Table 903.06.02-1 Requirements for SCC for Precast Concrete |
| --- |
| Property | Test Method | Requirement |
| Slump Flow | NJDOT C-4 | 16 to 24 inches |
| Visual Stability Index |  |  |
| Plastic Concrete | NJDOT C-4 | 1 maximum |
| Hardened Concrete | NJDOT C-5 | 1 maximum |

Perform mix design verification as specified in 903.03.02 or 903.05.02. For the verification batch, ensure that the air content is in the top half of the allowable range and the slump flow is between 22 and 24 inches. Perform air content, slump flow, and visual stability index (plastic concrete) testing on the verification batch. Make concrete cylinders for compression testing as specified in 903.03.02 or 903.05.02 and make 2 additional 4 × 8 inch cylinders for visual stability index on the hardened concrete. Saw the additional cylinders length-wise according to NJDOT C-5. The ME will perform the compressive strength testing and the visual evaluation to assign a visual stability index in order to approve the mix.

Section 904 – Precast and Prestressed Concrete

904.01.01  Component Materials

1**************************************************************************************************************************1

BDC15s-06 dated jul 30, 2015

the following sentence is added at the end:

For Precast Concrete, the minimum cement content specified in Table 903.03.06-3 is not required for Class A or Class B concrete.

1**************************************************************************************************************************1

904.01.02  Fabrication

1**************************************************************************************************************************1

BDC13s-14 dated jan 24, 2014

THE entire subpart is changed to:

Fabricate precast concrete at a plant as specified in 1011.01 and listed on the QPL.

- Placing Reinforcement Steel.  Before placing the concrete, place reinforcement steel in position as shown on the approved working drawings and as specified in 504.03.01.  Firmly tie the reinforcement to prevent displacement during placing of the concrete.

2**************************************************************************************2

BDC15s-06 dated jul 30, 2015

- Placing Concrete.  Place concrete as specified in 504.03.02.B, 504.03.02.C, 504.03.02.D, and 504.03.02.E.  Before placing concrete, ensure that reinforcement steel and any other embedded materials are free of loose rust, frost, dirt, oil, or contaminants that may prevent a bond with the concrete.  Consolidate concrete with internal vibrators.  The fabricator may use external vibration to supplement internal vibration.  If using SCC, minimize or eliminate the use of vibrators to prevent segregation.

2**************************************************************************************2

1**************************************************************************************************************************1

904.01.06 Quality Control and Acceptance Requirements

1**************************************************************************************************************************1

BDC13s-14 dated jan 24, 2014

THE FOLLOWING is added after the SECOND paragraph:

Follow the Department approved Buy America Compliance Plan. Provide documentation of compliance when requested by the ME.

1**************************************************************************************************************************1

904.02.01  Component Materials

1**************************************************************************************************************************1

BDC15s-06 dated jul 30, 2015

the following sentence is added at the end:

For Precast Concrete, the minimum cement content specified in Table 903.03.06-3 is not required for Class A or Class B concrete.

1**************************************************************************************************************************1

904.02.02 Fabrication

1**************************************************************************************************************************1

2**************************************************************************************2

BDC15s-06 dated jul 30, 2015

The first sentence in the first paragraph is changed to:

Place concrete as specified in 504.03.02.C, 504.03.02.D, and 504.03.02.E.

2**************************************************************************************2

2**************************************************************************************2

BDC13s-14 dated jan 24, 2014

THE second SENTENCEs IN THE FIRST PARAGRAPH is CHANGED TO:

Fabricate precast concrete at a plant as specified in 1011.01 and listed on the QPL.

2**************************************************************************************2

1**************************************************************************************************************************1

904.02.06  Quality Control and Acceptance Requirements

1**************************************************************************************************************************1

2**************************************************************************************2

BDC13s-14 dated jan 24, 2014

THE FOLLOWING is added after the SECOND paragraph:

Follow the Department approved Buy America Compliance Plan.  Provide documentation of compliance when requested by the ME.

2**************************************************************************************2

2**************************************************************************************2

BDC08s-02 dated Feb 17, 2009

step 2 in the third paragraph is changed to:

2.	Dimensions not conforming to the tolerances specified in Table 904.02.02-1.

2**************************************************************************************2

1**************************************************************************************************************************1

904.03.01  Component Materials

1**************************************************************************************************************************1

BDC15s-06 dated jul 30, 2015

the following is added at the end:

For Precast Concrete, the minimum cement content specified in Table 903.03.06-3 is not required for Class A or Class B concrete.

1**************************************************************************************************************************1

904.03.02 Fabrication

1**************************************************************************************************************************1

2**************************************************************************************2

BDC13s-14 dated jan 24, 2014

THE FIRST SENTENCE IN THE FIRST PARAGRAPH IS CHANGED TO:

Fabricate precast concrete at a plant as specified in 1011.01 and listed on the QPL.

2**************************************************************************************2

2.	Placing Concrete.

2**************************************************************************************2

BDC15s-06 dated jul 30, 2015

The first sentence in the first paragraph is changed to:

Place concrete as specified in 504.03.02.B, 504.03.02.C, 504.03.02.D, and 504.03.02.E.

2**************************************************************************************2

1**************************************************************************************************************************1

904.03.06 Quality Control and Acceptance Requirements

1**************************************************************************************************************************1

BDC13s-14 dated jan 24, 2014

THE FOLLOWING is added after the SECOND paragraph:

Follow the Department approved Buy America Compliance Plan.  Provide documentation of compliance when requested by the ME.

THE FOLLOWING is added after the last paragraph:

If the ME does not inspect the precast concrete item, submit certifications of compliance as specified in 106.07.

1**************************************************************************************************************************1

904.04.02 Fabrication

2**************************************************************************************2

BDC13s-14 dated jan 24, 2014

THE FIRST SENTENCE IN THE FIRST PARAGRAPH IS CHANGED TO:

Fabricate prestressed concrete at a plant as specified in 1011.02 and listed on the QPL.

2**************************************************************************************2

3.	Placing Concrete.

2**************************************************************************************2

BDC15s-06 dated jul 30, 2015

The second sentence in the first paragraph is changed to:

Place concrete as specified in 504.03.02.B, 504.03.02.C, 504.03.02.D, and 504.03.02.E.

2**************************************************************************************2

1**************************************************************************************************************************1

904.04.06 Quality Control, Quality Assurance, and Acceptance Requirements

1**************************************************************************************************************************1

BDC13s-14 dated jan 24, 2014

THE FOLLOWING IS ADDED after the SECOND paragraph:

Follow the Department approved Buy America Compliance Plan.  Provide documentation of compliance when requested by the ME.

THE FOLLOWING is added after the last paragraph:

If the ME does not inspect the precast concrete item, submit certifications of compliance as specified in 106.07.

1**************************************************************************************************************************1

Section 905 – Reinforcement Metals

905.01  Reinforcement Steel

1**************************************************************************************************************************1

BDC13s-14 dated jan 24, 2014

THE entire subpart is changed to:

Provide reinforcement steel manufactured at an AASHTO NTPEP (National Transportation Product Evaluation Program) certified mill.  For a list of NTPEP certified mills, see the following webpage:  http://data.ntpep.org/Module/REBAR/Overview.aspx .

For reinforcement steel, submit a certification of compliance as specified in 106.07.  Attach copies of the mill certifications for each heat of reinforcement steel.  The ME will randomly sample and test heats of reinforcement steel for quality assurance.  The ME will randomly inspect and sample galvanized and epoxy coated reinforcement steel for quality assurance.

1**************************************************************************************************************************1

905.01.03  Welded Wire Reinforcement

1**************************************************************************************************************************1

2**************************************************************************************2

BDC15s-06 dated jul 30, 2015

THE first PARAGRAPH is CHANGED TO:

Use plain or deformed steel welded wire reinforcement according to ASTM A1064. When used for concrete pavement, use welded wire reinforcement mats at least 5 feet in width.

2**************************************************************************************2

2**************************************************************************************2

BDC10s-09 dated sep 10, 2010

THE SECOND PARAGRAPH is CHANGED TO:

When approved as an alternate to galvanized reinforcement bars, use galvanized welded wire reinforcement that meets the requirements of ASTM A 641, Table 1, Class 1.

2**************************************************************************************2

1**************************************************************************************************************************1

905.01.05  Dowels

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

THe Entire subpart IS CHANGED TO:

Use plain reinforcement bars according to ASTM A 615, Grade 60.  Galvanize according to ASTM A 123.

1**************************************************************************************************************************1

905.03.03  Dowel Bars

1**************************************************************************************************************************1

BDC10s-01 dated Mar 29, 2010

THE first PARAGRAPH is CHANGED TO:

For dowel bars in transverse joints, use epoxy-coated, Grade 60, plain reinforcement steel according to ASTM A 615.  If shown on the Plans, use dowel bars fitted with end caps.  Ensure that the end caps are non-metallic and designed to prevent the entrance of grout or mortar into the expansion void.

1**************************************************************************************************************************1

Section 906 – Structural Steel

906.01  Structural Steel Materials

1**************************************************************************************************************************1

BDC15s-06 dated jul 30, 2015

THE ENTIRE subsection IS CHANGED TO:

Provide structural steel materials conforming to the requirements in Table 906.01-1 and as shown on the Plans.

| Table 906.01-1 Structural Steel Materials Requirements |
| --- |
| Product | Test Method | Type/Grade/Class |
| Structural Steel Plate1 | ASTM A 709 | Grade 36, 50, 50W, or HPS70W2 |
| Tie rods, plate washers, tie backs, turnbuckles, plates, shapes, and shims | ASTM A 709 | Grade 36 |
| Steel tube and pipe for Sign Structures 3, 4, 5 | ASTM A 53 or ASTM A 500 | Type S, Grade B or Type E, Grade B Grade B or C |
| Steel Piles |  |  |
| Steel H-piles | ASTM A 572 | Grade 50 |
| Steel sheet piles | ASTM A 572 | Grade 50 |
| Steel pipe piles | ASTM A 252 | Grade 2 |
| Casings for Drilled Shafts6 | ASTM A 252 | Grade 2 |
| Flooring |  |  |
| Grid Flooring | ASTM A 709 | Grade 36 |
| Formed Steel Flooring | ASTM A 1011 | Grade 30 |
| Steel Forgings | ASTM A 668 | Class C |
| Shear Connector Studs7 | ASTM A 108 | Grades G1015, 1018, or 1020 |
| Stay-In-Place (SIP) Forms8 | ASTM A 653 | Grades 33, 37, 40, 49, or 80 |
| 1. For steel used in tension zones, ensure that the steel conforms to Zone 2 impact testing requirements. 2. For the manufacture of Grade HPS70W, the Department will allow the use of the Thermo-Mechanical Controlled Process. 3. For sizes less than or equal to 24 inches in diameter, only use electric resistance welded single seam pipe. 4. For pipe with wall thickness greater than 1/2 inch, the fabricator may substitute API Specification 5L, Grade B. 5. ASTM A 500 Grade B or C is approved for use only with equivalent tensile and yield strengths as that specified for ASTM A 53 Grade B, Type E or S, with additional CVN testing for materials with wall thickness ½ inch or greater. Provide mill certs for approval by the ME prior to fabrication. 6. For casings, use smooth, non-corrugated steel pipe. 7. For shear connector studs, use cold-drawn bars that are killed or semi-killed. 8. For SIP, use a galvanized coating designation G235 or Z700. |

Before using, submit to the ME a representative sample of each size for material testing and approval.  Provide a mill certification that indicates the chemical and physical properties for each heat of material.  For SIP forms, steel forgings and shear connector studs, submit certifications of compliance, as specified in 106.07, with the mill certifications attached.

1**************************************************************************************************************************1

906.04.01  AISC Certification

1**************************************************************************************************************************1

BDC14s-05 dated Oct 28, 2015

THE ENTIRE subpart IS CHANGED TO:

Ensure that the structural steel fabricating plant is certified under the AISC Quality Certification Program in the applicable categories by the type of work performed.  See the following web page:

http://www.aisc.org/content.aspx?id=5388

1**************************************************************************************************************************1

906.04.05  Quality Control and Acceptance

1**************************************************************************************************************************1

BDC15s-06 dated jul 30, 2015

THE fourth paragraph is changed to:

Inspect and test structural steel bridge members according to ANSI/ AASHTO/ AWS D1.5 Bridge Welding Code, as modified by the following:

- Assembly and fabrication may not continue until completed work has been inspected and accepted by the ME.

- Grind flush complete-penetration butt welds scheduled for ultrasonic testing.

- Test 100 percent of complete joint penetration groove and butt welds, including butt welds in longitudinal stiffeners.

1**************************************************************************************************************************1

906.07  4-Bar Open Steel Parapet

1**************************************************************************************************************************1

BDC14s-05 dated Oct 28, 2015

subsection is renamed and changed to:

906.07  STEEL BAR BRIDGE RAILING

For steel bar bridge railing, including NJDOT standard steel 4-bar bridge railing, provide anchor bolts, washers, and exposed bolts as specified in 908.01.03, and all other bolts and nuts as specified in 908.01.01 and 908.01.02.  Provide rail bars according to ASTM A 500 Grade B, rail post according to ASTM A 709, Grade 50, and all other shapes and plates according to ASTM A 709, Grade 36.

Fabricate steel bar bridge railing according to 906.04  and paint according to 906.06 or galvanize according to 912.02.01.  Prohibit welded splices for steel rail tubes.

1**************************************************************************************************************************1

Section 908 – Bolts and Bolting Material

908.03  Direct Tension Indicators (DTI)

1**************************************************************************************************************************1

BDC15s-06 dated jul 30, 2015

THE ENTIRE subsection IS CHANGED TO:

Use direct tension indicators conforming to ASTM F 959. If galvanizing of the bolt assembly is required, mechanically galvanize DTIs according to ASTM B 695, Class 50. Test DTIs according to ASTM F 959 and verify according to NJDOT S-3.

Provide manufacturer’s certification and attach test results.

1**************************************************************************************************************************1

Section 909 – Drainage

909.02.01 Reinforced Concrete Pipe

1**************************************************************************************************************************1

BDC13s-14 dated jan 24, 2014

The following is added BEFORE the first sentence:

Manufacture reinforced concrete pipe at a plant listed on the QPL.

THE LAST paragraph is changed to:

Follow the Department approved Buy America Compliance Plan.  Provide documentation of compliance when requested by the ME.

For concrete pipe that is less than 60 inches in diameter, submit a certification of compliance as specified in 106.07.  The ME will randomly inspect and test small-diameter concrete pipe for quality assurance.

For concrete pipe that is 60 inches or more in diameter, notify the ME at least 2 weeks before shipping pipe to the Project.  The ME will inspect and approve large-diameter pipe in the supplier’s yard after manufacture.  Perform 3-point loading in the supplier’s yard as directed by the ME.  If the ME does not inspect the concrete pipe, submit certifications of compliance as specified in 106.07.

1**************************************************************************************************************************1

909.02.02 HDPE Pipe

1**************************************************************************************************************************1

BDC13s-14 dated jan 24, 2014

THE SECOND paragraph is changed to:

Use HDPE pipe from a manufacturer who is an AASHTO NTPEP (National Transportation Product Evaluation Program) certified manufacturer.  For a list of NTPEP certified manufacturer, see the following webpage:  http://data.ntpep.org/Module/PIPE/Overview.aspx .

1**************************************************************************************************************************1

1**************************************************************************************************************************1

BDC09s-11 dated Jan 26, 2010

THE FOLLOWING subpart IS ADDED:

909.02.09  Fiberglass Pipe for Bridge Storm Drainage

Fabricate fiberglass pipe conforming to ASTM D2996, RTRP-12EA1-2122 and fiberglass pipe fittings conforming to ASTM D3840.

Ensure that all fiberglass pipe, fittings and adhesives use pigmented resin throughout the wall and the color is concrete gray or designated color with UV stabilized resin.   Painted gel-coat or exterior coating is not acceptable.

Ensure that adhesives are in accordance with the pipe manufacturer and adhesive manufacturer’s recommendations.

1**************************************************************************************************************************1

Section 910 – Masonry Units

910.04  Stone Curb

1**************************************************************************************************************************1

provide lithology, color, and texture of stone curb

SME CONTACT – landscape architecture

1**************************************************************************************************************************1

910.05  Stone Facing for Pier Shafts

1**************************************************************************************************************************1

provide lithology, color, and texture of Stone Facing for Pier Shafts

SME CONTACT – landscape architecture

and

Structural Engineering

1**************************************************************************************************************************1

910.06  Stone Paving Block

1**************************************************************************************************************************1

provide color, texture, and uniformity of Stone Paving Block

SME CONTACT – landscape architecture

1**************************************************************************************************************************1

Section 911 – Signs, Sign Supports, and Delineators

911.02.02  Breakaway Sign Supports for Ground Mounted Signs

1**************************************************************************************************************************1

BDC09s-01 dated apr 09, 2010

THE ENTIRE subpart is changed to:

Fabricate and construct breakaway sign supports for ground mounted signs using materials conforming to the requirements in Table 911.02.02-1.

| Table 911.02.02-1 Materials for Breakaway Sign Supports |  |
| --- | --- |
| Item | Test Method | Type or Grade | Galvanizing |
| Aluminum Materials (other than bracket) | 911.01.01 |  |  |
| Bracket | B308 | 6061-T6 |  |
| Structural steel shapes | ASTM A709 | Grade 36 | ASTM A123 |
| Steel Sheet | ASTM A1011 | Grade 36 | ASTM A 653 |
| Bolts (except special bolt for coupling) | ASTM A325 |  | ASTM A153 |
| Special bolt for coupling | ASTM A449 |  | ASTM A153 |
| Cap Screw | ASTM A307 |  | ASTM A153 |
| Lock Washer | ANSI B18-21-1 |  | ASTM A153 |
| Nut | ASTM A563 | Grade DH | ASTM A153 |
| Coupling | AMS 6378 F |  | ASTM A153 |
| Steel Hinge Plate | AISI 4130 |  | ASTM 123 |
| Anchor Rod | AISI 1045 |  |  |
| Anchor Coil | AISI 1008 |  |  |
| Anchor Washer | 908.04 |  |  |
| Anchor Ferrule | 908.04 |  |  |

Submit mill certificates for the component materials.

1**************************************************************************************************************************1

911.02.03  Non-Breakaway Sign Supports for Ground Mounted Signs

1**************************************************************************************************************************1

BDC09s-01 dated apr 09, 2010

THE text of this subpart is deleted.

This subpart is INTENTIONALLY left blank

1**************************************************************************************************************************1

911.03  Flexible Delineators

1**************************************************************************************************************************1

BDC09s-08 dated DEC 07, 2009

1.	Delineator Dimensions.

b.	Guide Rail Mounted.

the entire text is changed to:

Ensure that the unit for beam guide rail mounted flexible delineators has a minimum width of 3 inches and a minimum thickness of 0.100 inch.  Use units of a height that will ensure that the top of the reflective area is 5 ± 2 inches above the top of post.

Design the base of the unit to mount over the I-beam blockout or to the top of a wood or synthetic blockout, of the beam guide rail.

c.	Barrier Curb Mounted.

the entire text is changed to:

For barrier curb mounted flexible delineators, use a delineator that is 3-1/2 × 3-1/2 inches, with a minimum thickness of 0.100 inch, and that has a base that forms a “T” shape with the panel for mounting on the side of the barrier curb, and is flexible or hinged so as to return to its original position after being struck.

THE FOLLOWING IS ADDED:

d.	Construction Barrier Curb Mounted.  For construction barrier curb top mounted flexible delineators, use a delineator that is 6 x 12 inches with a minimum thickness of 0.100 inch. For construction barrier curb side mounted flexible delineators, use a delineator that is 3-1/2 x 3-1/2 inches with a minimum thickness of 0.100 inch, and that has a base that forms a “T” shape with the panel for mounting on the barrier curb and is flexible or hinged so as to return to its original position after being struck.

4.	Retroreflective Sheeting.

b.	Guide Rail Mounted.

the entire text is changed to:

Ensure that the sheeting is a minimum of 3 inches square and is mounted on the upper portion of the delineator.

THE FOLLOWING IS ADDED:

d.	Construction Barrier Curb Mounted.  Ensure that the sheeting for top mounted flexible delineators is 6 x 12 inches and the sheeting for side mounted flexible delineators is 3-1/2 x 3-1/2 inches.

Submit a certification of compliance, as specified in 106.07, for delineators.

1**************************************************************************************************************************1

Section 912 – Paints, Coatings, Traffic Stripes, and Traffic Markings

912.03.01  Epoxy Traffic Stripes

1**************************************************************************************************************************1

BDC13s-08 dated Aug 19, 2013

The subpart Heading is changed to:

912.03.01  Traffic Stripes

1**************************************************************************************************************************1

A.	Epoxy Resin.

1**************************************************************************************************************************1

BDC13s-08 dated Aug 19, 2013

THE first SENTENCE IS CHANGED TO:

For pavement striping, use an epoxy resin that is a 2 component, 100 percent solids formulation conforming to the following requirements:

1**************************************************************************************************************************1

B.	Glass Beads.

1**************************************************************************************************************************1

BDC13s-09 dated jun 26, 2013

THE FIRST PARAGRAPH IS CHANGED TO:

Submit certifications of compliance as specified in 106.07 for each lot of glass beads used on the Contract. For each lot of glass beads, submit test results indicating the parts per million of lead, antimony and arsenic as determined by testing according to Environmental Protection Agency testing method 3052 and testing method 6010B or 6010C.  Ensure that glass beads do not contain more than 200 ppm of lead, 200 ppm of antimony, or 100 ppm of arsenic.

1**************************************************************************************************************************1

912.03.02  Thermoplastic Traffic Markings

1**************************************************************************************************************************1

BDC13s-08 dated Aug 19, 2013

The subpart Heading is changed to:

912.03.02  Traffic Markings

1**************************************************************************************************************************1

BDC13s-09 dated jun 26, 2013

THE ENTIRE SUBPART TEXT IS CHANGED TO:

2**************************************************************************************2

BDC13s-08 dated Aug 19, 2013

For traffic markings, use either preformed or hot extruded thermoplastic conforming to AASHTO M 249, except that for preformed thermoplastic, the minimum thickness requirement is 90 mils.  Use beads conforming to AASHTO M 247, Type 1, with a moisture resistant coating.  Ensure that glass beads do not contain more than 200 ppm of lead, 200 ppm of antimony, or 100 ppm of arsenic.

2**************************************************************************************2

Submit certifications of compliance, as specified in 106.07, for each batch of materials used on the Contract.  For each lot of glass beads, submit test results indicating the parts per million of lead, antimony and arsenic as determined by testing according to Environmental Protection Agency testing method 3052 and testing method 6010B or 6010C.

1**************************************************************************************************************************1

912.04.01  Latex Paint

1**************************************************************************************************************************1

BDC13s-09 dated jun 26, 2013 and Dec 15, 2016

THE ENTIRE SUBPART TEXT IS CHANGED TO:

For temporary traffic stripes, use latex traffic paint that is a fast-drying white, or non-lead yellow, ready-mixed pigmented binder emulsified in water and capable of anchoring reflective glass beads that are separately applied.  Ensure that the color matches FED-STD-595B color chip No. 33538 for yellow and No. 37886 for white.  Ensure that the paint has a maximum no-track time of 120 seconds when applied in a wet film.  In addition, ensure that the finished product meets the following:

1.	Volume of solids is a minimum 61 percent.

2.	Total solids are a minimum of 77.5 percent total non-volatiles by weight, when tested according to ASTM D 2369.

3.	Weight per gallon is a minimum 14 ± 0.2 pounds per gallon for each color.

4.	Hegman Grind is a minimum of 2 Hegman when tested according to ASTM D 1210.

5.	Viscosity is between 70 and 95 Krebs Units at 77 °F, when tested according to ASTM D 562.

Use glass beads conforming to AASHTO M247, Type 1, with a moisture resistance coating.  Ensure that glass beads do not contain more than 200 ppm of lead, 200 ppm of antimony, or 100 ppm of arsenic.

Submit a certification of compliance, as specified in 106.07, for latex and glass beads.  For each lot of glass beads, submit test results indicating the parts per million of lead, antimony and arsenic as determined by testing according to Environmental Protection Agency testing method 3052 and testing method 6010B or 6010C.

1**************************************************************************************************************************1

Section 913 – Guide Rail, Fence, and Railing

1**************************************************************************************************************************1

BDC14s-11 dated may 22, 2015

This Section is renamed to:

Section 913 – Guide Rail, Fence, Railing and BOX BEAM

1**************************************************************************************************************************1

913.01.01 Rail Element

1**************************************************************************************************************************1

BDC13s-14 dated jan 24, 2014

THE SECOND paragraph is changed to:

Submit a certification of compliance as specified in 106.07.

1**************************************************************************************************************************1

913.01.02 End Treatments

1**************************************************************************************************************************1

BDC13s-14 dated jan 24, 2014

THE SECOND paragraph is changed to:

Submit a certification of compliance as specified in 106.07.

1**************************************************************************************************************************1

913.01.03 Posts and Blockouts

1**************************************************************************************************************************1

BDC13s-14 dated jan 24, 2014

THE FOURTH paragraph is changed to:

Provide certifications of compliance, as specified in 106.07.

1**************************************************************************************************************************1

913.01.04 Rub Rail

1**************************************************************************************************************************1

BDC13s-14 dated jan 24, 2014

THE SECOND paragraph is changed to:

Submit a certification of compliance as specified in 106.07.

1**************************************************************************************************************************1

913.01.05  Miscellaneous Hardware

1**************************************************************************************************************************1

2**************************************************************************************2

BDC10s-10 dated Nov 16, 2010

SUBPART 3 OF THE FIRST PARAGRAPH IS CHANGED TO:

3.	Use plates for guide rail on bridges and buried guide rail terminals conforming to ASTM A 36 and galvanized according to ASTM A 123.

2**************************************************************************************2

2**************************************************************************************2

BDC13s-14 dated jan 24, 2014

THE SECOND paragraph is changed to:

Submit a certification of compliance as specified in 106.07.  The ME may randomly inspect hardware for quality assurance.

2**************************************************************************************2

1**************************************************************************************************************************1

913.03.01  Steel Railing

1**************************************************************************************************************************1

BDC14s-05 dated Oct 28, 2015

THE ENTIRE subpart IS CHANGED TO:

Fabricate steel bar bridge railing and steel railing components of combination railing system from structural steel as specified in 906.01 and 906.04.  For non-traffic steel railing, construct welds according to the requirements of AWS D1.1 Structural Welding Code.  Use bolts and bolting materials as specified in 908.01.  When specified, paint as specified in 906.06 or galvanize as specified in 912.02.01.  Submit certifications of compliance, as specified in 106.07 and copies of mill certifications.

1**************************************************************************************************************************1

1**************************************************************************************************************************1

BDC14s-11 dated may 22, 2015

THE FOLLOWING SUBsections is ADDED:

913.04  Box Beam for Construction Barrier Curb.

Ensure that the box beam is made of cold-formed welded and seamless structural tubing.  Ensure that the box beam conforms to ASTM A500, Cold-Formed Welded and Seamless Carbon Steel Structural Tubing in Rounds and Shapes, Grade B.

Ensure that the box beam is tested in accordance with ASTM E436 on a 2 x 9 inch galvanized specimen at -0.4°F and provide certified test result to the ME.

The Department will reject the material if the average percent shear area falls below 50.

Ensure that the identification number/information is placed on the material at an interval of 4 feet or less.

Ensure that the box beam is galvanized in accordance with ASTM A123.  Fasteners are galvanized and conform to the following unless specified otherwise in the contract documents:  Bolts ASTM A307 Grade A, nuts ASTM A563 Grade A or better, and washers ASTM F844.

1**************************************************************************************************************************1

Section 914 – Joint Materials

914.04.01  Preformed Elastomeric (Compression Type)

B.	Joint Sealer.

1**************************************************************************************************************************1

BDC08s-02 dated Feb 17, 2009

THE last SENTENCE OF THE second PARAGRAPH IS CHANGED TO:

If splicing of a sealer is allowed, ensure that the sealer at the splice point has no significant misalignment at its sides or top and that misalignment at the bottom does not exceed half of the bottom wall thickness.

1**************************************************************************************************************************1

Section 915 – Timber and Timber Treatment

915.05  Timber Treatment

1**************************************************************************************************************************1

BDC15s-06 dated jul 30, 2015

THE ENTIRE subsection IS CHANGED TO:

Treat wood species according to AASHTO M 133 and AWPA Standards U1-11 and T1-11 as summarized in Table 915.05-1, Table 915.05-2, and Table 915.05-3.

| 915.05-1 Treatment for SawnTimber Posts |
| --- |
| Type of Wood | Location/Environment | Allowable Treatments | AWPA Standard Reference for Minimum Retention Level |
| Southern Pine | Soil or Fresh Water | CCA or Pentachlorophenol | UC4A |
| Douglas Fir | Soil or Fresh Water | ACZA | UC4A |

| 915.05-2 Treatment for Round Timber Piles |
| --- |
| Type of Wood | Location/Environment | Allowable Treatments | AWPA Standard Reference for Minimum Retention Level |
| Southern Pine | Soil or Fresh Water | CCA | UC4C |
| Southern Pine | Marine | CCA | UC5B |
| Douglas Fir | Soil or Fresh Water | ACZA | UC4C |
| Douglas Fir | Marine | ACZA | UC5B |

| 915.05-3 Treatment for Timber Sheet Piling and Timber for Structures |
| --- |
| Type of Wood | Location/Environment | Allowable Treatments | AWPA Standard Reference for Minimum Retention Level |
| Southern Pine | Soil or Fresh Water | CCA, or Pentachlorophenol | UC4B |
| Southern Pine | Marine | CCA | UC5B |
| Douglas Fir | Soil or Fresh Water | ACZA | UC4B |
| Douglas Fir | Marine | ACZA | UC5B |

Notify the ME at least 14 days before treating timber.  If directed by the ME, perform an assay to determine the retention of preservative according to AASHTO M 133.  Submit certification of compliance as specified in 106.07.  Attach the assay report to the certification.

1**************************************************************************************************************************1

Section 917 – Landscaping Materials

917.10  Plant Materials

H.	Inspection.

1**************************************************************************************************************************1

complete and include THE FOLLOWING

sme contact – landscape architecture

THE second paragraph is changed to:

The Department may inspect plant materials before delivery to the Project Limits and upon delivery to the Project Limits before installation.  The Department may seal the inspected plant materials.  For plant material originating from nurseries farther than 100 miles from the Project Limits, stock plant material at a Contractor-provided holding yard that is acceptable to the Department.  The Department may inspect plant material originating from nurseries within 100 miles of the Project Limits at the nursery.  Ensure that all plant material is untied and located so that trunk or stem and branch structure can be easily inspected.  Provide sufficient notice to allow Department inspection at the nursery or holding yard and to allow time for Contractor reordering of rejected material.  Notify the RE at least ____(hours or days)___ in advance of delivery to the Project Limits for installation.  The Department will reject materials arriving with broken or missing seals, broken or loose balls, broken or pruned leaders, insufficient protection, or that have been damaged in transit.  The Department may randomly inspect the root system of the plant material by breaking open the earth balls.  Provide necessary assistance during Department inspections.

1**************************************************************************************************************************1

Section 918 – Electrical Materials

918.01  Conduit and Fittings

4.	Flexible Nonmetallic Conduit.

1**************************************************************************************************************************1

BDC13S-04 dated JUN 10, 2013

THIS part IS CHANGED TO:

Use coil able HDPE conduit made from virgin HDPE resin as per the minimum standard of PE345440E according to ASTM D3350.  Ensure conduit is circular and of uniform cross sectional area and dimensions in accordance with ASTM F2160.  Ensure conduit is of continuous length containing no welds or joints coiled on a reel.  Additionally, conduit’s inner and outer walls are to be smooth and the inner wall is to be lubricated with manufacturer’s recommended lubricant.  Conduit colors are to be integrally extruded throughout the conduit in the manufacturing process.  Ensure conduit is permanently marked with a laser ink imprinter or heat embossed white lettering showing the diameter, size, sequential length marks, owners name, ASTM, SDR, and/or Schedule rating.  Additional markings of date-of-manufacture, time, and batch-of-resin are to be identified and referenced to certifications and quality control test results.  Ensure manufacturer provides certification of the properties specified and mark/label the reels with purchase order, project name and/or other information for tracking and receiving.  Applicable material standards are required based on the following applications:

- Direct Burial.  Use conduit material with a rating of Schedule 80 conforming to ASTM F2160, NEMA TC-7 EPEC-80 and certified for its intended use.

- Innerduct.  Use conduit material with a rating of Schedule 40 conforming to ASTM F2160, NEMA TC-7 EPEC-40.

ITS conduits used for the installation of Fiber Optic Cable including tracer wire, are to be extruded integrally colored orange to indicate its use for Communications.

ITS conduits designated for electrical use are to be extruded integrally colored red to indicate its use for Electrical wiring.

Submit a certificate of compliance, as specified in 106.07, for all materials, components, and assemblies.

1**************************************************************************************************************************1

918.12  Pedestals, Poles, Transformer Bases, and Mast Bracket Arms

THE first sentence of the first PARAGRAPH is CHANGED TO:

Fabricate pedestals, poles, transformer bases, and mast bracket arms for traffic signal, highway lighting, and camera standards with materials according to the appropriate ASTM standard and the AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires and Traffic Signals.

SECTION 919 – MISCELLANEOUS

1**************************************************************************************************************************1

BDC10s-02 dated Oct 14, 2010

THE FOLLOWING IS ADDED:

919.15  POLYESTER MATTING

Provide polyester matting of commercial quality that is a composite of polyester base fiber and vinyl chloride resin and is permeable to air and water, but shall prevent sunlight from reaching the soil.  Ensure that the matting resists ultraviolet light, mildew and algae.  Ensure that the matting is self-extinguishing when removed from flame.  Ensure that the matting has a minimum thickness of 1/4 inch.

1**************************************************************************************************************************1

Division 1000 – Equipment

SECTION 1001 – TRAFFIC CONTROL EQUIPMENT

1**************************************************************************************************************************1

BDC10s-08 dated dec 29, 2010

include the following subsections if ANY OF THESE ITEMS are REQUESTED BY Traffic Operations

sme CONTACT – TrAFFIC OPERATIONS

The following subsection is added:

1001.04  PORTABLE VARIABLE MESSAGE SIGN With REMOTE COMMUNICATION

2**************************************************************************************2

BDC16s-03 dated Aug 24, 2016

THE ENTIRE subsection IS CHANGED TO:

Provide a NTCIP compliant portable variable message sign as described under 1001.02 with the exceptions noted below and each equipped with broadband cellular modem.

Ensure that the sign panel is color full matrix model that displays a combination of letters and graphic images.

Ensure that the sign panel is capable of displaying three lines of text with variable size characters.

Ensure nine characters are displayed per line for posting travel times.  For this nine character requirement, smaller size characters may be allowed that meets MUTCD guidelines.

Ensure that the panel is also capable of displaying eight (8) characters per line with a minimum character height of eighteen (18) inches.

Ensure that the PVMSRC can be integrated with the Department’s central DMS control software for remote operation.

2**************************************************************************************2

1001.05  Portable Trailer mounted CCTV CAMERA assembly

2**************************************************************************************2

these specifications are for portable cameras for use by toc.  if construction management requests a camera for construction use SPECIFICALLY document their requirement and revise the specifications to meet their requirement (whether streaming video archiving or high mp snap shots archiving is required).  when both toc and construction management requests this item in the same project include two separate pay items and list the differences in the two pay items.  in that case, the standard pay item is to be used for both items with the description ending with “toc use” or “construction use”.

sme CONTACTs – TrAFFIC OPERATIONS, Mobility and Systems Engineering (MSE) & bureau of construction management

Provide a Portable Trailer Mounted CCTV Camera Assembly (PTMCCA) with the following:

A.	Trailer Platform

1.	Maximum size, including tongue, 14 feet long by 7 feet wide by 8 feet high.

2.	NJDOT approved lighting package to include electrical brake and marker lights with wire connections.

3.	Primed and painted with powder coated orange color.

4.	Fitted with manual telescoping outriggers with adjustable jacks sized to counter full mast extension.

5.	Four 3500 pounds, drop leg, top wind screw jacks.

6.	All equipment secured to prevent theft or separation from platform.

7.	24/7 operation in all weather conditions.

8.	One locking NEMA-4 equipment box for operational controls.

9.	Removable wheels (with wheel locks) when trailer is in deployed position.

10.	Operation manual with a copy placed in the storage bin.

B.	Mast

1.	150 pounds payload capacity.

2.	29 feet to 32 feet of extension with capability to mount antenna at 20 feet, 25 feet or at the top, 10 feet maximum nested length of mast - 3 to 9 sections.

3.	Un–guyed.

4.	Driven by galvanized steel cable.

5.	Spiral conduit for cables.

6.	Compactly retractable when nested into storage container at the bottom & foldable for easy transport.

7.	Operated by a power winch with a safety brake.

8.	Capable of being raised or lowered during sustained wind speeds of 30 miles per hour.

C.	Power Source

Equip the PTMCCA with either a diesel charged or a solar charged battery system.  Ensure that the PTMCCA is also capable of operating on 120-volt AC electrical service.  The Department may require a solar charged battery system in noise sensitive areas.  Provide the power with a battery backup system capable of providing continuous operation when the primary power source fails.  Ensure that the power source meets the following requirements:

1.	Diesel.  Ensure that the fuel tank is capable of operating the sign for a period of 72 hours without refueling.  Equip with an exhaust muffler and a United States Department of Forestry approved spark arrester.  Ensure that the engine is shock mounted to reduce vibration and locked in a ventilated enclosure.

2.	Solar.  Provide solar panels capable of recharging the batteries at a rate of 4 hours of sun for 24 hours of camera usage.  Ensure that the battery capacity is capable of operating the sign for a period of 18 days without sunlight.

D.	Electronics

1.	Cellular (CDMA), microwave, or 802.11 bandwidth option.

2.	Work lights in all cabinets.

3.	Remote trailer diagnostics (battery level, charging output, etc.).

E.	Camera and Software

Ensure that the camera has the following characteristics:

1.	Dome Camera in a heavy duty plastic dome or with a weather resistant case.

2.	Impact resistant viewing window.

3.	Minimum resolution of NTSC 704 (H) x 480 (V).

4.	Backlight compensation.

5.	Image stabilization.

6.	Light Sensitivity 0.02 lux NIR Mode.

7.	Auto Focus with Manual Focus capability.

8.	Auto White Balance with Manual White Balance capability.

9.	Motorized Zoom up to 16x optical, 10x digital.

10.	Motorized Pan-Tilt, pan 360°, tilt 180°.

11.	Thermostatically controlled heater and defroster -50° to 140°F operating range.

12.	Windshield wiper.

13.	24/7 operation in all weather conditions.

14.	Time and date stamp.

Ensure the software provides the following functionality:

1.	Remote control of pan, tilt and zoom.

2.	Display of streaming video in MPEG format, motion-JPEG, and single snapshot JPEG images, remotely interchangeable by using central software.

3.	Preset controls of pan/tilt/zoom combinations.  Ensure all presets are accessible from a drop-down menu with descriptive name of preset.  Set first 8 presets with quick- launch icons with graphical representation of the preset views.

4.	Display of all the project’s web cams in a single view screen.

5.	Display of local time and weather conditions including temperature and humidity.

6.	Saving images and sending e-mail images.

3************************************************3

confirm with toc if project specific archiving is required or not and revise # 7 accordingly.meeting their requirement.

sme CONTACT – TrAFFIC OPERATIONS

7.	Viewing archived images via a graphical calendar control and storing archived images at least every five minutes.

3************************************************3

8.	Three levels of password protection: administrator, user, and guest, individual user accounts.

9.	Monitoring and controlling the cameras using web access.

2**************************************************************************************2

1**************************************************************************************************************************1

SECTION 1009 – HMA PLANT EQUIPMENT

1009.01  HMA PLANT

- Requirements for HMA Mixing Plants.

1**************************************************************************************************************************1

BDC11s-01 dated Mar 30, 2011

THE FOLLOWING IS ADDED AFTER THE SECOND PARAGRAGH:

The HMA producer is required to have a quality control (QC) program plan approved annually by the ME as per Materials Approval Procedure MAP-102. The HMA producer is required to ensure that the QC plan conforms to the requirements outlined in the report entitled “Hot Mix Asphalt Quality Control Program Plan” prepared by the Department of Transportation and New Jersey Asphalt Paving Association. Failure to follow these requirements will result in rejection of HMA materials supplied by the HMA producer and removal of the HMA supplier from the QPL.

1**************************************************************************************************************************1

1**************************************************************************************************************************1

BDC11s-01 dated Mar 30, 2011

THE FOLLOWING Subsection IS ADDED AFTER 1009.02:

1009.03  Asphalt-Rubber Binder Blending Equipment

Provide equipment for preparation of Asphalt-Rubber Binder.  Ensure that the unit is equipped with a crumb rubber feed system capable of continuously supplying the asphalt cement feed system, and is capable of fully blending the individual crumb rubber particles with the asphalt cement.  Use an asphalt-rubber binder storage tank that is equipped with a heating system capable of maintaining the temperature of the binder between 325 and 375 °F during the reaction.  Ensure the asphalt-rubber binder storage tank is also equipped with an internal auger mixing device, oriented horizontally in the tank, capable of maintaining a uniform mixture of the asphalt-rubber binder.

Ensure that the tanks for storage of asphalt-rubber binder are equipped to uniformly heat the material to the required temperature under effective and positive control at all times.  Ensure that heating is accomplished so that no flame comes in contact with the heating tank.

Provide a circulating system of sufficient capacity for the binder to ensure continuous circulation between the storage tank and proportioning units during the entire operating period.  Ensure that the discharge end of the binder circulating pipe is maintained below the surface of the binder in the storage tank to prevent discharge of hot binder into the open air.

Ensure that pipe lines and fittings are steam or oil jacketed, electrically or otherwise heated, and insulated to prevent heat loss.

Provide valves according to AASHTO T 40, except ensure that a sampling valve is also located in the lowest third of each storage tank.

If the plant has been equipped with a water injection type asphalt foaming system, ensure that the system will allow the proper amount of asphalt rubber binder to be supplied continuously or provide a by-pass to ensure that the proper amount of asphalt rubber binder is supplied to the mix.

1**************************************************************************************************************************1

Section 1011 – Precast and Prestressed Concrete Plant Equipment

1011.03  ME’s Office

1**************************************************************************************************************************1

BDC10s-09 dated sep 10, 2010

The second paragraph Subpart 2 &3 are changed to:

2.	One high-speed broad band connection with a minimum speed of 3 megabits per second (mbps) with dynamic IP address (DSL, Cable, etc.).

3.	Two desks and 2 chairs.

1**************************************************************************************************************************1

THE FOLLOWING SECTION IS ADDED:

1**************************************************************************************************************************1

BDC15s-01 dated mar 26, 2015

Section 1012 – pAVEMENT PRESERVATION EQUIPMENT

1012.01  Micro Surfacing and Slurry Seal Paver

Provide fully automated self-propelled continuous flow type equipment that is specifically designed, equipped, calibrated, and operated for mixing and spreading slurry seal and micro surfacing conforming to the approved mix design and application rate.  Immediately correct defects that adversely affect the functioning of the equipment or quality of the mixture. Perform calibration in the presence of the ME.  Ensure that the documentation includes an individual calibration of each material at various settings that can be related to the machine metering devices.  Any component replacement affecting material proportioning requires that the machine be recalibrated.  Do not use a machine on the project until the calibration has been completed and accepted.  Ensure the paver is equipped with the following:

- Mixing Equipment.  Ensure that the machine is specifically designed and manufactured to mix micro surfacing and slurry seal materials.  Mix the material in an automatic-sequenced, self-propelled, micro surfacing and slurry seal mixing machine.  Ensure that it is a continuous-flow mixing unit that accurately proportions and delivers the mix components, within 2 % of the required amount as per the mix design, into a revolving multi-blade double-shafted mixer.  Sufficient storage capacity for all mix components is required to maintain an adequate supply to the proportioning controls.

Ensure that the machine is capable of loading materials while continuing to apply micro surfacing and slurry seal.  Ensure that the continuous-run machine is equipped to provide the operator with full control of the forward and reverse speeds during application and is equipped with opposite-side driver stations to assist in alignment.  Ensure that the self-loading device, opposite-side driver stations, and forward and reverse speed controls are of original-equipment-manufacturer design.

Provide material control devices, readily accessible and so placed that the inspector may determine the amount of each material used at any time.

Provide machine with a water pressure system and nozzle type spray bar to provide a water spray ahead of and outside the spreader box.

Locate mineral filler feed so the proper amount of mineral filler is dropped on the aggregate before discharge into mixer.

- Spreading Equipment.  Provide spreading equipment that agitates and spreads the mixture uniformly in the surfacing box by means of twin shafted paddles or spiral augers fixed in the spreader box.  Ensure that a front seal is provided such that there is no loss of the mixture at the road contact point.  Ensure that there is an adjustable rear seal which will act as a final strike-off.  Ensure that the spreader box and rear strike-off is designed and operated so that a uniform consistency is achieved and a free flow of material is provided to the rear strike-off.  Ensure that the spreader box has suitable means provided to side shift the box to compensate for variations in the pavement geometry.

Ensure that a secondary strike-off is provided to improve surface texture.  Ensure that the secondary strike-off is adjustable to match the width of the spreader box and allows for varying pressures to control the surface texture.

- Electronic Mix Control and Diagnostic (EMCAD) System.  Ensure the paver is equipped with a computer mix control and diagnostic system that records, displays, and prints the following:

- Individual sensor counts for emulsion, aggregate, mineral filler, water, and additive.

- Aggregate, emulsion and mineral filler output in pounds per minute.

- Spread rate in pounds per square yard.

- Percentages of emulsion, mineral filler, water, and additive.

- Cumulative total quantities of aggregate. Emulsion, mineral filler, water, and additive.

- Scale factor for all materials.

Ensure the computer system is functional and capable of printing reports.

- Rut, Longitudinal Joint and Rumble Strip Filling Equipment.  Provide rut filling equipment with a steel V-configuration screed rut box commercially designed and manufactured to fill ruts as required. Ensure that the rut box can be adjusted to provide a mixture spread width of between 2 feet to 6 feet and have a moveable steel strike-off to control crown.

1012.02  Mechanical Fine Aggregate Spreader

Provide fully automated self-propelled fine aggregate spreading equipment with positive controls that is specifically designed, equipped, calibrated, and operated for spreading fine aggregate uniformly at the required width and application rate.  Immediately correct defects that adversely affect the functioning of the equipment or quality of the fine aggregate application. Perform calibration in the presence of the ME.  Ensure that the calibration documentation includes the fine aggregate at various application rate settings that can be related to the machine metering devices.  Any component replacement affecting application rate requires that the machine be recalibrated.  Do not use a machine on the project until the calibration has been completed and accepted.

1**************************************************************************************************************************1

NJDOT Test Methods

NJDOT B-3 – Selecting Cores for Maximum Specific Gravity Testing in Air Voids Determination

- Procedure.

1**************************************************************************************************************************1

BDC14s-12 dated Oct 30, 2014

THE FOLLOWING note IS ADDED after STEP 3:

NOTE:  For Recore Lots and Statistical Outlier Lots, do not randomly select a core for maximum specific gravity testing.  The entire core lot must be tested for maximum specific gravity.

THE FOLLOWING STEP IS ADDED after STEP 9:

10.	If the lot has an outlier or is a recore lot, the entire lot must be tested for maximum specific gravity. Calculate air voids using each individual core maximum specific and bulk specific gravity.

1**************************************************************************************************************************1

NJDOT B-8 – DETERMINING JOB MIX FORMULA FOR MODIFIED OPEN-GRADED FRICTION COURSE MIXES

C.	Procedure.

3.	Relative VMA Asphalt Content.

1**************************************************************************************************************************1

BDC11s-01 dated Mar 30, 2011

THE FOURTH SENTENCE IN THE FIRST PARAGRAPH IS CHANGED TO:

Determine the bulk specific gravity, Gmb from each specimen according to NJDOT B-6 or AASHTO T 331.

THE FOOTNOTE FOR Gmb IN THE SECOND EQUATION IS CHANGED TO:

Gmb = the bulk specific gravity of the specimen as determined by NJDOT B-6 or AASHTO T 331.

1**************************************************************************************************************************1

1**************************************************************************************************************************1

BDC11s-01 dated Mar 30, 2011

THE FOLLOWING TEST METHODS ARE ADDED:

NJDOT  B-10 – Overlay test for Determining Crack Resistance of HMA

A.	Scope.  This test method is used to determine the susceptibility of HMA specimens to fatigue or reflective cracking. This test method measures the number of cycles to failure.

B.	Apparatus.  Use the following apparatus:

1.	Overlay Tester.  An electro-hydraulic system that applies repeated direct tension loads to specimens.  The machine features two blocks, one is fixed and the other slides horizontally.  The device automatically measures and records a time history of load versus displacement every 0.1 sec at a selected test temperature.

The sliding block applies tension in a cyclic triangular waveform to a constant maximum displacement of 0.06 cm (0.025 in.).  This sliding block reaches the maximum displacement and then returns to its initial position in 10 sec. (one cycle).

2.	Temperature Control System.  The temperature chamber must be capable of controlling the test temperature with a range of 32 to 95 oF (0 to 35 oC).

3.	Measurement System.  Fully automated data acquisition and test control system.  Load, displacement, and temperature are simultaneously recorded every 0.1 sec.

4.	Linear Variable Differential Transducer (LVDT).  Used to measure the horizontal displacement of the specimen (+/- 0.25 in.).  Refer to manufacturer for equipment accuracy for LVDT.

5.	Electronic Load Cell.  Used to measure the load resulting from the displacement (5000 lb capacity).  Refer to manufacturer for equipment accuracy for load cell.

6.	Specimen Mounting System.  Used two stainless steel base plates to restrict shifting of the specimen during testing.  The mounting jig holds the two stainless steel base plates for specimen preparation.

7.	Cutting Template.

8.	Two Part Epoxy.  Two part epoxy with a minimum 24 hour tensile strength of 600 psi (4.1 MPa) and 24 hour shear strength of 2,000 psi (13.8 MPa).

9.	10 lb weight (4.5 kg).  Used to place on top of specimens while being glued to specimen platens.

10.	¼ inch Width Adhesive Tape.  Placed over gap in plates to prevent the epoxy from bonding the plates together.

11.	Paint or Permanent Marker.  Used to outline specimens on platens for placement of epoxy.

12.	3/8-in. Socket Drive Handle with a 3-in. (7.6 cm) extension.

C.	Procedure.  Perform the following steps:

1.	Sample Preparation.

a.	Laboratory Molded Specimens - Use cylindrical specimens that have been compacted using the gyratory compactor (AASHTO T 312).  Specimen diameter must be 6 inches (150 mm) and a specimen height must be 4.5 inches +/- 0.2 inches (115 +/- 5 mm).

Note 1 - Experience has shown that molded laboratory specimens of a known density usually result in a greater density (or lower air voids) after being trimmed.  Therefore, it is recommended that the laboratory technician produce molded specimens with an air void level slightly higher than the targeted trimmed specimen.  Determine the density of the final trimmed specimen in accordance with AASHTO T 166.

b.	Core Specimens – Specimen diameter must be 6 inches +/- 0.1 inch (150 mm +/- 2 mm).  Determine the density of the final trimmed specimen in accordance with AASHTO T166.

2.	Trimming of Cylindrical Specimen.  Before starting, refer to the sawing device manufacturer’s instructions for cutting specimens.

a.	Place the cutting template on the top surface of the laboratory molded specimen or roadway core.  Trace the location of the first two cuts by drawing lines using paint or a permanent maker along the sides of the cutting template.

b.	Trim the specimen ends by cutting the specimen perpendicular to the top surface following the traced lines.  Discard specimen ends.

c.	Trim off the top and bottom of the specimen to produce a sample with a height of (1.5 inches +/- 0.02 inches (38 mm +/- 0.5 mm).

d.	Measure the density of the trimmed specimen in accordance with AASHTO T 166.  If the specimen does not meet the density requirement as specified for performance testing for the mix being tested, then discard it and prepare a new specimen.

e.	Air dry the trimmed specimen to constant mass, where constant mass is defined as the weight of the trimmed specimen not changing by more than 0.05% in a 2 hour interval.

3.	Mounting Trimmed Specimen to Base Plates (Platens).

a.	Mount and secure the base plates (platens) to the mounting jig.  Cut a piece of adhesive tape approximately 4.0 inches (102 mm) in length.  Center and place the piece of tape over the gap between the base plates.

b.	Prepare the epoxy following manufacturer’s instructions.

c.	Cover a majority of the base plates (platens) with epoxy, including the tape.  Glue the trimmed specimen to the base plates.

d.	Place a 10 lb (4.5 kg) weight on top of the glued specimen to ensure full contact of the trimmed specimen to the base plates.  Allow the epoxy to cure for the time recommended by the manufacturer.  Remove the weight from the specimen after the epoxy has cured.

e.	Turn over the glued specimen so the bottom of the base plates faces upward.  Using a hacksaw, cut a notch through the epoxy which can be seen through the gap in the base plates.  The notch should be cut as evenly as possible and should just begin to reach the specimen underneath the epoxy.  Great care should be taken not to cut more than 1/16 inch (1.58 mm) into the specimen.

f.	Place the test sample assembly in the Overlay Tester’s environmental chamber for a minimum of 1 hour before testing.

4.	Start Testing Device.  Please refer to manufacturer’s equipment manual prior to operating equipment.

a.	Turn on the Overlay Tester.  Turn on the computer and wait to ensure communication between the computer and the Overlay Tester occurs.

b.	Turn on the hydraulic pump using the Overlay Tester’s software.  Allow the pump to warm up for a minimum of 20 minutes.

c.	Turn the machine to load control mode to mount the sample assembly.

5.	Mounting Specimen Assembly to Testing Device.  Enter the required test information into the Overlay Tester software for the specimen to be tested.

a.	Mount the specimen assembly onto the machine according to the manufacturer’s instructions and the following procedural steps.

1.	Clean the bottom of the base plates and the top of the testing machine blocks before placing the specimen assembly into the blocks.  If all four surfaces are not clean, damage may occur to the machine, the specimen, or the base plates when tightening the base plates.

2.	Apply 15 lb-in of torque for each screw when fastening the base plates to the machine.

6.	Testing Specimen.

a.	Perform testing at a constant temperature recommended by the New Jersey Department of Transportation for the mixture in question.  This is typically either 59 °F (15 °C) or 77 °F (25 °C).

Note 3 – Ensure the trimmed specimen has also reached the constant temperature required.

b.	Start the test by enabling the start button on the computer control program.  Perform testing until a 93% reduction or more of the maximum load measured from the first opening cycle occurs.  If 93% is not reached, run the test until a minimum of 1,200 cycles.

c.	After the test is complete, remove the specimen assembly from the Overlay Tester machine blocks.

D.	Report.  Include the following items in the report:

1.	Date and time molded or cored.

2.	NJDOT mixture identification.

3.	Trimmed specimen density.

4.	Starting Load.

5.	Final Load.

6.	Percent decline (or reduction) in Load.

7.	Number of cycles until failure.

8.	Test Temperature

NJDOT B-11- DETERMINING GRADATION OF CRUMB RUBBER FOR ASPHALT MODIFICATION

A.	Scope.  This method is used to determine the gradation of the crumb rubber for asphalt-rubber binder

B.	Apparatus.  Use the following apparatus:

1.	Oven capable of maintaining a temperatures of 140 ( 10 °F for drying sample to a constant weight.

2.	Rubber balls having a weight of 8.5 ± 0.5 grams, a diameter of 24.5 ± 0.5 mm, and a Shore Durometer “A” hardness of 50 ± 5 per ASTM Designation D 224

3.	No. 8, 16, 30, 50, 100, and 200 sieves conforming to AASHTO M 92.

4.	Mechanical sieve shaker conforming to AASHTO T 27.

5.	Balance conforming to AASHTO M 231 and having a minimum capacity of 100 grams with a precision of 0.1 gram.

C.	Procedure.  The crumb rubber for asphalt rubber binder is required to conform to the gradations specified below when tested in accordance with ASTM Designation C 136 except as follows:

1.	Obtain 100 ± 5 grams from the crumb rubber sample and dry to a constant weight at a temperature of not less than 135 °F nor more than 145 °F and record the dry sample weight.

2.	Place the crumb rubber sample and 5.0 grams of talc in a one pint jar, then shake it by hand for a minimum of one minute to mix the crumb rubber and the talc.  Continue shaking or open the jar and stir until the particle agglomerates and clumps are broken and the talc is uniformly mixed.

3.	Place one rubber ball on each sieve.  After sieving the combined material for 10 ± 1 minutes, disassemble the sieves.  Brush remaining material adhering to the bottom of a sieve into the next finer sieve.  Weigh and record the weight of the material retained on the No. 8 sieve and leave this material (do not discard) on the scale or balance.  Ensure that observed fabric balls remain on the scale or balance and are placed together on the side of the scale or balance to prevent the fabric balls from being covered or disturbed when placing the material from finer sieves on to the scale or balance.  Add the material retained on the next finer sieve (No. 16 sieve) to the scale or balance.  Weigh and record that weight as the accumulative weight retained on that sieve (No. 16 sieve).  Continue weighing and recording the accumulated weights retained on the remaining sieves until the accumulated weight retained in the pan has been determined.  Before discarding the crumb rubber sample, separately weigh and record the total weight of the fabric balls in the sample.

4.	Determine the weight of material passing the No. 200 sieve (or weight retained in the pan) by subtracting the accumulated weight retained on the No. 200 sieve from the accumulated retained weight in the pan.  If the material passing the No. 200 sieve (or weight retained in the pan) has a weight of 5 grams or less, cross out the recorded number for the accumulated weight retained in the pan and copy the number recorded for the accumulated weight retained on the No. 200 sieve and record that number (next to the crossed out number) as the accumulated weight retained in the pan.  If the material passing the No. 200 sieve (or weight retained in the pan) has a weight greater than 5 grams, cross out the recorded number for the accumulated weight retained in the pan, subtract 5 grams from that number and record the difference next to the crossed out number.  The adjustment to the accumulated with retained in the pan is made to account for the 5 grams of the talc added to the sample.  For calculation purposes, the adjusted accumulated weight is the same as the adjusted accumulated weight retained in the pan.  Determine the percent passing based on the adjusted total sample weight and recorded to the nearest 0.1 percent.

D.	Report.  Report all test results on ME provided forms.

NJDOT B-12 – DETERMINING Rotational Viscosity of Asphalt Rubber BINDER

A.	Scope.  This method presents procedures for sampling and testing of asphalt-rubber binder in the field using a hand held portable rotational analog or digital viscometer.

B.	Apparatus.  Use the following apparatus:

1.	Viscometer.  A hand held high range rotational viscometer.  Analog models with indicator needles and scaled dial displays or digital read out viscometers may be used.  Analog models that have been found acceptable include Rion Model VT-04E and Haake Model, VT-02.  Digital models that have been found acceptable include Haake VT 2 Plus.

2.	Rotor.  A cylinder with a diameter of 24 ± 1.1 millimeters, height of 53 ± 0.1 millimeters, and a vent hole attached to a spindle or shaft with length of 87 ± 2 millimeters that is compatible with the selected viscometer.  Acceptable rotors include Rion No. 1, Haake No 1, or an equivalent.

3.	Thermometer.  Digital with metal jacket probe accurate to 1 °F.

4.	Sample Containers.  Clean 1 gallon metal cans with lids and wire bale.

5.	Viscosity Standard Oils.  Fluids calibrated in absolute viscosity centipoise (cP).

6.	Viscometer Holder.  Clean metal container or stand for safely storing the viscometer between tests.

7.	Level Surface.  Level surface not directly on the ground.

8.	Heat Source.  A controllable heat source (i.e. a hot plate, gas stove, or burner) to maintain the temperature of the asphalt-rubber sample at 350 ± 3 °F while measuring viscosity.

9.	Personal Equipment.  Eye protection and heat resistant gloves.

C.	Procedure.  Perform the following steps:

1.	Calibration of Equipment.  Calibrate the equipment as follows:

a.	Verify the accuracy of the viscometer by comparing the viscosity results obtained with the hand held viscometer to 3 separate calibration fluids of known viscosities ranging from 1000 cP to 5000 cP.  The known viscosity value are based on the fluid manufacturer’s standard test temperature or based on the test temperature versus viscosity correlation table provided by the fluid manufacturer.

b.	The viscometer is considered accurate if the values obtained are within 300 cP of the known viscosity.

c.	Verify the calibration of the rotational viscometer using viscosity standards before use at each site.

2.	Sampling Asphalt-Rubber Binder.  Provide new sample containers and ensure that they are clean before using.  Before sampling, draw at least 1 gallon from an appropriate sample valve on the interaction tank and discard.  Then reopen the sample valve and draw at least 3/4 of a gallon for testing.

3.	Preparing Asphalt-Rubber Binder Samples for Testing.  Prepare the asphalt-rubber binder as follows:

a.	Immediately transport the sample to the testing area.  Ensure that the testing area is close to the sampling location to reduce the potential for temperature loss.

b.	Set the open asphalt-rubber binder sample container on the level surface on or over the heat source.

c.	To prevent scorching or burning, manually stir the asphalt-rubber binder sample using a metal stir rod or the temperature probe.

d.	Continue stirring until a consistent asphalt-rubber binder temperature of 350 ± 3 °F is achieved.  Record the actual test temperature with the corresponding viscosity measurement.

e.	Insert the viscometer spindle and rotor into the hot asphalt-rubber binder sample near the edge of the can.  Ensure that the spindle and rotor are not inserted deeper than the immersion depth mark on the shaft and are not plugging the vent hole.  During insertion, the spindle and rotor may be tilted slightly to keep the vent hole clear.

f.	Allow the rotor to acclimate to the temperature of the asphalt-rubber binder for approximately 1 minute.  During acclimation, stir the sample thoroughly and measure the temperature.

g.	Orient the sample and the rotor so that the rotor is near the center of the sample, align the depth mark on the shaft with the asphalt-rubber binder surface, and level the viscometer in order to measure viscosity.

4.	Testing.  Analog viscometers include a level bubble to help orient the device to ensure that the rotor and shaft remain vertical.  Digital viscometers may not include a level bubble.  If a level bubble is not included, attach a small adhesive bubble to the viscometer or use a framework with a level bubble.

Test the asphalt-rubber binder as follows:

a.	As soon as the viscometer is leveled and the depth mark is even with the asphalt-rubber binder surface, begin rotor rotation.  When using a digital viscometer, activate the continuous digital display according to the manufacturer’s recommendations.  Read and record the peak viscosity value (The peak measurement typically represents the viscosity of the asphalt-rubber binder; report and log that value.  As the rotor continues to turn, it “drills” into the sample and spins rubber particles out of its measurement area.  This may cause thinning of the material in contact with the rotor erroneously indicating a drop in the apparent viscosity of the asphalt-rubber binder) from the graduated scale labeled with the corresponding rotor number or from the digital display.

b.	After completing the first measurement, move the viscometer rotor away from the center of the sample can without removing it from the asphalt-rubber binder sample.  Turn off the rotor rotation.

c.	Stir the asphalt-rubber binder sample thoroughly.

d.	Repeat Steps 1, 2, and 3.  Take 3 measurements and average the results to determine the viscosity.

e.	Return the viscometer to its holder with the rotor suspended in a suitable solvent.  Before using the rotor again, wipe off the solvent and dry the rotor to avoid solvent contamination of the next sample.

D.	Calculations.  Some meters read in units of mPa·s (0.001 Pascal·seconds) or dPa·s (0.1 Pa·s), while others may read in centipoise (cPs) units.  The conversion is 1 Pa·s = 1000 cPs.

E.	Report.  Include the following items in the report:

1.	Date and time sampled.

2.	Location of asphalt-rubber binding blending plant.

3.	Test temperature and viscosity.

4.	Rotor designation.

5.	Viscometer model and serial n

1**************************************************************************************************************************1

NJDOT C-2 – Quick-Setting Patch Materials

C.	Procedure.

2.	Tests.  Test materials according to the following:

1**************************************************************************************************************************1

BDC15s-06 dated jul 30, 2015

THE b. is changed to:

b.	Strength Development.  For Type 1 and 2, test 2 cubes per test according to AASHTO T 106. For Type 1A and 1B, make two 4 × 8-inch cylinders per test according to AASHTO R 39. Cure specimens covered with a plastic cover over the cylinder for 3 hours and then cure without the plastic cover at 70.4 to 76.4 °F and 50 percent relative humidity until testing. Test according to AASHTO T 22

1**************************************************************************************************************************1

NJDOT R-1 – Operating Inertial Profiler Systems for Evaluating Pavement Profiles

1**************************************************************************************************************************1

BDC12s-03 dated May 02, 2012

thIS entire test method is changed to:

A.	Scope.  This test method describes the procedure for operating, verifying the calibration of an ASTM E 950 Class 1 Inertial Profiler System (IPS) and testing riding surface for pavement profiles evaluation.

B.	Apparatus.  Use an IPS that meets the requirements of AASHTO M 328 and ASTM E 950, Class 1 and the following:

1.	Certify the IPS according to AASHTO R 56 at least every 2 years.  If a system component is replaced, re-certify the system.  Perform the certification at a site approved by the Department.

2.	The data system provides the raw profile data in an ASCII format acceptable to the Department.

3.	The computer program uses a high-pass filter set at 300 feet and reads an ASCII or text file for computing the International Roughness Index (IRI) in inches per mile.

4.	The current version of ROADRUF, ProVal, or other Department approved pavement profile analysis software is used to compute the IRI.

C.	Procedure.  Perform the following steps:

1.	Operate the IPS according to AASHTO R 57 and ASTM E 950.

2.	On a daily basis before data collection, check the equipment and operating system for operational stability and calibration.  Perform necessary calibration procedures according to equipment manufacturer’s procedures and applicable standards.  Operators shall maintain a log documenting the calibration history.

3.	Ensure that the operators of the IPS have completed a profile training course, such as NHI Course 131100, have been trained specifically on the IPS they will be operating, and are proficient in the operation of the IPS.

4.	Make provisions to automatically start and stop the IPS recording at the beginning and end of testing.

5	Ensure retroreflective traffic striping tape or other approved mechanism is placed at the beginning and end of each direction of travel for automatically triggering the start and stop of profile measurements.

6.	Collect at least 0.05-mile of data before the area to be tested to allow the system to stabilize before profile measurements are obtained.  Collect data in a continuous run through the length to be tested.  If the run is interrupted, discard the results and re-run the length.

7	Test the full extent of each wheel path of each lane in the longitudinal direction of travel.  The wheel path is defined as being located approximately 3 feet on each side of the centerline of the lane and extending for the full length of the lane.  Lanes are defined by striping.

8	Run three tests each wheel path and report average of three runs each wheel path.

9.	Exclude locations where the traffic striping includes turn lanes that cause the through traffic lane to cross over a longitudinally paved joint, ramps, and lanes such as acceleration and deceleration lanes of less than 1,000 feet of continuous through treatment.

10	Report single IRI value average of 3 runs unless otherwise directed.  The single IRI value shall be each 0.01 mile length for each lane, ramp, and shoulder and 0.005 mile for each overlaid bridge structure.

Attachments

Depending on the project funding include as follows:

INclude fhwa attachments for FHWA funded projects

OR

INclude state attachments for wholly state funded projects

1*********************************************************************************************************************1

INclude THE FOLLOWING FOR fhwa funded projects

2**************************************************************************************2

BDC12s-09 dated July 20, 2012

FHWA Attachment No. 1

Required Contract Provisions Federal-Aid Construction Contracts

I.	General

II.	Nondiscrimination

III.	Nonsegregated Facilities

IV.	Davis-Bacon and Related Act Provisions

V.	Contract Work Hours and Safety Standards Act Provisions

VI.	Subletting or Assigning the Contract

VII.	Safety: Accident Prevention

VIII.	False Statements Concerning Highway Projects

IX.	Implementation of Clean Air Act and Federal Water Pollution Control Act

X.	Compliance with Governmentwide Suspension and Debarment Requirements

XI.	Certification Regarding Use of Contract Funds for Lobbying

ATTACHMENTS

A. Employment and Materials Preference for Appalachian Development Highway System or Appalachian Local Access Road Contracts (included in Appalachian contracts only)

# I.  GENERAL

1.  Form FHWA-1273 must be physically incorporated in each construction contract funded under Title 23 (excluding emergency contracts solely intended for debris removal).  The contractor (or subcontractor) must insert this form in each subcontract and further require its inclusion in all lower tier subcontracts (excluding purchase orders, rental agreements and other agreements for supplies or services).

The applicable requirements of Form FHWA-1273 are incorporated by reference for work done under any purchase order, rental agreement or agreement for other services.  The prime contractor shall be responsible for compliance by any subcontractor, lower-tier subcontractor or service provider.

Form FHWA-1273 must be included in all Federal-aid design-build contracts, in all subcontracts and in lower tier subcontracts (excluding subcontracts for design services, purchase orders, rental agreements and other agreements for supplies or services).  The design-builder shall be responsible for compliance by any subcontractor, lower-tier subcontractor or service provider.

Contracting agencies may reference Form FHWA-1273 in bid proposal or request for proposal documents, however, the Form FHWA-1273 must be physically incorporated (not referenced) in all contracts, subcontracts and lower-tier subcontracts (excluding purchase orders, rental agreements and other agreements for supplies or services related to a construction contract).

2.  Subject to the applicability criteria noted in the following sections, these contract provisions shall apply to all work performed on the contract by the contractor's own organization and with the assistance of workers under the contractor's immediate superintendence and to all work performed on the contract by piecework, station work, or by subcontract.

3.  A breach of any of the stipulations contained in these Required Contract Provisions may be sufficient grounds for withholding of progress payments, withholding of final payment, termination of the contract, suspension / debarment or any other action determined to be appropriate by the contracting agency and FHWA.

4.  Selection of Labor: During the performance of this contract, the contractor shall not use convict labor for any purpose within the limits of a construction project on a Federal-aid highway unless it is labor performed by convicts who are on parole, supervised release, or probation.  The term Federal-aid highway does not include roadways functionally classified as local roads or rural minor collectors.

# II.  NONDISCRIMINATION

The provisions of this section related to 23 CFR Part 230 are applicable to all Federal-aid construction contracts and to all related construction subcontracts of $10,000 or more.  The provisions of 23 CFR Part 230 are not applicable to material supply, engineering, or architectural service contracts.

In addition, the contractor and all subcontractors must comply with the following policies: Executive Order 11246, 41 CFR 60, 29 CFR 1625-1627, Title 23 USC Section 140, the Rehabilitation Act of 1973, as amended (29 USC 794), Title VI of the Civil Rights Act of 1964, as amended, and related regulations including 49 CFR Parts 21, 26 and 27; and 23 CFR Parts 200, 230, and 633.

The contractor and all subcontractors must comply with:  the requirements of the Equal Opportunity Clause in 41 CFR 60-1.4(b) and, for all construction contracts exceeding $10,000, the Standard Federal Equal Employment Opportunity Construction Contract Specifications in 41 CFR 60-4.3.

Note: The U.S. Department of Labor has exclusive authority to determine compliance with Executive Order 11246 and the policies of the Secretary of Labor including 41 CFR 60, and 29 CFR 1625-1627.  The contracting agency and the FHWA have the authority and the responsibility to ensure compliance with Title 23 USC Section 140, the Rehabilitation Act of 1973, as amended (29 USC 794), and Title VI of the Civil Rights Act of 1964, as amended, and related regulations including 49 CFR Parts 21, 26 and 27; and 23 CFR Parts 200, 230, and 633.

The following provision is adopted from 23 CFR 230, Appendix A, with appropriate revisions to conform to the U.S. Department of Labor (US DOL) and FHWA requirements.

1.  Equal Employment Opportunity: Equal employment opportunity (EEO) requirements not to discriminate and to take affirmative action to assure equal opportunity as set forth under laws, executive orders, rules, regulations (28 CFR 35, 29 CFR 1630, 29 CFR 1625-1627, 41 CFR 60 and 49 CFR 27) and orders of the Secretary of Labor as modified by the provisions prescribed herein, and imposed pursuant to 23 U.S.C. 140 shall constitute the EEO and specific affirmative action standards for the contractor's project activities under this contract. The provisions of the Americans with Disabilities Act of 1990 (42 U.S.C. 12101 et seq.) set forth under 28 CFR 35 and 29 CFR 1630 are incorporated by reference in this contract. In the execution of this contract, the contractor agrees to comply with the following minimum specific requirement activities of EEO:

a. The contractor will work with the contracting agency and the Federal Government to ensure that it has made every good faith effort to provide equal opportunity with respect to all of its terms and conditions of employment and in their review of activities under the contract.

b. The contractor will accept as its operating policy the following statement:

"It is the policy of this Company to assure that applicants are employed, and that employees are treated during employment, without regard to their race, religion, sex, color, national origin, age or disability.  Such action shall include: employment, upgrading, demotion, or transfer; recruitment or recruitment advertising; layoff or termination; rates of pay or other forms of compensation; and selection for training, including apprenticeship, pre-apprenticeship, and/or on-the-job training."

2.  EEO Officer: The contractor will designate and make known to the contracting officers an EEO Officer who will have the responsibility for and must be capable of effectively administering and promoting an active EEO program and who must be assigned adequate authority and responsibility to do so.

3.  Dissemination of Policy: All members of the contractor's staff who are authorized to hire, supervise, promote, and discharge employees, or who recommend such action, or who are substantially involved in such action, will be made fully cognizant of, and will implement, the contractor's EEO policy and contractual responsibilities to provide EEO in each grade and classification of employment.  To ensure that the above agreement will be met, the following actions will be taken as a minimum:

a.  Periodic meetings of supervisory and personnel office employees will be conducted before the start of work and then not less often than once every six months, at which time the contractor's EEO policy and its implementation will be reviewed and explained.  The meetings will be conducted by the EEO Officer.

b.  All new supervisory or personnel office employees will be given a thorough indoctrination by the EEO Officer, covering all major aspects of the contractor's EEO obligations within thirty days following their reporting for duty with the contractor.

c.  All personnel who are engaged in direct recruitment for the project will be instructed by the EEO Officer in the contractor's procedures for locating and hiring minorities and women.

d.  Notices and posters setting forth the contractor's EEO policy will be placed in areas readily accessible to employees, applicants for employment and potential employees.

e.  The contractor's EEO policy and the procedures to implement such policy will be brought to the attention of employees by means of meetings, employee handbooks, or other appropriate means.

4.  Recruitment: When advertising for employees, the contractor will include in all advertisements for employees the notation: "An Equal Opportunity Employer."  All such advertisements will be placed in publications having a large circulation among minorities and women in the area from which the project work force would normally be derived.

a.  The contractor will, unless precluded by a valid bargaining agreement, conduct systematic and direct recruitment through public and private employee referral sources likely to yield qualified minorities and women.  To meet this requirement, the contractor will identify sources of potential minority group employees, and establish with such identified sources procedures whereby minority and women applicants may be referred to the contractor for employment consideration.

b.  In the event the contractor has a valid bargaining agreement providing for exclusive hiring hall referrals, the contractor is expected to observe the provisions of that agreement to the extent that the system meets the contractor's compliance with EEO contract provisions.  Where implementation of such an agreement has the effect of discriminating against minorities or women, or obligates the contractor to do the same, such implementation violates Federal nondiscrimination provisions.

c.  The contractor will encourage its present employees to refer minorities and women as applicants for employment.  Information and procedures with regard to referring such applicants will be discussed with employees.

5.  Personnel Actions: Wages, working conditions, and employee benefits shall be established and administered, and personnel actions of every type, including hiring, upgrading, promotion, transfer, demotion, layoff, and termination, shall be taken without regard to race, color, religion, sex, national origin, age or disability.  The following procedures shall be followed:

a.  The contractor will conduct periodic inspections of project sites to insure that working conditions and employee facilities do not indicate discriminatory treatment of project site personnel.

b.  The contractor will periodically evaluate the spread of wages paid within each classification to determine any evidence of discriminatory wage practices.

c.  The contractor will periodically review selected personnel actions in depth to determine whether there is evidence of discrimination.  Where evidence is found, the contractor will promptly take corrective action.  If the review indicates that the discrimination may extend beyond the actions reviewed, such corrective action shall include all affected persons.

d.  The contractor will promptly investigate all complaints of alleged discrimination made to the contractor in connection with its obligations under this contract, will attempt to resolve such complaints, and will take appropriate corrective action within a reasonable time.  If the investigation indicates that the discrimination may affect persons other than the complainant, such corrective action shall include such other persons.  Upon completion of each investigation, the contractor will inform every complainant of all of their avenues of appeal.

6.  Training and Promotion:

a.  The contractor will assist in locating, qualifying, and increasing the skills of minorities and women who are applicants for employment or current employees.  Such efforts should be aimed at developing full journey level status employees in the type of trade or job classification involved.

b.  Consistent with the contractor's work force requirements and as permissible under Federal and State regulations, the contractor shall make full use of training programs, i.e., apprenticeship, and on-the-job training programs for the geographical area of contract performance.  In the event a special provision for training is provided under this contract, this subparagraph will be superseded as indicated in the special provision.  The contracting agency may reserve training positions for persons who receive welfare assistance in accordance with 23 U.S.C. 140(a).

c.  The contractor will advise employees and applicants for employment of available training programs and entrance requirements for each.

d.  The contractor will periodically review the training and promotion potential of employees who are minorities and women and will encourage eligible employees to apply for such training and promotion.

7.  Unions: If the contractor relies in whole or in part upon unions as a source of employees, the contractor will use good faith efforts to obtain the cooperation of such unions to increase opportunities for minorities and women.  Actions by the contractor, either directly or through a contractor's association acting as agent, will include the procedures set forth below:

a.  The contractor will use good faith efforts to develop, in cooperation with the unions, joint training programs aimed toward qualifying more minorities and women for membership in the unions and increasing the skills of minorities and women so that they may qualify for higher paying employment.

b.  The contractor will use good faith efforts to incorporate an EEO clause into each union agreement to the end that such union will be contractually bound to refer applicants without regard to their race, color, religion, sex, national origin, age or disability.

c.  The contractor is to obtain information as to the referral practices and policies of the labor union except that to the extent such information is within the exclusive possession of the labor union and such labor union refuses to furnish such information to the contractor, the contractor shall so certify to the contracting agency and shall set forth what efforts have been made to obtain such information.

d.  In the event the union is unable to provide the contractor with a reasonable flow of referrals within the time limit set forth in the collective bargaining agreement, the contractor will, through independent recruitment efforts, fill the employment vacancies without regard to race, color, religion, sex, national origin, age or disability; making full efforts to obtain qualified and/or qualifiable minorities and women.  The failure of a union to provide sufficient referrals (even though it is obligated to provide exclusive referrals under the terms of a collective bargaining agreement) does not relieve the contractor from the requirements of this paragraph.   In the event the union referral practice prevents the contractor from meeting the obligations pursuant to Executive Order 11246, as amended, and these special provisions, such contractor shall immediately notify the contracting agency.

8.  Reasonable Accommodation for Applicants / Employees with Disabilities:  The contractor must be familiar with the requirements for and comply with the Americans with Disabilities Act and all rules and regulations established there under.  Employers must provide reasonable accommodation in all employment activities unless to do so would cause an undue hardship.

9.  Selection of Subcontractors, Procurement of Materials and Leasing of Equipment: The contractor shall not discriminate on the grounds of race, color, religion, sex, national origin, age or disability in the selection and retention of subcontractors, including procurement of materials and leases of equipment.  The contractor shall take all necessary and reasonable steps to ensure nondiscrimination in the administration of this contract.

a.  The contractor shall notify all potential subcontractors and suppliers and lessors of their EEO obligations under this contract.

b.  The contractor will use good faith efforts to ensure subcontractor compliance with their EEO obligations.

10.  Assurance Required by 49 CFR 26.13(b):

a.  The requirements of 49 CFR Part 26 and the State DOT’s U.S. DOT-approved DBE program are incorporated by reference.

b.  The contractor or subcontractor shall not discriminate on the basis of race, color, national origin, or sex in the performance of this contract.  The contractor shall carry out applicable requirements of 49 CFR Part 26 in the award and administration of DOT-assisted contracts.  Failure by the contractor to carry out these requirements is a material breach of this contract, which may result in the termination of this contract or such other remedy as the contracting agency deems appropriate.

11.  Records and Reports: The contractor shall keep such records as necessary to document compliance with the EEO requirements.  Such records shall be retained for a period of three years following the date of the final payment to the contractor for all contract work and shall be available at reasonable times and places for inspection by authorized representatives of the contracting agency and the FHWA.

a.  The records kept by the contractor shall document the following:

(1) The number and work hours of minority and non-minority group members and women employed in each work classification on the project;

(2) The progress and efforts being made in cooperation with unions, when applicable, to increase employment opportunities for minorities and women; and

(3) The progress and efforts being made in locating, hiring, training, qualifying, and upgrading minorities and women;

b.  The contractors and subcontractors will submit an annual report to the contracting agency each July for the duration of the project, indicating the number of minority, women, and non-minority group employees currently engaged in each work classification required by the contract work.  This information is to be reported on Form FHWA-1391.  The staffing data should represent the project work force on board in all or any part of the last payroll period preceding the end of July.  If on-the-job training is being required by special provision, the contractor will be required to collect and report training data.  The employment data should reflect the work force on board during all or any part of the last payroll period preceding the end of July.

# III.  NONSEGREGATED FACILITIES

This provision is applicable to all Federal-aid construction contracts and to all related construction subcontracts of $10,000 or more.

The contractor must ensure that facilities provided for employees are provided in such a manner that segregation on the basis of race, color, religion, sex, or national origin cannot result.  The contractor may neither require such segregated use by written or oral policies nor tolerate such use by employee custom.  The contractor's obligation extends further to ensure that its employees are not assigned to perform their services at any location, under the contractor's control, where the facilities are segregated.  The term "facilities" includes waiting rooms, work areas, restaurants and other eating areas, time clocks, restrooms, washrooms, locker rooms, and other storage or dressing areas, parking lots, drinking fountains, recreation or entertainment areas, transportation, and housing provided for employees.  The contractor shall provide separate or single-user restrooms and necessary dressing or sleeping areas to assure privacy between sexes.

# IV.  Davis-Bacon and Related Act Provisions

This section is applicable to all Federal-aid construction projects exceeding $2,000 and to all related subcontracts and lower-tier subcontracts (regardless of subcontract size).  The requirements apply to all projects located within the right-of-way of a roadway that is functionally classified as Federal-aid highway.  This excludes roadways functionally classified as local roads or rural minor collectors, which are exempt.  Contracting agencies may elect to apply these requirements to other projects.

The following provisions are from the U.S. Department of Labor regulations in 29 CFR 5.5 “Contract provisions and related matters” with minor revisions to conform to the FHWA-1273 format and FHWA program requirements.

1.  Minimum wages

a.  All laborers and mechanics employed or working upon the site of the work, will be paid unconditionally and not less often than once a week, and without subsequent deduction or rebate on any account (except such payroll deductions as are permitted by regulations issued by the Secretary of Labor under the Copeland Act (29 CFR part 3)), the full amount of wages and bona fide fringe benefits (or cash equivalents thereof) due at time of payment computed at rates not less than those contained in the wage determination of the Secretary of Labor which is attached hereto and made a part hereof, regardless of any contractual relationship which may be alleged to exist between the contractor and such laborers and mechanics.

Contributions made or costs reasonably anticipated for bona fide fringe benefits under section 1(b)(2) of the Davis-Bacon Act on behalf of laborers or mechanics are considered wages paid to such laborers or mechanics, subject to the provisions of paragraph 1.d. of this section; also, regular contributions made or costs incurred for more than a weekly period (but not less often than quarterly) under plans, funds, or programs which cover the particular weekly period, are deemed to be constructively made or incurred during such weekly period. Such laborers and mechanics shall be paid the appropriate wage rate and fringe benefits on the wage determination for the classification of work actually performed, without regard to skill, except as provided in 29 CFR 5.5(a)(4). Laborers or mechanics performing work in more than one classification may be compensated at the rate specified for each classification for the time actually worked therein: Provided, That the employer's payroll records accurately set forth the time spent in each classification in which work is performed. The wage determination (including any additional classification and wage rates conformed under paragraph 1.b. of this section) and the Davis-Bacon poster (WH–1321) shall be posted at all times by the contractor and its subcontractors at the site of the work in a prominent and accessible place where it can be easily seen by the workers.

b.  (1) The contracting officer shall require that any class of laborers or mechanics, including helpers, which is not listed in the wage determination and which is to be employed under the contract shall be classified in conformance with the wage determination. The contracting officer shall approve an additional classification and wage rate and fringe benefits therefore only when the following criteria have been met:

(i) The work to be performed by the classification requested is not performed by a classification in the wage determination; and

(ii) The classification is utilized in the area by the construction industry; and

(iii) The proposed wage rate, including any bona fide fringe benefits, bears a reasonable relationship to the wage rates contained in the wage determination.

(2)  If the contractor and the laborers and mechanics to be employed in the classification (if known), or their representatives, and the contracting officer agree on the classification and wage rate (including the amount designated for fringe benefits where appropriate), a report of the action taken shall be sent by the contracting officer to the Administrator of the Wage and Hour Division, Employment Standards Administration, U.S. Department of Labor, Washington, DC 20210. The Administrator, or an authorized representative, will approve, modify, or disapprove every additional classification action within 30 days of receipt and so advise the contracting officer or will notify the contracting officer within the 30-day period that additional time is necessary.

(3)  In the event the contractor, the laborers or mechanics to be employed in the classification or their representatives, and the contracting officer do not agree on the proposed classification and wage rate (including the amount designated for fringe benefits, where appropriate), the contracting officer shall refer the questions, including the views of all interested parties and the recommendation of the contracting officer, to the Wage and Hour Administrator for determination. The Wage and Hour Administrator, or an authorized representative, will issue a determination within 30 days of receipt and so advise the contracting officer or will notify the contracting officer within the 30-day period that additional time is necessary.

(4)  The wage rate (including fringe benefits where appropriate) determined pursuant to paragraphs 1.b.(2) or 1.b.(3) of this section, shall be paid to all workers performing work in the classification under this contract from the first day on which work is performed in the classification.

c.  Whenever the minimum wage rate prescribed in the contract for a class of laborers or mechanics includes a fringe benefit which is not expressed as an hourly rate, the contractor shall either pay the benefit as stated in the wage determination or shall pay another bona fide fringe benefit or an hourly cash equivalent thereof.

d.  If the contractor does not make payments to a trustee or other third person, the contractor may consider as part of the wages of any laborer or mechanic the amount of any costs reasonably anticipated in providing bona fide fringe benefits under a plan or program, Provided, That the Secretary of Labor has found, upon the written request of the contractor, that the applicable standards of the Davis-Bacon Act have been met. The Secretary of Labor may require the contractor to set aside in a separate account assets for the meeting of obligations under the plan or program.

2.  Withholding

The contracting agency shall upon its own action or upon written request of an authorized representative of the Department of Labor, withhold or cause to be withheld from the contractor under this contract, or any other Federal contract with the same prime contractor, or any other federally-assisted contract subject to Davis-Bacon prevailing wage requirements, which is held by the same prime contractor, so much of the accrued payments or advances as may be considered necessary to pay laborers and mechanics, including apprentices, trainees, and helpers, employed by the contractor or any subcontractor the full amount of wages required by the contract.  In the event of failure to pay any laborer or mechanic, including any apprentice, trainee, or helper, employed or working on the site of the work, all or part of the wages required by the contract, the contracting agency may, after written notice to the contractor, take such action as may be necessary to cause the suspension of any further payment, advance, or guarantee of funds until such violations have ceased.

3.  Payrolls and basic records

a.  Payrolls and basic records relating thereto shall be maintained by the contractor during the course of the work and preserved for a period of three years thereafter for all laborers and mechanics working at the site of the work. Such records shall contain the name, address, and social security number of each such worker, his or her correct classification, hourly rates of wages paid (including rates of contributions or costs anticipated for bona fide fringe benefits or cash equivalents thereof of the types described in section 1(b)(2)(B) of the Davis-Bacon Act), daily and weekly number of hours worked, deductions made and actual wages paid. Whenever the Secretary of Labor has found under 29 CFR 5.5(a)(1)(iv) that the wages of any laborer or mechanic include the amount of any costs reasonably anticipated in providing benefits under a plan or program described in section 1(b)(2)(B) of the Davis-Bacon Act, the contractor shall maintain records which show that the commitment to provide such benefits is enforceable, that the plan or program is financially responsible, and that the plan or program has been communicated in writing to the laborers or mechanics affected, and records which show the costs anticipated or the actual cost incurred in providing such benefits. Contractors employing apprentices or trainees under approved programs shall maintain written evidence of the registration of apprenticeship programs and certification of trainee programs, the registration of the apprentices and trainees, and the ratios and wage rates prescribed in the applicable programs.

b.  (1) The contractor shall submit weekly for each week in which any contract work is performed a copy of all payrolls to the contracting agency.   The payrolls submitted shall set out accurately and completely all of the information required to be maintained under 29 CFR 5.5(a)(3)(i), except that full social security numbers and home addresses shall not be included on weekly transmittals. Instead the payrolls shall only need to include an individually identifying number for each employee ( e.g. , the last four digits of the employee's social security number). The required weekly payroll information may be submitted in any form desired. Optional Form WH–347 is available for this purpose from the Wage and Hour Division Web site at http://www.dol.gov/esa/whd/forms/wh347instr.htm or its successor site. The prime contractor is responsible for the submission of copies of payrolls by all subcontractors. Contractors and subcontractors shall maintain the full social security number and current address of each covered worker, and shall provide them upon request to the contracting agency for transmission to the State DOT, the FHWA or the Wage and Hour Division of the Department of Labor for purposes of an investigation or audit of compliance with prevailing wage requirements. It is not a violation of this section for a prime contractor to require a subcontractor to provide addresses and social security numbers to the prime contractor for its own records, without weekly submission to the contracting agency..

(2)  Each payroll submitted shall be accompanied by a “Statement of Compliance,” signed by the contractor or subcontractor or his or her agent who pays or supervises the payment of the persons employed under the contract and shall certify the following:

(i) That the payroll for the payroll period contains the information required to be provided under §5.5 (a)(3)(ii) of Regulations, 29 CFR part 5, the appropriate information is being maintained under §5.5 (a)(3)(i) of Regulations, 29 CFR part 5, and that such information is correct and complete;

(ii) That each laborer or mechanic (including each helper, apprentice, and trainee) employed on the contract during the payroll period has been paid the full weekly wages earned, without rebate, either directly or indirectly, and that no deductions have been made either directly or indirectly from the full wages earned, other than permissible deductions as set forth in Regulations, 29 CFR part 3;

(iii) That each laborer or mechanic has been paid not less than the applicable wage rates and fringe benefits or cash equivalents for the classification of work performed, as specified in the applicable wage determination incorporated into the contract.

(3)  The weekly submission of a properly executed certification set forth on the reverse side of Optional Form WH–347 shall satisfy the requirement for submission of the “Statement of Compliance” required by paragraph 3.b.(2) of this section.

(4)  The falsification of any of the above certifications may subject the contractor or subcontractor to civil or criminal prosecution under section 1001 of title 18 and section 231 of title 31 of the United States Code.

c.  The contractor or subcontractor shall make the records required under paragraph 3.a. of this section available for inspection, copying, or transcription by authorized representatives of the contracting agency, the State DOT, the FHWA,  or the Department of Labor, and shall permit such representatives to interview employees during working hours on the job. If the contractor or subcontractor fails to submit the required records or to make them available, the FHWA may, after written notice to the contractor, the contracting agency or the State DOT, take such action as may be necessary to cause the suspension of any further payment, advance, or guarantee of funds. Furthermore, failure to submit the required records upon request or to make such records available may be grounds for debarment action pursuant to 29 CFR 5.12.

4.  Apprentices and trainees

a.  Apprentices (programs of the USDOL).

Apprentices will be permitted to work at less than the predetermined rate for the work they performed when they are employed pursuant to and individually registered in a bona fide apprenticeship program registered with the U.S. Department of Labor, Employment and Training Administration, Office of Apprenticeship Training, Employer and Labor Services, or with a State Apprenticeship Agency recognized by the Office, or if a person is employed in his or her first 90 days of probationary employment as an apprentice in such an apprenticeship program, who is not individually registered in the program, but who has been certified by the Office of Apprenticeship Training, Employer and Labor Services or a State Apprenticeship Agency (where appropriate) to be eligible for probationary employment as an apprentice.

The allowable ratio of apprentices to journeymen on the job site in any craft classification shall not be greater than the ratio permitted to the contractor as to the entire work force under the registered program. Any worker listed on a payroll at an apprentice wage rate, who is not registered or otherwise employed as stated above, shall be paid not less than the applicable wage rate on the wage determination for the classification of work actually performed. In addition, any apprentice performing work on the job site in excess of the ratio permitted under the registered program shall be paid not less than the applicable wage rate on the wage determination for the work actually performed. Where a contractor is performing construction on a project in a locality other than that in which its program is registered, the ratios and wage rates (expressed in percentages of the journeyman's hourly rate) specified in the contractor's or subcontractor's registered program shall be observed.

Every apprentice must be paid at not less than the rate specified in the registered program for the apprentice's level of progress, expressed as a percentage of the journeymen hourly rate specified in the applicable wage determination. Apprentices shall be paid fringe benefits in accordance with the provisions of the apprenticeship program. If the apprenticeship program does not specify fringe benefits, apprentices must be paid the full amount of fringe benefits listed on the wage determination for the applicable classification. If the Administrator determines that a different practice prevails for the applicable apprentice classification, fringes shall be paid in accordance with that determination.

In the event the Office of Apprenticeship Training, Employer and Labor Services, or a State Apprenticeship Agency recognized by the Office, withdraws approval of an apprenticeship program, the contractor will no longer be permitted to utilize apprentices at less than the applicable predetermined rate for the work performed until an acceptable program is approved.

b.  Trainees (programs of the USDOL).

Except as provided in 29 CFR 5.16, trainees will not be permitted to work at less than the predetermined rate for the work performed unless they are employed pursuant to and individually registered in a program which has received prior approval, evidenced by formal certification by the U.S. Department of Labor, Employment and Training Administration.

The ratio of trainees to journeymen on the job site shall not be greater than permitted under the plan approved by the Employment and Training Administration.

Every trainee must be paid at not less than the rate specified in the approved program for the trainee's level of progress, expressed as a percentage of the journeyman hourly rate specified in the applicable wage determination. Trainees shall be paid fringe benefits in accordance with the provisions of the trainee program. If the trainee program does not mention fringe benefits, trainees shall be paid the full amount of fringe benefits listed on the wage determination unless the Administrator of the Wage and Hour Division determines that there is an apprenticeship program associated with the corresponding journeyman wage rate on the wage determination which provides for less than full fringe benefits for apprentices. Any employee listed on the payroll at a trainee rate who is not registered and participating in a training plan approved by the Employment and Training Administration shall be paid not less than the applicable wage rate on the wage determination for the classification of work actually performed. In addition, any trainee performing work on the job site in excess of the ratio permitted under the registered program shall be paid not less than the applicable wage rate on the wage determination for the work actually performed.

In the event the Employment and Training Administration withdraws approval of a training program, the contractor will no longer be permitted to utilize trainees at less than the applicable predetermined rate for the work performed until an acceptable program is approved.

c.  Equal employment opportunity. The utilization of apprentices, trainees and journeymen under this part shall be in conformity with the equal employment opportunity requirements of Executive Order 11246, as amended, and 29 CFR part 30.

d.  Apprentices and Trainees (programs of the U.S. DOT).

Apprentices and trainees working under apprenticeship and skill training programs which have been certified by the Secretary of Transportation as promoting EEO in connection with Federal-aid highway construction programs are not subject to the requirements of paragraph 4 of this Section IV. The straight time hourly wage rates for apprentices and trainees under such programs will be established by the particular programs. The ratio of apprentices and trainees to journeymen shall not be greater than permitted by the terms of the particular program.

5.  Compliance with Copeland Act requirements.   The contractor shall comply with the requirements of 29 CFR part 3, which are incorporated by reference in this contract.

6.  Subcontracts.   The contractor or subcontractor shall insert Form FHWA-1273 in any subcontracts and also require the subcontractors to include Form FHWA-1273 in any lower tier subcontracts. The prime contractor shall be responsible for the compliance by any subcontractor or lower tier subcontractor with all the contract clauses in 29 CFR 5.5.

7.  Contract termination: debarment.   A breach of the contract clauses in 29 CFR 5.5 may be grounds for termination of the contract, and for debarment as a contractor and a subcontractor as provided in 29 CFR 5.12.

8.  Compliance with Davis-Bacon and Related Act requirements.  All rulings and interpretations of the Davis-Bacon and Related Acts contained in 29 CFR parts 1, 3, and 5 are herein incorporated by reference in this contract.

9.  Disputes concerning labor standards. Disputes arising out of the labor standards provisions of this contract shall not be subject to the general disputes clause of this contract. Such disputes shall be resolved in accordance with the procedures of the Department of Labor set forth in 29 CFR parts 5, 6, and 7. Disputes within the meaning of this clause include disputes between the contractor (or any of its subcontractors) and the contracting agency, the U.S. Department of Labor, or the employees or their representatives.

10.  Certification of eligibility.

a.  By entering into this contract, the contractor certifies that neither it (nor he or she) nor any person or firm who has an interest in the contractor's firm is a person or firm ineligible to be awarded Government contracts by virtue of section 3(a) of the Davis-Bacon Act or 29 CFR 5.12(a)(1).

b.  No part of this contract shall be subcontracted to any person or firm ineligible for award of a Government contract by virtue of section 3(a) of the Davis-Bacon Act or 29 CFR 5.12(a)(1).

c.  The penalty for making false statements is prescribed in the U.S. Criminal Code, 18 U.S.C. 1001.

# V.  CONTRACT WORK HOURS AND SAFETY STANDARDS ACT

The following clauses apply to any Federal-aid construction contract in an amount in excess of $100,000 and subject to the overtime provisions of the Contract Work Hours and Safety Standards Act. These clauses shall be inserted in addition to the clauses required by 29 CFR 5.5(a) or 29 CFR 4.6.  As used in this paragraph, the terms laborers and mechanics include watchmen and guards.

1.  Overtime requirements.   No contractor or subcontractor contracting for any part of the contract work which may require or involve the employment of laborers or mechanics shall require or permit any such laborer or mechanic in any workweek in which he or she is employed on such work to work in excess of forty hours in such workweek unless such laborer or mechanic receives compensation at a rate not less than one and one-half times the basic rate of pay for all hours worked in excess of forty hours in such workweek.

2.  Violation; liability for unpaid wages; liquidated damages.  In the event of any violation of the clause set forth in paragraph (1.) of this section, the contractor and any subcontractor responsible therefore shall be liable for the unpaid wages. In addition, such contractor and subcontractor shall be liable to the United States (in the case of work done under contract for the District of Columbia or a territory, to such District or to such territory), for liquidated damages. Such liquidated damages shall be computed with respect to each individual laborer or mechanic, including watchmen and guards, employed in violation of the clause set forth in paragraph (1.) of this section, in the sum of $10 for each calendar day on which such individual was required or permitted to work in excess of the standard workweek of forty hours without payment of the overtime wages required by the clause set forth in paragraph (1.) of this section.

3.  Withholding for unpaid wages and liquidated damages. The FHWA or the contacting agency shall upon its own action or upon written request of an authorized representative of the Department of Labor withhold or cause to be withheld, from any moneys payable on account of work performed by the contractor or subcontractor under any such contract or any other Federal contract with the same prime contractor, or any other federally-assisted contract subject to the Contract Work Hours and Safety Standards Act, which is held by the same prime contractor, such sums as may be determined to be necessary to satisfy any liabilities of such contractor or subcontractor for unpaid wages and liquidated damages as provided in the clause set forth in paragraph (2.) of this section.

4.  Subcontracts.  The contractor or subcontractor shall insert in any subcontracts the clauses set forth in paragraph (1.) through (4.) of this section and also a clause requiring the subcontractors to include these clauses in any lower tier subcontracts. The prime contractor shall be responsible for compliance by any subcontractor or lower tier subcontractor with the clauses set forth in paragraphs (1.) through (4.) of this section.

# VI.  SUBLETTING OR ASSIGNING THE CONTRACT

This provision is applicable to all Federal-aid construction contracts on the National Highway System.

1.  The contractor shall perform with its own organization contract work amounting to not less than 30 percent (or a greater percentage if specified elsewhere in the contract) of the total original contract price, excluding any specialty items designated by the contracting agency.  Specialty items may be performed by subcontract and the amount of any such specialty items performed may be deducted from the total original contract price before computing the amount of work required to be performed by the contractor's own organization (23 CFR 635.116).

a.  The term “perform work with its own organization” refers to workers employed or leased by the prime contractor, and equipment owned or rented by the prime contractor, with or without operators.  Such term does not include employees or equipment of a subcontractor or lower tier subcontractor, agents of the prime contractor, or any other assignees.  The term may include payments for the costs of hiring leased employees from an employee leasing firm meeting all relevant Federal and State regulatory requirements.  Leased employees may only be included in this term if the prime contractor meets all of the following conditions:

(1) the prime contractor maintains control over the supervision of the day-to-day activities of the leased employees;

(2) the prime contractor remains responsible for the quality of the work of the leased employees;

(3) the prime contractor retains all power to accept or exclude individual employees from work on the project; and

(4) the prime contractor remains ultimately responsible for the payment of predetermined minimum wages, the submission of payrolls, statements of compliance and all other Federal regulatory requirements.

b.  "Specialty Items" shall be construed to be limited to work that requires highly specialized knowledge, abilities, or equipment not ordinarily available in the type of contracting organizations qualified and expected to bid or propose on the contract as a whole and in general are to be limited to minor components of the overall contract.

2.  The contract amount upon which the requirements set forth in paragraph (1) of Section VI is computed includes the cost of material and manufactured products which are to be purchased or produced by the contractor under the contract provisions.

3.  The contractor shall furnish (a) a competent superintendent or supervisor who is employed by the firm, has full authority to direct performance of the work in accordance with the contract requirements, and is in charge of all construction operations (regardless of who performs the work) and (b) such other of its own organizational resources (supervision, management, and engineering services) as the contracting officer determines is necessary to assure the performance of the contract.

4.  No portion of the contract shall be sublet, assigned or otherwise disposed of except with the written consent of the contracting officer, or authorized representative, and such consent when given shall not be construed to relieve the contractor of any responsibility for the fulfillment of the contract.  Written consent will be given only after the contracting agency has assured that each subcontract is evidenced in writing and that it contains all pertinent provisions and requirements of the prime contract.

5.  The 30% self-performance requirement of paragraph (1) is not applicable to design-build contracts; however, contracting agencies may establish their own self-performance requirements.

# VII.  SAFETY: ACCIDENT PREVENTION

This provision is applicable to all Federal-aid construction contracts and to all related subcontracts.

1.  In the performance of this contract the contractor shall comply with all applicable Federal, State, and local laws governing safety, health, and sanitation (23 CFR 635). The contractor shall provide all safeguards, safety devices and protective equipment and take any other needed actions as it determines, or as the contracting officer may determine, to be reasonably necessary to protect the life and health of employees on the job and the safety of the public and to protect property in connection with the performance of the work covered by the contract.

2.  It is a condition of this contract, and shall be made a condition of each subcontract, which the contractor enters into pursuant to this contract, that the contractor and any subcontractor shall not permit any employee, in performance of the contract, to work in surroundings or under conditions which are unsanitary, hazardous or dangerous to his/her health or safety, as determined under construction safety and health standards (29 CFR 1926) promulgated by the Secretary of Labor, in accordance with Section 107 of the Contract Work Hours and Safety Standards Act (40 U.S.C. 3704).

3.  Pursuant to 29 CFR 1926.3, it is a condition of this contract that the Secretary of Labor or authorized representative thereof, shall have right of entry to any site of contract performance to inspect or investigate the matter of compliance with the construction safety and health standards and to carry out the duties of the Secretary under Section 107 of the Contract Work Hours and Safety Standards Act (40 U.S.C.3704).

VIII.  FALSE STATEMENTS CONCERNING HIGHWAY PROJECTS

This provision is applicable to all Federal-aid construction contracts and to all related subcontracts.

In order to assure high quality and durable construction in conformity with approved plans and specifications and a high degree of reliability on statements and representations made by engineers, contractors, suppliers, and workers on Federal-aid highway projects, it is essential that all persons concerned with the project perform their functions as carefully, thoroughly, and honestly as possible.  Willful falsification, distortion, or misrepresentation with respect to any facts related to the project is a violation of Federal law.  To prevent any misunderstanding regarding the seriousness of these and similar acts, Form FHWA-1022 shall be posted on each Federal-aid highway project (23 CFR 635) in one or more places where it is readily available to all persons concerned with the project:

18 U.S.C. 1020 reads as follows:

"Whoever, being an officer, agent, or employee of the United States, or of any State or Territory, or whoever, whether a person, association, firm, or corporation, knowingly makes any false statement, false representation, or false report as to the character, quality, quantity, or cost of the material used or to be used, or the quantity or quality of the work performed or to be performed, or the cost thereof in connection with the submission of plans, maps, specifications, contracts, or costs of construction on any highway or related project submitted for approval to the Secretary of Transportation; or

Whoever knowingly makes any false statement, false representation, false report or false claim with respect to the character, quality, quantity, or cost of any work performed or to be performed, or materials furnished or to be furnished, in connection with the construction of any highway or related project approved by the Secretary of Transportation; or

Whoever knowingly makes any false statement or false representation as to material fact in any statement, certificate, or report submitted pursuant to provisions of the Federal-aid Roads Act approved July 1, 1916, (39 Stat. 355), as amended and supplemented;

Shall be fined under this title or imprisoned not more than 5 years or both."

IX.  IMPLEMENTATION OF CLEAN AIR ACT AND FEDERAL WATER POLLUTION CONTROL ACT

This provision is applicable to all Federal-aid construction contracts and to all related subcontracts.

By submission of this bid/proposal or the execution of this contract, or subcontract, as appropriate, the bidder, proposer, Federal-aid construction contractor, or subcontractor, as appropriate, will be deemed to have stipulated as follows:

1. That any person who is or will be utilized in the performance of this contract is not prohibited from receiving an award due to a violation of Section 508 of the Clean Water Act or Section 306 of the Clean Air Act.

2. That the contractor agrees to include or cause to be included the requirements of paragraph (1) of this Section X in every subcontract, and further agrees to take such action as the contracting agency may direct as a means of enforcing such requirements.

X.  CERTIFICATION REGARDING DEBARMENT, SUSPENSION, INELIGIBILITY AND VOLUNTARY EXCLUSION

This provision is applicable to all Federal-aid construction contracts, design-build contracts, subcontracts, lower-tier subcontracts, purchase orders, lease agreements, consultant contracts or any other covered transaction requiring FHWA approval or that is estimated to cost $25,000 or more –  as defined in 2 CFR Parts 180 and 1200.

1.  Instructions for Certification – First Tier Participants:

a.  By signing and submitting this proposal, the prospective first tier participant is providing the certification set out below.

b.  The inability of a person to provide the certification set out below will not necessarily result in denial of participation in this covered transaction. The prospective first tier participant shall submit an explanation of why it cannot provide the certification set out below. The certification or explanation will be considered in connection with the department or agency's determination whether to enter into this transaction. However, failure of the prospective first tier participant to furnish a certification or an explanation shall disqualify such a person from participation in this transaction.

c.  The certification in this clause is a material representation of fact upon which reliance was placed when the contracting agency determined to enter into this transaction. If it is later determined that the prospective participant knowingly rendered an erroneous certification, in addition to other remedies available to the Federal Government, the contracting agency may terminate this transaction for cause of default.

d.  The prospective first tier participant shall provide immediate written notice to the contracting agency to whom this proposal is submitted if any time the prospective first tier participant learns that its certification was erroneous when submitted or has become erroneous by reason of changed circumstances.

e.  The terms "covered transaction," "debarred," "suspended," "ineligible," "participant," "person,"  "principal," and "voluntarily excluded," as used in this clause, are defined in 2 CFR Parts 180 and 1200.  “First Tier Covered Transactions” refers to any covered transaction between a grantee or subgrantee of Federal funds and a participant (such as the prime or general contract).  “Lower Tier Covered Transactions” refers to any covered transaction under a First Tier Covered Transaction (such as subcontracts).  “First Tier Participant” refers to the participant who has entered into a covered transaction with a grantee or subgrantee of Federal funds (such as the prime or general contractor).  “Lower Tier Participant” refers any participant who has entered into a covered transaction with a First Tier Participant or other Lower Tier Participants (such as subcontractors and suppliers).

f.  The prospective first tier participant agrees by submitting this proposal that, should the proposed covered transaction be entered into, it shall not knowingly enter into any lower tier covered transaction with a person who is debarred, suspended, declared ineligible, or voluntarily excluded from participation in this covered transaction, unless authorized by the department or agency entering into this transaction.

g.  The prospective first tier participant further agrees by submitting this proposal that it will include the clause titled "Certification Regarding Debarment, Suspension, Ineligibility and Voluntary Exclusion-Lower Tier Covered Transactions," provided by the department or contracting agency, entering into this covered transaction, without modification, in all lower tier covered transactions and in all solicitations for lower tier covered transactions exceeding the $25,000 threshold.

h.  A participant in a covered transaction may rely upon a certification of a prospective participant in a lower tier covered transaction that is not debarred, suspended, ineligible, or voluntarily excluded from the covered transaction, unless it knows that the certification is erroneous.  A participant is responsible for ensuring that its principals are not suspended, debarred, or otherwise ineligible to participate in covered transactions.  To verify the eligibility of its principals, as well as the eligibility of any lower tier prospective participants, each participant may, but is not required to, check the Excluded Parties List System website (https://www.epls.gov/), which is compiled by the General Services Administration.

i.  Nothing contained in the foregoing shall be construed to require the establishment of a system of records in order to render in good faith the certification required by this clause. The knowledge and information of the prospective participant is not required to exceed that which is normally possessed by a prudent person in the ordinary course of business dealings.

j.  Except for transactions authorized under paragraph (f) of these instructions, if a participant in a covered transaction knowingly enters into a lower tier covered transaction with a person who is suspended, debarred, ineligible, or voluntarily excluded from participation in this transaction, in addition to other remedies available to the Federal Government, the department or agency may terminate this transaction for cause or default.

* * * * *

2.  Certification Regarding Debarment, Suspension, Ineligibility and Voluntary Exclusion – First Tier Participants:

a.  The prospective first tier participant certifies to the best of its knowledge and belief, that it and its principals:

(1)  Are not presently debarred, suspended, proposed for debarment, declared ineligible, or voluntarily excluded from participating in covered transactions by any Federal department or agency;

(2)  Have not within a three-year period preceding this proposal been convicted of or had a civil judgment rendered against them for commission of fraud or a criminal offense in connection with obtaining, attempting to obtain, or performing a public (Federal, State or local) transaction or contract under a public transaction; violation of Federal or State antitrust statutes or commission of embezzlement, theft, forgery, bribery, falsification or destruction of records, making false statements, or receiving stolen property;

(3)  Are not presently indicted for or otherwise criminally or civilly charged by a governmental entity (Federal, State or local) with commission of any of the offenses enumerated in paragraph (a)(2) of this certification; and

(4)  Have not within a three-year period preceding this application/proposal had one or more public transactions (Federal, State or local) terminated for cause or default.

b.  Where the prospective participant is unable to certify to any of the statements in this certification, such prospective participant shall attach an explanation to this proposal.

2.  Instructions for Certification - Lower Tier Participants:

(Applicable to all subcontracts, purchase orders and other lower tier transactions requiring prior FHWA approval or estimated to cost $25,000 or more - 2 CFR Parts 180 and 1200)

a. By signing and submitting this proposal, the prospective lower tier is providing the certification set out below.

b. The certification in this clause is a material representation of fact upon which reliance was placed when this transaction was entered into. If it is later determined that the prospective lower tier participant knowingly rendered an erroneous certification, in addition to other remedies available to the Federal Government, the department, or agency with which this transaction originated may pursue available remedies, including suspension and/or debarment.

c. The prospective lower tier participant shall provide immediate written notice to the person to which this proposal is submitted if at any time the prospective lower tier participant learns that its certification was erroneous by reason of changed circumstances.

d. The terms "covered transaction," "debarred," "suspended," "ineligible," "participant," "person," "principal," and "voluntarily excluded," as used in this clause, are defined in 2 CFR Parts 180 and 1200.  You may contact the person to which this proposal is submitted for assistance in obtaining a copy of those regulations.  “First Tier Covered Transactions” refers to any covered transaction between a grantee or subgrantee of Federal funds and a participant (such as the prime or general contract).  “Lower Tier Covered Transactions” refers to any covered transaction under a First Tier Covered Transaction (such as subcontracts).  “First Tier Participant” refers to the participant who has entered into a covered transaction with a grantee or subgrantee of Federal funds (such as the prime or general contractor).  “Lower Tier Participant” refers any participant who has entered into a covered transaction with a First Tier Participant or other Lower Tier Participants (such as subcontractors and suppliers).

e. The prospective lower tier participant agrees by submitting this proposal that, should the proposed covered transaction be entered into, it shall not knowingly enter into any lower tier covered transaction with a person who is debarred, suspended, declared ineligible, or voluntarily excluded from participation in this covered transaction, unless authorized by the department or agency with which this transaction originated.

f. The prospective lower tier participant further agrees by submitting this proposal that it will include this clause titled "Certification Regarding Debarment, Suspension, Ineligibility and Voluntary Exclusion-Lower Tier Covered Transaction," without modification, in all lower tier covered transactions and in all solicitations for lower tier covered transactions exceeding the $25,000 threshold.

g. A participant in a covered transaction may rely upon a certification of a prospective participant in a lower tier covered transaction that is not debarred, suspended, ineligible, or voluntarily excluded from the covered transaction, unless it knows that the certification is erroneous. A participant is responsible for ensuring that its principals are not suspended, debarred, or otherwise ineligible to participate in covered transactions.  To verify the eligibility of its principals, as well as the eligibility of any lower tier prospective participants, each participant may, but is not required to, check the Excluded Parties List System website (https://www.epls.gov/), which is compiled by the General Services Administration.

h.  Nothing contained in the foregoing shall be construed to require establishment of a system of records in order to render in good faith the certification required by this clause. The knowledge and information of participant is not required to exceed that which is normally possessed by a prudent person in the ordinary course of business dealings.

i.  Except for transactions authorized under paragraph e of these instructions, if a participant in a covered transaction knowingly enters into a lower tier covered transaction with a person who is suspended, debarred, ineligible, or voluntarily excluded from participation in this transaction, in addition to other remedies available to the Federal Government, the department or agency with which this transaction originated may pursue available remedies, including suspension and/or debarment.

* * * * *

Certification Regarding Debarment, Suspension, Ineligibility and Voluntary Exclusion--Lower Tier Participants:

1. The prospective lower tier participant certifies, by submission of this proposal, that neither it nor its principals is presently debarred, suspended, proposed for debarment, declared ineligible, or voluntarily excluded from participating in covered transactions by any Federal department or agency.

2. Where the prospective lower tier participant is unable to certify to any of the statements in this certification, such prospective participant shall attach an explanation to this proposal.

* * * * *

XI. CERTIFICATION REGARDING USE OF CONTRACT FUNDS FOR LOBBYING

This provision is applicable to all Federal-aid construction contracts and to all related subcontracts which exceed $100,000 (49 CFR 20).

1.  The prospective participant certifies, by signing and submitting this bid or proposal, to the best of his or her knowledge and belief, that:

a.  No Federal appropriated funds have been paid or will be paid, by or on behalf of the undersigned, to any person for influencing or attempting to influence an officer or employee of any Federal agency, a Member of Congress, an officer or employee of Congress, or an employee of a Member of Congress in connection with the awarding of any Federal contract, the making of any Federal grant, the making of any Federal loan, the entering into of any cooperative agreement, and the extension, continuation, renewal, amendment, or modification of any Federal contract, grant, loan, or cooperative agreement.

b.  If any funds other than Federal appropriated funds have been paid or will be paid to any person for influencing or attempting to influence an officer or employee of any Federal agency, a Member of Congress, an officer or employee of Congress, or an employee of a Member of Congress in connection with this Federal contract, grant, loan, or cooperative agreement, the undersigned shall complete and submit Standard Form-LLL, "Disclosure Form to Report Lobbying," in accordance with its instructions.

2.  This certification is a material representation of fact upon which reliance was placed when this transaction was made or entered into.  Submission of this certification is a prerequisite for making or entering into this transaction imposed by 31 U.S.C. 1352.  Any person who fails to file the required certification shall be subject to a civil penalty of not less than $10,000 and not more than $100,000 for each such failure.

3.  The prospective participant also agrees by submitting its bid or proposal that the participant shall require that the language of this certification be included in all lower tier subcontracts, which exceed $100,000 and that all such recipients shall certify and disclose accordingly.

ATTACHMENT A - EMPLOYMENT AND MATERIALS PREFERENCE FOR APPALACHIAN DEVELOPMENT HIGHWAY SYSTEM OR APPALACHIAN LOCAL ACCESS ROAD CONTRACTS

This provision is applicable to all Federal-aid projects funded under the Appalachian Regional Development Act of 1965.

1.  During the performance of this contract, the contractor undertaking to do work which is, or reasonably may be, done as on-site work, shall give preference to qualified persons who regularly reside in the labor area as designated by the DOL wherein the contract work is situated, or the subregion, or the Appalachian counties of the State wherein the contract work is situated, except:

a. To the extent that qualified persons regularly residing in the area are not available.

b. For the reasonable needs of the contractor to employ supervisory or specially experienced personnel necessary to assure an efficient execution of the contract work.

c. For the obligation of the contractor to offer employment to present or former employees as the result of a lawful collective bargaining contract, provided that the number of nonresident persons employed under this subparagraph (1c) shall not exceed 20 percent of the total number of employees employed by the contractor on the contract work, except as provided in subparagraph (4) below.

2.  The contractor shall place a job order with the State Employment Service indicating (a) the classifications of the laborers, mechanics and other employees required to perform the contract work, (b) the number of employees required in each classification, (c) the date on which the participant estimates such employees will be required, and (d) any other pertinent information required by the State Employment Service to complete the job order form.  The job order may be placed with the State Employment Service in writing or by telephone.  If during the course of the contract work, the information submitted by the contractor in the original job order is substantially modified, the participant shall promptly notify the State Employment Service.

3.  The contractor shall give full consideration to all qualified job applicants referred to him by the State Employment Service.  The contractor is not required to grant employment to any job applicants who, in his opinion, are not qualified to perform the classification of work required.

4.  If, within one week following the placing of a job order by the contractor with the State Employment Service, the State Employment Service is unable to refer any qualified job applicants to the contractor, or less than the number requested, the State Employment Service will forward a certificate to the contractor indicating the unavailability of applicants.  Such certificate shall be made a part of the contractor's permanent project records.  Upon receipt of this certificate, the contractor may employ persons who do not normally reside in the labor area to fill positions covered by the certificate, notwithstanding the provisions of subparagraph (1c) above.

5.  The provisions of 23 CFR 633.207(e) allow the contracting agency to provide a contractual preference for the use of mineral resource materials native to the Appalachian region.

6.  The contractor shall include the provisions of Sections 1 through 4 of this Attachment A in every subcontract for work which is, or reasonably may be, done as on-site work.

2**************************************************************************************2

FHWA Attachment No. 2

Standard Federal Equal Employment Opportunity Construction Contract Specifications (Executive Order 11246)

- As used in these Specifications:

- Covered area means the geographical area in which the Project is located.

- Director means Director, Office of Federal Contract Compliance Programs, United States Department of Labor or any person to whom the Director delegates authority.

- Employer identification number means the Federal Social Security number used on the Employer’s Quarterly Federal Tax Return, US Treasury Department Form 941.

- Minority includes:

- Black (a person having origins in any of the black African racial groups not of Hispanic origin);

- Hispanic (a person of Mexican, Puerto Rican, Cuban, Central or South American or other Spanish culture or origin, regardless of race);

- Asian and Pacific Islander (a person having originals in any of the original peoples of the Far East, Southeast Asia, the Indian Subcontinent, or the Pacific Islands); and

- American Indian or Alaskan Native (a person having origins in any of the original peoples of North America and maintaining identifiable tribal affiliations through membership and participating or community identification).

- Whenever the Contractor, or any subcontractor at any tier, subcontracts a portion of the work involving any construction trade, it shall physically include in each subcontract in excess of $10,000 the provisions of these specifications and the Notice which contains the applicable goals for minority and female participation and which is set forth in the solicitations from which this contract resulted.

- The Contractor shall implement the specific affirmative action standards provided in paragraphs 6a through p of these specifications. The goals set forth in the solicitation from which this contract resulted are expressed as percentages of the total hours of employment and training of minority and female utilization the Contractor should reasonably be able to achieve in each construction trade in which it has employees in the covered area. Covered Construction Contractors performing construction work in geographical areas where they do not have a Federal or federally assisted construction contract shall apply the minority and female goals established for the geographical area where the work is being performed. The Contractor is expected to make substantially uniform progress in meeting its goals in each craft during the period specified.

- Neither the provisions of any collective bargaining agreement nor the failure by a union with whom the Contractor has a collective bargaining agreement to refer either minorities or women shall excuse the Contractor’s obligations under these Specifications, Executive Order 111246, or the regulations promulgated pursuant thereto.

- In order for the nonworking training hours of apprentices and trainees to be counted in meeting the goals, such apprentices and trainees must be employed by the Contractor during the training period, and the Contractor must have made a commitment to employ the apprentices and trainees at the completion of their training, subject to the availability of employment opportunities. Trainees must be trained pursuant to training programs approved by the US Department of Labor.

- The Contractor shall take specific affirmative action to ensure equal employment opportunity. The evaluation of the Contractor’s compliance with these specifications shall be based upon its effort to achieve maximum results from its actions.  The Contractor shall document these efforts fully, and shall implement affirmative action steps at least as extensive as the following:

- Ensure and maintain a working environment free of harassment, intimidation, and coercion at all sites in all facilities at which the Contractor’s employees are assigned to work. The Contractor, where possible, will assign two or more women to each construction project. The contractor shall specifically ensure that all foreman, superintendents, and other on-site supervisory personnel are aware of and carry out the Contractor’s obligation to maintain such a working environment with specific attention to minority or female individual working at such sites or in such facilities.

- Establish and maintain a current list of minority and female recruitment sources, provide written notification to minority and female recruitment sources and to community organizations when the Contractor or its unions have employment opportunities available, and maintain a record of the organizations’ responses.

- Maintain a current file of the names, addresses and telephone numbers of each minority and female off-the-street applicant and minority or female referral from a union, a recruitment source or community and of what action was taken with respect to each such individual. If such individual was sent to the union hiring hall for referral and was not referred back to the Contractor by the union or, if referred back to the Contractor, this shall be documented in the file with the reason therefore, along with whatever additional actions the Contractor may have taken.

- Provide immediate written notification to the Director when the union or unions with which the Contractor has a collective bargaining agreement has not referred to the contractor a minority person or women sent by the Contractor, or when the Contractor has other information that the union referral process has impeded the Contractor’s efforts to meet its obligations.

- Develop on-the-job training opportunities and/or participate in training programs for the area which expressly include minorities and women including upgrading programs and apprenticeship and trainee programs relevant to the Contractor’s employment needs, especially those programs funded or approved by the Department of Labor. The Contractor shall provide notice of these programs to the source compiles under 6b above.

- Disseminate the Contractor’s EEO policy by providing notice of the policy to unions and training programs and requesting their cooperation in assisting the Contractor in meeting its EEO obligations by including it in any policy manual and collective bargaining agreement; by publicizing it in the company newspaper, annual report, etc; by specific review of the policy with all management personnel and with all minority and female employees at least once a year; and by posting the company EEO policy on bulletin boards accessible to all employees at each location where construction work is performed.

- Review, at least annually, the company’s EEO policy and affirmative action obligations under these specifications with all employees having any responsibility for hiring, assignment, layoff, termination or other employment decisions including specific review of these items with on site supervisory personnel such as Superintendents, General Foremen, etc., prior to the initiation of construction work at any job site. A written record shall be made and maintained identifying the time and place of these meetings, persons attending, subject matter discussed, and disposition of the subject matter.

- Disseminate the Contractor’s EEO policy externally by including it in any advertising in the news media, specifically including minority and female news media, and providing written notification to and discussing the Contractor’s EEO policy with other Contractors and Subcontractors with whom the Contractor does or anticipates doing business.

- Direct its recruitment efforts, both oral and written, to minority, female and community organizations, to schools with minority and female students and to minority and female recruitment and training organizations serving the Contractor’s recruitment area and employment needs. Not later than one month prior to the date for the acceptance of applications for apprenticeship or other training by any recruitment source, the Contractor shall send written notification to organizations such as the above, describing the openings, screening procedures, and tests to be used in the selection process.

- Encourage present minority and female employees to recruit other minority persons and females and, where reasonable, provide after school, summer and vacation employment to minority and female youth both on the site and in other areas of a Contractor’s work force.

- Validate all tests and other selection requirements where there is an obligation to do so under 41 CFR Part 60-3.

- Conduct, at least annually, an inventory and evaluation at least of all minority and female personnel for promotional opportunities and encourage these employees to seek or to prepare for, through appropriate training, etc., such opportunities.

- Ensure that seniority practices, job classifications, work assignments and other personnel practices do not have a discriminatory effect by continually monitoring all personnel and employment related activities to ensure that the EEO policy and the Contractor’s obligations under these specifications are being carried out.

- Ensure that all facilities and company activities are nonsegregated except that separate or single-user toilet and necessary changing facilities shall be provided to assure privacy between the sexes.

- Document and maintain a record of all solicitations of offers for subcontracts from minority and female construction Contraction and suppliers, including circulation of solicitations to minority and female contractor associations and other business associations.

- Conduct a review, at least annually, of all supervisors’ adherence to and performance under the Contractor’s EEO policies and affirmative action obligations.

- Contractors are encouraged to participate in voluntary associations which assist in fulfilling one or more of their affirmative action obligations (6a through p). The efforts of a Contractor association, joint contractor union, Contractor-Community, or other similar group of which the Contractor is a member and participant may be asserted as fulfilling any one or more of its obligations under 6A through p of these Specifications provided that the Contractor actively participates in the group, make every effort to assure that the group has a positive impact on the employment of minorities and females in the industry, ensures that the concrete benefits of the program are reflected in the Contractor’s minority and female work force participation, make a good faith effort to meet its individual goals and can provide access to documentation which demonstrates the effectiveness of actions taken on behalf of the Contractor. The obligation to comply, however, is the Contractor’s and failure of such a group to fulfill an obligation shall not be a defense for the Contractor’s noncompliance.

- A single goal for minorities and a separate single goal for women have been established. The Contractor, however, is required to provide equal employment opportunity and to take affirmative action for all minority groups, both male and female, and all women both minority and nonminority. Consequently, the Contractor may be in violation of the Executive Order if a particular group is employed in a substantially disparate manner (for example, even though the Contractor has achieved its goals for women generally, the Contractor may be in violation of the Executive Order if a specific minority group of women is underutilized).

- The Contractor shall not use the goals or affirmative action standards to discriminate against any person because of race, color, religion, sex, or national origin.

- The Contractor shall not enter any Subcontract with any person or firm debarred from Government contracts pursuant to Executive Order 11246.

- The Contractor shall carry out such sanctions and penalties for violation of these specifications and of the Equal Opportunity Clause, including suspensions, termination and cancellation of existing subcontracts as may be imposed or ordered pursuant to Executive Order 11246, as amended, and its implementing regulations, by the Office of Federal Contract Compliance Programs. Any Contractor who fails to carry out such sanctions and penalties shall be in violation of these specifications and Executive Order 11246 as amended.

- The Contractor, in fulfilling its obligations under these specifications, shall implement specific affirmative action steps, at least as extensive as those standards prescribed in paragraph 6 of these specifications, so as to achieve maximum results from its efforts to ensure equal employment opportunity. If the Contractor fails to comply with the requirements of the Executive Order, the implementing regulations or these specifications, the Director shall proceed in accordance with 41 CFR 60-4.8.

- The Contractor shall designate a responsible official to monitor all employment related activity to ensure that the company EEO policy is being carried out, to submit reports relating to the provisions hereof as may be required by the Government and to keep records.  Records shall at least include for each employee the name, address, telephone number, construction trade, union affiliation if any, employee identification number when assigned, social security number, race, sex, status (such as mechanic, apprentice, trainee, helper, or laborer), dates of changes in status, hours worked per week in the indicated trade, rate of pay, and locations at which the work was performed. Records shall be maintained in an easily understandable and retrievable form; however, to the degree that existing records satisfy this requirement, contractors shall not be required to maintain separate records.

- Nothing herein provided shall be construed as a limitation upon the application of other laws which establish different standards of compliance or upon the application of requirements for the hiring of local or other area residents (such as those under the Public Works Employment Act of 1977 and the community Development Block Grant Program).

- Noncompliance by the Contractor with the requirements of the Affirmative Action Program for Equal Employment Opportunity may be cause for delaying or withholding monthly and final payments pending corrective and appropriate measures by the Contractor to the satisfaction of the Department.

FHWA Attachment No. 3

NOTICE OF REQUIREMENT FOR AFFIRMATIVE ACTION TO ENSURE EQUAL OPPORTUNITY (EXECUTIVE ORDER 11246)

- The goals for minority and female participation, in the covered area, expressed in percentage terms for the Contractor’s aggregate work force in each trade, on all construction work are as shown on Page 2.

These goals are applicable to all the Contractor’s construction work (whether or not it is Federal or federally assisted) performed in the covered area. If the Contractor performs construction work in a geographical area located outside of the covered area, it shall apply the goals established for such geographical area where the work is actually performed. With regard to this second area, the Contractor also is subject to the goals for both its federally involved and nonfederally involved construction.

The Contractor’s compliance with the Executive Order and the regulations in 41 CFR Part 60-4 shall be based on its implementation of the Equal Opportunity Clause, specific affirmative action obligations required by the specifications set forth in 41 CFR 60-4. (3) a, and its efforts to meet the goals. The hours of minority and female employment and training must be substantially uniform throughout the length of the contract, and in each trade, and the Contractor shall make a good faith effort to employ minorities and women evenly on each of its projects. The transfer of minority or female employees or trainees from Contractor to Contractor or from project to project for sole purpose of meeting the Contractor’s goals shall be a violation of the contract, the Executive Order and the regulations in 41 CFR Part 60-4. Compliance with the goals will be measured against the total work hours performed.

- The Contractor will provide the Department with written notification in triplicate within 10 working days of award of any construction subcontract in excess of $10,000 at any tier for construction work under the contract resulting from this solicitation. The notification will list the name, address and telephone number of the subcontractor; employer identification number of the subcontractor; estimated dollar amount of the subcontract; estimated starting and completion dates of the subcontract; and the geographical area in which the contract is to be performed.

- As used in this Notice and in the Contract resulting from this solicitation the covered area is the county or counties in which the Project is located.

- If a project is located in more than one county, the minority work hours goal, only, will be determined by the county which serves as the primary source of hiring or, if workers are obtained almost equally from one or more counties, the single minority goal will be the average of the affected county goals.

Work Hour Goals In Each Trade For Minority And Female Participation

| COUNTY | MINORITY PARTICIPATION | FEMALE PARTICIPATION |
| --- | --- | --- |
|  | PERCENT | PERCENT |
| Atlantic | 18.2 | 6.9 |
| Bergen | 15 | 6.9 |
| Burlington | 17.3 | 6.9 |
| Camden | 17.3 | 6.9 |
| Cape May | 14.5 | 6.9 |
| Cumberland | 16 | 6.9 |
| Essex | 17.3 | 6.9 |
| Gloucester | 17.3 | 6.9 |
| Hudson | 12.8 | 6.9 |
| Hunterdon | 17 | 6.9 |
| Mercer | 16.4 | 6.9 |
| Middlesex | 15 | 6.9 |
| Monmouth | 9.5 | 6.9 |
| Morris | 17.3 | 6.9 |
| Ocean | 17 | 6.9 |
| Passaic | 12.9 | 6.9 |
| Salem | 12.3 | 6.9 |
| Somerset | 17.3 | 6.9 |
| Sussex | 17 | 6.9 |
| Union | 17.3 | 6.9 |
| Warren | 1.6 | 6.9 |

FHWA Attachment No. 4

State Of New Jersey Equal Employment Opportunity

For Contracts Funded By FHWA

The parties to this Agreement do hereby agree that the provisions of N.J.S.A. 10:2-1 through 10:2-4 and N.J.S.A. 10:5-31 et seq (PL 1975, c 127, as amended and supplemented) dealing with discrimination in employment on public contracts, and the rules and regulations promulgated pursuant thereunto, are hereby made a part of this contract and are binding upon them.

During the performance of this contract, the Contractor agrees as follows:

a.	The Contractor or subcontractor, where applicable, will not discriminate against any employee or applicant for employment because of age, race, creed, color, national origin, ancestry, marital status or sex. The Contractor will take affirmative action to ensure that such applicants are recruited and employed, and that employees are treated during employment, without regard to their age, race, creed, color, national origin, ancestry, marital status or sex. Such action shall include but not be limited to the following: employment, upgrading, demotion, or transfer, recruitment or recruitment advertising; layoff or termination; rates of pay or other forms of compensation; and selection for training, including apprenticeship. The Contractor agrees to post in conspicuous places, available to employees and applicants for employment, notices to be provided by the Division of Civil Rights/Affirmative Action setting forth provisions of this nondiscrimination clause;

b.	The Contractor or subcontractor, where applicable will, in all solicitations or advertisements for employees placed by or on behalf of the Contractor, state that all qualified applicants will receive consideration for employment without regard to age, race, creed, color, national origin, ancestry, marital status or sex;

c.	The Contractor or subcontractor, where applicable, will send to each labor union or representative of workers with which it has a collective bargaining agreement or other contract or understanding, a notice, to be provided by the Division of Civil Rights/Affirmative Action, advising the labor union or workers’ representative of the contractor’s commitments under this act and shall post copies of the notice in conspicuous places available to employees and applicants for employment.

d.	In the hiring of persons for the performance of work under this contract or any subcontract hereunder, or for the procurement, manufacture, assembling or furnishing of any such materials, equipment, supplies or services to be acquired under this contract, no contractor, nor any person acting on behalf of such contractor or subcontractor, shall, by reason of race, creed, color, national origin, ancestry, marital status, gender identity or expression, affectional or sexual orientation or sex, discriminate against any person who is qualified and available to perform the work to which the employment relates;

e.	No contractor, subcontractor, nor any person on his behalf shall, in any manner, discriminate against or intimidate any employee engaged in the performance of work under this contract or any subcontract hereunder, or engaged in the procurement, manufacture, assembling or furnishing of any such materials, equipment, supplies or services to be acquired under such contract, on account of race, creed, color, national origin, ancestry, marital status, gender identity or expression, affectional or sexual orientation or sex;

f.	There may be deducted from the amount payable to the contractor by the contracting public agency, under this contract, a penalty of $50.00 for each person for each calendar day during which such person is discriminated against or intimidated in violation of the provisions of the contract; and

g.	This contract may be canceled or terminated by the contracting public agency, and all money due or to become due hereunder may be forfeited, for any violation of this section of the contract occurring after notice to the contractor from the contracting public agency of any prior violation of this section of the contract.

The notices referred to in paragraphs a and c may be obtained at the preconstruction conference.

upon receiving the information, fill in the blank (GOALS FOR THIS PROJECT) on the appropriate FHWA attachment.

(FHWA ATTAchment NO. 5 for ESBE or FHWA attachment NO. 5 for DBE)

delete the inappropriate fhwa ATTACHMENT

FHWA Attachment No. 5

EMERGING SMALL BUSINESS ENTERPRISE UTILIZATION ATTACHMENT

FHWA FUNDED CONTRACTS

I	UTILIZATION OF EMERGING SMALL BUSINESS ENTERPRISE (ESBE) AS CONTRACTORS, MATERIALS SUPPLIERS AND EQUIPMENT LESSORS.

The New Jersey Department of Transportation (NJDOT) advises each contractor or subcontractor that failure to carry out the requirements set forth in this attachment shall constitute a breach of contract and, after the notification of the applicable federal agency, may result in termination of the agreement or contract by the Department or such remedy as the Department deems appropriate. Requirements set forth in this section shall also be physically included in all subcontracts in accordance with USDOT requirements.

II	POLICY.

It is the policy of the NJDOT that Emerging Small Business Enterprises (ESBE), as defined in Section IV, Part B below, shall have an opportunity to participate in the performance of contracts financed in whole or in part with federal funds. In furtherance of this policy the NJDOT has established an Emerging Small Business Enterprise Program. This program is designed to promote participation and shared economic opportunity by smaller firms who qualify as ESBE’s in NJDOT construction contracts and is undertaken pursuant to the authority contained in 23 CFR Part 26.

III.	CONTRACTOR’S ESBE OBLIGATION.

The contractor agrees to ensure that ESBE’s, as defined in Section IV, Part B below, have an equal opportunity to participate in the performance of contracts and subcontracts financed in whole or in part with federal funds. In performing work under this agreement with the NJDOT, the contractor shall take all necessary and reasonable steps in accordance with the provisions of this attachment to ensure that ESBE’s have the maximum opportunity to compete for and perform contracts. The contractor shall not discriminate on the basis of race, color, national origin, or sex in the performance of any contract obligation including, but not limited to, its performance of its obligations under this ESBE attachment.

IV.	GOALS FOR THIS PROJECT.

A.	This project includes a goal of awarding       percent of the total contract value to subcontractors, equipment lessors and/or material suppliers, which qualify as ESBE’s.

1.	Failure to meet the minimum goal placed on this project, or to provide a good faith effort to meet the minimum goal, may be grounds for rejection of the bid as being non-responsive.

2.	As a source of information only, an ESBE Directory is available from the Division of Civil Rights/Affirmative Action. Use of this listing does not relieve the contractor of its responsibility to seek out ESBE’s not listed, prior to bid. If a contractor proposes to use an ESBE contractor not listed in the ESBE Directory, the proposed ESBE firm must submit a completed certification application to the Division of Civil Rights/Affirmative Action, fifteen (15) days prior to bid date.

B.	DEFINITIONS.

1.	Emerging Small Business Enterprise is defined as: a for-profit business concern classified as a small business pursuant to the appropriate Small Business Administration regulations, and which is owned and controlled by individuals who do not exceed the personal net worth criteria ($1.32 Million) established in 49 CFR Part 26.

2.	Owned and Controlled is defined as: that at least 51% of the ownership interests as well as the management and daily business operations of the firm reside in individuals whose personal net worth does not exceed the requirements established in 49 CFR, Part 26.

V.	COUNTING ESBE PARTICIPATION.

A.	Each ESBE is subject to a certification procedure to ensure its ESBE eligibility status prior to the award of contract. In order to facilitate this process it is advisable for the bidder to furnish names of proposed ESBE’s to the Department 15 days before bid opening. Once a firm is determined to be a bona fide ESBE by the Division of Civil Rights/Affirmative Action, the total dollar value of the contract awarded to the ESBE is counted toward the applicable goal.

B.	The contractor may count toward its ESBE goal only expenditures to ESBE’s that perform a commercially useful function in the work of a contract. An ESBE is considered to perform a commercially useful function when it is responsible for execution of a distinct element of the work of a contract and carrying out its responsibility by actually performing, managing and supervising the work involved. To determine whether an ESBE is performing a commercially useful function, the contractor shall evaluate the amount of work contracted, industry practice and other relevant factors.

C.	If a ESBE does not perform or exercise responsibility for at least 30 percent of the total cost of its contract with its own work force, or the ESBE subcontracts a greater portion of the work of a contract than would be expected on the basis of normal industry practice for the type of work involved, you must presume that it is not performing a commercially useful function.

D.	If the prime contractor is a certified ESBE, payments made to the contractor for work performed by the contractor will be applied toward the ESBE goal. Payments made to the prime contractor for work performed by non-ESBE’s will not be applied toward the ESBE goal.

E.	The prime contractor may count 60 percent of its expenditures to ESBE suppliers that are not manufacturers, provided that the ESBE supplier performs a commercially useful function in the supply process. The contractor may count 100% of its expenditure to ESBE suppliers who are also manufacturers. Manufacturers receive 100% credit toward the ESBE goal.

VI	GOOD FAITH EFFORT.

To demonstrate sufficient reasonable efforts to meet the ESBE contract goals, a bidder shall document the steps it has taken to obtain ESBE participation, including but not limited to the following:

A.	Attendance at a pre-bid meeting, if any, scheduled by the Department to inform ESBE’s of prime contracting and subcontracting opportunities under a given solicitation.

B.	Advertisement in general circulation media, trade association publications, and small business publications for at least 20 days before bids are due. If 20 days are not available, publication for a shorter reasonable time is acceptable.

C.	Written notification to ESBE’s that their interest in the contract is solicited;

D.	Efforts made to select portions of the work proposed to be performed by ESBE’s in order to increase the likelihood of achieving the stated goal;

E.	Efforts made to negotiate with ESBE’s for specific bids including at a minimum:

1.	The names, addresses and telephone numbers of ESBE’s that were contacted;

2.	A description of the information provided to ESBE’s regarding the plans and specifications for the work to be performed; and

3.	A statement of why additional agreements with ESBE’s were not reached;

F.	Information regarding each ESBE the bidder contacted and rejected as unqualified and the reasons for the bidder’s conclusion;

G.	Efforts made to assist the ESBE in obtaining bonding or insurance required by the bidder or the department.

NOTE:	If the Division of Civil Rights/Affirmative Action determines that the apparent successful low bidder has failed to meet the requirements of this section, the bidder will be afforded the opportunity for an administrative reconsideration of that determination prior to the award or rejection of the contract. As part of the administrative reconsideration process, the bidder will have the opportunity to provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so. NJDOT will send the bidder a written decision on reconsideration, explaining the basis for finding that the bidder did or did not meet the goal or make adequate good faith efforts to do so. The result of the reconsideration process is not administratively appealable to the USDOT.

VII	SUBMISSION OF REQUIRED DOCUMENTS.

The following shall be submitted either with the bid or to the Division of Civil Rights and Affirmative Action no later than seven (7) State business days after the date of receipt of bids.

1.	ESBE Form CR-266F - Schedule of ESBE Participation. List all ESBE’s participating in the contract; listing the scope of work, dollar value and percent of total contract to be performed.

2.	Supplement to ESBE Form CR-266F - A list of all subcontractors who submitted bids or quotes on this project.

3.	Request for Exemption - In the event that the bidder fails to meet the specified goal, they must submit within Seven State business days of the bid, a written request for exemption to the goal. This request must include a written statement addressing Items A through G in Article VI of this attachment in addition to an accounting of the reason(s) why each items in the bid proposal was not subcontracted. Submittal of such request does not imply departmental approval. An assessment of the material will be conducted by the Department’s Division of Civil Rights/Affirmative Action.

4.	The name of the person who is serving as its ESBE Liaison Officer

VIII	ESBE LIAISON OFFICER.

A.	The contractor shall designate an ESBE Liaison Officer who shall be responsible for the administration if its ESBE program in accordance with the requirements of this attachment.

IX	OBLIGATIONS AFTER AWARD OF THE CONTRACT.

If at any time following the award of contract, the contractor intends to sublet any portion(s) of the work under said contract, or intends to purchase material or lease equipment not contemplated during preparation of bids, said contractor shall take the following actions:

1.	Notify the RE, in writing, of the type and approximate value of the work the contractor intends to accomplish by such subcontract, purchase order or lease.

2.	Attempt to obtain a qualified ESBE to perform the work.

3.	Submit the Post-Award ESBE Certification Form to the Regional Supervising Engineer with his application to sublet or prior to purchasing material or leasing equipment. Post Award ESBE forms may be obtained from the RE.

X	CONSENT BY DEPARTMENT TO SUBLETTING.

The Department will not approve any subcontract proposed by the Contractor unless and until said contractor has complied with the terms of this attachment.

XI	SELECTION AND RETENTION OF SUBCONTRACTORS.

A.	The contractor is further obligated to provide the RE with a listing of firms, organizations or enterprises solicited and those utilized as subcontractors on the proposed project. Such listing shall clearly delineate which firms are classified as an ESBE.

B.	The contractor shall identify all efforts it made to identify and retain an ESBE as a substitution subcontractor when the arrangements with the original ESBE proved unsuccessful shall be submitted in writing to the Department’s ESBE Coordinator for approval. Work in the category concerned shall not begin until such approval is granted in writing.

C.	Notification of a subcontractor’s termination will be sent to the Department by the contractor through the RE. Said termination notice will state whether the subcontractor is an ESBE and the reason for termination.

XII	CONCILIATION.

Allegations of breach of any obligation contained in these ESBE provisions will be investigated by the Federal Office of Contract Compliance in conjunction with the Division of Civil Rights/Affirmative Action of the New Jersey Department of Transportation and the Federal Highway Administration.

XIII	DOCUMENTATION.

A.	The Department or the federal funding agencies may at any time require such information as is deemed necessary in the judgment of the Department to ascertain the compliance of any bidder or contractor with the terms of these provisions.

B.	Record and Reports.

The Contractor shall keep such records as are necessary to determine compliance with its Emerging Small Business Enterprise Utilization obligations. The records kept by the contractor will be designed to indicate:

1.	The names of ESBE contractors, equipment lessors and material suppliers contacted for work on this project.

2.	Work, services and materials which are not performed or supplied by the prime contractor.

3.	The actual dollar value of work subcontracted and awarded to ESBE’s.

4.	Efforts taken in seeking out and utilizing ESBE’s. This would include solicitations, quotes and bids regarding project work items, supplies, leases, or other contract items.

5.	Documentation of all correspondence, contacts, telephone calls, or other actions taken to obtain the services of ESBE’s on this project.

6.	Records of all ESBE’s who have submitted quotes/bids to the contractor on the project.

C.	Submit reports, as required by the Department, on those contracts and other business transactions executed with ESBE’s in such form and manner as may be prescribed by the Department.

D.	All such records must be maintained for a period of three (3) years following acceptance of final payment and will be available for inspection by the Department.

XIV	PAYMENT TO SUBCONTRACTORS.

The Contractor agrees to pay its subcontractors in accordance with the Specifications

XV	NON-COMPLIANCE.

Failure by the bidder to comply with these provisions may result in rejection of the bid. The contractor may further be declared ineligible for future Department contracts.

FHWA Attachment No. 5

DISADVANTAGED BUSINESS ENTERPRISE UTILIZATION ATTACHMENT

FHWA FUNDED CONTRACTS

I	UTILIZATION OF DISADVANTAGED BUSINESSES AS CONTRACTORS, MATERIAL SUPPLIERS AND EQUIPMENT LESSORS.

The New Jersey Department of Transportation (NJDOT) advises each contractor or subcontractor that failure to carry out the requirements set forth in this attachment shall constitute a breach of contract and, after the notification of the applicable federal agency, may result in termination of the agreement or contract by the Department or such remedy as the Department deems appropriate. Requirements set forth in this section shall also be physically included in all subcontracts in accordance with USDOT requirements.

II	POLICY

It is the policy of NJDOT that Disadvantaged Business Enterprises, as defined in 49 CFR, Part 26; Titles I & V of the Intermodal Surface Transportation Efficiency Act of 1991 (ISTEA); the Transportation Equity Act for the 21st Century (TEA-21); and Section V, Part B below, shall have equal opportunity to participate in the performance of contracts financed in whole or in part with federal funds under this agreement. Consequently, the DBE requirements of 49 CFR, Part 26, Subsections A, C and F apply to this agreement.

III	CONTRACTOR’S DBE OBLIGATION

The NJDOT and its Contractor agree that Disadvantaged Business Enterprises, as defined in 49 CFR Part 26, Subpart A; and in the Intermodal Surface Transportation Efficiency Act of 1991 (ISTEA) and the Transportation Equity Act for the 21st Century (TEA-21), and Section V, Part B below, have equal opportunity to participate in the performance of contracts and subcontracts financed in whole or in part with federal funds provided under this agreement. In this regard, the NJDOT and all Contractors shall take all necessary and reasonable steps in accordance with 49 CFR, Part 26 to ensure that Disadvantaged Businesses are given equal opportunity to compete for and to perform on NJDOT federally funded contracts.  The NJDOT and its Contractors shall not discriminate on the basis of race, color, national origin, or sex in the award and performance of USDOT assisted contracts.

IV	COMPLIANCE

To signify and affirm compliance with the provisions of this attachment, the bidder shall complete the Schedule of DBE Participation (Form CR-266F) included in the bid package and all forms and documents required in Sections VII and VIII of these provisions which will be made a part of the resulting contract.

V	GOALS FOR THIS PROJECT

A.	This Project includes a goal of awarding      percent of the total contract value to subcontractors, equipment lessors and/or material suppliers that qualify as Disadvantaged Business Enterprises (DBEs).

1.	Failure to meet the minimum goal placed on this project, or to provide a “good faith effort” to meet the minimum goal, may be grounds for rejection of the bid as being non-responsive.

2.	As a source of information only, a Disadvantaged Business Enterprise Directory is available from the Division of Civil Rights and Affirmative Action. Use of this listing does not relieve the Contractor of their responsibility to seek out other DBE’s not listed, prior to bid.  If a contractor proposes to use a DBE contractor not listed in the DBE Directory, the proposed DBE firm must submit a completed certification application to the Division of Civil Rights and Affirmative Action, fifteen (15) days prior to bid date.

B.	DEFINITIONS

1.	Disadvantaged Business Enterprise is a firm, “Owned and controlled” by socially and economically disadvantaged individuals that is also a small business concern, as defined pursuant to Section 3 of the Small Business Act and Small Business Administration Regulations (13 CFR, Part 121) which also does not exceed the revenue cap on averaged annual gross receipts applicable to the firm’s particular Standard Industrial Classification (SIC Code).

2.	Owned and Controlled is defined as a firm which is at least fifty-one (51%) percent owned by one or more disadvantaged individuals, or in the case of a publicly owned business, at least fifty-one (51%) percent of the stock is owned by one or more disadvantaged individuals, and whose management and daily business operations are controlled by one or more such individuals.

3.	Any individual in one of the following groups who is also a U.S. Citizen or lawfully admitted permanent resident presumed to be socially and economically disadvantaged under the DBE Program.

- Black Americans – includes any persons having origins in any of the black racial groups of Africa;

- Hispanic Americans - includes persons of Mexican, Puerto Rican, Cuban, Dominican, Central or South American, or other Spanish or Portuguese culture; or origin, regardless of race;

- Native American - includes persons who are American Indians, Eskimos, Aleuts or Native Hawaiians;

- Asian-Pacific Americans - includes persons whose origins are from Japan, China, Taiwan, Korea, Burma (Myanmar), Vietnam, Laos, Cambodia (Kampuchea), Thailand, Malaysia, Indonesia, the Philippines, Brunei, Samoa, Guam, the U.S. Trust Territories of the Pacific Islands (Republic of Palau) the Commonwealth of the Northern Mariana Islands, Macao, Fiji, Tonga, Kiribati, Juvalu, Nauru, Federated States of  Micronesia or Hong Kong;

- Subcontinent Asian Americans - includes persons whose origins are from India, Pakistan, Bangladesh, Bhutan, the Maldives Islands, Nepal or Sri Lanka;

- Women - regardless of race;

- Other - Any additional groups whose members are designated as socially and economically disadvantaged by the Small Business Administration, at such time as the SBA designation becomes effective; or a determination made by the NJDOT’s Division of Civil Rights and Affirmative Action, on a case-by-case basis;

VI	COUNTING DBE PARTICIPATION

A.	Each DBE is subject to a certification procedure to ensure its DBE eligibility status prior to award of contract. In order to facilitate this process it is advisable for the bidder to furnish the names of proposed DBE’s to the Department fifteen (15) days before bid opening. Once a firm is determined to be a bona fide DBE by the Division of Civil Rights and Affirmative Action, the total dollar value of the contract awarded to the DBE is counted toward the applicable DBE goal.

B.	The Contractor may count toward its DBE goal only expenditures to DBE’s that perform a commercially useful function in the work of a contract. A DBE is considered to perform a commercially useful function when it is responsible for execution of a distinct element of the work of a contract and carrying out its responsibility by actually performing, managing and supervising the work involved.  To determine whether a DBE is performing a commercially useful function, the Contractor shall evaluate the amount of work subcontracted, industry practice and other relevant factors.

C.	If a DBE does not perform or exercise responsibility for at least 30 percent of the total cost of its contract with its own workforce, or the DBE subcontracts a greater portion of the work of a contract than would be expected on the basis of normal industry practice for the type of work involved, you must presume that it is not performing a commercially useful function.

D.	If the prime Contractor is a certified DBE, payments made to the Contractor for work performed by the Contractor will be applied toward the DBE goal. Payments made to the Contractor for work performed by non-DBE’s will not be applied toward the goal.

E.	The prime Contractor may count 60 percent of its expenditures to DBE suppliers who are not Manufacturers, provided that the DBE supplier performs a commercially useful function in the supply process.  The contractor may count 100% of its expenditure to DBE suppliers who are also manufacturers. Manufacturers receive 100% credit toward the DBE goal.

F.	When a DBE subcontractor sublets part of the work of its contract to another firm, the value of the subcontract work may be counted towards the DBE goals only if the subcontractor itself is a DBE.  Work that a DBE subcontractor subcontracts to a non-DBE firm, does not count toward DBE goals.

VII	GOOD FAITH EFFORT

To demonstrate sufficient reasonable efforts to meet the DBE contract goals, a bidder shall document the steps it has taken to obtain DBE participation, including but not limited to the following:

A.	Attendance at a pre-bid meeting, if any, scheduled by the Department to inform DBE’s of subcontracting opportunities under a given solicitation.

B.	Advertisement in general circulation media, trade association publications, as well as minority-focus media for at least 20 days before bids are due.  If 20 days are not available, publication for a shorter reasonable time is acceptable.

C.	Written notification to DBE’s that their interest in the contract is solicited;

D.	Efforts made to select portions of the work proposed to be performed by DBEs in order to increase the likelihood of achieving the stated goal;

E.	Efforts made to negotiate with DBE’s for specific sub-bids including at a minimum:

- The names, addresses and telephone numbers of DBE’s that were contacted;

- A description of the information provided to DBE’s regarding the plans and Specifications for portions of the work to be performed; and

- A statement of why additional agreements with DBE’s were not reached;

F	Information regarding each DBE the bidder contacted and rejected as unqualified and the reasons for the bidder’s conclusion;

G.	Efforts made to assist the DBE in obtaining bonding or insurance required by the Bidder or the Department.

NOTE: If the Division of Civil Rights and Affirmative Action determines that the apparent successful low bidder has failed to meet the requirements of this section, the bidder will be afforded the opportunity for administrative consideration prior to the award or rejection of the contract. As part of the administrative reconsideration process, the bidder will have the opportunity to provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so. NJDOT will send the bidder a written decision on reconsideration, explaining the basis for finding that the bidder did or did not meet the goal or make adequate good faith efforts to do so. The result of the reconsideration process is not administratively appealable to the USDOT.

VIII	AFFIRMATIVE ACTION PLANS

A.	General contractors are required to submit their firm’s Affirmative Action Program annually to the Division of Civil Rights and Affirmative Action.  Until such time as these programs are submitted and approved, Contractors must have their programs in the Division of Civil Rights and Affirmative Action no later than seven (7) State business days after the date of receipt of bids.

B.	This program will include, but is not limited to the following:

- The name of the Contractor’s D/ESBE Liaison Officer to administer the firm’s Disadvantaged Business Program.

- An explanation of the affirmative action methods used in seeking out and considering Disadvantaged Business Enterprises as subcontractors, material suppliers or equipment lessors.

- An explanation of affirmative action methods intended to be used in seeking out and considering Disadvantaged Business Enterprises as subcontractors, material suppliers or equipment lessors. This refers to the Contractor’s ongoing responsibility, i.e., Disadvantaged Business Enterprise/Affirmative Action activities after the award of the contract and for the duration of said project.

C.	The following shall be submitted either with the bid or to the Division of Civil Rights and Affirmative Action no later than seven (7) State business days after the date of receipt of bids.

- DBE Form CR-266F- Schedule of DBE Participation. List all DBE’s participating in the contract listing the scope of work, dollar value and percent of total contract to be performed.

- Supplement to DBE Form CR-266F - A list of all subcontractors who submitted bids or quotes on this project.

- Request for Exemption - In the event that the bidder fails to meet the specified goal, they must submit within seven State business days of the bid, a written request for exemption to the goal.  This request must include a written statement addressing Items A through G in Article VII of this attachment in addition to an accounting of the reason(s) why each items in the bid proposal was not subcontracted. Submittal of such request does not imply Departmental approval. An assessment of the material will be conducted by the Department’s Division of Civil Rights and Affirmative Action.

IX	AFFIRMATIVE ACTION AFTER AWARD OF THE CONTRACT

If at any time following the award of contract, the Contractor intends to sublet any portion(s) of the work under said contract, or intends to purchase material or lease equipment not contemplated during preparation of bids, said Contractor shall take affirmative action:

- To notify the RE, in writing, of the type and approximate value of the work which the Contractor intends to accomplish by such subcontract, purchase order or lease.

- To signify and affirm compliance with the provisions of this Section, the Contractor shall submit the Post-Award DBE Certification Form to the Regional Supervising Engineer with his application to sublet or prior to purchasing material or leasing equipment. Post Award DBE forms may be obtained from the RE.

- To give disadvantaged firms equal consideration with non-minority firms in negotiation for any subcontracts, purchase orders or leases.

- If a prime contractor fails to meet its original DBE obligation, they must request an exemption to the goal following criteria in Section VIII (C)(4) and provide a good faith effort thereof. This request must include a written statement addressing each of the Good Faith Efforts outlined in Section VII, A-G.

X	CONSENT BY DEPARTMENT TO SUBLETTING

The Department will not approve any subcontract proposed by the Contractor unless and until said Contractor has complied with the terms of this attachment.

XI	SELECTION AND RETENTION OF SUBCONTRACTORS

A.	The Contractor is further obligated to provide the RE with a listing of firms, organizations or enterprises solicited and those utilized as subcontractors on the proposed project. Such listing shall clearly delineate which firms are classified as disadvantaged.

B.	Efforts made to identify and retain a Disadvantaged Business Enterprise as a substitution subcontractor when the arrangements with the original DBE proved unsuccessful, shall be submitted in writing to the Department’s D/ESBE Liaison Officer for approval. Work in the category concerned shall not begin until such approval is granted in writing.

C.	Notification of a subcontractor’s termination will be sent to the Department by the Contractor through the RE. Said termination notice will include the subcontractor’s ethnic classification and reason for termination.

XII	CONCILIATION

In cases of alleged discrimination regarding these DBE provisions and guidelines, an investigation will be undertaken by the Federal Office of Contract Compliance in conjunction with the Division of Civil Rights and Affirmative Action of the New Jersey Department of Transportation and the Federal Highway Administration.

XIII	DOCUMENTATION

A.	The Department or the federal funding agencies may at any time require such information as is deemed necessary in the judgment of the Department to ascertain the compliance of any bidder or contractor with the terms of these provisions.

B.	Record and Reports.

The Contractor shall keep such records as are necessary to determine compliance with its Disadvantaged Business Enterprise Utilization obligations. The records kept by the Contractor will be designed to indicate:

- The names of disadvantaged subcontractors, equipment lessors and material suppliers contacted for work on this project.

- The type of work to be done, materials to be utilized or services to be performed other than the work of the prime contractor on the project.

- The actual dollar value of work subcontracted and awarded to DBE’s.

- The progress being made and efforts taken in seeking out and utilizing Disadvantaged Business Enterprises.  This would include solicitations, quotes and bids regarding project work items, supplies, leases, etc.

- Documentation of all correspondence, contacts, telephone calls, etc., to obtain the services of Disadvantaged Business Enterprises on this project.

- Records of all DBE’s and non-DBEs who have submitted quotes/bids to the Contractor on the project.

C.	Submit reports, as required by the Department, on those contracts and other business transactions executed with Disadvantaged Business Enterprises in such form and manner as may be prescribed by the Department.

D.	All such records must be maintained for a period of three (3) years following acceptance of final payment and will be available for inspection by the Department.

XIV	PAYMENT TO SUBCONTRACTORS

The Contractor agrees to pay its subcontractors in accordance with the Specifications.

XV	NON-COMPLIANCE

Failure by the bidder to comply with the Specifications may result in rejection of the bid. The Contractor may further be declared ineligible for future Department contracts.

FHWA Attachment No.6

EQUAL EMPLOYMENT OPPORTUNITY SPECIAL PROVISIONS

1.	General

a.	Equal employment opportunity requirements not to discriminate and to take affirmative action to assure equal employment opportunity as required by Executive Order 11246 and Executive Order 11375 are set forth in Required Contract Provisions (Form FHWA-1273) and these Special Provisions which are imposed pursuant to Section 140 of Title 23 USC, as established by Section 22 of the Federal Aid Highway Act of 1968. The requirements set forth in these Special Provisions shall constitute the specific affirmative action requirements for project activities under this contract and supplement the Equal Employment Opportunity requirements set forth in the Required Contract Provisions.

b.	The Contractor will work with the State agencies and the Federal Government in carrying out Equal Employment Opportunity obligations and in their review of activities under the contract.

c.	The Contractor and all subcontractors holding subcontracts, not including material suppliers, of $10,000 or more, will comply with the following minimum specific requirement activities of Equal Employment Opportunity.  The Contractor will include these requirements in every subcontract of $10,000 or more with such modification of language as is necessary to make them binding on the subcontractor.  (The equal employment opportunity requirements of Executive Order 11246, as set forth in Volume 6, Chapter 4, Section 1, Subsection 1 of the Federal-Aid Highway Program Manual, are applicable to material suppliers as well as contractors and subcontractors).

d.	Noncompliance by the Contractor with the requirements of the Affirmative Action Program for Equal Employment Opportunity may be cause for delaying or withholding monthly and final payments pending corrective and appropriate measures by the Contractor to the satisfaction of the Department.

2.	Equal Employment Opportunity Policy

The Contractor will accept as its operating policy the following statement which is designed to further the provisions of equal employment opportunity to all persons without regard to their race, color, religion, sex, or national origin, and to promote the full realization of equal employment opportunity through a positive continuing program:

It is the policy of this Company to assure that applicants are employed, and that employees are treated during employment, without regard to their race, religion, sex, color, or national origin.  Such action shall include employment, upgrading, demotion, or transfer; recruitment or recruitment advertising; layoff or termination; rates of pay or other forms of compensation; and selection for training, including apprenticeship, preapprenticeship, and on-the-job training.

3.	Equal Employment Opportunity Officer

The Contractor will designate and make known to the Department contracting officers an equal opportunity officer (hereinafter referred to as the EEO Officer) who will have the capability, authority and responsibility to effectively implement and promote an active contractor program of equal employment opportunity.

4.	Dissemination of Policy

a.	All members of the Contractor’s staff who are authorized to hire, supervise, promote, and discharge employees, or who recommended such action, or who are substantially involved in such action, will be made fully cognizant of, and will implement, the Contractor’s equal employment opportunity policy and contractual responsibilities to provide equal employment opportunity in each grade and classification of employment.  To ensure compliance, the following minimum actions will be taken:

(1)	An initial project site meeting with key supervisory and office personnel will be conducted before or at the start of work, and then not less than once every 6 months, at which time the Contractor’s equal employment opportunity program will be reviewed and explained.  The meetings will be conducted by the EEO Officer or other knowledgeable company official.

(2)	All new supervisory and office personnel will be given a thorough indoctrination by the EEO Officer or other knowledgeable company official covering all major aspects of the Contractor’s equal employment opportunity obligations within 30 days following their reporting for duty with the Contractor.

(3)	All personnel engaged in direct recruitment for the project will be instructed by the EEO Officer or appropriate company official concerning the Contractor’s procedures for locating and hiring minority and female employees.

b.	In order to make the Contractor’s equal employment opportunity policy known to all employees, prospective employees and potential sources of employees, i.e., schools, employment agencies, labor unions (where appropriate), college placement officers, etc., the Contractor will take the following actions:

(1)	Notices and posters setting forth the Contractor’s equal employment opportunity policy will be placed in areas readily accessible to employees, applicants for employment and potential employees.

(2)	The Contractor’s equal employment opportunity policy and the procedures to implement such policy will be brought to the attention of employees by means of meetings, employee handbooks, and/or other appropriate means.

5.	Recruitment

a.	When advertising for employees, the Contractor will include in all advertisements for employees the notation: “An Equal Opportunity Employer”.  All such advertisements will be published in newspapers or other publications having a large circulation among minority groups in the area from which the project work force would normally be derived.

b.	The Contractor will, unless precluded by a valid bargaining agreement, conduct systematic and direct recruitment through public and private employee referral sources likely to yield qualified minority and female applicants, including, but not limited to, State employment agencies, schools, colleges and minority-oriented organizations.  To meet this requirement, the Contractor will, through his EEO Officer, identify sources of potential minority and female employees, and establish procedures with such sources whereby applicants may be referred to the Contractor for employment consideration.

In the event the Contractor has a valid bargaining agreement providing for exclusive hiring hall referrals, he is expected to observe the provisions of that agreement to the extent that the system permits the Contractor’s compliance with the equal employment opportunity contract provisions.  (The US Department of Labor has held that where implementation of such agreements have the effect of discriminating against minorities or females, or obligates the Contractor to do the same, such implementation violates Executive Order 11246, as amended).

c.	The Contractor will encourage his present employees to refer minority and female applicants for employment by posting appropriate notices or bulletins in areas accessible to all such employees.  In addition, information and procedures pertaining to the referral of applicants will be discussed with employees.

6.	Personnel Actions

Wages, working conditions and employee benefits shall be established and administered, and personnel actions of every type, including hiring, upgrading, promotion, transfer, demotion, layoff, and termination, shall be taken without regard to race, color, religion, sex, or national origin.  The following procedures shall be followed:

a.	The Contractor will conduct a project site inspection at the start of work, and periodically thereafter, to ensure that working conditions and employee facilities do not indicate discriminatory treatment of project site personnel.

b.	The Contractor will periodically evaluate the spread of wages paid within each classification to determine any evidence of discriminatory wage practices.

c.	The Contractor will periodically review selected personnel actions in depth to determine whether there is evidence of discrimination.  Where evidence is found, the Contractor will promptly take corrective action.  If the review indicates that the discrimination may extend beyond the actions reviewed, such corrective action shall include all affected persons.

d.	The Contractor will promptly investigate all complaints of alleged discrimination made to the Contractor in connection with its obligations under this contract, and will resolve or attempt to resolve such complaints, within a reasonable time.  If the investigation indicates that the discrimination may affect persons other than the complainant, corrective action shall include such other persons.  Upon completion of each investigation, the Contractor will inform complainants of available avenues of appeal.

7.	Training Special Provisions

As part of the Contractor’s equal employment opportunity affirmative action program, training shall be provided as follows:

The Contractor shall provide on-the-job training aimed at developing full journey people in the type of craft or job classification involved.

The number of training positions will be____, where feasible, consisting of at least____ APPRENTICES and ____TRAINEES. TRAINEE HOURS=_____.

Apprentices are defined as registered members of an approved apprenticeship program recognized by the United States Department of Labor (USDOL) Bureau of Apprenticeship and Training (BAT) or a New Jersey State apprenticeship agency recognized by USDOL BAT (e.g., New Jersey Department of Education).  Graduates of the Pre-Apprenticeship Training Cooperative Program shall be classified as apprentices.  Trainees are defined as skilled, semi-skilled or lower level management individuals receiving training per one of the approved NJDOT “Revised Standard Training Guidelines” (available from the Division of Civil Rights).

Where feasible, at least 50% of the training positions will be assigned to Skilled Crafts which include but are not limited to Carpenters, Dockbuilders, Electricians, Ironworkers and Operating Engineers.

a.	Contractor Submission and NJDOT Approval of the Initial Training Program.

At or after the preconstruction conference and prior to the start of work, the Contractor shall submit a training program to the RE for his or her review and comments prior to Division of Civil Rights review and approval. The Contractor’s training program shall include:

(1)	the number of trainees or apprentices to be trained in all selected Training Positions,

(2)	the Standard Program Hours for all positions,

(3)	an estimate of the Minimum Available Hours actually feasible on the project toward completion of the Standard Program Hours per position,

(4)	a training schedule of Estimated Start Dates for the apprentices or trainees, developed and coordinated with the project’s work progress schedule,

(5)	Training Guidelines for all positions, and

(6)	which training will be provided by the Contractor and which by Subcontractors.

The number of apprentices and trainees shall be distributed among the work classifications on the basis of the Contractor’s needs and the availability of journeypeople in the various crafts within a reasonable area of recruitment.  The Contractor shall submit timely, revised training programs as required throughout the project to ensure that feasible and Maximum Available Training is provided.  Maximum Available Training is defined as bringing each apprentice or trainee onto the project when work first becomes available in his/her craft and providing all available training until hours are no longer available.

b.	Assignment of Training to Subcontractors

In the event that portions of the contract work are subcontracted, the Contractor shall determine how many, if any, of the apprentices or trainees are to be trained by subcontractors, provided, however, that the Contractor shall retain the primary responsibility for meeting the training requirements imposed by these Training Special Provisions. The Contractor shall also ensure that these Training Special Provisions are made applicable to such subcontracts.

c.	Requirements for Recruitment, Selection and Approval of Apprentices and Trainees

(1)	Apprentices or trainees should be in their first year of apprenticeship or training.  The Contractor shall interview and screen trainee candidates to determine if their actual work experience is equivalent to or exceeds that offered by the training program prior to submitting candidates, via the RE, to the Division for review and approval or disapproval.

(2)	Training and upgrading of minorities (e.g., Blacks, Asians or Pacific Islanders, Native Americans or Alaskan Natives, Hispanics) and females toward journeyperson status is a primary objective of these Training Special Provisions.  Accordingly, the Contractor shall make every effort to enroll minorities and females, by conducting systematic and direct recruitment through public and private sources likely to yield minority and female apprentices or trainees, to the extent that such persons are available within a reasonable area of recruitment.  This training commitment is not intended, and shall not be used, to discriminate against any applicant for training, whether a member of a minority group or not.

(3)	No employee shall be employed as an apprentice or trainee in any position in which he or she has successfully completed a training course leading to journeyperson status or in which he or she has been employed as a journeyperson.  The Contractor shall satisfy this requirement by including appropriate questions in the employment application or by other suitable means and by submitting an accurate and complete “Apprentice/Trainee Approval Memorandum.” (Form CR-1) Regardless of the methods used, the Contractor’s records should document the findings in each case.

(4)	Skilled craft trainees may complete up to 3,000 total training hours on NJDOT projects, with an extension of an additional 1,000 hours permitted on a case-by-case basis.  Semi-skilled and lower-level management trainees attain journeyperson status upon completion of a training guideline and may complete up to three (3) different positions.

d.	Apprenticeship and Training Programs

(1)	The minimum length and type of training for each position will be established in the training program selected by the Contractor and approved by NJDOT and the Federal Highway Administration.  NJDOT will approve a program if it is reasonably calculated to meet the equal employment opportunity obligations of the Contractor and to qualify the average apprentice or trainee for journeyperson status in the craft concerned by the end of the training period.

(2)	Apprenticeship programs registered with the US Department of Labor, Bureau of Apprenticeship and Training, or with a State apprenticeship agency recognized by USDOL BAT and training programs approved but not necessarily sponsored by the US Department of Labor, Employment and Training Administration, Bureau of Apprenticeship and Training shall also be considered acceptable provided such programs are being administered in a manner consistent with the equal employment obligations of Federal-aid highway construction contracts.  Approval or acceptance of a training program shall be obtained from the NJDOT Division of Civil Rights prior to commencing work on the positions covered by the Contractor’s training program.  The Division will review guidelines developed by the Contractor for approval or disapproval in accordance with the Training Guideline Approval Process described in the “Revised Standard Training Guidelines”.  The Division will also review existing guidelines for revision based on the same process.

(3)	It is the intention of these provisions that training be provided in construction crafts rather than clerk-typist or secretarial-type positions.  Training is permitted in lower level management positions (e.g., timekeepers), where the training is oriented toward project site applications.  Training in semi-skilled laborer positions is permitted provided that significant and meaningful training is available on the project site.  Some offsite, classroom training (e.g., safety, first aid instruction) may be permitted as long as such training is an integral part of an approved training program and does not comprise a significant part of the overall training.

e.	Reimbursement of the Contractor for Providing Training

(1)	The Contractor will be credited for each apprentice or trainee employed on the construction site who is currently enrolled or becomes enrolled in an approved program and will be reimbursed for such apprentices or trainees as provided hereinafter.  Payment will be made under the pay item Trainees at the bid price in the Proposal per person-hour of training given an employee on this contract in accordance with an approved training program. If approved, payment will be made for training persons in excess of the number specified herein.  This reimbursement will be made even though the Contractor receives additional training program funds from other sources, provided such other sources do not specifically prohibit the Contractor from receiving other reimbursement.  Offsite, classroom training reimbursement may only be made to the Contractor when the company does one or more of the following and the apprentices or trainees are concurrently employed on a Federal-aid project:  contributes to the cost of the training and/or provides instruction to apprentices or trainees or pays their wages during the offsite, classroom training (e.g., safety, first aid instruction) period.

(2)	The Contractor shall pay apprentices and trainees according to the project-specific New Jersey Department of Labor Prevailing Wage Rate Determination for the project.

f.	Documentation Required to be Signed by Apprentices or Trainees and provided to NJDOT

(1)	At the start of training, the Contractor shall provide the RE and each apprentice or trainee with an applicable “Training Guideline” and, at the conclusion of training, an accurate and complete “Training Certificate for Reporting Hours to NJDOT” (Form CR-3), showing hours of training satisfactorily completed.

(2)	The Contractor shall maintain and submit an accurate and complete “NJDOT Contractor’s 1409 Quarterly Training Report” (Form-CR-1409) to the RE within ten (10) days of the end of each training quarter (e.g., January 10, April 10, July 10, October 10); a copy shall also be given to each apprentice or trainee.

(3)	The Contractor shall maintain and submit accurate and complete “Biweekly Training Reports” (Form CR-2) to the RE, and each apprentice or trainee, as periodic reports documenting performance under these Training Special Provisions.

g.	Training and Promotion

(1)	The Contractor shall assist in locating, qualifying, and increasing the skills of minority and female employees, and applicants for employment.

(2)	The Contractor shall advise employees and applicants for employment of available training programs and entrance requirements.

(3)	The Contractor shall periodically review the training and promotion potential of minority and female employees and encourage eligible employees to apply for such training and promotion.

h.	Determining Good Faith Compliance

(1)	Per the approved program or guideline, the Contractor shall provide Maximum Available Training to apprentices and trainees by beginning their training as soon as feasible with the start of craft work utilizing the skill involved on the project construction site and by retaining them as long as training opportunities exist in their crafts or until their training program positions are completed.

(2)	The Contractor shall recall apprentices or trainees released due to reductions in force when the work scope permits and they are available to return.  When they are unavailable to resume training on the project site, the Contractor shall submit written proof of recall efforts and replacement candidates and/or positions in a timely manner.  The Contractor shall not terminate apprentices or trainees prior to completion of their training program positions without NJDOT consultation and authorization.  Apprentices or trainees are not required to be on board for the entire length of the contract.

(3)	The Contractor shall have fulfilled the contractual responsibilities under these Training Special Provisions if the company has provided Acceptable Training to the number of apprentices or trainees specified in this contract and/or by providing the remaining hours required to complete training positions begun by apprentices or trainees on other projects.  The number trained shall be determined on the basis of the total number enrolled on the contract for a significant period.

(4)	The Contractor shall be responsible for demonstrating all steps that have been taken in pursuance of enrolling minorities and females in the training program positions, prior to a determination as to whether the Contractor is in compliance with these Training Special Provisions.

(5)	The Contractor shall submit to the RE written training program summaries at the 50% time and/or cost stage of the contract and also prior to project completion, describing all good faith actions and particularly addressing Maximum Available Training for incomplete training positions, per the procedure found in the revised “Instructions for Implementing the Training Special Provisions”.

i.	Enforcement Measures and Contractor’s Rating

(1)	Payment will not be made if either the failure to provide the required training or the failure to hire the apprentice or trainee as a journeyperson is caused by the Contractor and evidences a lack of good faith on the part of the Contractor in meeting the requirements of these Training Special Provisions.

(2)	Per established procedures and scheduled Contract Compliance Reviews, the Contractor’s performance will be rated and reviewed periodically by the Department.

(3)	Noncompliance with these Training Special Provisions may be cause for delaying or withholding monthly and final payments, pending corrective and appropriate measures by the Contractor to the satisfaction of the Department, per Item 1d of these EEO Special Provisions.

8.	Unions

If the Contractor relies in whole or in part upon unions as a source of employees, the Contractor will make maximum effort to obtain the cooperation of such unions to increase opportunities for minorities and females within the unions, and to effect such union referrals to the construction project.  Actions by the Contractor, either directly or through a contractor’s association acting as agent, will include the procedures set forth below:

a.	The Contractor will use maximum effort to develop, in cooperation with the unions, joint training programs aimed at qualifying more minorities and females for union membership and increasing their skills in order to qualify for higher paying employment.

b.	The Contractor will use maximum effort to incorporate an equal employment opportunity clause into each union agreement to the end that such union will be contractually bound to refer applicants without regard to their race, color, religion, sex, or national origin.

c.	The Contractor will obtain information concerning the referral practices and policies of the labor unions except that to the extent such information is within the exclusive possession of the labor unions and they refuse to furnish this information to the Contractor, the Contractor shall so certify to the Department and shall set forth what efforts have been made to obtain this information.

d.	In the event the unions are unable to provide the Contractor with a reasonable flow of minority and female referrals within the time limit set forth in the collective bargaining agreement, the Contractor will through independent recruitment efforts, fill the employment vacancies without regard to race, color, religion, sex, or national origin, making full efforts to obtain qualified and/or qualifiable minorities and females.  (The US Department of Labor has held that it shall be no excuse that the union with which the Contractor has a collective bargaining agreement providing for exclusive referral failed to refer minority employees).  In the event the union referral practice prevents the Contractor from meeting the obligations pursuant to Executive Order 11246, as amended, and these special provisions, such Contractor shall immediately notify the Department.

9.	Subcontracting

a.	The Contractor will use maximum effort to solicit bids from and to utilize minority subcontractors or subcontractors with meaningful minority and female representation among their employees.  Contractors may use lists of minority-owned construction firms as issued by the Department.

b.	The Contractor will use maximum effort to ensure subcontractor compliance with the equal employment opportunity obligations.

10.	Documents and Reports

a.	The Contractor will maintain such documents as are necessary to determine compliance with the contract’s equal employment opportunity requirements.  Documents will include the following:

(1)	the number of minorities, non-minorities, and females employed in each work classification on the Project.

(2)	the progress and efforts being made in cooperation with unions to increase employment opportunities for minorities and females (applicable only to Contractors who rely in whole or in part on unions as a source of their work force).

(3)	the progress and efforts being made in locating, hiring, training, qualifying, and upgrading minority and female employees, and

(4)	the progress and efforts being made in securing the services of minority and female subcontractors or subcontractors with meaningful minority and female representation among their employees.

b.	All such documents must be retained for a period of 3 years following completion of the contract work and shall be available at reasonable times and places for inspection by authorized representatives of the Department and the Federal Highway Administration.

c.	The contractor and each subcontractor must submit monthly employment and wage data to the Department via a web based application using electronic Form CC-257R.  Instructions for registering and receiving the authentication code to access the web based application can be found at:

http://www.state.nj.us/transportation/business/civilrights/pdf/cc257.pdf

Instructions on how to complete Form CC257 are provided in the web application.  Submit Form CC-257R through the web based application within 10 days following the end of the reporting month.  Submission of this form also satisfies the requirement of the form FHWA 1391.

All employment and wage data must be accurate and consistent with the certified payroll records.  The contractor is responsible for ensuring that their subcontractors comply with these reporting requirements.  Failure by the contractor to submit Monthly Employment Utilization Report may impact the contractor’s prequalification rating with the Department.

FHWA Attachment No.7

SPECIAL CONTRACT PROVISIONS FOR INVESTIGATING, REPORTING AND RESOLVING EMPLOYMENT DISCRIMINATION AND SEXUAL HARASSMENT COMPLAINTS

The contractor hereby agrees to the following requirements in order to implement fully the nondiscrimination provisions of the Supplemental Specifications.

The Contractor agrees that in instances when it receives from any person working on the project site a verbal or written complaint of employment discrimination, prohibited under N.J.S.A. 10:5-1 et seq., 10:2-1 et seq., 42 U.S.C. 2000(d) et seq., 42 U.S.C. 2000 (e) et seq. and Executive Order 11246, it shall take the following actions:

1.	Within one (1) working day commence an investigation of the complaint which shall include but not be limited to interviewing the complainant, the respondent, and all possible witnesses to the alleged act or acts of discrimination or sexual harassment.

2.	Prepare and keep for its use and file a detailed written investigative report which includes the following information:

a)	Investigatory activities and findings.

b)	Dates and parties involved and activities involved in resolving the complaint.

c)	Resolution and corrective action taken if discrimination or sexual harassment is found to have taken place.

d)	A signed copy of resolution of complaint by complainant and contractor.

In addition to keeping in its files the above-noted detailed written investigative report, the contractor shall keep for possible future review by the Department all other records, including but not limited to, interview memos and statements.

3.	Upon the request of the Department, provides to the Department within ten (10) calendar days a copy of its detailed written investigative report and all other records on the complaint investigation and resolution.

4.	Take appropriate disciplinary action against any contractor employee, official or agent who has committed acts of discrimination or sexual harassment against any contractor employee or person working on the project. If the person committing the discrimination is a subcontractor employee, then the contractor is required to attempt to effectuate corrective and/or disciplinary action by the subcontractor in order to establish compliance with project’s contract requirements.

5.	Take appropriate disciplinary action against any contractor employee, official or agent who retaliates, coerces or intimidates any complaint and/or person who provides information or assistance to any investigation of complaints of discrimination or sexual harassment. If the person retaliating, coercing or intimidating a complainant or other person assisting an investigation is a subcontractor’s employee, then the contractor is required to attempt to effectuate corrective and/or disciplinary action by the subcontractor in order to establish compliance with the project’s contract requirements.

6.	Ensure to the maximum extent possible that the privacy interests of all persons who give confidential information in aid of the contractor’s employment discrimination investigation are protected.

In conjunction with the above requirements, the contractor shall develop and post a written sexual harassment policy for its work force.

Failure by the contractor to comply with the above requirements may be cause for the New Jersey Department of Transportation to institute against the contractor any and all enforcement proceedings and/or sanctions authorized by the contract or by state and/or federal law.

1**************************************************************************************************************************1

1**************************************************************************************************************************1

INclude THE FOLLOWING FOR wholly state funded projects

2**************************************************************************************2

BDCs14S-08 dated June 25 2014

## state Attachment No. 1

### STATE OF NEW JERSEY EQUAL EMPLOYMENT OPPORTUNITY special provisions

### FOR construction CONTRACTS FUNDED BY WHOLLY or partially STATE FUNDS

I.	GENERAL

It is the policy of the New Jersey Department of Transportation (hereafter “NJDOT”) that its contracts should create a workforce that reflects the diversity of the State of New Jersey.  Therefore, contractors engaged by the NJDOT to perform under a construction contract shall put forth a good faith effort to engage in recruitment and employment practices that further the goal of fostering equal opportunities to minorities and women.

The contractor must demonstrate to the NJDOT’s satisfaction that a good faith effort was made to ensure that minorities and women have been afforded equal opportunity to gain employment under the NJDOT’s contract with the contractor.  Payment may be withheld from a contractor’s contract for failure to comply with these provisions.

Evidence of a “good faith effort” includes, but is not limited to:

- The Contractor shall recruit prospective employees through the State Jobs4Jersey "OnRamp" website, managed by the Department of Labor and Workforce Development, available online at http://webos.dol.state.nj.us/Talent/Login.aspx.

Note:  Posting shall not be required where the employer intends to fill the job opening with a present employee, a laid-off former employee, or a job candidate from a previous recruitment, where pre-existing legally binding collective bargaining agreements provide otherwise, or where an exception has been granted to the NJDOT by the Department of Labor and Workforce Development.

- The Contractor shall keep specific records of its efforts, including records of all individuals interviewed and hired, including the specific numbers of minorities and women;

- The Contractor shall actively solicit and shall provide the NJDOT with proof of solicitation for employment, including but not limited to advertisements in general circulation media, professional service publications and electronic media; and

- The Contractor shall provide evidence of efforts described at 2 above to the NJDOT no less frequently than once every 12 months.

- The Contractor shall comply with the requirements set forth at N.J.A.C. 17:27.

The Contractor is required to implement and maintain a specific Affirmative Action Compliance Program of Equal Employment Opportunity in support of the New Jersey “Law Against Discrimination”,  N.J.S.A. 10:5-31 et seq., and according to the Affirmative Action Regulations set forth at N.J.A.C. 17:27-1.1 et seq.

The provisions of N.J.S.A. 10:2-1 through 10:2-4 and N.J.S.A. 10:5-31 et seq., as amended and supplemented) dealing with discrimination in employment on public contracts, and the rules and regulations promulgated pursuant thereunto, are hereby made a part of this contract and are binding upon the Contractor.

Noncompliance by the Contractor with the requirements of the Affirmative Action program for Equal Employment Opportunity may be cause for delaying or withholding monthly and final payments pending corrective and appropriate measures by the Contractor to the satisfaction of the Department.

The Contractor will cooperate with the state agencies in carrying out its Equal Employment Opportunity obligations and in their review of its activities under the contract.

The Contractor and all its subcontractors, not including material suppliers, holding subcontracts of $2,500 or more, will comply with the following minimum specific requirement activities of Equal Opportunity and Affirmative Action set forth in these special provisions. The Contractor will include these requirements in every subcontract of $2,500 or more with such modification of language in the provisions of such contracts as is necessary to make them binding on the subcontractor.

During the performance of this contract, the contractor agrees as follows:

1.	The Contractor or subcontractor, where applicable, will not discriminate against any employee or applicant for employment because of age, race, creed, color, national origin, ancestry, marital status, affectional or sexual orientation, gender identity or expression, disability, nationality or sex.  Except with respect to affectional or sexual orientation and gender identity or expression, the Contractor will ensure that equal employment opportunity is afforded to such applicants in recruitment and employment, and that employees are treated during employment, without regard to their age, race, creed, color, national origin, ancestry, marital status, affectional or sexual orientation, gender identity or expression, disability, nationality or sex.  Such equal employment opportunity shall include, but not be limited to the following: employment, upgrading, demotion, or transfer; recruitment or recruitment advertising; layoff or termination; rates of pay or other forms of compensation; and selection for training, including apprenticeship.  The Contractor agrees to post in conspicuous places, available to employees and applicants for employment, notices to be provided by the Public Agency Compliance Officer setting forth provisions of this nondiscrimination clause.

2.	The Contractor or subcontractor, where applicable will, in all solicitations or advertisements for employees placed by or on behalf of the Contractor, state that all qualified applicants will receive consideration for employment without regard to age, race, creed, color, national origin, ancestry, marital status, affectional or sexual orientation, gender identity or expression, disability, nationality or sex.

3.	The Contractor or subcontractor, where applicable, will send to each labor union or representative of workers with which it has a collective bargaining agreement or other contract or understanding, a notice, to be provided by the agency contracting officer advising the labor union or workers’ representative of the contractor’s commitments under this act and shall post copies of the notice in conspicuous places available to employees and applicants for employment.

4.	The Contractor or subcontractor, where applicable, agrees to comply with any regulations promulgated by the Treasurer pursuant to N.J.S.A. 10:5-31 et seq., as amended and supplemented from time to time and the Americans with Disabilities Act.

5.	When hiring or scheduling workers in each construction trade, the Contractor or subcontractor agrees to make  good faith efforts to employ minority and women  workers in each construction trade consistent with the targeted  employment goal prescribed by N.J.A.C. 17:27-7.2; provided, however, that the Department of Labor and Workforce Development, Construction EEO Monitoring Program may, in its discretion, exempt a Contractor or subcontractor from compliance with the good faith procedures prescribed by the following provisions, a, b, and c, as long as the Department of Labor and Workforce Development, Construction EEO Monitoring Program is satisfied that the Contractor or subcontractor is employing workers provided by a union which provides evidence, in accordance with  standards prescribed by the Department of Labor and Workforce Development, Construction EEO Monitoring Program, that its percentage of active “card carrying” members who are minority and women  workers is equal to or greater than the targeted  employment goal established in accordance with  N.J.A.C. 17:27-7.2.   The Contractor or subcontractor agrees that a good faith effort shall include compliance with the following procedures:

a.	If the Contractor or subcontractor has a referral agreement or arrangement with a union for a construction trade, the Contractor or subcontractor shall, within three business days of the contract award, seek assurances from the union that it will cooperate with the Contractor or subcontractor as it fulfills its affirmative action obligations under this contract and in accordance with the rules promulgated by the Treasurer pursuant to N.J.S.A. 10:5-31 et. seq., as supplemented and amended from time to time and the Americans with Disabilities Act.  If the Contractor or subcontractor is unable to obtain said assurances from the construction trade union at least five business days prior to the commencement of construction work, the Contractor or subcontractor agrees to afford equal employment opportunities  to  minority and women workers directly, consistent with this chapter.  If the Contractor’s or subcontractor’s prior experience with a construction trade union, regardless of whether the union has provided said assurances, indicates a significant possibility that the trade union will not refer sufficient minority and women workers consistent with affording equal employment opportunities as specified in this chapter,  the Contractor or subcontractor agrees to be prepared to provide such opportunities to minority and women workers directly, consistent with this chapter, by complying with the hiring or scheduling procedures prescribed under (b) below; and the Contractor or subcontractor further agrees to  take said action immediately if it determines or is so notified by the Department of Labor and Workforce Development, Construction EEO Monitoring Program that the union is not referring minority and women  workers consistent with the equal  employment opportunity goals set forth in this chapter.

b.	If good faith efforts to meet targeted employment goals have not or cannot be met  for each construction trade by adhering to the procedures of (a) above, or if the Contractor does not have a referral agreement or arrangement with a union for a construction trade, the Contractor or subcontractor agrees to take the following actions:

(1)	To notify the Public Agency Compliance Officer, the Department of Labor and Workforce Development, Construction EEO Monitoring Program, and minority and women referral organizations listed by the Department of Labor and Workforce Development, Construction EEO Monitoring Program pursuant to N.J.A.C. 17:27-5.3, of its workforce needs, and request referral of minority and women workers;

(2) To notify any minority and women workers who have been listed with it as awaiting available vacancies;

(3)	Prior to commencement of work, to request that the local construction trade union refer minority and women workers to fill job openings, provided the Contractor or subcontractor has a referral agreement or arrangement with a union for the construction trade;

(4)	To leave standing requests for additional referral to minority and women workers with the local construction trade union, provided the Contractor or subcontractor has a referral agreement or arrangement with a union for the construction trade, the State Training and Employment Service and other approved referral sources in the area;

(5)	If it is necessary to lay off some of the workers in a given trade on the construction site, layoffs shall be conducted in compliance with the equal employment opportunity and non-discrimination standards set forth in this regulation, as well as with applicable State and Federal  court decisions;

(6)	To adhere to the following procedure when minority and women workers apply or are referred to the Contractor or subcontractor:

(i)	The contractor or subcontractor shall interview the referred minority or women worker.

(ii)	If said individuals have never previously received any document or certification signifying a level of qualification lower than that required in order to perform the work of the construction trade, the Contractor or subcontractor shall in good faith determine the qualifications of such individuals.  The Contractor or subcontractor shall hire or schedule those individuals who satisfy appropriate qualification standards in conformity with the equal employment opportunity and non-discrimination principles set forth in this chapter.  However a Contractor or subcontractor shall determine that the individual at least possesses the requisite skills and experience recognized by a union, apprentice program or a referral agency, provided the referral agency is acceptable to the Department of Labor and Workforce Development, Construction EEO Monitoring Program.  If necessary, the Contractor or subcontractor shall hire or schedule minority and women workers who qualify as trainees pursuant to these rules.  All of the requirements, however, are limited by the provisions of (c) below.

(iii)	The name of any interested women or minority individual shall be maintained on a waiting list, and shall be considered for employment as described in paragraph (i) above whenever vacancies occur.  At the request of the Department of Labor and Workforce Development, Construction EEO Monitoring Program, the Contractor or subcontractor shall provide evidence of its good faith efforts to employ women and minorities from the list to fill vacancies.

(iv)	If, for any reason, said Contractor or subcontractor determines that a minority individual or a woman is not qualified or if the individual qualifies as an advanced trainee or apprentice, the Contractor or subcontractor shall inform the individual in writing of the reasons for the determination, maintain a copy of the determination in its files, and send a copy to the Public Agency Compliance Officer and to the Department of Labor and Workforce Development, Construction EEO Monitoring Program.

(7)	To keep a complete and accurate record of all requests made for the referral of workers in any trade covered by the contract, and on forms made available by the Department of Labor and Workforce Development, Construction EEO Monitoring Program and submitted promptly to the Department of Labor and Workforce Development, Construction EEO Monitoring Program upon request.

c.	The Contractor or subcontractor agrees that nothing contained in (b) above shall preclude the Contractor or subcontractor from complying with the hiring hall or apprenticeship policies in any applicable collective bargaining agreement or union hiring hall arrangement, and, where required by custom or agreement, it shall send journeymen and trainees to the union for referral, or to the apprenticeship program for admission, pursuant to such agreement or arrangement.  However,  where practices of a union or apprenticeship program will result in the exclusion of minorities and women  or the failure to refer minorities and women consistent with the targeted county employment goal, the contractor or subcontractor shall consider for employment persons referred pursuant to (b) above without regard to such agreement or arrangement; provided further, however, that the Contractor or subcontractor shall not be required to employ women and minority advanced trainees and trainees in numbers which result in the employment of advanced trainees and trainees as a percentage of the total workforce for the construction trade, which percentage significantly exceeds the apprentice to journey worker ratio specified in the applicable collective bargaining agreement, or in the absence of a collective bargaining agreement, exceeds the ratio established by practice in the area for said construction trade.  Also, the Contractor or subcontractor agrees that, in implementing the procedures of (b) above, it shall, where applicable, employ minority and women workers residing within the geographical jurisdiction of the union.

After notification of award, but prior to signing a construction contract, the Contractor shall submit to the Public Agency Compliance Officer and the Department of Labor and Workforce Development, Construction EEO Monitoring Program an initial project workforce report (Form AA 201) provided to the public agency by the Department of Labor and Workforce Development, Construction EEO Monitoring Program for distribution to and completion by the contractor, in accordance with N.J.A.C. 17:27-7.

The Contractor and each subcontractor must submit monthly employment and wage data to the Department via a web based application using electronic Form CC-257R.  Instructions for registering and receiving the authentication code to access the web based application can be found at:

http://www.state.nj.us/transportation/business/civilrights/pdf/cc257.pdf

Instructions on how to complete Form CC-257R are provided in the web application.  Submit Form CC-257R through the web based application within 10 days following the end of the reporting month.

All employment and wage data must be accurate and consistent with the certified payroll records.  The Contractor is responsible for ensuring that their subcontractors comply with these reporting requirements.  Failure by the Contractor to submit Monthly Employment Utilization Reports may impact the contractor’s prequalification rating with the Department.

d.	The Contractor and its subcontractors shall furnish such reports or other documents to the Department of Labor and Workforce Development, Construction EEO Monitoring Program as may be requested by the Department of Labor and Workforce Development, Construction EEO Monitoring Program from time to time in order to carry out the purposes of these regulations, and public agencies shall furnish such information as may be requested by the Department of Labor and Workforce Development, Construction EEO Monitoring Program for conducting a compliance investigation pursuant to Subchapter 10 of the Administrative Code (NJAC 17:27).

e.	The Contractor agrees to cooperate with the public agency in the payment of budgeted funds, as is necessary, for on-the-job and off-the-job programs for outreach and training of minority and female trainees employed on the construction projects.

II.	EQUAL EMPLOYMENT OPPORTUNITY POLICY

The Contractor agrees that it will accept and implement during the performance of this contract as its operating policy the following statement which is designed to further the provision of Equal Employment Opportunity to all persons without regard to their age, race, color, religion, creed, national origin, ancestry, marital status, affectional or sexual orientation, gender identity or expression, disability, nationality or sex and to promote the full realization of Equal Employment Opportunity through a positive continuing program:

“It is the policy of this company that it will not discriminate against any employee or applicant for employment because of age, race, creed, color, national origin, ancestry, marital status, affectional or sexual orientation, gender identity or expression, disability, nationality or sex and that it will take Affirmative Action to ensure that applicants are recruited and employed and that employees are treated during employment without regard to their age, race, creed, color, national origin, ancestry, marital status, affectional or sexual orientation, gender identity or expression, disability, nationality or sex.  Such action shall include, but not be limited to, the following:  employment, upgrading, demotion or transfer; recruitment or recruitment advertising; layoff or termination; rates of pay or other forms of compensation; and selection for training, including apprenticeship.”

III.	EQUAL EMPLOYMENT OPPORTUNITY OFFICER

The Contractor will designate and make known to the Department contracting officers an Equal Employment Opportunity Officer (hereafter “EEO Officer”) who will have the responsibility for and must be capable of effectively administering and promoting an active Equal Employment Opportunity program and be assigned adequate authority and responsibility to do so.

IV.	DISSEMINATION OF POLICY

A.	All members of the Contractor’s staff who are authorized to hire, supervise, promote, and discharge employees, or who recommend such action, will be made fully cognizant of, and will implement, the Contractor’s Equal Employment Opportunity Policy and contractual responsibilities to provide Equal Employment Opportunity in each grade and classification of employment.  To ensure that the above agreement will be met, the following actions will be taken as a minimum:

1.	Periodic meetings of supervisory and personnel office employees will be conducted before the start of work and then not less often than once every 6 months, at which time the Contractor’s Equal Employment Opportunity Policy and its implementation will be reviewed and explained.  The EEO Officer or other knowledgeable company official will conduct the meetings.

2.	All new supervisory or personnel office employees will be given a thorough indoctrination by the EEO Officer or other knowledgeable company official covering all major aspects of the Contractor’s Equal Employment Opportunity obligations within 30 days following their reporting for duty with the Contractor.

3.	All personnel who are engaged in direct recruitment for the project will be instructed by the EEO Officer or appropriate company official in the Contractor’s Procedures for locating and hiring minority and women workers.

B.	In order to make the Contractor’s Equal Employment Opportunity Policy known to all employees, prospective employees and potential sources of employees, i.e., schools, employment agencies, labor unions (where appropriate), college placement officers, etc., the Contractor will take the following actions:

1.	Notices and posters setting forth in the Contractor’s Equal Employment Opportunity policy, as set forth in Section 2 of these Equal Employment Opportunity Special Provisions will be placed in conspicuous places readily accessible to employees, applicants for employment and potential employees.

2.	The Contractor’s Equal Employment Opportunity Policy and the procedures to implement such policy will be brought to the attention of employees by means of meetings, employee handbooks, or other appropriate channels.

V.	RECRUITMENT

A.	In all solicitations and advertisements for employees placed by or on behalf of the Contractor, the Contractor will state that all qualified applicants will receive consideration for employment without regard to age, race, creed, color, national origin, ancestry, marital status, affectional or sexual orientation, gender identity or expression, disability, nationality or sex.  All such advertisements will be published in newspapers or other publications having a large circulation among minorities and women in the area from which the project workforce would normally be derived.

B.	The Contractor will, unless precluded by a valid bargaining agreement, conduct systematic and direct recruitment through public and private employee referral sources likely to yield qualified minority and women applicants, including, but not limited to state employment agencies, schools, colleges and minority and women organizations. To meet this requirement, the Contractor will, through his/her EEO Officer, identify sources of potential minority and women employees, and establish with such identified sources procedures whereby minority and women applicants may be referred to the Contractor for employment consideration.

C.	In the event the Contractor has a valid bargaining agreement providing for exclusive hiring hall referrals, he is expected to observe the provisions of that agreement to the extent that the system permits the Contractor’s compliance with Equal Employment Opportunity contract provisions. (The US Department of Labor has held that where implementations of such agreements have the effect of discriminating against minorities or women, or obligates the Contractor to do the same; such implementation violates Executive Order 11246, as amended).

D.	In the event that the process of referrals established by such a bargaining agreement fails to provide the Contractor with a sufficient number of minority and women referrals within the time period set forth in such an agreement, the Contractor shall comply with the provisions of “Section IX Unions” of the EEO Special Provisions.

VI.	ESTABLISHMENT OF GOALS FOR CONSTRUCTION CONTRACTORS

A.	The New Jersey Department of Transportation has established, pursuant to N.J.A.C. 17:27-7.2, the minority and women goals for each construction contractor and subcontractor based on availability statistics as reported by the New Jersey Department of Labor, Division of Planning and Research, in its report, “EEO Tabulation - Detailed Occupations by Race/Hispanic Groups” as follows:

MINORITY AND WOMEN EMPLOYMENT GOAL OBLIGATIONS FOR CONSTRUCTION CONTRACTORS AND SUBCONTRACTORS

| COUNTY | MINORITY % PERCENTAGE | WOMEN % PERCENTAGE |
| --- | --- | --- |
| Atlantic | 18 | 6.9 |
| Bergen | 22 | 6.9 |
| Burlington | 15 | 6.9 |
| Camden | 19 | 6.9 |
| Cape May | 5 | 6.9 |
| Cumberland | 27 | 6.9 |
| Essex | 53 | 6.9 |
| Gloucester | 9 | 6.9 |
| Hudson | 60 | 6.9 |
| Hunterdon | 3 | 6.9 |
| Mercer | 30 | 6.9 |
| Middlesex | 24 | 6.9 |
| Monmouth | 15 | 6.9 |
| Morris | 16 | 6.9 |
| Ocean | 7 | 6.9 |
| Passaic | 36 | 6.9 |
| Salem | 10 | 6.9 |
| Somerset | 20 | 6.9 |
| Sussex | 4 | 6.9 |
| Union | 45 | 6.9 |
| Warren | 5 | 6.9 |

The Department of Labor and Workforce Development, Construction EEO Monitoring Program has interpreted Section 7.2 of the State of New Jersey Affirmative Action Regulations as applicable to work hour goals for minority and women participation.

If a project is located in more than one county, the minority work hour goal will be determined by the county which serves as the primary source of hiring or, if workers are obtained equally from one or more counties, the single minority goal shall be the average of the individual goal for the affected counties.

B.	The State Department of Labor and Workforce Development, Construction EEO Monitoring Program may designate a regional goal for minority membership for a union that has regional jurisdiction. No regional goals shall apply to this project unless specifically designated elsewhere herein.

C.	When hiring workers in the construction trade, the Contractor and/or subcontractor agree to attempt, in good faith, to employ minority and women workers in each construction trade, consistent with the applicable county or, in special cases, regional goals.

D.	It is understood that the goals are not quotas. If the Contractor or subcontractor has attempted, in good faith, to satisfy the applicable goals, he will have complied with his obligations under these EEO Special Provisions. It is further understood that if the Contractor shall fail to attain the goals applicable to this project, it will be the Contractor’s obligation to establish to the satisfaction of the Department of Transportation that it has made a good faith effort to satisfy such goals. The Contractor or subcontractor agrees that a good faith effort to achieve the goals set forth in these special provisions shall include compliance with the following procedures:

1.	Requests shall be made by the Contractor or subcontractor to each union or collective bargaining unit with which the Contractor or subcontractor has a referral agreement or arrangement for the referral of minority and women workers to fill job openings. Requests shall also be made for assurances for the referral of minority and women workers to fill job openings. Requests shall also be made for assurances from such unions or collective bargaining units that they will cooperate with the Contractor or subcontractor in fulfilling the Affirmative Action obligations of the Contractor or subcontractor under this contract. Such requests shall be made prior to the commencement of construction under the contract.

2.	The Contractor and its subcontractors shall comply with Section IX, Unions of these EEO Special Provisions and, in particular, with Section IX, Paragraph D, if the referral process established in any collective bargaining arrangement is failing to provide the Contractor or subcontractor with a sufficient number of minority and women referrals.

3.	The Contractor and its subcontractors shall notify the Department’s Compliance Officer, the Department of Labor and Workforce Development, Construction EEO Monitoring Program of the Department of Treasury and at least one approved minority referral organization of the Contractor’s or subcontractors work force needs and of the Contractor’s or subcontractor’s desire for assistance in attaining the goals set forth herein. The notifications should include a request for referral of minority and women workers.

4.	The Contractor and its subcontractors shall notify the Department’s Compliance Officer and the Department of Labor and Workforce Development, Construction EEO Monitoring Program of the Department of Treasury in the event that a union or collective bargaining unit is not making sufficient minority and women referrals to enable the Contractor or subcontractor to attain the workforce goals for the Project.

5.	The Contractor and its subcontractors shall make standing requests to all local construction unions, the state training and employment service and other approved referral sources for additional referrals of minority and women workers until such time as the project workforce is consistent with the work hour goals for the project.

6.	The Contractor and its subcontractors shall make standing requests to all local construction unions, the state training and employment service and other approved referral sources for additional referrals of minority and women workers until such time as the project workforce is consistent with the work hour goals for the project.

7.	In the event that it is necessary to lay off some of the workers in a given trade on the construction site, the Contractor and its subcontractors shall ensure that fair layoff practices are followed regarding minority, women and other workers.

8.	The Contractor and its subcontractors shall comply with the other requirements of these EEO Special Provisions.

VII. 	PERSONNEL ACTIONS

Wages, working conditions, and employee benefits shall be established and administered, and personnel actions of every type, including hiring, upgrading, promotion, transfer, demotion, layoff, and termination, shall be taken without regard to age, race, color, creed, national origin, ancestry, marital status, affectional or sexual orientation, gender identity or expression, disability, nationality or sex.  The following procedures shall be followed:

A.	The Contractor will conduct periodic inspections of project sites to ensure that working conditions and employee facilities do not indicate discriminatory treatment of project site personnel.

B.	The Contractor will periodically evaluate the spread of wages paid within each classification to determine any evidence of discriminatory wage practices.

C.	The Contractor will periodically review selected personnel actions in-depth to determine whether there is evidence of discrimination. Where evidence is found, the Contractor will promptly take corrective action.  If the review indicates that the discrimination may extend beyond the actions reviewed, such corrective action shall include all affected persons.

D.	The Contractor will promptly investigate all complaints of alleged discrimination made to the Contractor in connection with his/her obligations under this contract, will attempt to resolve such complaints, and will take appropriate corrective action within a reasonable time. If the investigation indicates that the discrimination may affect persons other than the complainant, such corrective action shall include such other persons. Upon completion of each investigation, the Contractor will inform every complainant of all of his/her avenues of appeal.

VIII.	TRAINING AND PROMOTION

The Contractor will assist in locating, qualifying, and increasing the skills of minority group and women workers, and applicants for employment.

Consistent with the Contractor’s workforce requirements and as permissible under State regulations, the Contractor shall make full use of training programs, i.e., apprenticeship, and on-the-job training programs, for the geographical area of contract performance.  Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

The Contractor will advise employees and applicants for employment of available training programs and entrance requirements for each.

The Contractor will periodically review the training and promotion potential of minority group and women workers and will encourage eligible employees to apply for such training and promotion.

IX.	UNIONS

If the Contractor relies in whole or in part upon unions as a source of employees, the Contractor will use his/her best efforts to obtain the cooperation of such unions to increase opportunities for minority groups and women within the unions, and to effect referrals by such unions of minority and women workers.  Actions by the Contractor either directly or through a Contractor’s association acting, as agent will include the procedures set forth below:

A.	The Contractor will send to each labor union or representative of workers with which it has a collective bargaining agreement or other contract of understanding, a notice advising the labor union or workers’ representative of the Contractor’s commitments under both the law against discrimination and this contract and shall post copies of the notice in conspicuous places readily accessible to employees and applicants for employment. Further, the notice will request assurance from the union or worker’s representative that such union or worker’s representative will cooperate with the Contractor in complying with the Contractor’s Equal Employment Opportunity and Affirmative Action obligations.

B.	The Contractor will use their best efforts to develop, in cooperation with the unions, joint training programs aimed toward qualifying more minority group members and women for membership in the unions and increasing the skills of minority group employees and women so that they may qualify for higher paying employment.

C.	The Contractor will use their best efforts to incorporate an Equal Employment Opportunity clause into each union agreement to the end that such union will be contractually bound to refer applicants without regard to their age, race, color, creed, sex, national origin, ancestry, marital status, affectional or sexual orientation, gender identity or expression, disability, or nationality.

D.	The Contractor is to obtain information as to the referral practices and policies of the labor union except to the extent that such information is within the exclusive possession of the labor union and such labor union refuses to furnish such information to the Contractor, the Contractor shall so certify to the NJDOT and shall set forth what efforts have been made to obtain such information.

E.	In the event the union is unable to provide the Contractor with a reasonable flow of minority and women referrals within the time limit set forth in the collective bargaining agreement, the Contractor will, through independent recruitment efforts, fill the employment vacancies without regard to age, race, color, creed, sex, national origin, ancestry, marital status, affectional or sexual orientation, gender identity or expression, disability, or nationality making full efforts to obtain qualified and/or qualifiable minority group persons and women. (The US Department of Labor has held that it shall be no excuse that the union with which the Contractor has a collective bargaining agreement providing for exclusive referral failed to refer minority employees). In the event the union referral practice prevents the Contractor from meeting the obligations pursuant to Executive Order 11246, as amended, and these Special Provisions, such Contractor shall immediately notify the NJDOT.

X.	SUBCONTRACTING

A.	The Contractor will use his best efforts to solicit bids from and to utilize minority group and women subcontractors or subcontractors with meaningful minority group and women representation among their employees.  Contractors may use lists of minority owned and women owned construction firms as issued by the NJDOT and/or the New Jersey Unified Certification Program (NJUCP).

B.	The Contractor will use his best efforts to ensure subcontractor compliance with their Equal Employment Opportunity obligations.

XI.	RECORDS AND REPORTS

A.	The Contactor will keep such records as are necessary to determine compliance with the Contractor’s Equal Employment Opportunity obligations.  The records kept by the Contractor will be designed to indicate:

1.	The work hours of minority and non-minority group members and women employed in each work classification on the project;

2.	The progress and efforts being made in cooperation with unions to increase employment opportunities for minorities and women (applicable only to Contractors who rely in whole or in part on unions as a source of their workforce);

3.	The progress and efforts being made in locating, hiring, training, qualifying, and upgrading minority and women workers; and

4.	The progress and efforts being made in securing the services of minority group and women subcontractors or subcontractors with meaningful minority and women representation among their employees.

B.	All such records must be retained for a period of 3 years following completion of the contract work and shall be available at reasonable times and places for inspection by authorized representatives of the NJDOT.

C.	The Contractor shall submit monthly reports to the NJDOT after construction begins for the duration of the project, indicating the work hours of minority, women, and non minority group employees currently engaged in each work classification required by the contract work. This information is to be reported on a form supplied by the NJDOT.

XII	SPECIAL CONTRACT PROVISIONS FOR INVESTIGATING, REPORTING AND RESOLVING EMPLOYMENT DISCRIMINATION AND SEXUAL HARASSMENT COMPLAINTS

The Contractor hereby agrees to the following requirements in order to implement fully the nondiscrimination provisions of the Supplemental Specifications:

The Contractor agrees that in instances when it receives from any person working on the project site a verbal or written complaint of employment discrimination, prohibited under N.J.S.A. 10:5-1 et seq. 10:2-1 et seq., 42 U.S.C. 2000 (d) et seq., 42 U.S.C. 2000(e) et seq. And Executive Order 11246, it shall take the following actions:

1.	Within one (1) working day commence an investigation of the complaint, which will include but not be limited to interviewing the complainant, the respondent, and all possible witnesses to the alleged act or acts of discrimination or sexual harassment.

2.	Prepare and keep for its use and file a detailed written investigation report which includes the following information:

a)	Investigatory activities and findings.

b)	Dates and parties involved and activities involved in resolving the complaint.

c)	Resolution and corrective action taken if discrimination or sexual harassment is found to have taken place.

d)	A signed copy of resolution of complaint by complainant and Contractor.

(In addition to keeping in its files the above-noted detailed written investigative report, the Contractor shall keep for possible future review by the NJDOT all other records, including, but not limited to, interview memos and statements.)

3.	Upon the request of the NJDOT provides to the NJDOT within ten (10) calendar days a copy of its detailed written investigative report and all other records on the complaint investigation and resolution.

4.	Take appropriate disciplinary actions against any Contractor employee, official or agent who has committed acts of discrimination or sexual harassment against any Contractor employee or person working on the project. If the person committing the discrimination is a subcontractor employee, then the Contractor is required to attempt to effectuate corrective and/or disciplinary action by the subcontractor in order to establish compliance with project’s contract requirements.

5.	Take appropriate disciplinary action against any Contractor employee, official or agent who retaliates, coerces or intimidates any complainant and/or person who provides information or assistance to any investigation of complaints of discrimination or sexual harassment. If the person retaliating, coercing or intimidating a complainant or other person assisting in an investigation is a subcontractor’s employee, then the Contractor is required to attempt to effectuate corrective and/or disciplinary action taken by the subcontractor in order to establish compliance with the project’s contract requirements.

6.	Ensure to the maximum extent possible that the privacy interests of all persons who give confidential information in aid of the Contractor’s employment discrimination investigation are protected.

7.	In conjunction with the above requirements, the Contractor herein agrees to develop and post a written sexual harassment policy for its workforce.

8.	The Contractor also agrees that its failure to comply with the above requirements may be cause for the New Jersey Department of Transportation to institute against the Contractor any and all enforcement proceedings and/or sanctions authorized by the contract or by state and/or federal law.

2**************************************************************************************2

state Attachment No. 2

PAYROLL REQUIREMENTS FOR 100% STATE PROJECTS

1.	Each contractor and subcontractor shall furnish the RE with payroll reports for each week of contract work. Such reports shall be submitted within 10 days of the date of payment covered thereby and shall contain the following information:

A.	Each employee’s full name and the last four digits of social security number of each such employee.

B.	Each employee’s specific work classification (s).

C.	Entries indicating each employee’s basis hourly wage rate(s) and, where applicable, the overtime hourly wage rate(s). Any fringe benefits paid to the employee in cash must be indicated.

D.	Each employee’s daily and weekly hours worked in each classification, including actual overtime hours worked (not adjusted).

E.	Each employee’s gross wage.

F.	The itemized deductions made.

G.	The net wages paid.

2.	Each contractor or subcontractor shall furnish a statement each week to the RE with respect to the wages paid each of its employees engaged in contract work covered by the New Jersey Prevailing Wage Act during the preceding weekly payroll period. The statement shall be executed by the contractor or subcontractor or by an authorized officer or employee of the contractor or subcontractors who supervises the payment of wages. Contractors and subcontractors must use the certification set forth on New Jersey Department of Transportation Form FA-7 “Statement of Compliance,” or the same certification set forth on (1) U.S. Department of Labor Form WH-348, (2) the reverse side of U. S. Department of Labor Form WH-347, or (3) any form with identical wording.

3.	Contractor and subcontractor shall maintain complete social security numbers and home address for employees. Government agencies are entitled to request or review all relevant payroll information, including social security numbers and addresses of employees. Contractors and subcontractors are required to provide such information upon request.

state Attachment No. 3

AMERICANS WITH DISABILITIES ACT

100% STATE FUNDED CONTRACTS

Equal Opportunity For Individuals With Disabilities.

The CONTRACTOR and the STATE do hereby agree that the provisions of Title II of the American With Disabilities Act of 1990 (the “ACT”) (42 U.S.C. Section 12101 et seq.), which prohibits discrimination on the basis of disability by public entities in all services, programs, and activities provided or made available by public entities, and the rules and regulations promulgated pursuant thereunto, are made a part of this contract. In providing any aid, benefit, or service on behalf of the STATE pursuant to this contract, the CONTRACTOR, agrees that the performance shall be in strict compliance with the Act. In the event that the CONTRACTOR, its agents, servants, employees, or subcontractors violate or are alleged to have violated the Act during the performance of this contract, the CONTRACTOR shall defend the STATE in any action or administrative proceeding commenced pursuant to this Act. The CONTRACTOR shall indemnify, protect, and save harmless the STATE, its agents, servants, and employees from and against any and all suits, claims, losses, demands, or damages of whatever kind or nature arising out of or claimed to arise out of the alleged violation. The CONTRACTOR shall, at its own expense, appear, defend, and pay any and all charges for legal services and all costs and other expenses arising from such action or administrative proceeding or incurred in connection therewith. In any and all complaints brought pursuant to the STATE’S grievance procedure, the CONTRACTOR agrees to abide by any decision of the STATE which is rendered pursuant to said grievance procedure. If any action or administrative proceeding results in an award of damages against the STATE or if the STATE incurs any expense to cure a violation of the ADA which has been brought pursuant to its grievance procedure, the CONTRACTOR shall satisfy and discharge the same at its own expense.

The STATE shall, as soon as practicable after a claim has been made against it, give written notice thereof to the CONTRACTOR along with full and complete particulars of the claim. If any action or administrative proceeding is brought against the STATE or any of its agents, servants, and employees, the STATE shall expeditiously forward or have forwarded to the CONTRACTOR every demand, complaint, notice, summons, pleading, or other process received by the STATE or its representatives.

It is expressly agreed and understood that any approval by the STATE of the services provided by the CONTRACTOR pursuant to this contract will not relieve the CONTRACTOR of the obligation to comply with the Act and to defend, indemnify, protect, and save harmless the STATE pursuant to this paragraph.

It is further agreed and understood that the STATE assumes no obligation to indemnify or save harmless the CONTRACTOR, its agents, servants, employees and subcontractors for any claim which may arise out of their performance of this Agreement. Furthermore, the CONTRACTOR expressly understands and agrees that the provisions of this indemnification clause shall in no way limit the CONTRACTOR’S obligations assumed in this Agreement, nor shall they be construed to relieve the CONTRACTOR from any liability, nor preclude the STATE from taking any other actions available to it under any other provisions of this Agreement or otherwise at law.

state Attachment No. 4

SMALL BUSINESS ENTERPRISE UTILIZATION ATTACHMENT

100% STATE-FUNDED CONTRACTS

I.	UTILIZATION OF SMALL BUSINESS ENTERPRISE (SBE) BUSINESSES AS CONTRACTORS, MATERIAL SUPPLIERS AND EQUIPMENT LESSORS.

The New Jersey Department of Transportation advises each contractor or subcontractor that failure to carry out the requirements set forth in this attachment shall constitute a breach of contract and, after notification to the applicable State agency, may result in termination of the agreement or contract by the Department or such remedy as the Department deems appropriate. Requirements set forth in this section shall also be included in all subcontract agreements in accordance with State of New Jersey requirements.

II.	POLICY

It is the policy of the New Jersey Department of Transportation that Small Business Enterprises, as defined in N.J.A.C. 12A: 10A-1.2 et seq., and N.J.A.C. 17:14-1.2 et seq., shall have the maximum opportunity to participate in the performance of contracts financed wholly with 100% state funds.

III.	CONTRACTOR’S SMALL BUSINESS OBLIGATION

The New Jersey Department of Transportation and its Contractor agree to ensure that Small Business Enterprises (SBE), as defined in N.J.A.C. 12A: 10A-1.2 et seq., and N.J.A.C. 17:14-1.2 et seq., have maximum opportunity to participate in the performance of contracts and subcontracts financed wholly with 100% state funds. In this regard, the New Jersey Department of Transportation and all Contractors shall take all necessary and reasonable steps to ensure that Small Business Enterprises are utilized on, compete for, and perform on NJDOT construction contracts. The New Jersey Department of Transportation and its Contractors shall not discriminate on the basis of race, color, national origin, or sex in the award and performance of State-funded contracts.

IV.	COMPLIANCE

To signify and affirm compliance with the provisions of this attachment, the bidder shall complete the Schedule of Small Business Participation “Form CR-266S” included in the Proposal and all forms and documents required in Sections VII and VIII of these provisions which will be made a part of the resulting contract.

V.	SMALL BUSINESS GOALS FOR THIS PROJECT

#### NOTE:	SUBCONTRACTING GOALS ARE NOT APPLICABLE IF THE PRIME CONTRACTOR IS A REGISTERED SMALL BUSINESS ENTERPRISE (SBE) FIRM.

A.	This project includes a goal of awarding ___ % percent of the total contract value to subcontractors qualifying as SMALL BUSINESSES.

B.	Only Small Business Enterprises registered prior to the date of bid, or prospective Small Business Enterprises that have submitted to the New Jersey Commerce and Economic Growth Commission on or before the day of bid, a completed “State of New Jersey Small Business Vendor Registration Form” and all the required support documentation, will be considered in determining whether the contractor has met the established goals for the project. Early submission of required documentation is encouraged.

C.	If a prospective Small Business Enterprise fails to meet the eligibility standards for participation the department’s Small Business Program, the contractor shall, prior to the award, make reasonable outreach efforts to replace that ineligible subcontractor with a registered Small Business whose participation is sufficient to meet the goal for the contract.

D.	Prospective Small Businesses whose registration applications are denied or rejected by the New Jersey Commerce and Growth Commission are ineligible for participation on the project to meet Small Business goals, regardless of any pending appeal action in progress.

E.	A directory of registered Small Businesses Enterprise firms is available upon request to the New Jersey Commerce and Growth Commission or the New Jersey Department of Transportation, Division of Civil Rights/Affirmative Action. The directory is to be used as a source of information only and does not relieve the Contractor of their responsibility to seek out Small Businesses Enterprises not listed.

VI.	COUNTING SMALL BUSINESS ENTERPRISE PARTICIPATION

A.	Each Small Business Enterprise (SBE) is subject to a registration procedure to ensure their SBE eligibility prior to the award of contract. In order to facilitate this process, it is advisable for the bidder to furnish the names of proposed SBEs to the Department before bid opening. Once a firm is determined to be a bona fide SBE by the New Jersey Commerce and Growth Commission, the total dollar value of the contract awarded to the SBE is counted toward the applicable goal.

B.	The Contractor may count toward its SBE goal only expenditures to SBEs that perform a commercially useful function in the work of a contract. A SBE is considered to perform a commercially useful function when it is responsible for execution of a distinct element of the work of a contract and carrying out its responsibility by actually performing, managing and supervising the work involved. To determine whether a SBE is performing a commercially useful function, the Contractor shall evaluate the amount of work subcontracted, industry practice and other relevant factors.

C.	If an SBE does not perform or exercise responsibility for at least 30 percent of the total cost of its contract with its own work force, or the SBE subcontracts a greater portion of the work of a contract than would be expected on the basis of normal industry practice for the type of work involved, you must presume that it is not performing a commercially useful function.

D.	If a Contractor is part of a Joint Venture and one or more of the Sole Proprietorships, Partnerships, Limited Liability companies or Corporations comprising the Joint Venture is a registered SBE, the actual payments made to the Joint Venture for work performed by the SBE member, will be applied toward the goal. Payments made to the Joint Venture for work performed by a non-small business firm will not be applied toward the applicable goal.

E.	If the Contractor is a registered SBE, payments made to the Contractor for work performed by the Contractor will be applied toward the SBE goal.  Payments made to the Contractor for work performed by non-SBE’s will not be applied toward the goal.

F.	When a SBE subcontracts part of the work of its contract to another firm, the value of the subcontracted work may be counted towards the SBE goals only if the SBE’s subcontractor is also a SBE. Work that a SBE subcontracts to a non-SBE firm does not count toward the assigned goal.

VII.	SUBMISSION OF CONTRACTOR’S AFFIRMATIVE ACTION PLANS

A.	Contractors are required to submit annually on their due date, their firm’s Affirmative Action Program to the Division of Civil Rights/Affirmative Action. Contractors must have an approved Affirmative Action Program in the Division of Civil Rights/Affirmative Action no later than seven (7) State business days after receipt of bids. No recommendations to award will be made without an approved Affirmative Action Program on file in the Division of Civil Rights/Affirmative Action.

B.	The Annual Affirmative Action Program will include, but is not limited to the following:

1.	The name of the company’s Liaison Officer who will administer the Small Business Enterprise Program.

2.	An explanation of the affirmative action methods used in seeking out and considering Small Business Enterprises as subcontractors, material suppliers or equipment lessors.

3.	An explanation of affirmative action methods which will be used in seeking out future Small Business Enterprises as subcontractors, material suppliers or equipment lessors after the award of the contract and for the duration of said project.

C.	The following shall be submitted either with the bid or to the Division of Civil Rights/Affirmative Action no later than seven (7) state business days after the receipt of bids.

1.	SBE FORM CR-266S Schedule of SBE Participation. The Contractor shall list all SBEs that will participate in the contract including scope of work, actual dollar amount and percent of total contract to be performed. This form should be submitted only if the goal level established for the contract has been met or exceeded;

Note: If a change occurs to the Contractor’s original Form A submission which was previously approved by the Division of Civil Rights/Affirmative Action, a Revised Form CR-266S must be submitted naming the replacement Small Business Enterprise subcontractors. A written explanation should be included with the submission of the revised Form CR-266S.

2.	Request for Exemption - In the event the Contractor is unable to meet the specified goal level, that Contractor must submit a written request for a partial or full exemption from the SBE goal. This request shall include the names of all SBE firms that the contractor will utilize on the contract and shall describe the specific work to be performed by each SBE together with the actual dollar amount of that work. Additionally, this request must address the Contractor’s efforts to make Reasonable Outreach Efforts as enumerated in Section VIII.

3.	Additional Information - The Department in its sole discretion may request additional information from the Contractor prior to award of the contract in order to evaluate the Contractor’s compliance with the SBE requirements of the bid proposal. Such information must be provided within the time limits established by the department. The Contractor shall, prior to the award of the contract, submit a completed SBE “Form CR-266S”, even if it has been granted an exemption from the SBE goal.

VIII.	REASONABLE OUTREACH EFFORTS

If a Contractor fails to meet the goal for Small Business Enterprise participation, the Contractor shall document its reasonable outreach efforts to meet the SBE goal. Reasonable outreach shall include, but not be limited to the following:

A.	Attendance at a pre-bid meeting, if any, scheduled by the Department to inform SBE’s of subcontracting opportunities under a given solicitation.

B.	Advertisement in general circulation media, trade association publications, and small business enterprise-focus media for at least 20 days before bids are due. If 20 days are not available, publication for a shorter reasonable time is acceptable.

C.	Written notification to SBE’s that their interest in the contract is solicited;

D.	Efforts made to select portions of the work proposed to be performed by SBEs in order to increase the likelihood of achieving the stated goal;

E.	Efforts made to negotiate with SBE’s for specific sub-bids including at a minimum

1.	The names, addresses and telephone numbers of SBE’s that were contacted;

2.	A description of the information provided to SBE’s regarding the plans and specifications for portions of the work to be performed; and

3.	A statement of why additional agreements with SBE’s were not reached;

F.	Information regarding each SBE the bidder contacted and rejected as unqualified and the reasons for the bidder’s conclusion;

G.	Efforts made to assist the SBE in obtaining bonding or insurance required by the Bidder or the Department.

IX.	ADMINISTRATIVE RECONSIDERATION

A.	If the Division of Civil Rights/Affirmative Action determines that the apparent successful bidder has failed to make reasonable outreach efforts to meet the requirements of this section, the Department must, before awarding the contract, provide the bidder an opportunity for administrative reconsideration.

B.	As part of this reconsideration, the bidder will have the opportunity to provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so. NJDOT will send the bidder a written decision on reconsideration, explaining the basis for finding that the bidder did or did not meet the SBE goal or make an adequate good faith effort to do so.

C.	Within seven (7) State business days of being informed by the Division of Civil Rights/Affirmative Action that it is not a responsible bidder because it has not made or documented sufficient outreach efforts to SBEs, a bidder may make a request in writing to the Director, Division of Procurement, PO Box 605, Trenton, New Jersey, 08625-0605; Telephone (609) 530-6355. The Director, Division of Procurement, does not participate in the initial determination of whether reasonable outreach was performed by the Contractor.

X.	RESPONSIBILITY AFTER AWARD OF THE CONTRACT

If at any time following the award of contract, the Contractor intends to sublet any portion(s) of the work under said contract, or intends to purchase material or lease equipment not contemplated during preparation of bids, said Contractor shall take affirmative action:

A.	To notify the RE, in writing, of the type and approximate value of the Contractor intends to accomplish by such subcontract, purchase order or lease.

B.	To signify and affirm compliance with the provisions of this Section, the Contractor shall submit the Post-Award SBE Certification Form to the Regional Supervising Engineer with his application to sublet or prior to purchasing material or leasing equipment. Post Award SBE forms may be obtained from the RE.

C.	To give small business enterprise firms equal consideration with non-small business firms in negotiation for any subcontracts, purchase orders or leases.

XI.	CONSENT BY DEPARTMENT TO SUBLETTING

A.	The Department will not approve any subcontracts proposed by the Contractor unless and until said contractor has complied with the terms of this SBE Utilization Attachment.

B.	The Contractor shall provide the RE with a listing of firms, organizations or enterprises to be used as subcontractors on the proposed project. Such listing shall clearly delineate which firms are classified as SBEs.

C.	Notification of a subcontractor’s termination shall be sent to the Department by the Contractor through the RE.

XII.	CONCILIATION

In cases of alleged discrimination regarding these and all equal employment opportunity provisions and guidelines, investigations and conciliation will be undertaken by the Division of Civil Rights/Affirmative Action, New Jersey Department of Transportation.

XIII.	DOCUMENTATION

A.	Records and Reports

The Contractor shall keep such records as are necessary to determine compliance with its Small Business Enterprise Utilization obligations. The records kept by the Contractor will be designed to indicate:

1.	The names of the small business enterprise subcontractors, equipment lessors and material suppliers contacted for work on this project.

2.	The type of work to be done, materials to be utilized or services to be performed other than by the prime contractor on the project.

3.	The actual dollar amount of work awarded to SBE’s.

4.	The progress and efforts being made in seeking out and utilizing Small Business Enterprise firms. This would include solicitations, quotes and bids regarding project work items, supplies, leases, etc.

5.	Documentation of all correspondence, contacts, telephone calls, etc, to obtain the services of Small Business Enterprise firms on this project.

B.	The contractor shall submit reports, as required by the Department, on those contracts and other business transactions executed with Small Business Enterprise firms in such form and manner as may be prescribed by the Department.

C.	All such records must be maintained for a period of three (3) years following acceptance of final payment and will be available for inspection by the Department.

XIV.	PAYMENT TO SUBCONTRACTORS

The Contractor agrees to pay its subcontractors in accordance with the Specifications.

XV.	SANCTIONS

Failure of a Contractor to comply with these provisions may result in bid rejection, reduced classification, suspension, debarment, or the institution of other appropriate action by the New Jersey Department of Transportation.

1**************************************************************************************************************************1