## Contractor Invoice Package
Infrastructure Programs
Contractor Invoice Package Checklist
Project ID Number | Invoice Request Number
Project Name | Date
Subrecipient | Preparer
Invoice Package | [6 empty] | Does this section make more sense here after they go through the process of attaching the required items in the checklist?
Item | Yes | No | N/A | SIROMS BPM File Location | File Naming Convention | Instructions
Complete Invoice Package |  |  |  | CON_INVOICE | Contractor Invoice No XX_Month(s) 20XX | All items listed in the below checklist were included in the Invoice Package.
Invoice Package Parts | [6 empty] | Team Comments - MBI to verify if this works with their process.
Item | Yes | No | N/A | SIROMS BPM File Location | File Naming Convention | Instructions | Changed Comments to Instructions and moved the Yes/No/ N/A line under each sub heading line.
Cover Letter |  |  |  | N/A | N/A | Include the % complete, work period, total invoice amount, amount being submitted for reimbursement, any program income received, and lists of invoice package parts. | Can we create a template Cover Letter for the Subrecipients to complete as part of the checklist?
Purchase Order |  |  |  | N/A | N/A | Provide original purchase order from the Municipality/County for the project.
Canceled Check/Electronic Wire Proof from Subrecipient to Contractor of Payment |  |  |  | N/A | N/A | Provide a copy of your proof of payment.
Schedule of Values (SOV) |  |  |  | N/A | N/A | The SOV is the formal Grant tracking log of quantities and payments.
Stored Material Tracking (If Applicable) |  |  |  | N/A | N/A | If payment is being sought for stored material, must provide: location, photos, invoice, proof of insurance, etc.
Actual Pay Application from Contractor |  |  |  | N/A | N/A | Contractor to submit their pay application (in their format) to Subrecipient.
Engineer’s Certificate |  |  |  | N/A | N/A | Engineer/CMCI Team to sign off on requested payment amount.
Grant Compliance Certificate |  |  |  | NA | NA | Subrecipient (or designated Rep.) to certify all required forms listed below are submitted.
Request for Information (RFI) Log |  |  |  | N/A | N/A | Prepared by the Designer of Record.
Submittal Log |  |  |  | N/A | N/A | Prepared by the Designer of Record.
Material Back-Up Documentation |  |  |  | N/A | N/A | Provide copies of delivery slips for material brought to the site.
Monthly Inspection Summary Reports |  |  |  | CON_MONTHLY PRG | Monthly Report_Month 20XX | Subrecipient's Engineer/Construction Management/Inspection team to provide a monthly summary of work performed and % complete.
Associated Invoice Compliance (Statement of Assurances) Document Monitoring
Item | Yes | No | N/A | SIROMS BPM File Location | File Naming Convention | Instructions
Certified Payroll Report (CPR) (i.e. Federal Form 347/348) |  |  |  | CON_CPR&FRINGE | CPR_Month 20XX | CPR format needs to be similar to Federal Form 347/348. See notes 1 & 2.
Contractor’s letter authorizing signatory for CPRs |  |  |  | CON_CPR&FRINGE | Signatory Letter_Company Name | Ensure this was obtained prior to first invoice from Contractor and Subs.
Proof of Federal and State Labor Law and Grant Posters on site. |  |  |  | CON_OTHER | Prevailing Wage Posters | Ensure this was obtained prior to first invoice and filed in SIROMS.
Union & Cash Fringe Back-Up/Apprentice Back-Up |  |  |  | CON_CPR&FRINGE | Fringe_Month 20XX | Provide proof that benefits are being paid with letters of good standing from Unions for each Contractor/Subcontractor. Provide proof that apprentices are in a bonafide program.
Wage Rate Table |  |  |  | CON_WAGE RATE | Wage Rates_Month 20XX | Update Wage Rate Table as required from Contractor and Subs.
Contractor Form AA202 |  |  |  | CON_AA201 | AA202_Month 20XX | To be provided by the Contractor and Subs.
HUD 11s |  |  |  | CON_HUD 11 | HUD 11_Month 20XX | Employee interviews conducted by CMCI team.
Section 3 Plan - Monthly Update |  |  |  | CON_SECTION 3 | SECTION 3_Month 20XX | To be provided by the Contractor
Contractor’s NJ Small /Woman / Minority / Veteran Business Enterprise (SWMVBE) Contract & Subcontract Activity Report X Quarter 202X |  |  |  | CON_SMVWBE | SMVWBE_Quarter X 20XX | To be provided by the Contractor
Contractor’s Section 3 Utilization Plan for the X Quarter 202X |  |  |  | CON_SECTION 3 | Section 3_Quarter X 20XX | To be provided by the Contractor
System for Award Management (SAM) Verification (PDF Proof from SAM.gov) |  |  |  | CON_OTHER | SAMS_Contractor Name | Ensure this was obtained prior to first invoice - Update as needed. | SAMS changed to SAM
Notes:
1.) Sampling of actual Paystubs are needed for first invoice from Contractor/Subs. Once paystubs are received and verified against first invoice Certified Payrolls/347s, they will not be required again unless determined necessary.
2.) Orignal hard copy wet-ink signatures of certified payrolls are required with each invoice package.