## Website_Appl_Status_Updates
Project Lead | Docket Number | Applicant | Description | Municipality | County | State | State Regional Office | GWPA | SPW Location | NJ Critical Water Supply Area | Type of Renewal or New Project | Type of Project | Type of Water Supply | Import / Export | App. Received Date | # Days In House | Date of NAR | Approval Type / AA | Date AA Posted on Web | ProjStatusType
EE | D-1973-193 CP-3 | PSEG Nuclear, LLC | REVISED NAR (05-02-2015): An application to renew the approval of the existing PSEG Hope Creek Generating Station and its surface water withdrawal and consumptive water use. The surface water withdrawal of approximately 2.0 billion gallons per 30 days (bg/30 days) will contine to be used for cooling tower make-up, of which approximately 0.39 bg/30 days is consumptively used. The application also includes a facility description update to reflect current operations at the HCGS. The cooling tower blowdown discharge combines with treated eflfuent from the PSEG wastewater treatment plant prior to discharge, and is being reviewed under a concurrent application, No. D-1987-070-4. The existing facility will continue to withdrawal from and discharge to the Delaware River Water Quality Zone 5 and is located in Lower Alloways Creek Township, Salem County, New Jersey. ORIGINAL NAR (10-13-2011): An application to modify the previous DRBC approvals for a surface water withdrawal and a wastewater/non-contact cooling water discharge associated with the PSEG Hope Creek Generating Station. The surface water withdrawal is for cooling tower make-up. The facility discharge consists of combined treated effluent from the on-site WWTP and cooling tower make-up water backwash. An application was received on 11/3/2008 for the modification to the heat dissipation area associated with the cooling tower blowdown discharge, a facility description update, and a transfer of ownership from PSE&G to PSEG Nuclear LLC. A supplemental application was submitted on 5/19/2011 for the replacement of the existing 0.14 mgd (hydraulic design) WWTP with a new WWTP, hydraulically designed for 0.05 mgd. However, the wastewater treatment plant construction is being reviewed by the DRBC under a concurrent application, No. D-1987-070-2. The existing facility will continue to withdrawal from and discharge to the Delaware River Water Quality Zone 5 and is located in Lower Alloways Creek Township, Salem County, New Jersey. | LOWER ALLOWAYS CREEK TWP | SALEM | NJ | NJDEP | NO |  |  | B | IWTP | Industrial Wastewater |  | 2008-11-03 | 6415.3541 | 2015-06-29 | Docket |  | Pending
RD | D-2001-031 -2 | Calpine Corporation | An application to renew and modify the approval of the existing 1,100-megawatt Bethlehem Energy Center power generation facility and its associated surface water withdrawal and non- contact cooling water (cooling tower blowdown) discharge. The facility will continue to discharge an average of 0.5 mgd and up to 6.18 mgd of untreated cooling tower blowdown from one (1) existing outfall. The modification consists of a request to increase the existing surface water withdrawal allocation of up to 234 mg/30 days to up to 348.9 mg/30 days from one (1) existing surface water intake on the Lehigh River for non-contact cooling, on-site domestic sanitary, and process water uses. There are no modifications to the facility proposed; the existing facility has the ability to withdraw the requested increase in allocation. The facility will continue to discharge to the Lehigh River at River Mile 183.66 - 9.5 (Delaware River - Lehigh River), within the drainage area to the section of the non-tidal Delaware River known as the Lower Delaware, which is classified as Special Protection Waters, in the City of Bethlehem, Northampton County, Pennsylvania. | BETHLEHEM CITY | NORTHAMPTON | PA | PADEP NERO | NO | Lower |  | B | IWTP / SWWD | Industrial |  | 2012-05-07 | 5134.3541 | 2012-12-20 | Docket |  | Pending
EE | D-1981-050 CP-3 | Pennsylvania American Water Company | An application to approve a total combined withdrawal of up to 146.32 mgm of water from 11 existing surface water sources (2 streams, 3 reservoirs, 3 quarries and 3 springs) and 22 existing groundwater sources for use in three interconnected public water systems (Bangor, West Bangor and Blue Mountain Systems) that serve 16 municipalities in Northampton and Monroe Counties, Pennsylvania. The groundwater wells are completed in the Martinsburg, Shawangunk and Bloomsburg Formations in the Martins Creek, Aquashicola Creek, Little Bushkill Creek and Upper Bushkill Creek Watersheds in Upper Mount Bethel, Plainfield, Washington and Bushkill Townships and Wind Gap Borough in Northampton County, Pennsylvania and Ross and Hamilton Townships in Monroe County, Pennsylvania. The surface water sources are located in the Martins Creek, Cherry Creek and Aquashicola Creek Watersheds in Upper Mount Bethel Township and Pen Argyl Borough in Northampton County, Pennsylvania and Hamilton Township, Monroe County, Pennsylvania. The project is located within the drainage area to the Lower and Middle Delaware, which are classified as Special Protection Waters. | UPPER MOUNT BETHEL TWP | NORTHAMPTON | PA | PADEP NERO | NO | Lower |  | B | GWD / SWWD | Public Water Supply |  | 2014-05-20 | 4391.3541 | 2014-06-26 | Docket |  | Pending
EE | D-1990-049 CP-5 | Schuylkill County Municipal Authority | (Revised December 2025) An application to renew the approval of a surface water withdrawal and water importation and exportation project to supply up to 229.4 mgm (7.4 mgd) of surface water from six existing reservoirs for public water supply to municipalities located in the Delaware River Basin (DRB) and Susquehanna River Basin (SRB). The applicant imports up to 4.712 mgm of water from the Gordon Well located in the SRB and exports up to 31 mgm of water from the DRB to its service areas located in the SRB. The requested surface water allocation is an increase to the surface water allocation of 180 million gallons per 30 days (6 mgd) approved in the previous DRBC docket. The surface water reservoirs are located on Indian Run, Wolf Creek, Kauffman Run, Pine Run, Mud Run and an unnamed tributary to Mill Creek, all tributary to the Schuylkill River in Branch, New Castle, Ryan and Blythe Townships in Schuylkill County, Pennsylvania. (Original)An application to renew the approval of a surface water withdrawal and water importation and exportation project to continue to supply up to 186 mgm of surface water from six existing reservoirs for public water supply to 14 municipalities located in the Delaware River Basin (DRB) and Susquehanna River Basin (SRB). The applicant imports up to 4.712 mgm of water from the Gordon Well located in the SRB and exports up to 31 mgm of water from the DRB to its service areas located in the SRB. There is no requested increase to the withdrawal, importation or exportation allocations contained in the previous approval. The DRB surface water reservoirs are located on Indian Run, Wolf Creek, Kauffman Run, Pine Run, Mud Run and an unnamed tributary to Mill Creek, all tributary to the Schuylkill River in Branch Township, New Castle Township, Ryan Township and Blythe Township in Schuylkill County, Pennsylvania. | BRANCH TWP | SCHUYLKILL | PA | PADEP NERO | NO |  |  | A | GWD / SWWD | Public Water Supply |  | 2014-09-15 | 4273.3541 | 2026-01-08 | Docket |  | Pending
DK | D-1996-021 -5 | JBS Souderton, Inc. | An application to renew approval of the applicant's existing 1.5 mgd industrial wastewater treatment plant (IWTP) and its discharge. The IWTP will continue to discharge treated effluent into Skippack Creek, which is a tributary of Perkiomen Creek, which is a tributary of the Schuylkill River, at River Mile 92.47 - 32.3 - 3.0 - 12.8 (Delaware River - Schuylkill River - Perkiomen Creek - Skippack Creek), located in Franconia Township, Montgomery County, Pennsylvania. | FRANCONIA TWP | MONTGOMERY | PA | PADEP SERO | YES |  |  | A | IWTP | Industrial Wastewater |  | 2017-02-06 | 3398.3541 | 2017-04-18 | Docket |  | Pending
EE | D-1981-024 CP-9 | Palmerton Municipal Authority | (Amended 2025) An application to renew the approval of an allocation of 25 million gallons per month (mgm) of groundwater from existing Wells 4, 6, 7 and the Foundry Well and an allocation of 71 mgm from three existing intakes on the Pohopoco and Aquashicola Creeks; and the approval of allocations of 19.4 mgm from new well TW-1 and 2.8 mgm from new well TW-C. Water from the existing wells and new well TW-C is for public water supply and water from the existing intakes and new well TW-1 is for use by Horsehead Corporation for industrial processes and cooling. Wells 4, 6 and 7 and are completed in the Bloomsburg Formation, Well TW-1 is completed in the Poxono Island Formation in the Aquashicola Creek Watershed and the Foundry Well and new well TW-C is completed in the Bloomsburg Formation in the Lower Lehigh River Watershed. The Pohopoco Creek Intake is located in the Borough of Parryville and the wells and Aquashicola Intakes are located in the Borough of Palmerton in Carbon County, Pennsylvania within the drainage area of the section of the main stem Delaware River known as the Lower Delaware, which the Commission has classified as Special Protection Waters. (Amended) An application to renew the approval of: (a) an allocation of 25 million gallons per month (mgm) of groundwater from existing Wells Nos. 4, 6, 7 and the Foundry Well; (b) an allocation of 71 mgm from three existing intakes on the Pohopoco and Aquashicola creeks; and (c) approval of an allocation of 19.4 mgm from new Well No. TW-1. Water from the existing wells is used for public water supply and water from the existing intakes and Well No. TW-1 is for use by Horsehead Corporation for industrial processes and cooling. Wells Nos. 4, 6 and 7 are completed in the Bloomsburg Formation, Well No. TW-1 is completed in the Poxono Island Formation in the Aquashicola Creek Watershed and the Foundry Well is completed in the Bloomsburg Formation in the Lower Lehigh River Watershed. The Pohopoco Creek Intake is located in the Borough of Parryville and the wells and Aquashicola Intakes are located in the Borough of Palmerton in Carbon County, Pennsylvania within the drainage area of the section of the main stem Delaware River known as the Lower Delaware, which the Commission has classified as Special Protection Waters. (original)An application to renew the approval of an allocation of: (a) 25 million gallons per month (mgm) of groundwater from Wells Nos. 4, 6, 7 and the Foundry Well for public water supply; and (b) a total allocation of 71 mgm of surface water from one intake on the Pohopoco Creek and two intakes on the Aquashicola Creek for use by the Horsehead Corporation for industrial processes and cooling. Wells Nos. 4, 6 and 7 are completed in the Bloomsburg Formation in the Aquashicola Creek Watershed and the Foundry Well is completed in the Bloomsburg Formation in the Lower Lehigh River Watershed. The Pohopoco Creek Intake is located in the Borough of Parryville and the wells and Aquashicola Intakes are located in the Borough of Palmerton in Carbon County, Pennsylvania within the drainage area of the section of the main stem Delaware River known as the Lower Delaware, which the Commission has classified as Special Protection Waters. | PALMERTON BORO | CARBON | PA | PADEP NERO | NO | Lower |  | A | GWD / SWWD | Industrial |  | 2019-03-04 | 2642.3541 | 2026-03-11 | Docket |  | Pending
RD | D-2019-005 -1 | Tower Springs, LLC | An application to approve a groundwater withdrawal of up to 17.712 mgm to supply the applicant's bottled water facility from existing Wells Nos. FF-1 and FF-2. The project wells are completed in the Bloomsburg Formation. The project is located in the Lizard Creek Watershed in West Penn Township, Schuykill County, Pennsylvania within the drainage area of the section of the non-tidal Delaware River known as the Lower Delaware, which the Commission has classified as Special Protection Waters. | WEST PENN TWP | SCHUYLKILL | PA | PADEP NERO | NO | Lower |  | C | GWD | Bottled Water |  | 2019-06-10 | 2544.3541 | 2019-08-01 | Docket |  | Pending
EE | D-2016-003 CP-2 | Crossroads Ventures, LLC |  | FLEISCHMANNS VILLAGE | DELAWARE | NY | NYSDEC | NO | Upper |  | A | GWD | Commercial |  | 2019-12-04 | 2367.3541 |  | Docket |  | Pending
DK | D-1965-039 CP-4 | Village of Liberty | An application to renew the approval of an existing 2 mgd WWTP and its discharge. Treated effluent will continue to be discharged to an UNT of the East Branch Mongaup River, above Swinging Bridge Reservoir, at River Mile 261.1 - 23.56 - 8.12 - 0.86 (Delaware River - Mongaup River - East Branch Mongaup River - UNT) via Outfall No. 001, within the drainage area of the section of the main stem Delaware River known as the Upper Delaware, which the Commission has classified as Special Protection Waters, in the Village of Liberty, Sullivan County, New York. | LIBERTY VILLAGE | SULLIVAN | NY | NYSDEC | NO | Upper |  | A | WWTP |  |  | 2020-12-09 | 1996.3541 | 2021-01-12 | Docket |  | Pending
EE | D-2021-003 -1 | Ontelaunee Power Operating Company, LLC | An application to approve a groundwater withdrawal of up to 6.5 million gallons per month from new well PW-1 for industrial cooling at the existing 650 MW power plant. The existing power plant is approved by the Commission to consumptively use up to 120 million gallons per 30 days of water which is purchased from the Reading Area Water Authority for cooling purposes. The purpose of the new groundwater withdrawal is to reduce the amount of municipal water used. The well is completed in the Allentown Formation in the Swabia Creek Watershed in Ontelaunee Township, Berks County, Pennsylvania. | ONTELAUNEE TWP | BERKS | PA | PADEP SCRO | NO |  |  | C | Power | Thermoelectric |  | 2021-02-25 | 1918.3541 | 2021-04-12 | Docket |  | Pending
EE | D-2011-020 CP-2 | Eagle Creek Hydro Power, LLC | An application to renew the approval of the existing Mongaup Falls and Rio Hydroelectric Projects approved in Docket D-2011-020 CP-1 and to amend and combine DRBC Docket No. D-2001-038 CP-3 (Swinging Bridge Hydroelectric Project) into a single docket. The Swinging Bridge Dam is located at River Mile 261.1 – 11.9 (Delaware River – Mongaup River), in the Towns of Lumberland and Forestburgh, Sullivan County, New York. The Mongaup Falls Dam is located approximately 2.9 miles below the Swinging Bridge Dam at River Mile 261.1 – 9.1 (Delaware River - Mongaup River), in the Towns of Lumberland and Forestburgh, Sullivan County, New York. The Rio Dam is located approximately 4.5 miles downstream of the Mongaup Falls Dam at River Mile 261.1 - 4.6 (Delaware River - Mongaup River), in the Town of Deerpark, Orange County and the Town of Lumberland, Sullivan County, New York. The three hydroelectric projects collectively known as the Mongaup River Hydroelectric Projects are located within the drainage area of the section of the non-tidal Delaware River known as the Upper Delaware, which the Commission has classified as Special Protection Waters. | DEERPARK TOWN | ORANGE | NY | NYSDEC | NO | Upper |  | B | Power |  |  | 2021-04-14 | 1870.3541 | 2021-07-15 | Docket |  | Pending
EE | D-2021-006 -1 | MC Project Company, LLC | An application to renew the approval of a 7.77 mgd existing industrial waste treatment facility and its discharges of cooling water and cooling tower blowdown and a 0.024 mgd sewage treatment facility and its discharge at the Martins Creek Electric Generating Station. The electric generating facility and its discharges were previously approved by the Commission in Docket No. D-1970-025 CP. This docket will renew the approval and update information from the previous docket. Treated wastewater and effluent will continue to be discharged to the Delaware River at River Mile 194.26 in Water Quality Zone 1D via Outfall Nos. 010 and 013, within the drainage area to the lower Delaware, which is classified as Special Protection Waters, in Lower Mount Bethel Township, Northampton County, Pennsylvania. This application was originally noticed on October 5, 2021, as DRBC Docket No. D-2021-004-1. Due to administrative reasons, the DRBC Docket number for this application has been changed to D-2021-006-1. | LOWER MOUNT BETHEL TWP | NORTHAMPTON | PA | PADEP NERO | NO | Lower |  | A | IWTP |  |  | 2021-09-07 | 1724.3541 | 2022-03-22 | Docket |  | Pending
EE | D-2012-026 -2 | Philadelphia Energy Solutions Refining and Marketing (R&M), LLC | An application to renew the approval of a surface water withdrawal of up to 661.1 million gallons per month (mgm) from the Point Breeze and Girard Point intakes. The withdrawals were used for industrial cooling and industrial processes at the former refinery. The project intakes are located on the tidal Schuylkill River, within Water Quality Zone 4, in the City of Philadelphia, Philadelphia County, Pennsylvania. | PHILADELPHIA CITY | PHILADELPHIA | PA | PADEP SERO | NO |  |  | A | SWWD |  |  | 2022-03-14 | 1536.3541 | 2022-04-14 | Docket |  | Pending
RP | D-1992-018 CP-5 | Delaware County Regional Water Quality Control Authority - DELCORA | An application to renew the approval of the docket holder’s Western Regional WWTP and its 44 mgd discharge. There are no other modifications to the WWTP facilities proposed. The WWTP will continue to discharge to Water Quality Zone 4 of the tidal Delaware at River Mile 80.7 in the City of Chester, Delaware County, Pennsylvania. OLD An application to approve the docket holder's increase of capacity from its existing 50 mgd Western Regional Treatment Plant (WRTP) WWTP to 70 mgd upon transfer of service area flow and completion of proposed upgrades. The proposed upgrades will aid in the management of the partial service area currently served by the Philadelphia Water Department (PWD), Combined Sewer Overflows (CSO) generated by the City of Chester, and revised dilution effluent limits from the increase in discharge flow rates. The proposed project will include upgrades of the existing treatment systems at WRTP, its collection and conveyance systems, and the docket holder's Wastewater Tunnel Program. The existing effluent outfall discharges through a bulkhead that is proposed to be replaced with an extended outfall pipe with a multiport diffuser, at an extended location. The existing outfall no. 001 discharges to Water Quality Zone 4 of the Delaware River at River Mile 80.7, in the City of Chester, Delaware County, Pennsylvania. | CHESTER CITY | DELAWARE | PA | PADEP SERO | YES |  |  | A | WWTP |  |  | 2022-04-07 | 1512.3541 | 2024-07-24 | Docket |  | Pending
EE | D-2006-043 CP-3 | Pocono Manor Investors, L.P. | An application to renew the approval of a groundwater allocation of 12.71 million gallons per month from Wells 1, 2 and 3 for public water supply. The project wells are completed in the Catskill Formation within the drainage area of Indian Run and Swiftwater Creek in the Brodhead Creek Watershed, within the drainage area of the section of the main stem Delaware River known as the Middle Delaware, which the Commission has classified as Special Protection Waters, in Pocono Township, Monroe County, Pennsylvania. | POCONO TWP | MONROE | PA | PADEP NERO | NO | Middle |  | A | GWD |  |  | 2022-05-10 | 1479.3541 | 2022-05-18 | Docket |  | Pending
EE | D-2023-001 -1 | Sun NG Kittatinny RV LLC | An application to approve various improvements to an existing seasonally-operated campground facility located in a flood hazard area. The project involves the removal of several existing buildings, the construction of a new welcome center, a maintenance building, an aquatic play area, a mini-golf course as well as upgrades to electrical infrastructure, landscaping and fencing, solid waste collection infrastructure, roadways, and parking. The proposed project will reduce the number of existing campsites from 342 to 339 campsites and will convert 283 of the existing campsites to Recreation Vehicle type. Water for the project will continue to be supplied by existing onsite wells. The project will generate 29,080 gallons per day (0.0291 mgd) of wastewater which will be disposed through 9 existing and 16 proposed septic systems. The project is located in the Town of Highland, Sullivan County, New York within the drainage area to the section of the non-tidal Delaware River known as the Upper Delaware, which the Commission has designated as Special Protection Waters. | HIGHLAND TOWN | SULLIVAN | NY | NYSDEC | NO | Upper |  | C | WWTP |  |  | 2023-02-10 | 1203.3541 | 2023-02-23 | Docket |  | Pending
RD | D-2003-019 CP-3 | Pennsylvania American Water Company | An application to renew the approval of an existing groundwater withdrawal of up to 11.28 mgm to supply the applicant's Pine Ridge public water supply distribution system from existing Well Nos. 1, 2, 3, 4, 5 and 6. Well Nos. 1 and 5 are completed in the Trimmers Formation and Well Nos. 2, 3, 4 and 6 are completed in the Towamensing Member of the CatskillFormation. The requested allocation is not an increase from the previous allocation. The wells are located in Little Bushkill Watershed in Lehman Township, Pike County, Pennsylvania within the drainage area of the section of the main stem Delaware River known as the Middle Delaware, which is classified as Special Protection Waters. | LEHMAN TWP | PIKE | PA | PADEP NERO | NO | Middle |  | A | GWD |  |  | 2023-03-16 | 1169.3541 | 2023-03-30 | Docket |  | Pending
EE | D-2023-002 -1 | New Jersey Economic Development Authority | Revised NAR An application for review of the dredging of the Delaware River for Phase 2 of the New Jersey Wind Port, an expansion of the marshalling port currently under construction to support offshore wind energy development in New Jersey and throughout the eastern United States. Phase 2 is intended to support the simultaneous marshalling of two offshore wind development projects as well as manufacturing supply chain support. The project includes the development of a second marshalling facility, manufacturing support facilities and redevelopment of existing portions of the Salem and Hope Creek Generating Station and former USACE Artificial Island CDF Cell No. 3, installation of new wharf structures and dredging of new berthing pockets. Approximately 3,000,000 cubic yards of dredged material will be excavated to accommodate the modifications to the existing approach channel (deepening) and expanded berthing pockets. The project is located at River Mile 52 of the Delaware River in Lower Alloways Creek Township, Salem County, New Jersey. Original NAR An Application for review of the dredging of the Delaware River for Phase 2 of the New Jersey Wind Port, a marshalling port currently under construction to support offshore wind energy development in New Jersey and throughout the eastern United States. Phase 2 of the NJWP is intended to support simultaneous marshalling of two offshore wind development projects as well as supply chain support through manufacturing. Phase 2 of the NJWP includes the development of a second marshalling facility, manufacturing support facilities and relocation of existing facilities at the Salem and Hope Creek Generating Station. The proposed expanded development of the NJWP will include the redevelopment of existing portions of the Salem and Hope Creek Generating Station, former USACE Artificial Island CDF Cell No.3, installation of new wharf structures, dredging of new berthing pockets, and dredging of a new turning basin. Approximately 4,000,000 cubic yards of dredged material will be excavated to accommodate the modifications to the existing approach channel (deepening), new turning basin and expanded berthing pockets. The project is located at River Mile 52 of the Delaware River in Lower Alloways Creek Township, Salem County, New Jersey. | LOWER ALLOWAYS CREEK TWP | SALEM | NJ | NJDEP | NO |  |  | C | Dredging |  |  | 2023-06-05 | 1088.3541 | 2024-09-10 | Docket |  | Pending
RP | D-2013-007 CP-3 | Parkland School District | An application to approve the applicant's proposed construction project of two (2) new sequencing batch reactors (SBR), new tertiary filter, new ultraviolet disinfetion, and ancillary equipment to increase the design hydraulic capacty to 55,000 gpd average (0.55 mgd), 82,500 gpd (0.0825 mgd) peak, and organic capacity o 80 lbs/day CBOD5. Currently, the WWTP is not able to meet its current NPDES Permit limits for total nitrogen due to an increased organic and hydraulic loading to the WWTP that currently exceeds the original design. The WWTP will continue to discharge treated effluent into Jordan Creek, a tributary of the Lehigh River, at River Mile 183.7 - 16.3 - 8.6 (Delaware River - Lehigh River - Jordan Creek), via Outfall No. 001, located in South Whitehall Township, Lehigh County, Pennsylvania, within the drainage area of the section of the non-tidal Delaware River known as the Lower Delaware, which is classified as Special Protection Waters. | SOUTH WHITEHALL TWP | LEHIGH | PA | PADEP NERO | NO | Lower |  | B | WWTP |  |  | 2023-06-28 | 1065.3541 | 2026-05-26 | Docket |  | Pending
EE | D-2000-053 CP-3 | HELLERTOWN BOROUGH AUTHORITY | An application to renew the approval of an existing groundwater withdrawal of up to 22.7 mgm from existing Wells W-1 and W-2 and Reservoir R-1 supplied by a collection of fourteen (14) existing spring sources for public water supply. The project wells and springs are located in the Saucon Creek Watershed within the drainage area of the Lower Delaware, which the Commission has classified as Special Protection Waters, in Hellertown Borough and Lower Saucon Township, Northampton County, Pennsylvania. | HELLERTOWN BORO | NORTHAMPTON | PA | PADEP NERO | NO | Lower |  | A | GWD |  |  | 2023-09-14 | 987.3541 | 2023-10-18 | Docket |  | Pending
RP | D-2016-011 -4 | Aqua Pennsylvania Wastewater, Inc. | An application to approve the docket holder's proposed project to modify its existing 0.070 mgd Thornhurst WWTP. Modifications include the replacement of the existing influent screening equipment, replacement of equalization pumping equipment, uprgrade of aeration and equalization blower equipment, replacement of chlorine disinfection with ultraviolet disinfection, and appuertant equipment. The docket holder will continue to discharge treated effluent to Pond Creek, upstream of F.E. Walter Reservoir, at River Mile 183.7 - 88.8 - 2.5 (Delaware River - Lehigh River - Pond Creek), via Outfall No. 001, within the drainage area to the Lower Delaware Special Protection Waters, in Thornhurst Township, Lackawanna County, Pennsylvania. | THORNHURST TWP | LACKAWANNA | PA | PADEP NERO | NO | Lower |  | A | WWTP |  |  | 2023-10-10 | 961.3541 | 2024-01-30 | Docket |  | Pending
EE | D-2013-002 CP-2 | Village of Liberty | An application to renew the approval of a surface water and groundwater withdrawal project to supply up to 45.0 mgm of water to the applicant’s public water system from an existing intake located in Lily Pond and up to 30.0 mgm of groundwater from the existing Elm Street Well and a total allocation of 75.0 mgm. The requested allocations are increases to the currently approved surface water, groundwater and combined total allocations of 7.75 mgm, 23.25 mgm and 24.9 mgm, respectively. The surface water withdrawal is located in the Beaver Kill Watershed in the Town of Liberty, Sullivan County, New York and the groundwater well is completed in unconsolidated sand and gravel in the Monguap River Watershed in the Village of Liberty, Sullivan County, New York. The project is located within the drainage area of the Upper Delaware, which the Commission has classified as Special Protection Waters. | LIBERTY TOWN | SULLIVAN | NY | NYSDEC | NO | Upper |  | A | GWD / SWWD |  |  | 2023-11-30 | 910.3541 | 2023-12-07 | Docket |  | Pending
EE | D-1994-047 CP-3 | Nesquehoning Borough Authority | An application to renew the approval to withdraw up to 22.3 million gallons per month of groundwater from Wells 1, 2, 3, 4 and 5 for public water supply. The project wells are completed in the Mauch Chunk Formation in the Nesquehoning Creek watershed in Nesquehoning Borough, Carbon County, Pennsylvania, within the drainage area to the Lower Delaware, which the Commission has classified as Special Protection Waters. | NESQUEHONING BORO | CARBON | PA | PADEP NERO | NO | Lower |  | A | GWD |  |  | 2023-12-08 | 902.3541 | 2024-01-30 | Docket |  | Pending
EE | D-1969-210 CP-16 | Constellation Energy | An application to renew approval of the applicant's existing Limerick Generating Station (LGS) and its water withdrawals and discharge. The applicant requests continuation of: (a) surface water withdrawals from the Schuylkill River, Perkiomen Creek, Wadesville Mine Pool, and the Tamaqua Area Water Authority’s Still Creek Reservoir and Owl Creek Reservoir of up to 58.2 mgd and 1,742.2 mgm; (b) groundwater withdrawals from Well Nos. 1 and 3 of up to 3.2 mgm and 2.9 mgm, respectively; and (c) a discharge of up to 14.2 mgd of non-contact cooling water (NCCW) and treated industrial wastewater via Outfall No. 001. The wells are located in the Commission’s designated Southeastern Pennsylvania Ground Water Protected Area (SEPA GWPA) in the Sprogels Run-Schuylkill River Watershed. The LGS will continue to discharge NCCW and treated industrial wastewater to the Schuylkill River at River Mile 92.47 - 48.01 (Delaware River - Schuylkill River) in Limerick Township, Montgomery County, Pennsylvania. | LIMERICK TWP | MONTGOMERY | PA | PADEP SERO | NO |  |  | A | IWTP / SWWD |  |  | 2023-12-12 | 898.3541 | 2024-01-30 | Docket |  | Pending
RP | D-2001-002 CP-6 | Upper Bern Township | An application to approve upgrdes to the existing treatment process of the 0.155 mgd wastewater treatment plant (WWTP) and its discharge. The upgrades include installation of a second BESST treatment train and to convert the existing two basin SBR treatment train into a sludge holding tank and influent equalization tank. The WWTP will continue to discharge treated effluent to Wolf Creek, above the Blue Marsh Reservoir, at River Mile 92.47 - 76.8 - 15.6 - 5.1 - 2.3 (Delaware River - Schuylkill River - Tulpehocken Creek - Northkill Creek - Wolf Creek) in Upper Bern Township, Berks County, Pennsylvania. | UPPER BERN TWP | BERKS | PA | PADEP SCRO | NO |  |  | B | WWTP |  |  | 2024-02-01 | 847.3541 | 2024-06-18 | Docket |  | Pending
RP | D-1988-014 CP-5 | Roamingwood Sewer and Water Association | An application to renew the approval of the existing 1.755 mgd Roamingwood WWTP and its discharge. The WWTP will continue to discharge treated effluent to Ariel Creek, which is a tributary of Wallenpaupack Creek upstream of Lake Wallenpaupack, which is a tributary of the Lackawaxen River, at River Mile 277.7 - 15.8 - 14.2 - 3.5 (Delaware River - Lackawaxen River - Wallenpaupack Creek - Ariel Creek). The WWTP is located within the drainage area of the section of the main stem Delaware River known as the Upper Delaware, which is classified as Special Protection Waters, in Salem Township, Wayne County, Pennsylvania. | SALEM TWP | WAYNE | PA | PADEP NERO | NO |  |  | A | WWTP |  |  | 2024-02-09 | 839.3541 | 2024-03-05 | Docket |  | Pending
RP | D-2011-009 -3 | Republic Environmental Systems (Pennsylvania), LLC | An application to renew the approval of the applicant's 0.1 mgd IWTP that receives non-hazardous and hazardous wastes from off-site generators within the continental United States, primarily from Pennsylvania, New York, and New Jersey (both within and outside the basin) at their facility located in Hatfield Township, Montgomery County, Pennsylvania. Approximately 20% of the industrial wastewater collected at the facility is pre-treated and conveyed to the Hatfield Township Municipal Authority WWTP for ultimate discharge to the West Branch Neshaminy Creek. The remainder is trucked to other centralized waste treatment facilities, landfills, or cement kilns throughout the United States (most of which is sent to Du Pont Chambers Works, GROWS Landfill, or Keystone Cement; all of which are located within the basin). | HATFIELD BORO | MONTGOMERY | PA | PADEP SERO | NO |  |  | A | IWTP |  |  | 2024-02-14 | 834.3541 | 2024-03-05 | Docket |  | Pending
RP | D-1989-082 -5 | Pike County Environmental Enterprises, LLC | An application to renew approval of the 0.10 mgd WWTP and its discharge. The WWTP will continue to discharge treated effluent to Water Quality Zone 1B of the Delaware River at River Mile 256.6, via Outfall No. 001, within the drainage area of the section of the main stem Delaware River known as the Middle Delaware, which the Commission has classified as Special Protection Waters, in Westfall Township, Pike County, Pennsylvania. | WESTFALL TWP | PIKE | PA | PADEP NERO | NO | Upper |  | B | WWTP |  |  | 2024-03-28 | 791.3541 | 2024-05-21 | Docket |  | Pending
RP | D-2009-004 CP-4 | Naval Surface Warfare Center Philadelphia Division | An application to renew approval of the applicant's discharge of non-contact cooling water (NCCW) and process water from the Naval Ship Systems Engineering Station (NAVSSES). The NAVSSES will continue to withdraw water from the Navy Reserve Basin (NRB), which is located on the tidal Schuylkill River in Delaware River Water Quality Zone 4, for temporary, intermittent, land-based tests of ship systems and to discharges up to 0.045 mgd of process water from Outfall No. 005 directly to Delaware River Water Quality Zone 4. For Outfall 001, all thermal connections to the river water system have been disconnected. All equipment is now cooled via a new Building 633 cooling tower system. The facility is located in the City of Philadelphia, Philadelphia County, Pennsylvania. | PHILADELPHIA CITY | PHILADELPHIA | PA | PADEP SERO | NO |  |  | B | Other |  |  | 2024-05-21 | 737.3541 | 2024-06-18 | Docket |  | Pending
EE | D-2024-002 -1 | Rising Light Ridge, LLC | An application to approve a new 0.0273 mgd Rising Light Ridge Camp Facility WWTP and its proposed discharge. The new WWTP facilities will consist of a sequencing batch reactor WWTP with pre and post storage/equalization, UV disinfection and advanced treatment as needed. Treated wastewater will be conveyed to a proposed 7.49-acre spray irrigation disposal field during the peak season and to two (2) proposed at-grade sewage disposal beds during the off-season. The proposed spray fields and sewage disposal beds discharge are located in the Bear Creek Watershed, within the drainage area to the section of the main stem Delaware River known as the Lower Delaware, which the Commission has classified as Special Protection Waters, in Bear Creek Township, Luzerne County, Pennsylvania. | BEAR CREEK TWP | LUZERNE | PA | PADEP NERO | NO | Lower |  | C | WWTP |  |  | 2024-11-25 | 549.3541 | 2025-04-23 | Docket |  | Pending
RD | D-1981-067 CP-5 | MYERSTOWN WATER AUTHORITY | An application to renew the approval of an existing groundwater withdrawal with an increase in allocation from 34.1 mgm to 34.5 mgm to supply the applicant's public water supply system from existing Well Nos. 3, 5, 6 and 8. Well Nos. 3, 5 and 6 are completed in Hamburg Formation. Well No. 8 is completed in the Ontelaunee Formation. The requested allocation is not an increase from the previous allocation. The project is located in theTulpehocken Creek Watershed, in the Borough of Myerstown and Jackson Township, Lebanon County, Pennsylvania. | JACKSON TWP | LEBANON | PA | PADEP SCRO | NO |  |  | B | GWD |  |  | 2024-11-27 | 547.3541 | 2024-12-18 | Docket |  | Pending
RD | D-2001-048 CP-3 | Aqua Pennsylvania, Inc. |  | NORTH COVENTRY TWP | CHESTER | PA | PADEP SERO | YES |  |  | A | GWD |  |  | 2024-11-27 | 547.3541 |  | Docket |  | Pending
EE | D-1969-059 -3 | Chemours Company, The | An application to renew the allocation of 1,314 million gallons per month (mgm) of surface water from an existing intake on the Delaware River for industrial cooling and industrial processes at the Chambers Works chemical manufacturing facility. Although the intake is currently idle, the applicant maintains the intake and anticipates that future growth at the site would require the allocation to support current operations, future growth in production and any future tenants that would develop and operate industrial processes at the site. The Delaware River intake is located in Water Quality Zone 5 in Pennsville Township, Salem County, New Jersey. | PENNSVILLE TWP | SALEM | NJ | NJDEP | NO |  |  | A | SWWD |  |  | 2024-12-09 | 535.3541 | 2025-02-05 | Docket |  | Pending
EE | D-1999-054 -2 | LMBE Project Company, LLC | An application to renew the approval of an existing 600 megawatt (MW) electric generating facility and approve an increase in consumptive use. Water is supplied by the adjacent Martins Creek Energy Facility intake on the Delaware River. The applicant requested to increase its water allocation and consumptive use from 4.84 mgd to 5.976 mgd. The increase is due to the use of power augmentation equipment to increase electric generation efficiency. The use of this equipment requires additional water demands. The increase in water use will not require an increase in the existing approved surface water allocation of 785.54 million gallons per month at the Martins Creek Facility. The project is located in Lower Mount Bethel Township, Northampton County, Pennsylvania within Lower Delaware Special Protection Waters. | LOWER MOUNT BETHEL TWP | NORTHAMPTON | PA | PADEP NERO | NO |  |  | A | SWWD |  |  | 2025-01-27 | 486.3541 | 2025-03-20 | Docket |  | Pending
EE | D-2000-014 -2 | Ontelaunee Power Operating Company, LLC | An application to renew the approval of an existing 544 megawatt (MW) electric generating facility and its associated consumptive use of water and discharge. The facility will continue to consumptively use up to a maximum of 124 mgm of water purchased from the Reading Area Water Authority. The electric generating facility is located in Ontelaunee Township, Berks County, Pennsylvania. | ONTELAUNEE TWP | BERKS | PA | PADEP SCRO | NO |  |  | A | IWTP / SWWD |  |  | 2025-01-30 | 483.3541 | 2025-03-20 | Docket |  | Pending
RP | D-2015-014 -3 | Camp Hachshara-Moshava of NY, Inc. dba Camp Moshava | An application to renew the approval of the applicant's existing 0.036 mgd WWTP and its discharge. The WWTP will continue to discharge treated effluent to an unnamed tributary of Indian Orchard Brook at River Mile 277.7 - 23.1 - 1.8 - 0.5 (Delaware River - Lackawaxen River - Indian Orchard Brook - UNT Indian Orchard Brook) located within the drainage area of the section of the main stem Delaware River known as the Upper Delaware, which the Commission has classified as Special Protection Waters, in Berlin Township, Wayne County, Pennsylvania. | BERLIN TWP | WAYNE | PA | PADEP NERO | NO | Upper |  | A | WWTP |  |  | 2025-03-03 | 451.3541 | 2025-03-20 | Docket |  | Pending
RP | D-1987-028 CP-4 | Upper Montgomery Joint Authority | An application to renew the approval to construct an upgrade to the docket holder's existing WWTP. The proposed upgrade consists of replacing the existing trickling filter treatment system with a new biological nutrient removal (BNR) system and increasing the hydraulic design capacity from 2.5 mgd to 2.77 mgd. The WWTP will continue to discharge treated effluent to Perkiomen Creek at River Mile 92.47 - 32.3 - 25.0 (Delaware River - Schuylkill River - Perkiomen Creek), via Outfall No. 001, in Upper Hanover Township, Montgomery County, Pennsylvania. | UPPER HANOVER TWP | MONTGOMERY | PA | PADEP SERO | NO |  |  | B | WWTP |  |  | 2025-03-24 | 430.3541 | 2025-04-23 | Docket |  | Pending
RP | D-1973-199 CP-6 | Boyertown Boro | An application to renew the approval of the existing 0.75 mgd WWTP and its discharge. The existing WWTP will continue to discharge treated effluent to West Branch Swamp Creek at River Mile 92.47 - 32.3 - 12.9 - 11.9 (Delaware River - Schuylkill River - Perkiomen Creek - Swamp Creek) via Outfall No. 001, in Douglass Township, Montgomery County, Pennsylvania. | DOUGLASS TWP | MONTGOMERY | PA | PADEP SERO | NO |  |  | A | WWTP |  |  | 2025-04-08 | 415.3541 | 2025-04-23 | Docket |  | Pending
BA | D-1992-003 CP-4 | Pennsylvania American Water Company | (1/14/2026) An application to approve modifications and upgrades to the existing 7.1 mgd WWTP, with a request for a total dissolved solids (TDS) variance to increase the monthly average effluent limit from 1,500 mg/l to 1,600 mg/l in order to maintain compliance. The proposed construction is part of a Corrective Action Plan and includes modifications to the existing influent pumping station and the addition of a new influent pumping station, dual force mains, diversion chambers, and flow equalization tanks. The WWTP will continue to discharge treated effluent to the Schuylkill River at River Mile 92.5-65.3 (Delaware River – Schuylkill River) in Exeter Township, Berks County, Pennsylvania. (12/1/2025) An application to approve modifications and upgrades to the existing 7.1 mgd WWTP , with a request for a total dissolved solids (TDS) variance to increase the monthly average effluent limit from 1,500 mg/l to 2,000 mg/l. The proposed construction is part of a Corrective Action Plan and includes modifications to the existing influent pumping station and the addition of a new influent pumping station, dual force mains, diversion chambers, and flow equalization tanks. The WWTP will continue to discharge treated effluent to the Schuylkill River at River Mile 92.5-65.3 (Delaware River – Schuylkill River) in Exeter Township, Berks County, Pennsylvania. (5/29/25) An application to approve modifications and upgrades to the existing 7.1 mgd WWTP. The proposed construction is part of a Corrective Action Plan and includes modifications to the existing influent pumping station and the addition of a new influent pumping station, dual force mains, diversion chambers, and flow equalization tanks. The WWTP will continue to discharge treated effluent to the Schuylkill River at River Mile 92.5-65.3 (Delaware River – Schuylkill River) in Exeter Township, Berks County, Pennsylvania. | EXETER TWP | BERKS | PA | PADEP SCRO | NO |  |  | B | WWTP |  |  | 2025-04-10 | 413.3541 | 2026-03-11 | Docket |  | Pending
BA | D-1970-052 CP-3 | Philadelphia (City of) | An application to renew the approval of the existing 210 mgd WWTP and its discharge, and to approve a modification of the WWTP facilities. The modification consists of an additional Preliminary Treatment Facility (PTF) for the purpose of increasing the wet weather flow capacity. The WWTP will remain designed for 210 mgd and continue to discharge treated effluent to Water Quality Zone 3 of the Delaware River at River Mile 104.2 in the City of Philadelphia, Philadelphia County, Pennsylvania. | PHILADELPHIA CITY | PHILADELPHIA | PA | PADEP SERO | NO |  |  | A | WWTP |  |  | 2025-04-29 | 394.3541 | 2025-05-29 | Docket |  | Pending
EE | D-2014-020 -2 | Villa Roma Country Club | An application to renew the approval of an existing groundwater and surface water withdrawal of up to 12.276 mgm to supply domestic, irrigation, and/or snow-making water from Wells 2, 4, 6, 7, 8, 9, 10, 12 and 13 and Pond Intakes 11 and 15. The wells are completed in the Honesdale Formation. The project is located in the Lower East Branch Callicoon Creek Watershed within the drainage area of the section of the main stem Delaware River known as the Middle Delaware, which the Commission has classified as Special Protection Waters, in the Town of Delaware, Sullivan County, New York. | DELAWARE TOWN | SULLIVAN | NY | NYSDEC | NO | Middle |  | A | GWD / SWWD |  |  | 2025-04-29 | 394.3541 | 2025-09-18 | Docket |  | Pending
DK | D-1985-052 CP-2 | Liberty Town | An application to include the proposed increase from 0.425 mgd to 0.960 mgd at the Swan Lake Domestic Wastewater Treatment Plant (DWTP) in the Delaware River Basin Commission’s Comprehensive Plan. The plant will continue to serve the Swan Lake/Briscoe Road Sewer Districts in the Town of Liberty, Sullivan County, New York. Section 3.8 Review of the project will be conducted in accordance with the New York State Department of Environmental Conservation (NYSDEC) and DRBC 2016 Administrative Agreement (AA). Treated effluent will continue to be discharged to an unnamed tributary to Swan Lake, at River Mile 261.1 – 19.7 – 6.7 (Delaware River – Mongaup River – West Branch Mongaup River) in Water Quality Zone 1B. | LIBERTY TOWN | SULLIVAN | NY | NYSDEC | NO | Upper |  | C | WWTP |  |  | 2025-05-09 | 384.3541 | 2025-07-01 | Docket |  | Pending
BA | D-1974-061 CP-7 | Spring City Borough | An application to renew the approval of the existing 0.61 mgd WWTP and its discharge. The WWTP will continue to discharge treated effluent to the Schuylkill River at River Mile 92.47 – 41.3 (Delaware River – Schuylkill River) in Spring City Borough, Chester County, Pennsylvania. | SPRING CITY BORO | CHESTER | PA | PADEP SERO | NO |  |  | A | WWTP |  |  | 2025-05-12 | 381.3541 | 2025-05-29 | Docket |  | Pending
BA | D-2003-010 -3 | Arrowhead Sewer Company, Inc. | An application to renew approval of the applicant's existing 0.525 mgd WWTP and its discharge. The WWTP will continue to discharge treated effluent to the Lehigh River, at River Mile 183.7 - 90.5 (Delaware River - Lehigh River) via Outfall No. 001, located in Coolbaugh Township, Monroe County, Pennsylvania, within the drainage area of the Lower Special Protection Waters (SPW). | COOLBAUGH TWP | MONROE | PA | PADEP NERO | NO | Lower |  | A | WWTP |  |  | 2025-06-18 | 344.3541 | 2025-07-01 | Docket |  | Pending
RD | D-2004-004 CP-5 | Pennsylvania American Water Company |  | LOWER PROVIDENCE TWP | MONTGOMERY | PA | PADEP SERO | YES |  |  | A | GWD |  |  | 2025-06-26 | 336.3541 |  | Docket |  | Pending
EE | D-1970-025 CP-3 | MC Project Company, LLC | An application to approve an increase in allocation from 785.54 million gallons per month (mgm) to 900 mgm of surface water from an existing intake on the Delaware River. Water is used for makeup water and cooling purposes at the Martins Creek Steam Electric Station and the Lower Mount Bethel Energy Facility, located on an adjacent property. The increase in surface water allocation is needed to meet growing demand associated with a projected increase in electric generation for the PJM market as supplied through the Martins Creek and Lower Mount Bethel Energy generating stations. The project is located in Lower Mount Bethel Township, Northampton County, Pennsylvania within the drainage area of the section of the main stem Delaware River known as the Lower Delaware, which the Commission has classified as Special Protection Waters. | LOWER MOUNT BETHEL TWP | NORTHAMPTON | PA | PADEP NERO | NO | Lower |  | B | SWWD |  |  | 2025-07-14 | 318.3541 | 2025-08-21 | Docket |  | Pending
EE | D-1972-146 -3 | Saputo Cheese USA, Inc. | An application to renew the approval of an allocation of 29 mgm of groundwater from existing Wells 1, 2, 3 and 4 for industrial cooling, industrial processes and potable supply at an existing dairy processing manufacturing facility. The wells are completed in unconsolidated sand and gravel in the West Branch Delaware River Watershed in the Town of Delhi, Delaware County, New York within the drainage area of the section of the main stem Delaware River known as the Upper Delaware, which the Commission has classified as Special Protection Waters. | DELHI TOWN | DELAWARE | NY | NYSDEC | NO | Upper |  | A | GWD |  |  | 2025-07-16 | 316.3541 | 2025-08-21 | Docket |  | Pending
BA | D-1999-020 CP-6 | Community Utilities of Pennsylvania, Inc. | An application to renew the approval of the applicant's existing 0.56 mgd WWTP and its discharge. The WWTP will continue to discharge treated effluent to an unnamed tributary (UNT) of Brodhead Creek at River Mile 213.0 - 8.7 - 1.5 (Delaware River - Brodhead Creek - UNT of Brodhead Creek) via Outfall No. 1, within the drainage area of the Middle Special Protection Waters, in Stroud Township, Monroe County, Pennsylvania. | SMITHFIELD TWP | MONROE | PA | PADEP NERO | NO | Middle |  | A | WWTP |  |  | 2025-07-29 | 303.3541 | 2025-08-21 | Docket |  | Pending
EE | D-1988-045 CP-5 | Roamingwood Sewer and Water Association | An application to renew the approval of a groundwater withdrawal of up to 20.67 million gallons per month from existing Wells 1, 2, 3, 4, and 5 for public water supply. The wells are completed in the Poplar Gap Member of the Catskill Formation in the Ariel Creek Watershed in Lake and Salem Townships, Wayne County, Pennsylvania within the drainage area to the Upper Delaware, which the Commission has classified as Special Protection Waters. | LAKE TWP | WAYNE | PA | PADEP NERO | NO | Upper |  | A | GWD |  |  | 2025-08-15 | 286.3541 | 2025-09-18 | Docket |  | Pending
EE | D-1987-026 -6 | Trogon Development LLC | An application to renew approval of the docket holder’s existing 1.3 mgd intermittent discharge of treated industrial wastewater (coal-ash leachate) and stormwater from the closed Beagle Club Ash Disposal (BCAD) Site. The project includes an approved total dissolved solids (TDS) determination consisting of an effluent concentration limit of 3,500 mg/l (monthly average) and 7,000 mg/l (daily maximum) for the existing discharge. The BCAD site will continue to discharge up to 1.3 mgd to the Schuylkill River at River Mile 92.47 - 71.3 (Delaware River – Schuylkill River) in Cumru Township, Berks County, Pennsylvania. | CUMRU TWP | BERKS | PA | PADEP SCRO | NO |  |  | A | IWTP |  |  | 2025-08-25 | 276.3541 | 2025-12-03 | Docket |  | Pending
RD | D-1992-009 -4 | WAYNESBOROUGH COUNTRY CLUB | An application to renew the approval of an existing groundwater withdrawal of up to 6.2 mgm for irrigation of the applicant's golf course from two existing Wells 1978-Blue, 15 and new Well 2025. The project wells are completed in the Wissahickon and Mafic Gneiss Formations. The requested allocation is not an increase from the previous allocation. The project is located in the Commission's designated Southeastern Pennsylvania Ground Water Protected Area (SEPA GWPA) in the Crum Creek Watershed in Easttown, Chester County, Pennsylvania. | EASTTOWN TWP | CHESTER | PA | PADEP SERO | YES |  |  | B | GWD |  |  | 2025-09-02 | 268.3541 | 2025-12-03 | Docket |  | Pending
EE | D-2000-044 -3 | Marcus Hook Energy, L.P. | An application to renew the approval of an existing surface water withdrawal of up to 11 mgd from an existing intake in the Delaware River for use at the Marcus Hook Energy Center, a 750 megawatt combined cycle cogeneration facility. The energy center is located in Marcus Hook Borough, Delaware County, Pennsylvania and New Castle County, Delaware. The intake, owned by Energy Transfer Partners, is located at River Mile 78.5 in Water Quality Zone 4 in New Castle County, Delaware. | MARCUS HOOK BORO | DELAWARE | PA | PADEP SERO | NO |  |  | A | SWWD |  |  | 2025-09-03 | 267.3541 | 2025-09-18 | Docket |  | Pending
BA | D-1988-054 -9 | Waste Management Disposal Services of Pennsylvania, Inc. | An application to renew approval of the applicant's existing 0.3 mgd landfill leachate treatment plant (LTP) and its discharge. The LTP will continue to discharge treated effluent directly to Delaware River Water Quality Zone 2 at River Mile 125.6 in Falls Township, Bucks County, Pennsylvania. | FALLS TWP | BUCKS | PA | PADEP SERO | NO |  |  | B | IWTP |  |  | 2025-09-10 | 260.3541 | 2025-12-03 | Docket |  | Pending
RP | D-1970-072 -8 | Global Advanced Metals USA, Inc. |  | COLEBROOKDALE TWP | BERKS | PA | PADEP SERO | NO |  |  | A | IWTP |  |  | 2025-09-25 | 245.3541 |  | Docket |  | Pending
RD | D-1986-069 -3 | ABB Inc. | An application to renew the approval of an existing groundwater withdrawal associated with the remediation of groundwater contaminated with trichloroethylene (TCE) and tetrachloroethylene (PCE) with a withdrawal of up to 3.348 mgm from existing Wells W-1, W-2 and W-7. The wells are completed in the Stockton Formation. The GTP discharges to an unamed tributary of the Pennypack Creek via Outfall No. 1 at River Mile 109.75 - 19.7 - 1.8 (Delaware River - Pennypack Creek - UNT of the Pennypack Creek). The project is located in the Commission's designated Southeastern Pennsylvania Ground Water Protected Area (SEPA GWPA) in the Pennypack Creek Watershed in Warminster Township, Bucks County, Pennsylvania. | WARMINSTER TWP | BUCKS | PA | PADEP SERO | YES |  |  | A | IWTP / GWD |  |  | 2025-09-26 | 244.3541 | 2025-12-03 | Docket |  | Pending
RD | D-1965-076 CP-14 | Forest Park Water | An application to renew the approval of an existing surface water withdrawal with an increase in allocation from 48.8 mgd to 61.3 mgd from the Delaware River and from 40.0 mgd to 56.0 mgd from the North Branch Neshaminy Creek to supply the applicant's public water supply distribution systems. The project intakes are located in the Delaware River and North Branch Neshaminy Creek Watersheds in Plumstead Township and Chalfont Borough, both in Bucks County, Pennsylvania. The Forest Park Water Filtration Plant is located in Chalfont Borough, Bucks County, Pennsylvania. | CHALFONT BORO | BUCKS | PA | PADEP SERO | YES | Lower |  | B | SWWD |  |  | 2025-10-02 | 238.3541 | 2025-12-03 | Docket |  | Pending
RD | D-2016-005 -2 | Brookside Country Club | An application to renew the approval of an existing groundwater withdrawal of up to 8.208 mgm for irrigation of the applicant's golf course from two existing Wells 1 and 2. The project wells are completed in Brunswick Formation. The requested allocation is not an increase from the previous allocation. The project is located in the Commission's designated Southeastern Pennsylvania Ground Water Protected Area (SEPA GWPA) in the Sprogels Run Watershed in the Borough of Pottstown and Lower Pottsgrove Township, Montgomery County, Pennsylvania. | POTTSTOWN BORO | MONTGOMERY | PA | PADEP SERO | YES |  |  | A | GWD |  |  | 2025-10-09 | 231.3541 | 2025-12-03 | Docket |  | Pending
BA | D-1987-024 CP-5 | West Grove Borough Authority | An application to renew the approval of the docket holder's existing 0.25 mgd WWTP and its discharge. The existing WWTP will continue to discharge to Middle Branch White Clay Creek at River Mile 70.2 - 10.0 - 15.9 - 9.5 (Delaware River - Christina River - White Clay Creek - Middle Branch White Clay Creek) via Outfall No. 001, in London Grove Township, Chester County, Pennsylvania. | LONDON GROVE TWP | CHESTER | PA | PADEP SERO | NO |  |  | A | WWTP |  |  | 2025-10-15 | 225.3541 | 2025-12-03 | Docket |  | Pending
RD | P-1995-020 -4 | Central Bucks School District | An application to renew the approval of an existing groundwater withdrawal with an increase in allocation from 1.18 mgm to 1.324 mgm to supply the applicant's Central Bucks East High School and Holicong Middle School water supply systems from new Well 3. The approval will also remove Well PW-1 from the permit. Well 3 is completed in the Stockton Formation. The project is located in the Commission's designated Southeastern Pennsylvania Ground Water Protected Area (SEPA GWPA) in the Lahaska Creek Watershed in Buckingham Township, Bucks County, Pennsylvania. | BUCKINGHAM TWP | BUCKS | PA | PADEP SERO | YES |  |  | B | GWD |  |  | 2025-10-16 | 224.3541 | 45994 | Permit |  | Pending
RP | D-2007-025 CP-5 | Upper Makefield Township | An application to renew the approval of the docket holder's existsing 0.055 mgd Enclave WWTP and its discharge. The WWTP will continue to discharge treated effluent to Houghs Creek at River Mile 140.5 - 3.7 (Delaware River - Houghs Creek) via Outfall No. 001, which is located within the drainage area to the Lower Delaware Special Protection Waters, in Upper Makefield Township, Bucks County, Pennsylvania. | UPPER MAKEFIELD TWP | BUCKS | PA | PADEP SERO | YES | Lower |  | A | WWTP |  |  | 2025-10-20 | 220.3541 | 2025-12-03 | Docket |  | Pending
RP | D-1975-093 CP-7 | Community Utilities of Pennsylvania, Inc. | An application to renew the approval of the existing 0.25 mgd Tamiment WWTP and its discharges to land (via spray irrigation) and surface water. The WWTP will continue to spray irrigate treated effluent at the Tamiment Golf Course. Treated effluent that is not spray irrigated will continue to discharged to an unnamed tributary to Little Bush Kill, which is tributary to Bush Kill, at River Mile 226.9 - 0.8 - 1.5 - 1.85 (Delaware River - Bush Kill - Little Bush Kill - UNT Little Bush Kill), within the drainage area of the section of the main stem Delaware River known as the Middle Delaware, which the Commission has classified as Special Protection Waters, in Lehman Township, Pike County, Pennsylvania. | LEHMAN TWP | PIKE | PA | PADEP NERO | NO | Upper |  | A | WWTP |  |  | 2025-10-24 | 216.3541 | 2026-03-11 | Docket |  | Pending
RD | D-1990-050 CP-5 | Aqua Pennsylvania, Inc. | An application to renew the approval of an existing groundwater withdrawal with an increase in system allocation from 92.0 mgm to 107.0 mgm to supply the applicant's public water supply distribution system from existing Wells Bell Tavern Well 1, Shoen Rd Well 3, Robert Dean Well 5, Robert Dean Well 6, Stonehedge Well 8, Saybrooke Well 9, Saybrooke Well 10, Bell Tavern Well 11 and new Well Milford Well 7R. Project wells Bell Tavern Well 1, Shoen Rd Well 3, Robert Dean Well 5, Robert Dean Well 6, Stonehedge Well 8 and Bell Tavern Well 11 are completed in Cambrian Quartz Dolomite. Project Wells Saybrooke Well 9, Saybrooke Well 10 and Milford Well 7R are completed in Granitic Gneiss. New well Milford Well 7R will be replacing Milford Well 7, which will be abandoned as soon as Milford Well 7R is put into operation. Wells Shoen Rd Well 3, Robert Dean Well 5 and Robert Dean Well 6 are located within the Commission's designated Southeastern Pennsylvania Ground Water Protected Area (SEPA GWPA) in the West Valley Creek Watershed. Well Bell Tavern Well 1 and Bell Tavern Well 11 are located in the East Brandywine Creek Watershed, Wells Milford Well 7R and Stonehedge Well 8 are located in the Marsh Creek Watershed and Wells Saybrooke Well 9 and Saybrooke Well 10 are located in the Black Horse Creek Watershed all in Upper Uwchlan Township, Chester County, Pennsylvania. | EAST CALN TWP | CHESTER | PA | PADEP SERO | YES |  |  | B | GWD |  |  | 2025-11-04 | 205.3541 | 2025-12-03 | Docket |  | Pending
RD | D-2017-013 -2 | Merion Golf Club | An application to renew the approval of an existing surface water withdrawal and a new ground water withdrawal with an increase in system allocation from 12.416 mgm to 20.954 mgm to irrigate the applicant's East and West golf courses from existing surface water Intakes 11 Fairway Intake East and 10 Fairway Intake East, Wet Well West and Impounded Spring West, which feeds into an unnamed tributary (UNT) of Darby Creek and new Wells TW-1 West and TW-4B West. The approval will also include the construction of Wells TW-1 West and TW-4B West and the renovation of the West golf course. The project is located in the Cobbs Creek Watershed, Haverford Township, Delaware County, Pennsylvania. | HAVERFORD TWP | DELAWARE | PA | PADEP SERO | NO |  |  | B | GWD / SWWD |  |  | 2025-11-20 | 189.3541 | 2025-12-03 | Docket |  | Pending
EE | D-1967-240 -3 | Energy Transfer Marketing & Terminals L.P. | An application to renew the approval to withdraw up to 590.0 million gallons per month of surface water from existing intake No. RW-7 for industrial cooling, hydrostatic testing and other industrial uses at the Docket Holder’s Marcus Hook Terminal and for use at the Marcus Hook Energy Center for electric and stream generation and surface water withdrawals from intakes RW-5 and RW-6 for emergency fire flow purposes. Intake No. RW-7 will continue to withdrawal surface water from the Delaware River in New Castle County, Delaware. Fire water intakes RW-5 and Dock 2B are located on the Delaware River in Marcus Hook Borough, Delaware County, Pennsylvania. | CLAYMONT CDP | NEW CASTLE | DE | DNREC | NO |  |  | A | SWWD |  |  | 2025-11-24 | 185.3541 | 2026-03-11 | Docket |  | Pending
RP | D-2010-040 -3 | Vicinity Energy | An application to renew the approval of the existing Vicinity Energy Philadelphia (VEP) discharge of up to 48.3 mgd of industrial wastewater generated at the electric generating cogenerating facility through existing Outfall No. 001. Outfall No. 001 will continue to discharge industrial wastewater to the tidal portion of the Schuylkill River, in Delaware River Water Quality Zone 4, at River Mile 92.47 - 5.6 (Delaware River - Schuylkill River) in the City of Philadelphia, Pennsylvania. | PHILADELPHIA CITY | PHILADELPHIA | PA | PADEP SERO | NO |  |  | A | IWTP |  |  | 2025-12-03 | 176.3541 | 2026-01-08 | Docket |  | Pending
BA | D-2000-055 CP-6 | UPPER UWCHLAN TOWNSHIP | An application to renew the approval of the docket holder's existing 0.6 mgd Route 100 Regional WWTP and its discharge. The WWTP will continue to discharge treated effluent to a combination of spray and drip irrigation fields located in the drainage area of the East Branch Brandywine Creek and Lower Schuylkill River watersheds. The WWTP is located in Upper Uwchlan Township, Chester County, Pennsylvania. | UPPER UWCHLAN TWP | CHESTER | PA | PADEP SERO | NO |  |  | A | WWTP |  |  | 2025-12-11 | 168.3541 | 2026-01-08 | Docket |  | Pending
RD | D-1991-042 CP-5 | ALBURTIS BOROUGH | An application to renew the approval of an existing groundwater withdrawal of up to 11.87 mgm to supply the applicant's public water supply distribution system from existing Wells 1, 2, 3A and 4. Project Wells 1 and 2 are completed in Hornblende Gneiss and Wells 3A and 4 are completed in the Leithsville Formation. The requested allocation is not an increase from the previous allocation. The project is located in the Swabia Creek Watershed in the Borough of Alburtis and Lower Macungie Township, Lehigh County, Pennsylvania within the drainage area to section of the main stem Delaware River known as the Lower Delaware, which the Commission has classified as Special Protection Waters. | ALBURTIS BORO | LEHIGH | PA | PADEP NERO | NO | Lower |  | A | GWD |  |  | 2025-12-12 | 167.3541 | 2026-01-08 | Docket |  | Pending
RD | D-1994-050 CP-4 | DELAWARE VALLEY UNIVERSITY | An application to renew the approval of an existing groundwater withdrawal with a decrease in allocation from 7.192 mgm to 3.614 mgm to supply to water for agricultural purposes and to irrigate the athletic fields on the applicant's campus from existing Well Nos. 1, 3, 6, 7 and 8. Well Nos. 4 and 5 will also be removed from the docket with this approval. The project wells are completed in Stockton Formation. The project is located in the Commission's designated Southeastern Pennsylvania Ground Water Protected Area (SEPA GWPA) in the Neshaminy Creek Watershed in Doylestown Township, Bucks County, Pennsylvania. | DOYLESTOWN TWP | BUCKS | PA | PADEP SERO | YES |  |  | A | GWD |  |  | 2025-12-12 | 167.3541 | 2026-01-08 | Docket |  | Pending
RD | D-2016-004 -2 | Birdsboro Power LLC | An application to renew the approval of a 450 megawatt (MW) electric generating plant and its associated consumptive use of water. The facility will purchase cooling water from the Birdsboro Municipal Authority (BMA), which purchases water from the Reading Area Water Authority (RAWA). The estimated average and maximum daily water use for the facility is 3.0 mgd and 4.0 mgd, respectively. The estimated average and maximum consumptive use for the facility is 2.65 mgd and 3.55 mgd, respectively. The facility will be located in the Borough of Birdsboro, Berks County, Pennsylvania. | BIRDSBORO BORO | BERKS | PA | PADEP SCRO | NO |  |  | A | Power |  |  | 2025-12-12 | 167.3541 | 2026-01-08 | Docket |  | Pending
RD | D-2006-010 CP-5 | Bedminster Municipal Authority | An application to renew the approval of the existing 0.06 mgd Pennland Farms WWTP and its discharge. The WWTP will continue to discharge treated effluent to an UNT of Deep Run at River Mile 157.0 – 4.7 – 7.1 – 0.1 (Delaware River – Tohickon Creek – Deep Run – UNT of Deep Run) via Outfall No. 001, within the drainage area of the section of the main stem Delaware River known as the Lower Delaware, which the Commission has classified as Special Protection Waters, in Bedminster Township, Bucks County, Pennsylvania. | BEDMINSTER TWP | BUCKS | PA | PADEP SERO | NO | Lower |  | A | WWTP |  |  | 2025-12-16 | 163.3541 | 2026-01-08 | Docket |  | Pending
EE | D-2003-033 CP-3 | Aqua Pennsylvania, Inc. | An application to renew the approval of an existing groundwater withdrawal with an increase in allocation from 24.13 million gallons per month (mgm) to 26.24 mgm from 11 existing wells for the purpose of public water supply. The wells are completed in felsic gneiss, intermediate gneiss and graphitic gneiss within the West Branch Brandywine and East Branch Brandywine Watersheds, in East Brandywine, West Brandywine and Honey Brook Townships, Chester County, Pennsylvania. | EAST BRANDYWINE TWP | CHESTER | PA | PADEP SERO | NO |  |  | B | GWD |  |  | 2025-12-17 | 162.3541 | 2026-05-26 | Docket |  | Pending
BA | D-1996-045 CP-5 | Lansdale Borough | An application to renew the approval of the docket holder’s existing 3.2 mgd WWTP and its discharge. The existing WWTP will continue to discharge treated effluent to an unnamed tributary (UNT) to West Branch Neshaminy Creek at River Mile 115.63 - 40.0 - 5.35 - 1.25 (Delaware River - Neshaminy Creek - West Branch Neshaminy Creek - UNT to West Branch Neshaminy Creek) via Outfall No. 001 in Lansdale Borough, Montgomery County, Pennsylvania. | LANSDALE BORO | MONTGOMERY | PA | PADEP SERO | NO |  |  | A | WWTP |  |  | 2025-12-18 | 161.3541 | 2026-01-08 | Docket |  | Pending
EE | D-2013-020 -3 | BlueTriton Brands, Inc. | Revised NAR: An application to renew the approval of a groundwater withdrawal of up to 11.696 million gallons per month from Well No. IW-1 and the discharge of the withdrawn groundwater to Greenwalk Creek. The project will continue to intercept groundwater containing elevated concentrations of total dissolved solids, sulfate and calcium, apparently emanating from upgradient former slate mining areas, in order to manage the docket holder’s downgradient existing sources. The project is located in the Greenwalk Creek Watershed in Washington Township, Northampton County, Pennsylvania within the drainage area of the section of the main stem Delaware River known as the Lower Delaware, which the Commission has classified as Special Protection Waters. Original NAR: An application to renew the approval of a groundwater withdrawal of up to 8.640 million gallons per month from Well No. IW-1 and the discharge of the withdrawn groundwater to Greenwalk Creek. The requested allocation is a reduction from the allocation of 11.696 mgm currently approved by the Commission. The project will continue to intercept groundwater containing elevated concentrations of total dissolved solids, sulfate and calcium, apparently emanating from upgradient former slate mining areas, in order to manage the docket holder’s downgradient existing sources. The project is located in the Greenwalk Creek Watershed in Washington Township, Northampton County, Pennsylvania within the drainage area of the section of the main stem Delaware River known as the Lower Delaware, which the Commission has classified as Special Protection Waters. | WASHINGTON TWP | NORTHAMPTON | PA | PADEP NERO | NO | Lower |  | A | GWD |  |  | 2025-12-18 | 161.3541 | 2026-05-26 | Docket |  | Pending
EE | D-1988-052 -6 | Grand Central Sanitary Landfill, Inc. | An application to renew the approval of the docket holder’s existing 0.1 mgd leachate treatment plant (LTP) and its discharge. Treated effluent will continue to be discharged to an unnamed tributary (UNT) to Little Bushkill Creek at River Mile 184.1 - 8.5 - 8.1 - 0.1 (Delaware River - Bushkill Creek - Little Bushkill Creek - UNT Little Bushkill Creek) via Outfall No. 001, within the drainage area of the section of the non-tidal Delaware River known as the Lower Delaware, which the Commission has classified as Special Protection Waters, in Plainfield Township, Northampton County, Pennsylvania. | PLAINFIELD TWP | NORTHAMPTON | PA | PADEP NERO | NO | Lower |  | A | IWTP |  |  | 2025-12-22 | 157.3541 | 2026-04-08 | Docket |  | Pending
RD | D-2001-015 CP-7 | Aqua Pennsylvania, Inc. | An application to renew the approval of an existing groundwater withdrawal with an increase in system allocation from 39.33 mgm to 41.0 mgm to supply the applicant's public water supply distribution system from existing Wells SWC-1, SWC-2, SWC-4, SWC-5, SWC-8, SWC-10, SWC-11, SWC-12, CP-9, IR-1, IR-2, SWC-13, SWC-14 and new Wells CG-1 and KW-1. All the project wells are completed in the Brunswick Formation, except for Well CP-9 which is completed in the Lockatong Formation. The project is located in the Commission's designated Southeastern Pennsylvania Ground Water Protected Area (SEPA GWPA) in the Swamp Creek, Minister Creek, Scioto Creek and Zacharias Creek Watersheds in New Hanover, Douglass, Upper Fredrick and Worcester Townships, Montgomery County, Pennsylvania. | DOUGLASS TWP | MONTGOMERY | PA | PADEP SERO | YES |  |  | B | GWD |  |  | 2025-12-22 | 157.3541 | 2026-01-08 | Docket |  | Pending
RP | D-2017-006 -2 | Barton Court MHP | An application to approve the existing 0.0117 mgd Barton Court Mobile Home Park WWTP. The WWTP will continue to discharge treated effluent to an unnamed tributary (UNT) to Pocono Creek, at River Mile 213 - 4.0 - 0.82 - 8.1 - 1.0 (Delaware River - Broadhead Creek - McMichael Creek - Pocono Creek - UNT Pocono Creek) in the drainage area of the section of the non-tidal Delaware River known as the Middle Delaware, which the Commission has classified as Special Protection Waters, in Pocono Township, Monroe County, Pennsylvania. | POCONO TWP | MONROE | PA | PADEP NERO | NO | Middle |  | A | WWTP |  |  | 2026-01-07 | 141.3541 | 2026-03-11 | Docket |  | Pending
RD | D-1992-044 CP-5 | NORTH PENN WATER AUTHORITY | An application to renew the approval of an existing groundwater withdrawal and decrease the allocation from 143 mgm to 97.19 mgm from ten (10) existing wells; and to receive up to 561.1 mgm ( 18.1 mgd) of potable water via an interconnection with the Forest Park Water Treatment Plant. The application will also approve the removal of seven (7) existing wells from the previous approval. The North Penn Water Authority wells are all completed Brunswick Formation, except for Well NB-2 which is completed in the Stockton Formation. The project is located within the Commission's designated Southeastern Pennsylvania Ground Water Protected Area (SEPA GWPA) in the East Branch Perkiomen, Indian, Skippack, Towamencin, Wissahickon and Pine Run Watersheds in Franconia, Lower Salford, Towamencin, Upper Gywnedd Townships and Lansdale Borough, all in Montgomery County and West Rockhill and New Britain Borough in Bucks County, Pennsylvania. | NEW BRITAIN BORO | BUCKS | PA | PADEP SERO | YES |  |  | B | GWD / SWWD |  |  | 2026-01-08 | 140.3541 | 2026-03-11 | Docket |  | Pending
RD | D-2006-033 CP-4 | Pennsylvania American Water Company | An application to renew the approval of an existing groundwater withdrawal of up to 19.19 mgm to supply the applicant's Blue Mountain Lakes public water supply distribution system from existing Wells PW-1, PW-2 and PW-3. Wells PW-1 and PW-2 are completed in the Mahatango Formation and Well PW-3 is completed in the Trimmers Rock Formation. The requested allocation is not an increase from the previous allocation. The project is located in the Brodhead Creek Watershed in Stroud Township, Monroe County, Pennsylvania within the drainage area to section of the main stem Delaware River known as the Lower Delaware, which the Commission has classified as Special Protection Waters. | STROUD TWP | MONROE | PA | PADEP NERO | NO | Middle |  | A | GWD |  |  | 2026-01-12 | 136.3541 | 2026-03-11 | Docket |  | Pending
RD | D-2006-019 -6 | Brookdale Enterprises, LLC | An application to renew the approval of the existing 0.049 mgd WWTP and its discharge. The WWTP will continue to discharge treated effluent to Brookdale Lake at River Mile 213.0 - 3.9 - 0.9 - 11.4 - 2.85 - 0.15 (Delaware River - Brodhead Creek - McMichael Creek - Pocono Creek - Scot Run - Brookdale Lake) via Outfall No. 001, within the drainage area of the section of the main stem Delaware River known as the Middle Delaware, which the Commission has classified as Special Protection Waters, in Pocono Township, Monroe County, Pennsylvania. | POCONO TWP | MONROE | PA | PADEP NERO | NO | Middle |  | A | WWTP |  |  | 2026-01-30 | 118.3541 | 2026-03-11 | Docket |  | Pending
BA | D-1983-009 -5 | Environmental Resource Holdings, LLC (ERH) | An application to renew the approval of the existing Environmental Resource Holdings, LLC (formerly Occidental Chemical Corporation (OxyChem)) treatment system and associated discharge. The facility will continue to pump and treat up to 0.30 mgd of groundwater and stormwater before discharging to the Delaware River in Water Quality Zone 5 at River Mile 61.7, located in Delaware City, New Castle County, Delaware. | DELAWARE CITY | NEW CASTLE | DE | DNREC | NO |  |  | A | IWTP |  |  | 2026-02-25 | 92.3541 | 2026-04-08 | Docket |  | Pending
RP | D-2002-029 CP-5 | Towamencin Municipal Authority | An application to renew approval of the applicant's 6.5 mgd WWTP and its discharge. The WWTP will continue to discharge treated effluent to Towamencin Creek, tributary to Skippack Creek, tributary to Perkiomen Creek, tributary to the Schuylkill River, at River Mile 92.5 - 32.3 - 3.0 - 7.6 -1.4 (Delaware River -Schuylkill River - Perkiomen Creek - Skippack Creek - Towamencin Creek), in Towamencin Township, Montgomery County, Pennsylvania. | TOWAMENCIN TWP | MONTGOMERY | PA | PADEP SERO | NO |  |  | A | WWTP |  |  | 2026-03-02 | 87.3541 | 2026-05-26 | Docket |  | Pending
EE | D-2000-012 CP-3 | First State Generation, LLC | An application to renew the approval to withdraw up to 8,804 million gallons per month (mgm) of surface water from the Pumphouse 2 Intake and up to 18,296 mgm of surface water from the Pumphouse 3 Intake from the Delaware River (total combined allocation of 27,100 mgm) for non-contact cooling, cooling tower makeup, fire suppression and intake screen backwashing at the existing Edge Moor and Hay Road Energy Centers. The facility is located in the City of Wilmington and New Castle County, Delaware, and the intakes withdraw water at approximately River Mile 72.1 in Delaware River Water Quality Zone 5. | WILMINGTON CITY | NEW CASTLE | DE | DNREC | NO |  |  | A | SWWD |  |  | 2026-03-12 | 77.3541 | 2026-04-08 | Docket |  | Pending
BA | D-1993-062 CP-5 | Lake Adventure Comm. Assoc. | An application to renew an approval of the existing 0.16 mgd WWTP and its discharge. The existing WWTP will continue to discharge treated effluent to land via spray irrigation and to an unnamed tributary (UNT) to Birchy Creek at River Mile 273.2 - 13.2 - 0.2 - 0.7 (Delaware River - Shohola Creek – Birchy Creek – UNT Birchy Creek) via Outfall No. 001 located in Dingman Township, Pike County, Pennsylvania. The WWTP discharges within the drainage area to the Middle Delaware River Special Protection Waters. | DINGMAN TWP | PIKE | PA | PADEP NERO | NO | Middle |  | A | WWTP |  |  | 2026-03-19 | 70.3541 | 2026-05-26 | Docket |  | Pending
RD | D-1975-028 CP-6 | Pen Argyl Municipal Authority | An application to renew the approval of the existing 0.95 mgd WWTP and its discharge. The WWTP will continue to discharge treated effluent to an unnamed tributary (UNT) of Waltz Creek at River Mile 190.65 - 4.7 - 4.1 - 0.6 (Delaware River - Martins Creek - Waltz Creek - UNT of Waltz Creek) via Outfall No. 001, within the drainage area of the section of the main stem Delaware River known as the Lower Delaware, which the Commission has classified as Special Protection Waters, in the Borough of Pen Argyl, Northampton County, Pennsylvania. | PEN ARGYL BORO | NORTHAMPTON | PA | PADEP NERO | NO | Lower |  | A | WWTP |  |  | 2026-03-23 | 66.3541 | 2026-04-08 | Docket |  | Pending
EE | D-1970-120 -5 | Cambridge-Lee Industries, LLC | An application to renew the applicant's existing discharge of industrial process water from its copper pipe manufacturing facility. The facility will continue to discharge 0.0155 million gallons per day (mgd) of cooling tower blowdown and pretreatment system backwash via Outfall No. 001, and 0.929 mgd of cooling tower blowdown and noncontact cooling water (NCCW) via Outfall No. 002. The facility will continue to discharge industrial process water from two outfalls (Outfall Nos. 001 and 002) to the Schuylkill River at River Mile 92.47 - 86.5 (Delaware River - Schuylkill River), located in Ontelaunee Township, Berks County, Pennsylvania. | ONTELAUNEE TWP | BERKS | PA | PADEP SCRO | NO |  |  | A | IWTP |  |  | 2026-03-25 | 64.3541 | 2026-04-08 | Docket |  | Pending
RD | D-2006-008 -3 | GREEN WALK TROUT HATCHERY, INC. | An application to renew the approval of an existing groundwater withdrawal of up to 13.392 mgm to supply the applicant's trout hatchery from existing Wells W-2, W-5 and W-6. The project wells are screened in the unconsolidated deposits overlying the Martinsburg Formation. The requested allocation is not an increase from the previous allocation. The project wells are located in the Waltz Creek Watershed in Washington Township, Northampton County, Pennsylvania within the drainage area of the section of the main stem Delaware River known as the Lower Delaware which the Commission has classified as Special Protection Waters. | WASHINGTON TWP | NORTHAMPTON | PA | PADEP NERO | NO | Lower |  | A | GWD |  |  | 2026-04-13 | 44.3541 | 2026-05-26 | Docket |  | Pending
RP | D-2009-024 -4 | Camp Lohikan | An application to renew the approval of the applicant's existing 0.03 mgd WWTP and its land discharge via spray irrigation. Treated effluent will continue to be spray irrigated to two spray fields located in the Equinunk Creek watershed, within the drainage area to the section of the main stem Delaware River known as the Upper Delaware, which the Commission has classified as Special Protection Waters, in Buckingham Township, Wayne County, Pennsylvania. | BUCKINGHAM TWP | WAYNE | PA | PADEP NERO | NO | Upper |  | A | WWTP |  |  | 2026-04-14 | 43.3541 | 2026-05-26 | Docket |  | Pending
RD | D-2001-061 CP-6 | Upper Hanover Authority | An application to renew the approval of the existing 0.4 mgd Macoby Creek WWTP and its discharge. The existing WWTP will continue to discharge treated effluent to Macoby Creek at River Mile 92.47 - 32.3 - 19.5 - 5.3 (Delaware River - Schuylkill River - Perkiomen Creek - Macoby Creek) via Outfall No. 001 in Upper Hanover Township, Montgomery County, Pennsylvania. | UPPER HANOVER TWP | MONTGOMERY | PA | PADEP SERO | NO |  |  | A | WWTP |  |  | 2026-04-29 | 28.3541 | 2026-05-26 | Docket |  | Pending
BA | D-1999-017 CP-3 | Kennett Square Borough | An application to renew the approval of an existing 1.1 mgd WWTP and its discharge. The WWTP will continue to discharge treated effluent to the West Branch Red Clay Creek at River Mile 70.73 - 10.0 - 2.6 - 13.4 - 3.3 (Delaware River - Christina River - White Clay Creek - Red Clay Creek - West Branch Red Clay Creek) via Outfall No. 001 in Kennett Township, Chester County, Pennsylvania. | KENNETT SQUARE BORO | CHESTER | PA | PADEP SERO | NO |  |  | A | WWTP |  |  | 2026-04-30 | 27.3541 | 2026-05-26 | Docket |  | Pending
BA | D-2026-001 CP-1 | Morrisville Municipal Authority | An application to approve a new WWTP and its associated discharge with a proposed annual average flow of 8.0 mgd, to be constructed at the Keystone Trade Center. Treated effluent is proposed to be discharged to the Delaware River at River Mile 127 via a new outfall located in Falls Township, Bucks County, PA. | MORRISVILLE BORO | BUCKS | PA | PADEP SERO | NO |  |  | C | WWTP |  |  | 2026-04-30 | 27.3541 | 2026-05-26 | Docket |  | Pending

## narlist
Docket Number | Applicant | NAR Description
D-1993-062 CP-5 | Lake Adventure Comm. Assoc. | An application to renew an approval of the existing 0.16 mgd WWTP and its discharge. The existing WWTP will continue to discharge treated effluent to land via spray irrigation and to an unnamed tributary (UNT) to Birchy Creek at River Mile 273.2 - 13.2 - 0.2 - 0.7 (Delaware River - Shohola Creek – Birchy Creek – UNT Birchy Creek) via Outfall No. 001 located in Dingman Township, Pike County, Pennsylvania. The WWTP discharges within the drainage area to the Middle Delaware River Special Protection Waters.
D-1999-017 CP-3 | Kennett Square Borough | An application to renew the approval of an existing 1.1 mgd WWTP and its discharge. The WWTP will continue to discharge treated effluent to the West Branch Red Clay Creek at River Mile 70.73 - 10.0 - 2.6 - 13.4 - 3.3 (Delaware River - Christina River - White Clay Creek - Red Clay Creek - West Branch Red Clay Creek) via Outfall No. 001 in Kennett Township, Chester County, Pennsylvania.
D-2001-061 CP-6 | Upper Hanover Authority | An application to renew the approval of the existing 0.4 mgd Macoby Creek WWTP and its discharge. The existing WWTP will continue to discharge treated effluent to Macoby Creek at River Mile 92.47 - 32.3 - 19.5 - 5.3 (Delaware River - Schuylkill River - Perkiomen Creek - Macoby Creek) via Outfall No. 001 in Upper Hanover Township, Montgomery County, Pennsylvania.
D-2002-029 CP-5 | Towamencin Municipal Authority | An application to renew approval of the applicant's 6.5 mgd WWTP and its discharge. The WWTP will continue to discharge treated effluent to Towamencin Creek, tributary to Skippack Creek, tributary to Perkiomen Creek, tributary to the Schuylkill River, at River Mile 92.5 - 32.3 - 3.0 - 7.6 -1.4 (Delaware River -Schuylkill River - Perkiomen Creek - Skippack Creek - Towamencin Creek), in Towamencin Township, Montgomery County, Pennsylvania.
D-2003-033 CP-3 | Aqua Pennsylvania, Inc. | An application to renew the approval of an existing groundwater withdrawal with an increase in allocation from 24.13 million gallons per month (mgm) to 26.24 mgm from 11 existing wells for the purpose of public water supply. The wells are completed in felsic gneiss, intermediate gneiss and graphitic gneiss within the West Branch Brandywine and East Branch Brandywine Watersheds, in East Brandywine, West Brandywine and Honey Brook Townships, Chester County, Pennsylvania.
D-2006-008 -3 | Green Walk Trout Hatchery, Inc. | An application to renew the approval of an existing groundwater withdrawal of up to 13.392 mgm to supply the applicant's trout hatchery from existing Wells W-2, W-5 and W-6. The project wells are screened in the unconsolidated deposits overlying the Martinsburg Formation. The requested allocation is not an increase from the previous allocation. The project wells are located in the Waltz Creek Watershed in Washington Township, Northampton County, Pennsylvania within the drainage area of the section of the main stem Delaware River known as the Lower Delaware which the Commission has classified as Special Protection Waters.
D-2009-024 -4 | Camp Lohikan | An application to renew the approval of the applicant's existing 0.03 mgd WWTP and its land discharge via spray irrigation. Treated effluent will continue to be spray irrigated to two spray fields located in the Equinunk Creek watershed, within the drainage area to the section of the main stem Delaware River known as the Upper Delaware, which the Commission has classified as Special Protection Waters, in Buckingham Township, Wayne County, Pennsylvania.
D-2013-007 CP-3 | Parkland School District | An application to approve the applicant's proposed construction project of two (2) new sequencing batch reactors (SBR), new tertiary filter, new ultraviolet disinfetion, and ancillary equipment to increase the design hydraulic capacty to 55,000 gpd average (0.55 mgd), 82,500 gpd (0.0825 mgd) peak, and organic capacity o 80 lbs/day CBOD5. Currently, the WWTP is not able to meet its current NPDES Permit limits for total nitrogen due to an increased organic and hydraulic loading to the WWTP that currently exceeds the original design. The WWTP will continue to discharge treated effluent into Jordan Creek, a tributary of the Lehigh River, at River Mile 183.7 - 16.3 - 8.6 (Delaware River - Lehigh River - Jordan Creek), via Outfall No. 001, located in South Whitehall Township, Lehigh County, Pennsylvania, within the drainage area of the section of the non-tidal Delaware River known as the Lower Delaware, which is classified as Special Protection Waters.
D-2013-020 -3 | BlueTriton Brands, Inc. | Revised NAR: An application to renew the approval of a groundwater withdrawal of up to 11.696 million gallons per month from Well No. IW-1 and the discharge of the withdrawn groundwater to Greenwalk Creek. The project will continue to intercept groundwater containing elevated concentrations of total dissolved solids, sulfate and calcium, apparently emanating from upgradient former slate mining areas, in order to manage the docket holder’s downgradient existing sources. The project is located in the Greenwalk Creek Watershed in Washington Township, Northampton County, Pennsylvania within the drainage area of the section of the main stem Delaware River known as the Lower Delaware, which the Commission has classified as Special Protection Waters. Original NAR: An application to renew the approval of a groundwater withdrawal of up to 8.640 million gallons per month from Well No. IW-1 and the discharge of the withdrawn groundwater to Greenwalk Creek. The requested allocation is a reduction from the allocation of 11.696 mgm currently approved by the Commission. The project will continue to intercept groundwater containing elevated concentrations of total dissolved solids, sulfate and calcium, apparently emanating from upgradient former slate mining areas, in order to manage the docket holder’s downgradient existing sources. The project is located in the Greenwalk Creek Watershed in Washington Township, Northampton County, Pennsylvania within the drainage area of the section of the main stem Delaware River known as the Lower Delaware, which the Commission has classified as Special Protection Waters.
D-2026-001 CP-1 | Morrisville Municipal Authority | An application to approve a new WWTP and its associated discharge with a proposed annual average flow of 8.0 mgd, to be constructed at the Keystone Trade Center. Treated effluent is proposed to be discharged to the Delaware River at River Mile 127 via a new outfall located in Falls Township, Bucks County, PA.