## Slide 1: Reclaiming Educator Time: Centralizing SGOs and PDPs for Impact
A Joint Presentation by Delsea Regional and Elk Township School Districts
Teacher Climate and Culture Institute
June 29, 2025
Notes: This title slide introduces the presentation, which focuses on reducing administrative burdens by centralizing Student Growth Objectives (SGOs) and Professional Development Plans (PDPs). The initiative is led by Delsea Regional and Elk Township as part of the Teacher Climate and Culture Institute. Reclaiming Educator Time Through Centralized SGOs and PDPs

## Slide 2: Welcome & Introduction
Delsea Regional and Elk Township: Partnering for Teacher Climate and Culture
Focus: Reducing Administrative Burden to Increase Instructional Impact
Reflection Prompt:
  What’s your current SGO/PDP process like?
On your sticky note: What’s your current SGO/PDP process like?
Notes: This slide welcomes attendees and introduces the two district partners. It frames the presentation as a solution to reclaim teacher time and improve school culture by streamlining SGOs and PDPs.

## Slide 3: Problem Statement
Student Growth Objectives (SGOs) and Professional Development Plans (PDPs): Originally Designed for Growth
Reality: Time-Consuming Compliance Tasks
Goal: Reclaim Teacher Time for Instructional Excellence
Reflection Prompt:
  What part of SGOs/PGDPs take the most time?
On your sticky note: What part of SGOs/PGDPs take the most time?
Notes: This slide outlines how SGOs and PDPs have shifted from tools for growth to compliance tasks. It establishes the need to reduce time spent on paperwork and redirect that time to instructional planning.

## Slide 4: Our Solution: Centralized SGOs and PDPs
Streamlined Templates
Shared Alignment with District Goals
Teacher Opt-In and Voice Embedded
Notes: This slide introduces the solution: a centralized system using shared templates aligned to district goals. Teachers can opt in and maintain voice in the process, helping reduce burden while maintaining meaning.

## Slide 5: Goal Alignment
SGO
  Gateway Statement: Improve performance on schoolwide measure
  Scoring Plan: Prevalence of High Effect-Size Instructional Strategies and Classroom Conditions
Professional Development Plan
  Professional Development Goals for High Effect-Size Instructional Strategies and Classroom Conditions
Notes: This slide highlights how both SGOs and PDPs are focused on high-impact strategies and classroom conditions. The alignment ensures that teacher growth plans are meaningful and instructionally relevant.

## Slide 6: Further Alignment
Administrator Goals
  Number of Walkthroughs (which identify the presence of High Effect-Size Instructional Strategies (HESIS) and High Effect-Size Classroom Conditions (HESCC)
District Goals (Usually for Superintendent)
  Improvement on School or Districtwide Measures
Notes: This slide shows how administrator walkthroughs and superintendent goals are aligned to teacher plans. Everyone is working toward the same instructional targets, reinforcing systemwide coherence.

## Slide 7: Everything is Aligned (Note: text version is on next slide)
Administrators Goals
SGO/PDP Goals
District Goals
Discussion Prompt: Where could alignment be strengthened in your school district?
Discussion: Where could alignment be strengthened in your school district?
Notes: This slide uses a visual pyramid to summarize how SGOs, PDPs, admin walkthroughs, and district goals all connect through shared measures and high-effect-size instructional practices.

## Slide 8: Everything is Aligned – Text Version
Curriculum guides inform daily instruction
SGOs are built from curriculum pacing and targets
PDPs align to instructional focus areas
Evaluation tools reflect both planning and delivery Everything connects to our shared instructional goals
Discussion Prompt: Where could alignment be strengthened in your school district?
Notes: This text-based slide provides a screen reader–friendly version of the pyramid. It describes the alignment from teacher SGOs and PDPs to administrator and district goals using consistent measures and strategies.

## Slide 9: Targeted Area of Focus
Delsea: Secondary (Grades 6-12)
Elk: Elementary (PreK-6)
Both: Prioritize Teacher Time, Preserve Instructional Integrity
Notes: This slide explains how the work was divided: Delsea focused on secondary (grades 6–12) and Elk on elementary (PreK–6). Both prioritized teacher time and instructional focus.

## Slide 10: Non-negotiables
Must have schoolwide or districtwide measure:
  Renaissance Star
  Achieve3000 Level Set
  HMH Growth Measure (Houghton Mifflin Harcourt)
Collaboration is Key
  Everything is run through the School Improvement Panel (ScIP)
  Evaluation Process is one of the responsibilities of a ScIP – a natural place for collaboration and planning.
Language of Instruction
  Visible Learning, Classroom Instruction that Works, High Reliability Schools, and more.
Notes: This slide identifies foundational requirements, including schoolwide/districtwide measures, collaboration through the ScIP, and instructional coherence through shared frameworks like Visible Learning.

## Slide 11: Implementation Steps
Summer
  Meet with ScIP, define instructional priorities for the upcoming year
  Meet with instructional team/ data coordinator to establish universal goals
  Host instructional support workshops throughout the summer
  Monthly administrative walkthrough pair schedule created
Back to School In-service
  Share goals with staff as a part of annual evaluation refresher training
Notes: This slide outlines the first steps taken: summer meetings with ScIP and instructional teams, setting districtwide goals, and scheduling walkthroughs. Teachers were introduced to the goals during in-service.

## Slide 12: Implementation Continued
Beginning of year schoolwide measure is given to students
SGOs and PDPs entered by teachers into Student Information System by October 15th.
  Most were complete by the end of September Back to School Inservice
  From October 15 to October 30 – All forms are processed in the Assistant Superintendent’s Office
Paired Walkthroughs occur: 10 per month Sept to March (Nov and Dec are combined).
Notes: This slide continues the timeline. Teachers administered schoolwide assessments and entered SGOs/PDPs by October 15. Forms were processed centrally, and monthly walkthroughs began.

## Slide 13: Mid-Year Check
SGO results are reviewed by instructional teams and Professional Learning Community leaders.
  While Goal Adjustment has not been needed, the ScIP convenes in January to meet and discuss progress before the February 15th deadline.
    Since we have the middle of year benchmark information, we already know if students met the gateway statement of improvement on an academic measure.
Notes: Midyear data reviews helped teams assess student progress. The ScIP convened in January to evaluate outcomes and ensure goals remained appropriate. In most cases, improvement was already evident.

## Slide 14: Spring
March – walkthroughs are completed, scoring plan entered into SGOs by the Superintendent’s Office
April – End of Year Benchmark is given
  Remember, we are only looking at improvement – we have usually met the standard in January. The April measure is a back-up.
Notes: Walkthroughs ended in March, and final SGO scores were entered. An April benchmark was given as a backup, though most goals had been met by January. The process emphasized improvement over perfection.

## Slide 15: Impact Measures
Time-to-Completion: < 10 minutes per SGO/PDP
Teacher Satisfaction Surveys
NJSCI Indicators
Increased Instructional Coaching Touchpoints
Notes: This slide outlines the impact: SGOs and PDPs now take less than 10 minutes to complete, instructional coaching touchpoints increased, and both teacher satisfaction and NJSCI indicators improved.

## Slide 16: Results Achieved
Teachers: More Time for Planning & Collaboration
Leaders: Stronger Alignment with School Improvement Goals
Students: Improved Instructional Focus
Notes: Teachers gained more time for collaboration, leaders saw stronger alignment with school goals, and students benefited from a more focused instructional environment.

## Slide 17: Lessons Learned
Voluntary Participation Builds Trust
Teacher-Centric Design Ensures Sustainability
Small Districts Can Drive Big Change
Notes: Key takeaways include the value of voluntary participation, teacher-driven design, and the ability of small districts to create scalable, sustainable change.

## Slide 18: Replication & Scaling
Highly Replicable Model
Key Considerations:
Protected Summer Design Time
Clear Communication Channels
Flexibility to Adapt Templates
Reflection Prompt:
  What would you replicate immediately?
On your sticky note: What would you replicate immediately?
Notes: This slide emphasizes that the model is highly replicable. Success depends on summer planning time, clear communication, and the flexibility to adapt templates to local needs. This slide invites participants to reflect on their current process. Reflection prompt: What would you replicate immediately?

## Slide 19: Best Practices for Success
Start with Highly Effective Pilot Teams
Align SGOs/PDPs with Real Instructional Goals
Prioritize Authentic Reflection, Not Just Compliance
Use Feedback Loops Religiously
Local Planning
Notes: Best practices include starting with strong pilot teams, aligning SGOs/PDPs with real goals, using reflection rather than compliance as the anchor, and building in feedback loops. This slide invites participants to pause and identify which of these practices they’re already using and which might be areas for deeper investment.

## Slide 20: Next Steps for Us
Delsea: Deepen Instructional Coaching Systems
Elk: Share Model with Other Small Districts
Both: Refine, Sustain, and Inspire
Reflection Prompt:
  One action you will take next week…
Exit Ticket: One action you will take next week…
Notes: Delsea plans to expand instructional coaching. Elk will share their model with other districts. Both will refine and sustain the work, aiming to inspire broader change. This final slide invites participants to identify a single next step based on today’s session. Ask them to take a moment and write down one action they will try, revisit, or implement next week.

## Slide 21: Follow Us on Social Media
Facebook: @njdeptofed
Instagram: @newjerseydoe
LinkedIn: New Jersey Department of Education
Threads: @NewJerseyDOE
X: @NewJerseyDOE
YouTube: @newjerseydepartmentofeduca6565
Notes: This slide shares NJDOE social media accounts across platforms to invite continued engagement with this work and future updates.

## Slide 22: Thank You!
New Jersey Department of Education: https://www.njgov/education/
Anthony Fitzpatrick – afitzpatrick@delsearegional.us
Brianna Rucci – brucci@delsearegional.us
Teresa Johnson – tjohnson@delsearegional.us
George Clark – gclark@delsearegional.us
Notes: The final slide offers contact information for the presenters and thanks the audience. It encourages follow-up and collaboration beyond the session.