## F-1
F-1
2026-06-30
Anytown School District
Capital Projects Fund
Summary Schedule of Project Expenditures
Year Ended June 30, 20XX
GAAP
|  | Revised | Expenditures to Date |  | Unexpended
|  | Budgetary | Prior | Current | Appropriations
Project Title/Issue | Approval Date | Appropriations | Years | Year | 6/30/20XX
Addition to Middle School | 3/1/20XX | 2085000 | 0 | 990623 | 1094377
Roof Repairs to Elementary School | 6/30/20XX | 437500 | 400000 | 37500 | 0
Addition to High School | 5/1/20XX | 8000000 | 6785849 | 888751 | 325400
Totals |  | 10522500 | 7185849 | 1916874 | 1419777

## F-2
F-2
2023-06-30
Anytown School District
Summary Schedule of Revenues, Expenditures, and Changes in Fund Balance - Budgetary Basis
Budgetary Basis | Budgerary Basis
Year Ended June 30, 20XX
Revenues and Other Financing Sources:
State sources - SDA grant |  | 834000
Bond proceeds and transfers |  | 1050000
Contribution from private source |  | 888751
Transfer from capital reserve |  | 0
Transfer from capital outlay |  | 200000
Total Revenues |  | 2972751
Expenditures and Other Financing Uses:
Purchased professional and technical services |  | 94251
Land and improvements |  | 93874
Construction services |  | 839998
Equipment purchases |  | 888751
Total Expenditures |  | 1916874
Excess (Deficiency) of revenues over (under) expenditures |  | 1055877
Fund Balance - Beginning |  | 251000
Fund Balance - Ending |  | 1306877

## F-2(a)
F-2a
2023-06-30
Anytown School District
Schedule of Project Revenues, Expenditures, Project Balance, and Project Status - Budgetary Basis
Addition to Middle School
From Inception and for the Year Ended June 30, 20XX
| Prior Periods | Current Period | Totals | Revised Authorized Cost
Year
Revenues and Other Financing Sources:
State sources - SDA grant | 0 | 834000 | 834000 | 834000
Bond proceeds and transfers | 0 | 1050000 | 1050000 | 1050000
Contribution from private source | 0 | 0 | 0 | 0
Transfer from capital reserve | 0 | 0 | 0 | 0
Transfer from capital outlay | 0 | 200000 | 200000 | 201000
Total Revenues | 0 | 2084000 | 2084000 | 2085000
Expenditures and Other Financing Uses:
Purchased professional and technical services | 0 | 89141 | 89141 | 235000
Land and improvements | 0 | 93874 | 93874 | 500000
Construction services | 0 | 807608 | 807608 | 1350000
Equipment purchases | 0 | 0 | 0 | 0
Total Expenditures | 0 | 990623 | 990623 | 2085000
Excess (Deficiency) of revenues over (under) expenses | 0 | 1093377 | 1093377 | 0
Additional Project Information:
Project Number | 011-05-0468
Grant Date/Letter of Notification | 7/1/20XX
Bond Authorization/Referendum Date | 6/1/20XX
Bonds Authorized | 1050000
Bonds Issued | 1050000
Original Project Authorized Cost | 2050000
Additional Authorized Cost | 35000
Revised Authorized Cost | 2085000
Percentage Increase Over
Original Authorized Cost | 1.707%
Percentage Completion | 45%
Original Target Completion Date | 6/1/20XX
Revised Target Completion Date | N/A

## F-2(b)
F-2b
2023-06-30
Anytown School District
Schedule of Project Revenues, Expenditures, Project Balance, and Project Status - Budgetary Basis
Roof Repairs to Elementary School
From Inception and for the Year Ended June 30, 20XX
| Prior Periods | Current Period | Totals | Revised Authorized Cost
Year
Revenues and Other Funding Sources:
State sources - SDA grant | 175000 | 0 | 175000 | 175000
Bond proceeds and transfers | 0 | 0 | 0 | 0
Contribution from private source | 100000 | 0 | 100000 | 100000
Transfer from capital reserve | 0 | 0 | 0 | 0
Transfer from capital outlay | 162500 | 0 | 162500 | 162500
Total Revenues | 437500 | 0 | 437500 | 437500
Expenditures and Other Financing Uses:
Purchased professional and technical services | 21900 | 5110 | 27010 | 27010
Land and improvements | 0 | 0 | 0 | 0
Construction services | 378100 | 32390 | 410490 | 410490
Equipment purchases | 0 | 0 | 0 | 0
Total Expenditures | 400000 | 37500 | 437500 | 437500
Excess (Deficiency) of revenues over (under) expenses | 37500 | -37500 | 0 | 0
Additional Project Information:
Project Number | 010-04-0231
Grant Date/Letter of Notification | 5/1/20XX
Bond Authorization/Referendum Date | NA
Bonds Authorized | NA
Bonds Issued | NA
Original Project Authorized Cost | 437500
Additional Authorized Cost | 0
Revised Authorized Cost | 437500
Percentage Increase Over
Original Authorized Cost | 0%
Percentage Completion | 100%
Original Target Completion Date | 9/1/20XX
Actual Completion Date | 6/15/20XX

## F-2(c)
F-2c
2023-06-30
Anytown School District
Schedule of Project Revenues, Expenditures, Project Balance, and Project Status - Budgetary Basis
Addition to High School
From Inception and for the Year Ended June 30, 20XX
| Prior Periods | Current Period | Totals | Revised Authorized Cost
Year
Revenues and Other Funding Sources:
State sources - SDA grant | 0 | 0 | 0 | 0
Bond proceeds and transfers | 7000000 | 0 | 7000000 | 7000000
Contribution from private source | 0 | 888751 | 888751 | 900000
Transfer from capital reserve |  | 0 | 0 | 100000
Transfer from capital outlay | 0 | 0 | 0 | 0
Total Revenues | 7000000 | 888751 | 7888751 | 8000000
Expenditures and Other Financing Uses:
Purchased professional and technical services | 49000 | 0 | 49000 | 70000
Land and improvements | 0 | 0 | 0 | 0
Construction services | 6736849 |  | 6736849 | 7930000
Equipment purchases | 0 | 888751 | 888751 | 0
Total Expenditures | 6785849 | 888751 | 7674600 | 8000000
Excess (Deficiency) of revenues over (under) expenses | 214151 | 0 | 214151 | 0
Additional Project Information:
Project Number | 012-04-0468
Grant Date/Letter of Notification | 5/1/20XX
Bond Authorization/Referendum Date | 9/15/20XX
Bonds Authorized | 7000000
Bonds Issued | 7000000
Original Project Authorized Cost | 8000000
Additional Authorized Cost | 0
Revised Authorized Cost | 8000000
Percentage Increase Over
Original Authorized Cost | 0%
Percentage Completion | 100%
Original Target Completion Date | 9/1/20XX
Actual Completion Date | 6/15/20XX