## Sheet1
Township of Berkeley Planning and Implementation Agreement (PIA)
First Draft - September 29, 2009
Topic | Item No. | Activity | Local Effort | State Assistance | Time Frame
Sustainability | A1 | Greenhouse Gas (GHG) Audit: Apply for a grant to conduct an energy and GHG emissions audit. Evaluate energy and emissions. | Township Planning Board | The Board of Public Utiliies will be implementing a grant program | 2010-2011 subject to grant availability
Sustainability | A2 | Emissions Reduction Plan: Apply for a grant to prepare a Greenhouse Gas Emissions Reduction Plan consistent with NJ Global Warming Response Act. | Township Planning Board | NJDEP Regional Green House Gas Emissions grant program | 2010-2011 subject to grant availability
Sustainability | A3 | Green Building and Sustainability Master Plan Element: to provide for, encourage and promote sustainable construction |  | NJDEP Regional Green House Gas Emissions grant program | awaiting reponse from NJDEP for grant application submission
Sustainability | A4 | Green Future Roadmap Program: participate in and accomplish required criteria to be designated as a green and sustainable community. | Planning Board, actions and policies | NJDEP technical assistance | Register w. Sustainabile NJ in 2009 and become Certified in 2010
Land Use | B1 | Zoning Ordinances: amend specific ordinances to maintain center designation | Town Council and Planning Board to consider amending ordinances accordingly | OSG Technical Assistance | 2010
Fair Share Plan and Housing Element | C1 | Justify the outstanding credits for growth share through TDR program. | Township Planning Board |  | Ongoing - In Mediation
Fair Share Plan and Housing Element | C2 | Draft Implementing Ordinances / Documents: including Zoning Ordinance Amendments, Development Fee Ordinance, Spending Plan and Redevelopment Plan | Township Planning Board |  | Draft Ordinances submitted as part of Response to RRAI - September 2009
Conservation | D1 | Prepare an update to the NRI (or ERI) to reflect current conditions | Environmental Commission, Planning Board | ANJEC | January 2011
Conservation | D2 | Complete a Conservation Master Plan Element: to be based on NRI | Environmental Commission, Planning Board |  | Pending NRI Completion, October 2011
Conservation | D3 | Environmental Justice Inventory: complete assessment to ensure planning efforts do not disproportionately affect minority and low income individuals | Environmental Commission, Planning Board |  | Draft work by December 2010
Conservation | D4 | Protection Plan for Stream Corridors: complete a plan that establishes a waterways map that considers all required buffers, setbacks, and transition areas. | Environmental Commission, Planning Board |  | Draft work by March 2010
Conservation | D5 | Habitat Conservation Program: to include the creation, enhancement, restoration, acquisition, or preservation of suitable habitat for threatened or endangered species. | Environmental Commission, Planning Board | Technical and financial assistance | Ongoing
Conservation | D6 | Total Maximum Daily Load (TMDL) Implementation Plan: institute an implementation plan for the Barnegat Bay, Cedar Creek Estuary, and Toms River Estuary | Environmental Commission, Planning Board |  | Draft work by March 2011
Conservation | D7 | Septic Management Plan | Planning Board |  | Draft work by March 2011
Transportation | E1 | Circulation Element: update to address Airport Safety Zoning Act and the impact of the Robert J. Miller Airpark | Planning Board Amendment Analysis |  | Draft work product by January 2010
Transportation | E2 | State Highway Access Management (SHAM) Code: address conformance of zoning to applicable state highways | Redevelopment Plan, Town Council, and Planning Board | When requested, NJDOT will give priority consideration to providing technical assistance consistent with program requirements and subject to the availability of state resources. | Draft work products December 2010
Utilities | F1 | Stormwater Management Amendments: identify portions of the Master Plan, official map and development regulations (including zoning ordinance) that need to be amended to incorporate nonstructural strategies and timeframe for amendments. | Planning Board |  | Ongoing
Recycling | G1 | Statement of Consistency: submit consistency statement with the Ocean County Waste Management Plan | Planning Board |  | December 2009
Open Space and Recreation | H1 | Identify the entity that will become the steward of lands with severed development rights and update Open Space and Recreation Plan to identify any lands identified as ROSI lands | NJDEP ROSI designation and Planning Board |  | July 2010
Historic Resources | I1 | Create an inventory of current or potentially eligible historic and cultural resources | Planning Board: Create an Inventory |  | July 2010
Historic Resources | I2 | Create a Historic Preservation Plan based on Cultural Resource Inventory and adopted into the municipal Master Plan | Twp. Planning Board |  | Ongoing
Historic Resources | I3 | Adopt a historic preservation ordinance that provides for the designation and protection of historic sites and includes design guidelines. | Land Development Ordinancen to be amended to provide for Historic Preservation |  | July 2010
Transfer of Development Rights (TDR) Program | H1 | County Approvals: Submit the proposed Development Transfer Ordinance and accompanying documentation to the Ocean County Planning Board for review and recommendations. | Planning Board |  | Draft work products September 2008, Final 2010
Transfer of Development Rights (TDR) Program | H2 | REMA: Public Hearing shall be held on the real estate market analysis prior to the meeting at which the development transfer ordinance receives first reading. | Planning Board meeting |  | July 2010