## Sheet1
Toms River Township, Ocean County Endorsed by State Planning Commission on 1/2/2018 Plan and Implementation Agreeement
# | Activity | Local Effort | State/County Assistance | Deliverable | Time Table | Biennial Comment
0.1 | Update Master Plan | Tom River updates Master Plan which reflects the Township's Plan Endorsement petition. | As requested | Master Plan Update | To be completed prior to SPPM being updated and within six months of SPC action granting PE. | Completed in 207. SPPM updated in January 2018.
0.2 | Update land use and zoning ordinances to reflect agreed upon changes. | Tom River updates land use and zoning ordinances to reflect uses and intensity of development commensurate with their proposed changes to planning areas, designated centers and cores. | As requested | Revisions to Land Development and Zoning Code | To be completed prior to SPPM being updated and within six months of SPC action granting PE. | Completed in 207. SPPM updated in January 2018.
0.3 | Development of CAFRA Consistency Statement | Toms River develops and submits for NJDEP review and acceptance a CAFRA Consistency Statement. | NJDEP | CAFRA Consistency Statement |  | Completed in 2017. CAFRA Notice publishes in August of 2018.
0.4 | OPA updates SPPM with the proposed map amendments from the SPC PE resolution - Centers, Cores, and Planning Area Changes | Toms River Township demonstrates satisfaction of conditions established by the SPC. | OPA revises SPPM and submits map changes to the New Jersey State Register | Changed SPPM for Toms River Township | Upon demonstration by Toms River that Master Plan has been updated to reflect growth strategy and associated land use and zoning changes implemented. | Completed in 2017. SPPM updated in January 2018.
0.5 | Evaluate the inclusion on the Toms River Township Recreational and Open Space Inventory maintain by the NJDEP Green Acres Program of additional undeveloped township owned lands. | Toms River will investigate and evaluate the inclusion of appropriate township owned lands on the Recreational and Open Space Inventory maintain by the NJDEP Green Acres Program where there are significant environmental limitations to development and/or that add to community resiliency. | DEP | List of township owned lands determined to be suitable for inclusion on the Recreational and Open Space Inventory for the Township maintained by the NJDEP Green Acres Program. | Within 6 months of Plan Endorsement | Completed in 2017. CAFRA Notice publishes in August of 2018.
0.6 | Improving quality of storm water runoff to Barnegat Bay from redevelopment sites. | Working with NJDEP, develop and implement a strategy through appropriate revisions to the Land Development Ordinance and related ordinances that will improve the quality of storm water runoff to Barnegat Bay from sites undergoing redevelopment that would otherwise be exempt from providing storm water runoff controls. | DEP | Appropriate changes to Land Development and related ordinances that implement storm water quality improvement controls on redevelopment sites. | Within 6 months of Plan Endorsement | Completed in 2017. CAFRA Notice publishes in August of 2018.
0.7 | Stream Corridor Protection Plan | Using current Code requirements and/or such modifcations as necessary, submit document to NJDEP that the Township has or will have local controls in place that requires the protection and preservation of riparian coridors. | DEP | Stream Corridor Protection Plan or demonstration of equivalent riparian protection strategy under existing ordinances and/or such modifcations as necessary. | Within 6 months of Plan Endorsement | Completed in 2017. CAFRA Notice publishes in August of 2018.
1. General
1.1 | NJDEP consideration of SPPM changes for use in CAFRA. | Toms River Township demonstrates satisfaction of conditions established by the SPC that are precedent to changes requested by the township to the SPPM and the submission to NJDEP of a CAFRA Consistency Statement. |  | Notice in the New Jersey Register of NJDEP determination of SPPM changes in the CAFRA area. | NJDEP will complete a review of SPPM changes proposed and accepted by the SPC within 90 days of the receiving notice from OPA that the conditions precedent to the SPPM changes have been satisfied. | Completed in 2017. CAFRA Notice publishes in August of 2018.
1.2 | Plan Endorsement biannual review | By a date agreed upon between the SPC and the Township and biennually thereafter, Toms River Township shall submit within six months of the action a report to OPA and the public concerning the terms of this PIA and related efforts pursuant to NJAC 5:85-7.12(c). | OPA will provide template | Evaluation of Plan Endorsement and any township requested amendments to the Plan. | As required by NJAC 5:85 | Template provided in January of 2021 and used for this first Biennial Report.
1.25 | Plan Endorsement review | If Toms River adopts any new or significant change to the reexamination report, land use ordinance or other planning documents submitted as part of the Plan Endorsement, the Township shall submit a report to OPA and the public concerning the terms of this PIA and related efforts pursuant to NJAC 5:85-7.12(c). | OPA will provide template | Evaluation of Plan Endorsement and any township requested amendments | As required by NJAC 5:85 | Addendum No. 1, adopted July 3, 2019, to Part 2 (Land Use Element) of 2017 Reexamination Report attached to this Biennial Report.
1.3 | Inter-governmental Corrdination | Coordinate with planning efforts of adjoining municipalities, the County and State and regional planning efforts particularly concerning: regional planning, transportation, economic development, tourism, natural resource protection and open space and recreation. | County Planning Board, OPA, DOT, DEP, NJ Transit |  | Ongoing | Coordination with Ocean County on Downtown Circulation Improvements and BUILD Grant from FHWA, as well as inclusion of County Social Service in Hooper-Caudina Redevelopment.
1.4 | Center, Node, Core boundary modifications | As part of the biannual review the State Planning Commission agrees to reevaluate boundaries based on implementation of the PIA. | County Planning Board, OPA, DOT, DEP, NJ Transit |  | Ongoing | Township requests two boundary amendments in this Biennial Report.
2.1 | Master Plan | Review and update Master Plan goals and objectives as directed by the MLUL. The remaining elements need to be updated to reflect the community vision that was conducted as well as the Growth Management Plan and including Center Boundaries, update: C. Circulation D. Housing E. Historic Preservation F. Community Facilities G. Utilities H. Economic Development I. Conservation of Open Space |  |  | Ongoing Reexamination as required by the M.L.U.L. | Addendum No. 1, adopted July 3, 2019, to Part 2 (Land Use Element) of 2017 Reexamination Report attached to this Biennial Report.
2.6 | Plan Review | Establish a continuing program for re-evaluating the policies established by the Land Use Plan Element |  |  | Ongoing | Ongoing
3. Housing
3.1 | Address housing needs | Continue compliance with any affordable housing obligations. |  |  | Ongoing | Ongoing Mid-Point Review Attached
4. Open Space/Recreation
4.1 | Open Space Plan & Update ROSI | Continually prioritize high value open space lands for acquisition. Implement the Open Space Plan Element of the Township Master Plan that identifies parcels for potential acquisition. | Ocean County and DEP- Green Acres |  | Ongoing as acquisitions are made or when plans change. | Ongoing as acquisitions are made or when plans change.
4.2 | Pedestrian Linkages | Design, obtain funding and construct the trail network and pedestrian linkages with assistance provided by Environmental Commission. | DOT, County |  | Ongoing | Ongoing 2019 Bicycle-Pedestrian Tech Memo Attached.
4.3 | Open Space Linkages | Create linkages between open space and recreation sites. | DEP |  | Ongoing | Ongoing
6. Transportation and Circulation
6.1 | The Circulation Element of the Master Plan should be updated. | The Township shall propose a detailed circulation strategy that describes circulation patterns and justifies how these proposals would help enhance mobility without negatively impacting bicyclists and pedestrians. The updated Circulation Element should include a clear statement that recognizes the role of state roads for conveying through rather than local traffic. The plan should provide access to local businesses on local roads. The statement should acknowledge that the State does not have the funds to widen Route 9 in the foreseeable future and that Toms River has investigated alternative roadway connections to lessen the traffic congestion on Route 9. More details are needed. It is also important that the plan integrates existing bus and shuttle services to address capacity issues. | DOT, NJ Transit & OPA | Ciculation Element | 1 year | Adopted in 2017. Bicycle Pedestrian Tech Memo completed in 2019.
6.2 | Any new infill development/redevelopment that occurs along existing linear highway corridors should be concentrated as much as possible to connect to existing uses and promote walking and biking among uses. | In collaboration with the appropriate traffic engineering staff, improve mobility and connectivity by incorporating and connecting infrastructure such as sidewalks, bump-outs, on-street parking, bike lanes, trails, paths and refuge islands; and reduce the negative impact of linear corridor features such as multiple driveways, excessive pedestrian crossing distances, light poles or wayfinding sign poles in the center of sidewalks, and elimination of green strips between sidewalk and curb at bus stop locations. | DOT & NJTransit |  | 2-5 years | 2017 Master Plan Land Use Element identified vacant land along Hooper Avenue Corridor for investigation for Area In Need of Redevelopment to link Esplanade Office Park with Seacourt Pavilion and to reinforce Ocean County Mall. Redevelopment Plan provides opportunities for multimodal linkages.
6.3 | Continue to work with NJ Transit and DOT to improve Bus service along route 9. | Develop an implementable plan to improve Bus service along Route 9. | NJTransit & DOT |  | 2-5 years | 2-5 years
6.35 | Transit Village | Explore eligibility and suitability of Transit Village designation through a preapplication meeting. | DOT & NJTransit |  | 2-5 years | 2-5 years
6.5 | TOD Development | Develop and utilize best TOD and center-based design strategies where appropriate. | DOT & NJTransit |  | 2-5 years | Adopted Downtown Phase 1 Waterfront Redevelopment Plan that emphasizes TOD.
6.45 | Access Management | Continue to work with NJTPA, NJ DOT and Lakewood to address access management planning along Route 9 and other state highways. | DOT in conjunction with NJTPA's Route 9 corridor study |  | 2-5 years | 2-5 years
6.5 | Goods movement | As part of the Circulation Plan update, incorporate a strategy for dealing with retail, commercial or truck freight traffic along state, county and municipal roadways as it relates to existing and future land use patterns. | DOT in conjunction with NJTPA's Route 9 corridor study |  | 1.5 years | Circulation Element adopted in 2017.
6.6 | Transportation Demand Management (TDM) | As part of the Circulation Plan update, incorporate a strategy to utilize transportation demand management (TDM) measures for trip reduction where applicable, such as ridesharing, vanpooling, transit and park-and-rides. | NJTPA, Greater Mercer TMA, NJTransit and DOT in conjunction with NJTPA's Route 9 corridor study. |  | 1.5 years | Downtown Phase 1 Waterfront Redevelopment Plan requires TDM Plan for every project.
8. Economic Development
8.4 | Implement Redevelopment Plans | Maximize the net capture of visitors to State, County and local open space areas. | DEP , BAC, EDA |  | Ongoing | Three redevelopment plans (attached) have been adopted. Another has been completed and is under review by Council.
8.45 | Tourism | Maximize the net capture of visitors to State, County and local open space areas. | DEP |  | Ongoing | Three redevelopment plans emphasize water and bus transportation, restaurant & entertainment. Hidden History Trail project is being implemented to foster cultural heritage tourism (see attached final report).
8.5 | Financial Assistance | Apply for public and private community development grants. | EDA, OPA, NPP, HUD, CDBG and DOT, DCA |  | Ongoing | Grants obtained from FHWA, NJDEP, NJDOT and Ocean County Tourism in past two years.
8.7 | Farmers Market | Promote the creation of a Farmers Market to promote the Jersey Fresh brand in the Regional Center. | Dept of Ag |  | 1 year | TR Business Improvement District (TRBID) operates a downtown farmers market every Weds.
9. Creating a Sense of Place
9.1 | Strengthen Regional Center Identity | Build upon Toms River’s economic and cultural identity to establish a destination for Ocean County and Monmouth Counties. | DOT, DEP and OPA |  | 5 years | Joint efforts by the Township and TRBID have resulted in a new artisan distillery, microbrewery and theater company opening in downtown in past two years.
9.2 | Streetscape Design | Develop a streetscape design, which includes signage to identify the Center. | DOT, Ocean County and OPA |  | 2 years | Applied for TAP grants for Main Street streetscape in 2018 and 2020.
9.3 | Destination Guide | Publish an easy to use destination guide that lists events and places of interest to market the Regional Center. | Ocean County |  | 2 years, ongoing | Hidden History Trail joint venture of TRBID and Township Historic Preservation Commission to be launched in 2021 (attached brochure.
9.4 | Educational Programs | Encourage educational programs for conservation of lands, historic resources, community facilities and local businesses. | SHPO |  | Ongoing | See Hidden History Trail
10. Map Amendments
10.1 | Add appropriate Overlay Zones to Zoning Ordinance/Map. | The municipality's zoning ordinance should be updated to include CES overlays for critical habitat as identified in the SPPM. | OPA | Updated zoning ordinance | Ongoing
10.2 | Habitat Suitability Determination | A Habitat Suitability Determination shall be prepared pursuant to N.J.A.C. 7:15-4.6 for project area with identified habitat Rank 3, 4, or 5. | DEP | Submit Habitat Suitability Determination to DEP | Ongoing