## Sheet1
Brick Township - Planning and Implementation Agreement (DRAFT) | [5 empty] | 2007-03-28 | Monitoring
June 8, 2007 (revised from April 11, 2007) |  |  |  |  | 2007-06-20
NOTE: Wholly new or deleted items identified under Topic column in brackets and capital letters [THUS]; other additions indicated in boldface and underlined thus; other deletions indicated in brackets [thus].
Topic | # | Subtopic | Activity (local action unless otherwise indicated) | State/County Assistance | Timetable (MM/DD/YY) |  | Status Notes | Complete?
General | A1 | CAFRA Center Boundary, revised planning area boundaries | Township to submit drafts of all new and revised planning documents required by this PIA to OSG and DEP. | OSG, DEP | 20 days prior to adoption by township
General | A2 | Plan Endorsement review | By [May 21, 2009] June 20, 2009 and biennially thereafter, the Township shall submit a report to OSG and the public concerning the terms of this PIA and related efforts pursuant to NJAC 5:85-7.12(c). |  | [May 21, 2009] June 20, 2009 and ongoing
General | A3 | Inter-governmental coordination | Coordinate with planning efforts of adjoining municipalities, the County and State and regional planning efforts particularly concerning: regional planning, transportation, economic development, tourism, natural resource protection and open space and recreation. | County Planning Board, OSG, DOT, DEP | Ongoing
General | A4 | Revised Plan Endorsement Process | Once the new Plan Endorsement process is in place, the Township will have the option to work with state agencies to outline an action plan and timetable to attain the new standard for the benefit of additional state assistance. This action plan may be merged with this PIA, due to overlapping activities. | OSG and other state agencies | 90 days afrer new rules and guidelines are adopted
Land Use & Zoning | B1 | Master Plan update | Update and adopt new Land Use Element so that it is consistent with the revised Center and Planning Area boundaries and related State Plan criteria. The Master Plan shall also provide the basis for ordinances that have been discussed in draft form during the Plan Endorsement process. | OSG | [7/21/2007] Adopted as of 6/6/07
Land Use & Zoning | B2 | General zoning update | Manage growth within Town Center and other appropriate areas through zoning, density controls, and ensuring consistency with the existing sewer service areas. | DEP and OSG | Ongoing
Land Use & Zoning | B3 | Interim zoning update | The Township will revise any zoning and redevelopment plans for areas outside the Center and Suburban Planning Area to prohibit uses and development that would adversely affect the environmentally sensitive features in those areas. This will include rezoning any property currently held under Green Acres restrictions as conservation parcels to reduce possibility of encroachment of these areas by adjacent uses. | DEP and OSG | [7/21/2007] 7/10/07
Land Use & Zoning | B4 | Regulations | Ordinances for zoning, resource protection, and site plan and subdivision review revisions shall provide for the implementation of appropriate environs protection measures. | DEP and OSG | [7/21/2007] 7/10/07
Housing | C1 | Affordable housing | The Township shall revise its Housing Element & Fair Share Plan as necessary pending any rule changes. | COAH | 180 days after resolution of COAH third round rules
Housing | C2 | Affordable housing | Ensure appropriate levels of affordable housing, accessible to basic public and retail services, through implementation of Housing Plan. | COAH | Ongoing
Open Space & Recreation | D1 | Open Space & Recreation Plan update | Produce open space & recreation element for Master Plan update to ensure provision of accessible regional- and neighborhood-level open space and recreation facilities to serve existing population and new growth. The plan must identify and examine open space and recreation resources important to the municipality, and map out an implementation strategy to protect, manage and improve them. | DEP | [2/21/2008] 3/20/08
Open Space & Recreation | D2 | Open Space | Continue to preserve and acquire open space parcels through open space trust funds and Green Acres Program. | DEP and Ocean County | Ongoing
Environmental Resources | E1 | Habitat Conservation | Finalize and adopt habitat protection ordinance. | DEP | [7/21/2007] 7/10/07
Environmental Resources | E2 | Water Conservation Plan | Prepare and implement Water Conservation Plan to: • reduce water consumption levels • reduce the loss and waste of water • improve efficiency in the use of water • increase recycling and reuse in the water supply • extend the life of current water supplies by reducing the rate of growth in demand | DEP, BTMUA | [5/21/2009] 6/20/09
Environmental Resources | E3 | Stream Corridor Protection | Finalize and adopt riparian buffer ordinance. | DEP | [7/21/2007] 8/20/07
Transportation & Circulation | F1 | Circulation Plan Update | Update circulation plan to incorporate concepts and standards from DOT's Mobility and Community Form guidelines. | DOT* | [2/21/2008] 3/20/08
Transportation & Circulation | F10 | Access Management | Partner with NJ DOT to create an Access Management Plan along the Route 70 Corridor. The Township will incorporate any necessary changes to the Township's Zoning Ordinance so that it is in conformance with the Highway Access Code for lands adjacent to Routes 35, 70 and 88. The Township will also conditionally approve subdivision and site plans based on consistency with the requirements of the Highway Access Code. The Township will also undertake a capacity analysis that addresses traffic generation under build-out scenarios for current zoning and proposed redevelopment. | DOT* in conjunction in Route 70 study | [7/21/2007] 8/20/07
Transportation & Circulation | F11 | Safe Routes to Schools | Depending on funding, create a comprehensive plan to provide pedestrian linkages between schools and residential neighborhoods through the Safe Routes to School program. (Note: The Township currently has an application filed with the Safe Routes to School Program for the 2007 funding cycle) | DOT* prioritized consideration | Conditional
Transportation & Circulation | F12 | Bus Transit | Create and/or improve bus stop facilities, particularly on Routes 70 and 88. Coordinate transit improvements with land use planning activities (e.g. infill, redevelopment, pedestrian access). | NJ TRANSIT (pending availability of resources), DOT* | Ongoing
Transportation & Circulation | F2 | Circulation Plan Implementation | Improve problem areas that are identified through the reexamination of the Circulation Plan | DOT* | Ongoing
Transportation & Circulation | F3 | Circulation Plan Implementation | Coordinate with State, County and adjacent municipalities to better synchronize signals at inter-jurisdictional intersections. | DOT*, Ocean County, neighboring municipalities | Ongoing
Environmental Resources | F4 | Steep Slopes | Produce a steep slope ordinance in areas of coastal bluffs | DEP | [5/21/2008] 6/20/08
Transportation & Circulation | F4 | Circulation Plan Implementation | Implement short-term improvements on state right-of-ways according to DOT Traffic Engineering guidelines. | DOT to review and, if proposals are appropriate, allow Township to make short-term improvements | [5/21/2009] 6/20/09
Transportation & Circulation | F5 | Integrated Transportation - Land Use | Implement strategies identified in the Route 70 Corridor Study to alleviate traffic congestion, reduce accident rates, improve traffic calming, and support mixed-use commercial development. | DOT* | [5/21/2010] 6/20/10
Transportation & Circulation | F6 | Pedestrian / Bicycling | Increase pedestrian and bicycle connectivity between parks, open space, schools, residential neighborhoods and commercial centers. | DOT* | Ongoing
Transportation & Circulation | F7 | Strategic improvements | Implement roadway and intersection improvements on Routes 35, 70 and 88 in conjunction with G1, G3. Certain improvements shall meet DOT Traffic Engineering guidelines as part of the scoping process for any new projects. | DOT* | [5/21/2010] 6/20/10
Transportation & Circulation | F8 | Goods movement | As part of Circulation Plan update, incorporate a strategy for dealing with retail, commercial or truck freight traffic along state, county and municipal roadways as it relates to existing and future land use patterns. | DOT* in conjunction in Route 70 study | [2/21/2008] 3/20/08
Transportation & Circulation | F9 | Transportation Demand Management (TDM) | As part of Circulation Plan update, incorporate a strategy to utilize transportation demand management (TDM) measures for trip reduction where applicable, such as ridesharing, vanpooling, transit and park-and-rides. | DOT* in conjunction in Route 70 study | [2/21/2008] 3/20/08
Infrastructure | G1 | Wastewater Management Plan | Update Wastewater Management Plan annually to ensure sewer service area is consistent with designated growth areas. | DEP, Ocean County | Annual
Infrastructure | G2 | Wastewater Management Plan | Submit to Ocean County and DEP an amended Wastewater Management Plan for Northern Ocean County that accommodates new development and redevelopment within the limits of the Center and Planning Area 2 and removes lands that are outside these areas from the sewer service area limits, unless already served by existing sewer connections or have a documented pre-existing sanitary health problem due to on-site wastewater disposal. | Ocean County | [7/21/2007] 8/20/07
Infrastructure | G4 | Wastewater Management Plan |  | DEP review and action on the amended Wastewater Management Plan | 6 months after County submits to DEP
Urban Design / Sense of Place | H1 | Revitalization | Identify other areas for application of mixed-use overlay and streetscape ordinances. | OSG | 2007-10-31
Urban Design / Sense of Place | H2 | Revitalization | As any new redevelopment, infill and/or rehabilitation opportunities arise, work with OSG to plan for high-quality design and development consistent with other elements of this PIA. | OSG and interagency teams (DOIT, BRIT) | Ongoing
* When requested, NJDOT will give priority consideration to providing technical assistance consistent with program requirements and subject to the availability of state resources.