## PIA
# | ACTIVITY | LOCAL EFFORT | STATE/COUNTY ASSISTANCE | DELIVERABLE | TIME TABLE
0.1 | Update land use and zoning ordinances to reflect agreed upon changes | Lakewood updates land use and zoning ordinances to reflect uses and intensity of development comensurate with their proposed changes to planning areas, designated centers, nodes and cores. |  |  | Will be completed within 18 months or 1 1/2 years after receiving Conditional Plan Endorsement.
0.2 | Adopt Protection Ordinances | Lakewood SPM after zoning ordinance is adopted • Riparian Corridor Ordinance • Water Conservation Ordinance • Wellhead Protection Ordinance | NJDEP offer guidance |  | Will be addressed after receiving Conditional Plan Endorsement and before SPPM boundary changes and prior to start of CAFRA review period.
0.3 | CAFRA Consistency | Lakewood submit CAFRA Consistency Statement to DEP | NJDEP offer guidance |  | Will be addressed after receiving Conditional Plan Endorsement and before SPPM boundary changes and prior to start of CAFRA review period.
0.4 | WQMP | Work with the County to complete the municipal chapter of the County Plan | NJDEP, Ocean County |  | DEP adopted the Ocean County WQMP with the Lakewood chapter December 2015.
0.5 | Kettle Creek | Lakewood will provide NJDEP with a current list of all municipally-owned parcels which lie outside of the adopted Sewer Service Area mapping within the Kettle Creek watershed , Crystal Lake Preserve area and adjacent to the Metedeconk River or tributaries. The intent of such list is to identify those parcels which will be permanently preserved either by addition by the Township to the Recreation and Open Space Inventory (ROSI) maintained by the NJDEP Green Acres Program or preserved by a mechanism that is agreed to by NJDEP and the Township for mitigative purposes as may be required by a CAFRA permit issued within the Township. Prior to changes to the State Plan Policy Map, such mechanism will be enacted by Township ordinance, establish a date certain by which such preservation is to take place, and shall be binding upon the Township. | NJDEP |  | Will be addressed after receiving Conditional Plan Endorsement and before SPPM boundary changes and prior to start of CAFRA review period.
0.6 | Adopt Zoning Map and Ordinances | Revise the official zoning map and ordinances based on the Smart Growth Plan | OPA |  | Will be completed within 18 months or 1 1/2 years after receiving Conditional Plan Endorsement.
0.7 | OPA updates SPC Map with ammendments from the SPC PE resolution - Centers, Nodes and Planning Area changes | Zoning and protection ordinances adopted by Lakewood | OPA submits map changes to the State Register |  | Shortly after Lakewood updates the Land Use ordinance and Zoning Maps.
0.8 | CAFRA Consistency | Lakewood submit CAFRA Consistency Statement | After SPC resolution adoped, OPA submits map changes to th State Register |  | Within 30 days after Lakewood Updates zoning and OPA updates State Plan Map resolution
0.9 | Water Supply Management Plan | Lakewood Twp. coordinates with Lakewood Township MUA and New Jersey American Water to develop a 10 year plan to ensure adequate water supply, including adequate firm capacity, for existing development and future growth. | NJDEP offer guidance and technical support including a template and designate a single point of contact to assist the Township |  | 1 - 2 years
1. General
1.1 | NJDEP consideration of SPPM changes for use in CAFRA. | Zoning changes and zoning map changes that reflect SPC map changes |  |  | NJDEP will complete review and publish a notice of the review findings within 90 days of the SPPM changes
1.2 | Plan Endorsement biannual review | By a date agreed upon between the SPC and the Township and biannually thereafter and within 6 months after adoption of any new or significant change to the reexamination report, land use ordinance or other planning documents submitted as part of the Plan Endorsement.. Biennially, Lakewood Township shall submit a report to OPA and the public concerning the terms of this PIA and related efforts pursuant to NJAC 5:85-7.12(c). | OPA will provide a template |  | Ongoing
1.3 | Inter-governmental coordination | Coordinate with planning efforts of adjoining municipalities, the County and State and regional planning efforts particularly concerning: regional planning, transportation, economic development, tourism, natural resource protection and open space and recreation. | County Planning Board, OPA, NJDOT, NJDEP, NJTransit |  | Ongoing
1.4 | Center, Node, Core boundary modifications | As part of the biannual review the State Planning Commission agrees to reevaluate boundaries based on implemenation of the PIA. | County Planning Board, OPA, NJDOT, NJDEP, NJTransit |  | Ongoing
2.1 | Master Plan | Review and update Master Plan goals and objectives as directed by the MLUL. The remaining elements need to be updated to reflect the community vision that was conducted as well as the Growth Management Plan and including Center Boundaries, update: C. Circulation D. Housing E. Historic Preservation F. Community Facilities G. Utilities H. Economic Development I. Conservation of Open Space |  |  | Reexamination as required by the M.L.U.L.
0 | General Zoning | The Township will revise any zoning and redevelopment plans for areas outside the Center and Suburban Planning Area to prohibit uses and development that would adversely affect the environmentally sensitive features in those areas. | DEP and OPA |  | 6 months
2.2 | Impact Fees | Implement provisions of the Unified Development Ordinance to promote Township affordable housing goals and the use of impact fees for authorized development by the Township Committee. |  |  | 6 months
2.3 | Historic Preservation Element | While laudable efforts have protected the Strand Theater and Georgian Court, the Township lacks a comprehensive framework to protect the stock of historic buildings particularly in downtown. It is recommended that the Township incorporate into its Master Plan an Historic Preservation Element. | OPA and NJDEP as appropriate |  | 2 -3 years
2.4 | Community Facilities | Continue to review the needs of community facilities to determine the need for replacement or additions including, but not limited to: schools, fire substations, police station, highway department and recreational facilities. | OPA and NJDEP |  | 2-3 years
2.5 | Educational Programs | Encourage educational programs for conservation of lands, historic resources, community facilities and local businesses. | County |  | Ongoing
2.6 | Plan Review | Establish a continuing program for re-evaluating the policies established by the Land Use Plan Element |  |  | Ongoing
3. Housing
3.1 | Projected Need for Affordable Housing | In light of the Township's rapid growth and development, and the concerns mentioned during public review of the SGP, Lakewood will ensure that they adhere to the Fair Housing Act. | Courts as well as Local, County, State, Federal government if applicable. |  | Ongoing, To be reported in the biennial review
3.2 | Rehabilitation | Consider partnering with Ocean County to utilize resources like tax abatement and CDBG funding to rehabilitate the aging housing stock. | Ocean County |  | 2-3 years
3.3 | Housing Mixture | Identify opportunities to create diverse housing mixture and affordable housing in the centers. | HMFA as well as Local, County, State, Federal government as applicable. |  | Ongoing
3.4 | Housing - Affordable Housing Sites | Ensure that any new sites identified for affordable housing be free of environmental constraints that would render them not developable as described in the amended Draft Housing Element and Fair Share Plan and applicable regulations. | Courts as well as Local, County, State, Federal government as applicable. |  | Ongoing
3.5 | Ensure compliance with the affirmative marketing requirements of N.J.A.C. 5:80-26.1 et seq. | There were a number of public comments made during the public comment period of the SGP that not all affordable housing was marketed fairly. The biannual report should address steps being taken to ensure that it is. | Courts as well as Local, County, State, Federal government if applicable. | Report in the biannual review | Ongoing
4. Open Space/Recreation
4.1 | Open Space Plan & Update ROSI | Continually prioritize high value open space lands for acquisition. Implement the Open Space Plan Element of the Township Master Plan that identifies parcels for potential acquisition. | Ocean County and NJDEP-Green Acres |  | Ongoing as acquisitions are made or when plans change.
4.2 | Pedestrian Linkages | Design, obtain funding and construct the trail network and pedestrian linkages with assistance provided by Environmental Commission. | NJDOT, County |  | 1-5 years
4.3 | Open Space Linkages | Create linkages between open space and recreation sites. | NJDEP |  | 2 years
4.4 | Non-contiguous Cluster Ordinance | Create and implement a Non-contiguous Cluster Ordinance that will preserve land in Lakewood. | OPA and NJDEP |  | 1.5 years
5.1 | Natural Resource Inventory | Update the Natural Resource Inventory that was produced during Plan Endorsement with assistance provided by the Environmental Commission. | NJDEP |  | Ongoing as acquisitions are made and new environmental data is available.
5.2 | Stream Corridor Protection Plan | Create and implement a Stream Corridor Protection Plan to protect waterways located within the Township. | NJDEP |  | 2-5 years
6. Transportation and Circulation
6.11 | Update the Circulation Element of the Master Plan | The Township shall propose a detailed circulation strategy that describes circulation patterns and justifies how these proposals would help enhance mobility without negatively impacting pedestrians. The updated Circulation Element should include a clear statement that recognizes the role of state roads for conveying through rather than local traffic. The plan should provide access to local businesses on local roads. The statement should acknowledge that the State does not have the funds to widen Route 9 in the foreseeable future and that Lakewood has investigated alternative north-south roadways to lessen the traffic congestion on Route 9. More details are needed. It is also important that the plan integrates existing bus and shuttle services to address capacity issues. | NJDOT, NJTransit & OPA | Circulation Element | 1 year
6.15 | Implement the Parking Study funded through the OPA Smart Growth Grant | Ensure that opportunities for growth do not impede the ability to construct and to effectively address parking. Utilize best TOD and center-based design strategies. | NJDOT, NJTransit |  | 2-5 years
6.2 | Work with NJDOT (and NJT where service is involved) to specifically, adopt a Complete Streets policy that recognizes pedestrian and their needs to access transit, jobs, and neighborhoods. The complete streets approach begins with an understanding that land use and transportation are integral to one another and planning needs to operate with that understanding. | As circulation plans are developed follow NJ DOT’s policy to enable safe access and mobility of pedestrians, bicyclists, transit users of all ages and abilities, in addition to motorists that should be developed with context-sensitivity and a firm understanding that Land Use and Circulation planning are integrated with the other.; specifically, adopt a Complete Streets policy. | NJDOT, NJTransit |  | Lakewood adopted a Complete Streets policy on October 17, 2013
6.25 | Work with NJT to implement appropriate Express Bus service along Route 9. | Develop an implementable plan to improve Express Bus service along Route 9. | NJTransit |  | 2-5 years
6.3 | TOD Development | Develop and utilize best TOD and center-based design strategies where appropriate. | NJDOT, NJTransit |  | 2-5 years
6.4 | Access Management | Continue to work with NJTPA, NJ DOT and Toms River to address access management planning along Route 9 and other state highways. | DOT in conjunction with NJTPA's Route 9 corridor study |  | 2-5 years
6.5 | Goods movement | As part of the Circulation Plan update, incorporate a strategy for dealing with retail, commercial or truck freight traffic along state, county and municipal roadways as it relates to existing and future land use patterns. | NJDOT in conjunction with NJTPA's Route 9 corridor study |  | 1.5 years
6.6 | Transportation Demand Management (TDM) | As part of the Circulation Plan update, incorporate a strategy to utilize transportation demand management (TDM) measures for trip reduction where applicable, such as ridesharing, vanpooling, transit and park-and-rides | NJTPA, Greater Mercer TMA, NJTransit and NJDOT in conjunction with NJTPA's Route 9 corridor study |  | 1.5 years
6.7 | Transportation - Route 9 right of way | The Township will implement land use controls consistent with the desirable typical section (DTS) for Route 9 in the Access Code. The Township's HD zoning along Route 9 south of downtown provides for setbacks to help preserve a right of way for future Route 9 widening. However, based on field observation, there appears to be significant development close to the highway. The Township shall provide copies of variances and other provisions that have allowed for encroaching development. | OPA and NJDOT |  | 1 year
6.8 | Airport Activities | Prepare a discussion in the Land Use Element of the Master Plan that describes appropriate land uses adjacent to the airport. The role the airport plays should also be discussed in the Circulation Element. Market the airport for greater economic development in the Township. | NJDOT |  | 1 year
6.9 | Mass Transit Improvements | Remain actively engaged with NJ Transit & Ocean County to explore mass transit options. | NJTransit & Ocean County |  | 2-5 years
6.1 | Lakewood TID | Implement the TID | Lakewood, NJDOT |  | Ongoing
7. Infrastructure
7.1 | Stormwater Management Plan | The Township will adopt a stormwater management ordinance and implement its stormwater management program in accordance with NJDEP regulations. | NJDEP and Ocean County |  | 1 year
7.2 | Wellhead Protection Plan | Create and implement a Wellhead Protection Plan to protect water supply wells. | NJDEP |  | 2 years
8. Economic Development
8.1 | Urban Enterprise Zone | Continue to actively promote the UEZ programs (employment, financial, public safety). | NJDCA |  | Ongoing
8.2 | Business Retention/ Expansion |  | NJEDA |  | Ongoing
8.3 | Revolving Loan Fund | Ensure that the evolving loan fund is promoting small business development with assistance provided by the Chamber of Commerce. | NJEDA |  | Ongoing
8.4 | Tourism | Maximize the net capture of visitors to State, County and local open space areas. | NJDEP, NJTourism |  | Ongoing
8.5 | Financial Assistance | Apply for public and private community development grants | NJEDA, OPA, NPP, HUD, CDBG, NJDCA, and NJDOT |  | Ongoing
8.6 | Entertainment/retail/restaurant | Identify further retail opportunities adjacent to the BlueClaws stadium. | OPA, County |  | 1 year
8.7 | Farmers Market | Promote the creation of a Farmers Market to promote the Jersey Fresh brand in the Regional Center. | NJDOA |  | 1 year
9. Creating a Sense of Place
9.1 | Strengthen Regional Center Identity | Build upon Lakewood’s economic and cultural identity to establish a destination for Ocean County and Monmouth Counties. | NJDOT, NJDEP andOPA |  | 5 years
9.2 | Streetscape Design | Develop a streetscape design, which includes signage to identify the Center. | NJDOT, Ocean County and OPA |  | 2 years
9.3 | Destination Guide | Publish an easy to use destination guide that lists events and places of interest to market the Regional Center | Ocean County |  | 2 years, ongoing
9.4 | Educational Programs | Encourage educational programs for conservation of lands, historic resources, community facilities and local businesses. | NJ DEP -SHPO |  | Ongoing
9.5 | Transit Station | Examine land uses around the proposed rail station and propose transit-oriented development. | NJTransit—NJDOT, Transit Village Initiative, OPA |  | 2-5 years
Additions to PIA for MLUL, Resiliency and Environmental Justcice
C1 | Climate Resilience Planning | Lakewood should review its existing data, maps, HMP Annex and assessments and compile any additional data into an assessment and strategy to satisfy the requirements for the Community Change Related Hazard Vulernalaility Assessment (CCRHVA) in the MLUL per NJDEP. Expand on the local annex to the county HMP to include climate impacts for temperature, precipitation, flooding, heat island, and vulnerability of public and private potable wells, pump stations and wasterwater treatment. o Identify and document any utility sites, facilities, equipment, conveyance piping, overhead utility lines, etc. that may be vulnerable to climate impacts or other environmental hazards. • Confirm the condition and capacity of these utility sites, facilities, equipment, etc. • DEP strongly advises against new utility development in areas identified as vulnerable to natural hazards in current and projected condition. Findings from the CCRHVA should guide strategies and actions to increase resilience and reduce risk moving forward. | Ocean County, OPA, NJDEP, SJ, | Develop, adopt, and implement a Climate Change-Related Hazard Vulnerability Assessment (CCRHVA) that meets the requirements of the MLUL per P.L.2021, c.6. | 1-4 years
C2 | Climate Resilience Planning | Lakewoid should update its ordinance to be consistent with the Department’s riverine model code coordinated Flood Damage 20 Prevention Ordinance. For guidance please review the riverine model ordinance at https://www.nj.gov/dep/floodcontrol/modelord.htm and FEMA guidance at https://www.fema.gov/floodplain-management/manage-risk/local. Date of Flood Loss ordinance? ( Ecode360) NJDEP updated the model ordinance in December 2020 to be compliant with NFIP. The model coastal ordinance provided by NJDEP can be found at https://www.nj.gov/dep/floodcontrol/modelord.htm The DEP is available to provide assistance to Bedminster Note: The DEP provides guidance based on current rules for municipal FHA ordinance updates (see above). The Department of Environmental Protection (Department) is proposing amendments to the rules governing Stormwater Management (SWM), N.J.A.C. 7:8, and the Flood Hazard Area Control Act (FHACA) Rules, N.J.A.C. 7:13. and is available for review at https://www.nj.gov/dep/rules/notices/20221205b.html | NJDEP | Review and update the Flood Damage Protection Ordinance with the current NJ Riverine Model Ordinance (revised 2020) at https://www.nj.gov/dep/floodcontrol/modelord.htm in order to stay compliant with NFIP. | 1-3 years
C3 | Climate Resilience Planning | Check HMP or ask NJOEM for the Township’s # of Repetitive Loss and Severe Repetitive Loss properties, # NFIP properties; # claims, etc. (ex. 132 NFIP policies with 101 losses (including 36 Ida losses) during participation). Map these | NJDEP, OEM, FEMA | Review the Blue Acres Program and determine if it is a feasible option for [owners of] Repetitive Loss properties that have not been mitigated, and/or are in flood hazard areas. | Ongoing
D1 | Land Use | Review plans and ordinances and remove impediments to, and encourage, green design throughout the communtiy. Make necessary modifications to ensure that innovative and sustainable construction alternatives and materials (such as green roofs) are permitted. Consider approving incentives for using innovative roofing alternatives and materials. Sustainable Jersey points and support | OPA, NJDEP technical assistance |  | 1-3 years
D2 | Land Use | Review and update Master Plan and all associated elements to consider climate resiliency and socially vulnerable populations. Sustainable Jersey points and support. Address MLUL requirements. | NJDEP, Sustainable NJ, OPA | Review and update Master Plan | 1-3 years after CCRHVA
D3 | Land Use | The municipality shall enhance its zoning regulations and building codes to encourage building outside of the flood zone and to minimize construction in flood prone areas to reconstruction of existing buildings. Flood zone area new construction or redevelopment of existing buildings should avoid high density concentration and areas of severe flooding. Placement of critical facilities and utilities in flood zones should be avoided whenever possible. Affordable housing should be sited to avoid flood zone and hazardous areas. Flood damage prevention ordinance date? The municipality needs to follow all regulations set forth by the NJDEP with regards to flood hazard area regulation, wetlands, etc. It does not site or recommend siting any affordable housing projects within a flood zone or a hazardous area. | NJDEP (Bureau of Climate Resilience Planning) |  | 1-3 years After CCRHVA
D6 | Land Use | The municipality's zoning ordinance should be updated to include overlays that address stormwater management, aquifer recharge, steep slopes, 100 year and 500 year flood zones and critical habitat and habitat corridors. This includes a CES overlay for structures in the 100 year and 500 year flood zone and environmentally sensitive areas (ESA). | NJ DEP, OPA | Add appropriate Overlay Zones to Zoning Ordinance/Map. | After CCRHVA
D8 | Land Use | Reconcile and update Area in Need of Redevelopment and Area in Need of Rehabilitation Data | NJDCA, OPA | Ensure that data is maintained and accurate | Ongoing
E1 | Sustainability | Develop green building and sustainable design guidelines for new development - consider requiring “green buildings” (LEED, Green Globes) in redevelopment areas, to the extent practicable. | SJ, OPA |  | Ongoing
E2 | Sustainability | Streamline zoning code and permiting requirements to encourage solar and geothermal. Sustainable Jersey points and support | NJDEP, NJBPU, SJ |  | 1-2 year
F1 | Conservation | Tree Protection Ordinance , Tree Risk Assessment Plan as needed. Consider NJUCG accreditation | NJDEP - Bureau of Sustainability; NJDEP Parks and Forestry; NJ Forest Fire Service; Sustainable Jersey |  | 2-3 years
F2 | Conservation | Adopt a wellhead protection ordinance in addition to the Environmentally Critical Area protection with specifics to protect water quality and public health. Compare to Woolwich (https://ecode360.com/14140851) or Haddonfield (https://ecode360.com/10200060). Also, NJDEP Urban and Community Forestry guidelines are here: https://www.state.nj.us/dep/parksandforests/forest/community/Information_for_Municipalities.html | NJDEP | Adopt a wellhead protection ordinance | 2-3 years
F3 | Conservation | Develop and adopt a Water Conservation Ordinance that is mutually agreeable to the Township and DEP | NJDEP | Develop and adopt a Water Conservation Ordinance | 2-3 years
F6 | Conservation | Review and update as necessary the Natural Resource Inventory, including climate change observations and concerns as they are relevant. DEP can assist with identifying what to update. | NJDEP | Review and update as necessary the Natural Resource Inventory | 1-3 years After CCRHVA
F7 | Conservation | Review and update as necessary the inventory of contaminated sites, identify if any of these Known Contaminated Sites (KCS) are within the proposed center and/or are vulnerable to climate change. Incorporate findings from the CCRHVA, and CES overlays as appropriate. | NJDEP | Update the natural resources inventory documents to account for any changes since the last inventory as well as climate change considerations. | 1-3 years After CCRHVA
F8 | Conservation | Adopt a streem corridor/Riparian Zone protection ordinance Review and update with climate impact considerations, findings from the CCRHVA, and CES overlays as appropriate. The Township follows the mapping and inventory provided by the NJDEP. This activity could be undertaken as a component of the ERI task above | NJDEP | Adopt or update a streem corridor/Riparian Zone protection ordinance | 1-3 years After CCRHVA
F9 | Conservation | Update ROSI Pay particular attention to the C1 waters in the Township. Review and update with climate impact considerations, findings from the CCRHVA, and CES overlays as appropriate. | Ocean County, NJDEP | Update ROSI | Within 4 years
F10 | Conservation | Contine to work with County to provide and expand corridors of open space and natural features to protect historic structures, support habitat connectivity and adapt to changing climate condition | Ocean County, NJDEP Green Acres | https://dep.nj.gov/otpla/rosi/ | ongoing
GI | Transportation & Circulation | Incorporate Complete and Green Streets policy and Implementation Plan into the Circulation Element of the Master Plan All new transportation projects that impact any Right-of-Way made within Lakewood will be consistent with this plan and the adopted Complete Streets Policy. | NJDOT, NJ TPA, Ocean County | Provide update during biennial review | 2-3 years
G5 | Transportation & Circulation | Explore ways to manage goods movement in the community and incorporate into future Master Plan updates. | NJDOT, NJ TPA, Ocean County | Samples provided Township will seek funding to implement Safe Streets plan Complete and Green Streets updates to master plan, development regulations | When updating Master Plan
I1 | Energy | Develop a community Green House Gas (GHG) Reduction Action Plan, including GHG reduction targets. GHG reduction actions should be incorporated into land use element of master plan. 1) Conduct Local Government Energy Audit (LGEA) of municipal facilities and operations, at a minimum, and community-wide audits, if feasible, and 2) using the results of these audits, develop action plans for reducing municipal energy consumption and GHG emissions - use NJ’s 2020 GHG emissions reduction target as a goal | Bd of Public Utilities (BPU) Clean Energy Program provides funding for municipal energy audits: (http://www.njcleanenergy.com/commercial-industrial/programs/local-government-energy-audit/local-government-energy-audit NJDOT can offer guidance | Develop a community Green House Gas (GHG) Reduction Action Plan | Timeline as provided PE guidelines (2 years with phasing)
I2 | Energy | Energy Tracking & Management - establish energy use baselines, tracking, mgt & reporting systems | NJTPA prepared a greenhouse gas (GHG) inventory. (insert appropriate link here XXX) https://www.sjtpo.org/Documents/AirQuality/GreenhouseGasInventoryReport.pdf This inventory provides county and municipal-level GHG emissions information for various major community sectors/activities (e.g., residential, transportation, waste generation) (See Appendix A pages 1-4). XXX can acquire its local inventory data and use it as a baseline Sustainable Jersey points and support | Energy Tracking & Management | Year 1
I3 | Energy | Implement energy efficiency Measure for facilities | Sustainable Jersey points and support https://www.sustainablejersey.com/actions/#open/action/482 | Report in biennial report | 2 years and phased
I4 | Energy | Greening the municipal fleet: • Fleet Inventory and target for green fleet conversion. | Sustainable Jersey points and support | Report in biennial report | must do year 1
I5 | Energy | Greening the municipal fleet: • purchase electric vehicles to achieve 20% reduction in fuel use w/in 4 years . | NJBPU, NJDEP, SJ possible $$ | Report in biennial report | must initiate by yr. 2 (can be multi-year)
I6 | Energy | Greening the municipal fleet: * Trip optimization software * Proper vehicle maintenance * Driver training *purchase electric vehicles to achieve 20% reduction in fuel use w/in 4 years . | NJBPU, NJDEP, SJ possible $$ | Report in biennial report | recommended
I7 | Energy | Renewable Energy Generation: *Onsite Solar or *Geothermal system or *buy electric from a renewable source or *community solar project or *Renewable Energy Aggregation | NJBPU, NJDEP, SJ possible $$ | Report in biennial report | must do 3 within 4 years
I8 | Energy | • Public EV charging infrastructure feasibility and supporting ordinances | NJBPU, NJDEP, SJ possible $$ | Sustainable Jersey points and support | 1-2 years
I9 | Energy | Make your town EV Friendly (choose 3) *update zoning ordinances to require pre-wiring for EV chargers as part of a redevelopment plan or for a specific zone(1-2 yrs.); *Adopt a PEV ordinance to include regulation and design standards for EVSE, EV parking spaces and design guidelines for installation of EVSE (1-2 yrs.); * Training for local officials and require local first responders to participate in education on PE and EVSE(1-2 yrs.); *Incentivize EV ready by reducing or waiving permit fees and providing recognition for businesses/entities that do it (2-3 yrs.); *Commitment from 3 or more partners for workplace or multi-family chargers (2-5 yrs.). | BPU, DEP, SJ possible $$ | Township adopts EV ordinance. (Endorsed communities must do at least 3 | 3 years
J1 | Infrastructure | Review and update as necessary Utilities Element of the Master Plan. Confirm the condition and capacity of the stormwater drainage system and water supply. Incorporate climate change implications. | NJDEP Sustainable Jersey points and support | Update Utilities Element of the Master Plan | 1-3 years after CCRHVA
J5 | Infrastructure/ Utilities | Evaluate and update regularly the Stormwater Management Plan and Ordinance for consistency with the current Stormwater Management Rules. Be sure to submit MS-4 Permit reports each May. | NJDEP and Ocean County technical assistance | Evaluate and update regularly the Stormwater Management Plan and Ordinance | 1-2 years
M1 | Planning | Update the Community Facilities Plan | Technical assistance | Updates to the Stormwater Mgmt Plan and Ordinance | 3 years
N1 | Environmental Justice | Follow the requirements of EO23 pursuant to NJDEP guidelines to review, identify, and update documents as necessary. | NJDEP | Monitor for changes in municipality that may warrant more environmental justice actions in the future. | Ongoing
Note on A33: Barry Ableman:
Note on C52: Swords, Andrew: Last sentence - unclear what the purpose is, and what the resulting action would be. Any action needed by NJDOT?

## Color explanation
Completed | 11
Completed and continuing | 16
On going | 29 | 56 | Items | On original PIA
New, Resiliency and Environmental Justice | 32