## Full PIA
Township of Beverly Plan & Implementation Agreement
# | Topic | Req (*) | Activity | Local Effort | Assistance | Time Frame | Comments
A1 | Administrative | * | One year from endorsement and biennially thereafter, report to the SPC about the status of your planning efforts, ordinance adoption and other accomplishments form the PIA. | Planning Board and governing body | OPA | Continuous, see comments. | First year = Annual Report then Biennial Reports for the next 8 years on PIA action status..
A2 | Administrative | * | After adoption, the municipality shall submit any new or modified land use ordinance or other planning documents to OPA. | Planning Board and governing body | Technical assistance | Include in biennial report.
B1 | Public Info & Community Engagement |  | Begin participating in the Sustainable Jersey program by engaging a Green Team and recruitiung capable volunteer residents and others to support actions committed to by the municipality. | Governing body, Green Team | OPA, SJ | ongoing | Is community currently registered with Sustainable Jersey? Certified? (check report for list of actions completed. ) Many PE actions could be undertaken by a Green Team and gain significant points for Bronze or even Silver certification and maybe even a Gold Star. If no Green Team, could an environemtnal Commission or equiveleant serve?
B2 | Public Info & Community Engagement |  | Many actions would benefit from public engagement including education about issues, resident assistance with actions, participation in decision making and support for a path to resiliency and sustainability. An early action should be a public forum(s) designed to recruit short and long-term public engagement, sharing information/goals, highlighting opportunities for participation, volunteerism and meaningful involvement in community planning and decision making. | Governing body, Planning Board, Green Team, chamber (s), churches, schools, other local and regional organizations as partners/invitees. | OPA, DEP, local groups & regional NGOs/universities | Year 1 and periodically thereafter to update/engage residents on progress on key issues. | Forum(s) should be designed with a well developed outreach element to ensure equitable inclusion and meaningful turn out and facilitated to maximize results.
B3 | Public Info & Community Engagement |  | Consider uploading municipal codes to Ecode360 or equivalent searchable online storage system | Governing Body with Clerk |  |  | Access to ordinances creates a better informed and engaged citizenry and assists professionals and volunteers when working for the city.
C1 | Climate Resilience Planning | * | Develop, adopt, and implement a climate change-related hazard vulnerability assessment (CCRHVA) that meets the requirements of the MLUL per P.L.2021, c.6. | All municipal hands should be engaged. | BCBC, OPA, DVRPC, DEP, SJ | 1-4 years | Municipality should review its existing data, maps, HMP Annex and assessments and compile any additional data into an assessment and strategy to satisfy the requirements for the CCRHVA in the MLUL per NJDEP. Expand on the local annex to the county HMP to include climate impacts for temperature, precipitation, flooding, heat island, and vulnerability of public and private potable wells, pump stations and wasterwater treatment. o Identify and document any utility sites, facilities, equipment, conveyance piping, overhead utility lines, etc. that may be vulnerable to climate impacts or other environmental hazards. o Confirm the condition and capacity of these utility sites, facilities, equipment, etc. o DEP strongly advises against new utility development in areas identified as vulnerable to natural hazards in current and projected condition. Findings from the CCRHVA should guide strategies and actions to increase resilience and reduce risk moving forward.
C2 | Climate Resilience Planning | * | Review and update the Flood Damage Protection Ordinance with the current NJ Model Ordinance (revised 2020) at in order to stay compliant with NFIP. | Planning Board and governing Body | DEP | 1-4, contingent on DEP assistance | Date of Flood Loss ordinance? ( Ecode360) NJDEP updated the model ordinance in December 2020 to be compliant with NFIP. The model ordinance provided by NJDEP can be found at https://www.nj.gov/dep/floodcontrol/modelord.htm
C3 | Climate Resilience Planning |  | Review the Blue Acres Program and see if it might be an option for the Non-mitigated repetitive loss properties in the community. | Governing Body | DEP, OEM, FEMA |  | Check HMP for # Repetitive loss properties and Severe Repetitive Loss property, # NFIP properties; # claimes etc.
D1 | Land Use | * | Review plans and ordinances and remove impediments to, and encourage, green design throughout the communtiy. Make necessary modifications to ensure that innovative and sustainable construction alternatives and materials (such as green roofs) are permitted. Consider approving incentives for using innovative roofing alternatives and materials. | Planning Board and governing Body | OPA, NJDEP technical assistance | 1-3 years | Sustainable Jersey points and support
D2 | Land Use | * | Review and update Master Plan and all associated elements to consider climate resiliency and socially vulnerable populations. | Planning Board and governing Body | DEP, Sustainable NJ, BCBC | 1-4 years after CCRHVA | Sustainable Jersey points and support. Address MLUL requirements, address vulnerabilities and build on strategies identified in CCRHVA
D3 | Land Use | * | The municipality shall enhance its zoning regulations and building codes to encourage building outside of the flood zone and to minimize construction in flood prone areas to reconstruction of existing buildings. Flood zone area new construction or redevelopment of existing buildings should avoid high density concentration and areas of severe flooding. Placement of critical facilities and utilities in flood zones should be avoided whenever possible. Affordable housing should be sited to avoid flood zone and hazardous areas. | Planning Board | DEP (Bureau of Climate Resilience Planning) | 1-3 years After CCRHVA (years 3-6) | The municipality follows all regulations set forth by the NJDEP with regards to flood hazard area regulation, wetlands, etc. It does not site or recommend siting any affordable housing projects within a flood zone or a hazardous area.
D4 | Land Use |  | Consider adopting an Accessory Dwelling Unit (ADU) Ordinance in residential zones | Planning Board | OPA/SJ
D5 | Land Use |  | Update the Open Space & Recreation Plan (OSRP). Explore open space and recreation opportunities with the State and County. Explore purchases of additional properties for active recreation, preservation and flood protection. | Work with County | Green Acres Funding and County as applicable. | 1-3 years after CCRHVA | Petitioner will work closely with Green Acres, local advisory committee, County, County Improvement Authority and property owners to negotiate the purchase of properties to be permanent open space. Expand corridors of open space a natural features to support habitat connectivity and adaptation to changing conditions.
D6 | Land Use | * | Add appropriate Overlay Zones to Zoning Ordinance/Map. | Planning Board | County | Ongoing. Up to 6 years after Plan Endorsement | The municipality's zoning ordinance should be updated to include overlays that address stormwater management, aquifer recharge, steep slopes, 100 year and 500 year flood zones and critical habitat and habitat corridors. This includes a CES overlay for structures in the 100 year and 500 year flood zone and environmentally sensitive areas (ESA).
D8 | Land Use |  | Develop a Vacant Land Inventory and identify any unoccupied structures that would lend themselves to affordable housing. | Governing body, planning board | DCA, OPA, DEP
D9 | Land Use | * | Adopt a Housing Plan/Element If not in place | Govering Body/Land use Board |  | 3-6 years
D10 | Land Use |  | It is recommended that municipality consider going to the courts for a fair Share Housing Judgement of Compliance and Repose. | Governing Body/Land Use Board
E1 | Energy | * | Public EV charging infrastructure feasibility and supporting ordinances | Planning Board, Governing Body & Green Team | BPU, DEP, SJ possible $$ | 1-2 years | Sustainable Jersey points and support
E2 | Energy |  | Make your town EV Friendly (choose 3) *update zoning ordinances to require pre-wiring for EV chargers as part of a redevelopment plan or for a specific zone(1-2 yrs.); *Adopt a PEV ordinance to include regulation and design standards for EVSE, EV parking spaces and design guidelines for installation of EVSE (1-2 yrs.); * Training for local officials and require local first responders to participate in education on PE and EVSE(1-2 yrs.); *Incentivize EV ready by reducing or waiving permit fees and providing recognition for businesses/entities that do it (2-3 yrs.); *Commitment from 3 or more partners for workplace or multi-family chargers (2-5 yrs.). | Planning Board, Governing Body & Green Team | BPU, DEP, SJ possible $$ | (Endorsed communities must do at least 3.) | Sustainable Jersey points and support
E3 | Energy | * | Develop a community GHG Reduction Action Plan, including GHG reduction targets. GHG reduction actions should be incorporated into land use element of master plan. 1) Conduct Local Government Energy Audit (LGEA) of municipal facilities and operations, at a minimum, and community-wide audits, if feasible, and 2) using the results of these audits, develop action plans for reducing municipal energy consumption and GHG emissions - use NJ’s 2020 GHG emissions reduction target as a goal | Planning Board, Governing Body & Green Team | Bd of Public Utilities (BPU) Clean Energy Program provides funding for municipal energy audits: (http://www.njcleanenergy.com/commercial-industrial/programs/local-government-energy-audit/local-government-energy-audit | Timeline as provided PE guidelines (2 years with phasing) | see DVRPC report
E4 | Energy | * | Energy Tracking & Management - establish energy use baselines, tracking, mgt & reporting systems | Govering Body |  | Year 1 | https://www.sustainablejersey.com/actions/#open/action/482
E5 | Energy | * | Greening the municipal fleet: • Fleet Inventory and target for green fleet conversion. | Govering Body | Sustainable Jersey points and support | must do within 3 years
E6 | Energy | * | Renewable Energy Generation: *Onsite Solar or *Geothermal system or *buy electric from a renewable source or *community solar project or *Renewable Energy Aggregation | Govering Body | BPU, DEP, SJ possible $$ | 1-3 items within 6 years | Sustainable Jersey points and support
E7 | Energy |  | Implement energy efficiency measure for facilities | Govering Body | BPU, DEP, SJ possible $$ |  | Sustainable Jersey points and support
E8 | Energy |  | Greening the municipal fleet: * Trip optimization software * Proper vehicle maintenance * Driver training *purchase electric vehicles to achieve 20% reduction in fuel use w/in 4 years . | Govering Body | BPU, DEP, SJ possible $$ | recommended | Sustainable Jersey points and support
E9 | Energy |  | Greening the municipal fleet: • purchase electric vehicles to achieve 20% reduction in fuel use w/in 4 years . | Govering Body | BPU, DEP, SJ possible $$ | must initiate by yr. 2 (can be multi-year) | Sustainable Jersey points and support
E10 | Energy |  | Municipality should investigate State grant opportunities for the installation of publicly accessible electrive vehicle charging stations in the downtown area. | Governing Body & Green Team, (if applicable) | BPU, DEP, SJ
F1 | Conservation | * | Tree Protection Ordinance , Tree Risk Assessment Plan as needed. Consider NJUCG accreditation | Planning Board, Governing Body & Green Team | DEP - Bureau of Sustainability; NJDEP Parks and Forestry; NJ Forest Fire Service; Sustainable Jersey | 2-3 years | Compare to Woolwich (https://ecode360.com/14140851) or Haddonfield (https://ecode360.com/10200060). Also, NJDEP Urban and Community Forestry guidelines are here: https://www.state.nj.us/dep/parksandforests/forest/community/Information_for_Municipalities.html
F2 | Conservation | * | Adopt a wellhead protection ordinance in addition to the Environmentally Critical Area protection with specifics to protect water quality and public health. | Planning Board, Governing Body & Green Team | DEP | 2-3 years | Sample provided
F3 | Conservation | * | Develop and adopt a Water Conservation Ordinance that is mutually agreeable to the Township and DEP | Planning Board, Governing Body & Green Team | DEP | 2-3 years | Sample provided
F5 | Conservation | * | Review and update as necessary the Natural Resource Inventory, including climate change observations and concerns as they are relevant. DEP can assist with identifying what to update. | Planning Board, Governing Body & Green Team | DEP, County | 3-5 years after CCRHVA | Incorporate findings from the CCRHVA, and CES overlays as appropriate.
F6 | Conservation | * | Review and update as necessary the inventory of contaminated sites, identify if any of these Known Contaminated Sites (KCS) are within the proposed center and/or are vulnerable to climate change. | Planning Board, Governing Body & Green Team |  | 1-3 years After CCRHVA | Review and update with climate impact considerations, findings from the CCRHVA, and CES overlays as appropriate. The Township follows the mapping and inventory provided by the NJDEP.
GI | Transportation & Circulation | * | Adopt/Incorporate Complete and Green Streets policy and Implementation Plan into the Circulation Element of the Master Plan. | Planning Board, Governing Body & Green Team | NJDOT, SJ, SJTPO | 3-6 years | Samples provided
G2 | Transportation & Circulation | * | Create/Update the Circulation Element of Master Plan to address opportunities for shared parking, goods movement, improvements to bicycle and pedestrian access and transit, along with continued growth in the community. In particular, reduce congestion and ensure that non-vehicular transportation is encouraged. | Planning Board, Governing Body & Green Team | NJDOT, SJTPO | 3-6 years | Municipality agrees to work on the Circulation Element.
I1 | Infrastructure | * | Review and update as necessary Utilities Element of the Master Plan. Confirm the condition and capacity of the stormwater drainage system and water supply. Incorporate climate change implications. | Governing Body, Planning Board, Municipal utilities authority | NJ American Water, County, DEP, American Rescue Plan | 1-3 years after CCRHVA | New utility lines and associated infrastructure should be planned to avoid flood prone areas and existing utility infrastructure currently in or projected to be flood prone in the future should be addressed.
I2 | Infrastructure | * | Confirm that the County has submitted a WMP with a local Chapter and a new FWSA map pursuant to 7:15-4.2 (c) | County with municipal | NJDEP
I3 | Infrastructure | * | Evaluate and update regularly the Stormwater Management Plan and Ordinance for consistency with the current Stormwater Management Rules. Be sure to submit MS-4 Permit reports each May. | Engineer, Governing Body and Planning Board | DEP and County | Ongoing
I4 | Infrastructure |  | Adopt an Impervious Surface Reduction Ordinance. Incorporate expected increases in precipitation and temperature related to adverse impacts of climate change into an impervious surface reduction ordinance. Include measures to manage stormwater on-site rather than as runoff ; Future redevelopment projects shall incorporate means to minimize and/or reduce new and/or existing impervious surfaces. | Governing body | NJDEP
I5 | Infrastructure/ Utilities | * | Initiate conversations with the county about a regional wastewater plant out o f the flood zone | Governing Body, Planning Board, Municipal utilities authority | NJDEP
J1 | Sustainability |  | Develop green building and sustainable design guidelines for new development - consider requiring “green buildings” (LEED, Green Globes) in redevelopment areas, to the extent practicable. | Planning Board, Governing Body & Green Team | SJ, OPA |  | Sustainable Jersey points and support
J2 | Sustainability | * | Streamline zoning code and permiting requirements to encourage solar, wind and geothermal. | Planning Board, Governing Body & Green Team | DEP, BPU, SJ | 3-6 years | Tied to Land Use Element update. Sustainable Jersey points and support
J4 | Sustainability |  | Review recycling code to ensure consistency. |  | SJ, OPA, County
K1 | Economic Development |  | Prepare an economic sustainability plan working regionally as appropriate. |  | County, OPA, DVRPC, DEP, SJ
L1 | Historic Resources | * | Create/update Historic Preservation Inventory. Historic structures should be protected with enhanced stormwater management plans and flood minimization plans. | Governing Body | SHPO, County | Report on progress in biennial review | Review the NJ Historical Commission’s (NJ Department of State) grant program at http://www.nj.gov/state/divisions/historical/grants. Work with SHPO to develop planning documents some guidance is provided at : https://www.nj.gov/dep/hpo/images/_MULT_DG_32_v2_ID14078r.pdf
M1 | Planning | * | Update the Community Facilities Plan | Planning Board | Technical assistance | 3 years
N1 | Environmental Justice | * | Follow the requirements of EO23 pursuant to NJDEP guidelines to review, identify, and update documents as necessary |  | NJDEP | 1-3 years after provision of guidance | Monitor for changes in municipality that may warrant more environmental justice actions in the future.