## required v recommended
# | * Req | ID | Time Frame | PIA Template DRAFT 9-6-22* | Plan | Ordinance | Element | Other
1 | * | A1 | Ongoing | Municipality will forward new or modifies land use ordinances and/or planning documents to OPA |  |  |  | x
2 | * | A2 | Yr 1 then 2nd, 4th, 6th & 8th yr. | Municipality sends 1 annual then biannual status reports |  |  |  | x
3 | * | C1 | 1-3 years | Climate Change-Related Hazard Vulnerability Assessment (CCRHVA) | x
4 | * | C2 | Per DEP assistance TBD | Flood Damage Protection Ordinance |  | x
5 | * | D1 | 1-3 years | Review/modify plans and ordinances to encourage green design |  | x
6 | * | D2 | 1-3 years after CCRHVA | Review/update Master Plan and associated elements for climate resiliency |  |  |  | x
7 | * | D3 | 1-3 years After CCRHVA | Enhance zoning regulations and building codes for flood zones. |  | x
8 | * | D6 | 1-2 years after PE | Add Overlay Zone(s) to Zoning Ordinance/Map |  | x
9 | * | D7 | 1-3 years | Establish affordable housing obligation/plan/spending plan as needed
10 | * | E1 | 1-2 years | Public EV charging infrastructure feasibility and supporting ordinaces |  | x
11 | * | E2 | 1-2 yers | Make your town EV friendly Ordinance (required by state) |  | x
12 | * | E3 | 3 years with phasing | GHG Reduction Action Plan | x
13 | * | E4 | 1-2 years | Develop energy tracking baseline |  |  |  | x
14 | * | E5 | Within 3 years | Fleet Inventory and target for greening municipal fleet |  |  |  | x
15 | * | E6 | 1-3 within 6 years | Renewable energy generation (onsite solar or geothermal, electric from renewable resources, community solar or renewable energy aggregation). |  |  |  | x
16 | * | F2 | 2-3 years | Wellhead Protection Ordinance |  | x
17 | * | F3 | 2-3 years | Water Conservation Ordinance |  | x
18 | * | F4 | 1-4 years | Conservation/Habitat Conservation element |  |  | x
19 | * | F5 | 3-5 years After CCRHVA | Environmental Resource Inventory ERI (esp climate change considerations) |  |  | x
20 | * | F6 | 1-3 years After CCRHVA | Cross-check Known Contaminated Sites (KCS) against climate vulnerabililty |  |  |  | x
21 | * | F7 | 2-3 years | Stream Corridor/Riparian Zone Ordinance |  | x
22 | * | G1 | 2-3 years | Complete & Green Streets Policy |  | x
23 | * | G2 | W/in 3 years of CCRHVA | Update Circulation Element of Master Plan with climate vulnerability data |  |  | x
24 | * | I1 | 1-3 years after CCRHVA | Review Utilities Element of the Master Plan esp for climate vulnerability |  |  | x
25 | * | J2 | 1-2 year | Ordinance encouraging /allowing solar, wind & geothermal |  | x
26 | * | M1 | 1-3 years after CCRHVA | Community Facilities Plan element esp considering climate vulnerabilities |  |  | x
27 | * | M2 | Report in biennial | Develop 5 yr Capital Improvement Plan (per MLUL)
28 | * | M3 | Conditional | Farmland Preservation Element |  |  | x
29 | * | K1 | Conditional | Historic Preservation inventory |  |  |  | x
30 | * | N1 | 1-3 years | Implement the EJ requirements of EO23 + review/update documents |  |  |  | x
* 1 year after Endorsement and on a 2 yr cycle thereafter, send OPA a status of these actions and when ordinances/plans are adopted, copy them to OPA.
31 |  | B1 | Public Info & Engagement | Use resources/framework of SJ |  |  |  | x
32 |  | B2 | Public Info & Engagement | Annual or semiannual communtiy forum |  |  |  | x
33 |  | C3 | Climate Resilience Planning | Consider Blue Acres |  |  |  | x
34 |  | C4 | Climate Resilience Planning | Consider CRS program |  |  |  | x
35 |  | D4 | Land Use | Accessory Dwelling Unit (ADU) Ordinance |  | x
36 |  | D5 | Land Use | Update OSRP for access to Green Acres/BC Open Space grants. |  |  | x
37 |  | D8 | Land Use | Vacant Land Inventory |  |  |  | x
38 |  | E7 | Energy | Implement energy efficiency measures for facilities |  |  |  | x
39 |  | E8 | Energy | Trip optimization; vehicle maintanecE; Driver training; and/or purchase ev's |  |  |  | x
40 |  | F1 | 1-3 years | Tree Protection Ordinance/Tree Risk Assessment Plan |  | x
41 |  | G3 | Transportaion | Implement expansinon of bike/ped network |  |  |  | x
42 |  | H1 | Transit | Improve transit options |  |  |  | x
43 |  | I2 | Infrastructure | Submit local chapter with County WMP as required |  |  |  | x
44 |  | I3 | Infrastructure | Regularly update Stormwater SPPP and submit MS-4 Permit Report |  |  |  | x
45 |  | I4 | Infrastructure | Aqdopt an Impervious Surface Reduction Ordinance |  | x
46 |  | I5 | Infrastructure | Initiate conversations with the County about regional wastewater plant |  |  |  | x
47 |  | I6 | Infrastructure | Discuss permit options for drainageway, maintenance/emergency repairs |  |  |  | x
48 |  | J1 | Energy & Sustainability | Green building and sustainable design guidelines |  | x
49 |  | J3 | Energy & Sustainability | Green Building & Sustainability Element |  |  | x
50 |  | J4 | Energy & Sustainability | Statement of consistency & Recycling Ordinance |  | x
51 |  | K1 | Economic Development | Develop Sustainable Economic Development Plan/Coordinate regionally | x
52 |  | L2 | Historic Resources | Prepare Historic Resources element |  |  |  | x

## 1 page summary
in | * Req | ID | Time Frame | PIA Template DRAFT 11-28-22* | Plan | Ordinance | Element | Other
1 | * | A1 | Ongoing | Municipality will forward new or modifies land use ordinances and/or planning documents to OPA |  |  |  | x
2 | * | A2 | Yr 1 then 2nd, 4th, 6th & 8th yr. | Municipality sends 1 annual then biannual status reports |  |  |  | x
3 |  | B1 | Public Info & Engagement | Use resources/framework of SJ |  |  |  | x
4 |  | B2 | Public Info & Engagement | Annual or semiannual communtiy forum |  |  |  | x
5 | * | C1 | 1-3 years | Climate Change-Related Hazard Vulnerability Assessment (CCRHVA) | x
6 | * | C2 | Per DEP assistance TBD | Flood Damage Protection Ordinance |  | x
7 |  | C3 | Climate Resilience Planning | Consider Blue Acres
8 |  | C4 | Climate Resilience Planning | Consider CRS program
9 | * | D1 | 1-3 years | Review/modify plans and ordinances to encourage green design |  | x
10 | * | D2 | 1-3 years after CCRHVA | Review/update Master Plan and associated elements for climate resiliency |  |  |  | x
11 | * | D3 | 1-3 years After CCRHVA | Enhance zoning regulations and building codes for flood zones. |  | x
12 |  | D4 | Land Use | Accessory Dwelling Unit (ADU) Ordinance |  | x
13 |  | D5 | Land Use | Update OSRP for access to Green Acres/BC Open Space grants. |  |  | x
14 | * | D6 | 1-2 years after PE | Add Overlay Zone(s) to Zoning Ordinance/Map (1% Flood/ESA 25) |  | x
15 | * | D7 | 1-3 years | Establish affordable housing obligation/plan/spending plan as needed
16 |  | D8 | Land Use | Vacant Land Inventory |  |  |  | x
17 | * | E1 | 1-2 years | Public EV charging infrastructure feasibility and supporting ordinaces |  | x
18 | * | E2 | 1-2 yers | Make your town EV friendly Ordinance (required by state) |  | x
19 | * | E3 | 3 years with phasing | GHG Reduction Action Plan | x
20 | * | E4 | 1-2 years | Develop energy tracking baseline |  |  |  | x
21 | * | E5 | Within 3 years | Fleet Inventory and target for greening municipal fleet |  |  |  | x
22 | * | E6 | 1-3 within 6 years | Renewable energy generation (onsite solar or geothermal, electric from renewable resources, community solar or renewable energy aggregation). |  |  |  | x
23 |  | E7 | Energy | Implement energy efficiency measures for facilities
24 |  | E8 | Energy | Trip optimization; vehicle maintanecE; Driver training; and/or purchase ev's
25 |  | F1 | 1-3 years | Tree Protection Ordinance/Tree Risk Assessment Plan |  | x
26 | * | F2 | 2-3 years | Wellhead Protection Ordinance |  | x
27 | * | F3 | 2-3 years | Water Conservation Ordinance |  | x
28 | * | F4 | 1-4 years | Conservation/Habitat Conservation element |  |  | x
29 | * | F5 | 1-3 years After CCRHVA | Environmental Resource Inventory ERI (esp climate change considerations) |  |  | x
30 | * | F6 | 1-3 years After CCRHVA | Cross-check Known Contaminated Sites (KCS) against climate vulnerabililty |  |  |  | x
31 | * | F7 | 1-3 years | Stream Corridor/Riparian Zone Ordinance |  | x
32 | * | G1 | 2-3 years | Complete & Green Streets Policy |  | x
33 | * | G2 | W/in 3 years of CCRHVA | Update Circulation Element with climate vulnerability data |  |  | x
34 |  | G3 | Transportation | Implement expansion of bike/ped network |  |  |  | x
35 |  | H1 | Transit | Improve transit options
36 | * | I1 | 1-3 years after CCRHVA | Review Utilities Element of the Master Plan esp for climate vulnerabilty |  |  | x
37 |  | I2 | Infrastructure | Submit local chapter with County WMP as required
38 |  | I3 | Infrastructure | Regularly update Stormwater SPPP and submit MS-4 Permit Report
39 |  | I4 | Infrastructure | Adopt an Impervious Surface Reduction Ordinance |  | x
40 |  | I5 | Infrastructure | Initiate conversations with the County about regional wastewater plant
41 |  | I6 | Infrastructure | Discuss permit options for drainageway, maintenance/emergency repairs
42 |  | J1 | Sustainability | Green building and sustainable design guidelines |  | x
43 | * | J2 | 1-2 year | Ordinance encouraging /allowing solar, wind & geothermal |  | x
44 |  | J3 | Sustainability | Green Building & Sustainability Element |  |  | x
45 |  | J4 | Sustainability | Statement of consistency & Recycling Ordinance
46 |  | K1 | Economic Development | Develop Sustainable Economic Development Plan/Coordinate regionally
47 |  | L1 | Historic Resources | Prepare Historic Resources element |  |  |  | x
48 | * | L2 | Conditional | Historic Preservation inventory |  |  |  | x
49 | * | M1 | 1-3 years after CCRHVA | Community Facilities Plan element esp considering climate vulnerabilities |  |  | x
50 | * | M2 | Report in biennial | Develop 5 yr Capital Improvement Plan (per MLUL)
51 | * | M3 | Conditional | Farmland Preservation Element |  |  | x
52 | * | N1 | 1-3 years | Implement the EJ requirements of EO23 + review/update doicuments |  |  |  | x
* 1 year after Endorsement and on a 2 yr cycle thereafter, send OPA a status of these actions and when ordinances/plans are adopted, copy them to OPA.

## Full Detail
Bedminster Draft PIA 5/1/2023
# | Topic | Req (*) | Activity | Local Effort | Assistance | Time Frame | Comments
A1 | Administrative | * | After SPC adopts resolution granting PE: OPA sends certified resolution to NJ State Register, updates GIS layer, sends fully signed documents to petitioner and posts signed and certified documents on OPA website. |  | OPA | ASAP Upon completion of all resolutions
A2 | Administrative | * | One year from endorsement and biennially thereafter, report to the SPC about the status of your planning efforts, ordinance adoption and other accomplishments form the PIA. | Planning Board and governing body | OPA | 1st Due XXXX; then so on | First year = Annual Report then Biennial Reports for the next 8 years on PIA action status..
A3 | Administrative | * | After adoption, the municipality shall submit any new or modified land use ordinances or other planning documents. | Planning Board and governing body | Technical assistance | Include in biennial report.
B1 | Public Info & Community Engagement |  | Continue participating in the Sustainable Jersey (SJ) program by engaging a Green Team and recruitiung capable volunteer residents and others to support actions committed to by the municipality. | Governing body, Green Team | OPA, SJ | ongoing | Bedminster received Bronze certification in 2015, but should continue to be engaged with SJ
B2 | Public Info & Community Engagement |  | Many actions would benefit from public engagement including education about issues, resident assistance with actions, participation in decision making and support for a path to resiliency and sustainability. An early action should be a public forum(s) designed to recruit short and long-term public engagement, sharing information/goals, highlighting opportunities for participation, volunteerism and meaningful involvement in community planning and decision making. | Governing body, Planning Board, Green Team, chamber(s), churches, schools, other local and regional organizations as partners/ invitees. | OPA, DEP, local groups & regional NGOs/universities | Year 1 and periodically thereafter to update/engage residents on progress on key issues. | Forum(s) should be designed with a well developed outreach element to ensure equitable inclusion and meaningful turn out and facilitated to maximize results.
C1 | Climate Resilience Planning | * | Develop, adopt, and implement a Climate Change-Related Hazard Vulnerability Assessment (CCRHVA) that meets the requirements of the MLUL per P.L.2021, c.6. | All municipal hands should be engaged. | Somerset County, OPA, DEP, SJ, | 1-4 years | Bedminster should review its existing data, maps, HMP Annex and assessments and compile any additional data into an assessment and strategy to satisfy the requirements for the Community Change Related Hazard Vulernalaility Assessment (CCRHVA) in the MLUL per NJDEP. Expand on the local annex to the county HMP to include climate impacts for temperature, precipitation, flooding, heat island, and vulnerability of public and private potable wells, pump stations and wasterwater treatment. o Identify and document any utility sites, facilities, equipment, conveyance piping, overhead utility lines, etc. that may be vulnerable to climate impacts or other environmental hazards. o Confirm the condition and capacity of these utility sites, facilities, equipment, etc. o DEP strongly advises against new utility development in areas identified as vulnerable to natural hazards in current and projected condition. Findings from the CCRHVA should guide strategies and actions to increase resilience and reduce risk moving forward. The Highlands Council is currently developing guidance materials for municipalities that will assist in completion of CCRHVA's and in incorporation of climate resiliency planning into munipal master plans. The Council will provide grant funding for these initiatives. Contact the Highlands Council by phone at 908-879-6737 or email at highlands@highlands.nj.gov. Website: www.nj.gov/njhighlands.
C2 | Climate Resilience Planning | * | Review and update the Flood Damage Protection Ordinance with the current NJ Riverine Model Ordinance (revised 2020) at https://www.nj.gov/dep/floodcontrol/modelord.htm in order to stay compliant with NFIP. | Planning Board and governing Body | DEP | 1-3 years | Bedminster should update its ordinance to be consistent with the Department’s riverine model code coordinated Flood Damage 20 Prevention Ordinance. For guidance please review the riverine model ordinance at https://www.nj.gov/dep/floodcontrol/modelord.htm and FEMA guidance at https://www.fema.gov/floodplain-management/manage-risk/local. Date of Flood Loss ordinance? ( Ecode360) NJDEP updated the model ordinance in December 2020 to be compliant with NFIP. The model coastal ordinance provided by NJDEP can be found at https://www.nj.gov/dep/floodcontrol/modelord.htm The DEP is available to provide assistance to Bedminster Note: The DEP provides guidance based on current rules for municipal FHA ordinance updates (see above). The Department of Environmental Protection (Department) is proposing amendments to the rules governing Stormwater Management (SWM), N.J.A.C. 7:8, and the Flood Hazard Area Control Act (FHACA) Rules, N.J.A.C. 7:13. and is available for review at https://www.nj.gov/dep/rules/notices/20221205b.html
C3 | Climate Resilience Planning |  | Review the Blue Acres Program and determine if it is a feasible option for [owners of] Repetitive Loss properties that have not been mitigated, and/or are in flood hazard areas. | Governing Body | DEP, OEM, FEMA |  | Check HMP or ask NJOEM for the Township’s # of Repetitive Loss and Severe Repetitive Loss properties, # NFIP properties; # claims, etc. (ex. 132 NFIP policies with 101 losses (including 36 Ida losses) during participation). Map these
D1 | Land Use | * | Review plans and ordinances and remove impediments to, and encourage, green design throughout the communtiy. Make necessary modifications to ensure that innovative and sustainable construction alternatives and materials (such as green roofs) are permitted. Consider approving incentives for using innovative roofing alternatives and materials. | Planning Board and governing Body | OPA, NJDEP technical assistance | 1-3 years | Sustainable Jersey points and support This activity is eligible for Highlands Council grant funding
D2 | Land Use | * | Review and update Master Plan and all associated elements to consider climate resiliency and socially vulnerable populations. | Planning Board and governing Body | DEP, Sustainable NJ | 1-3 years after CCRHVA | Sustainable Jersey points and support. Address MLUL requirements. This activity is eligible for Highlands Council grant funding.
D3 | Land Use | * | The municipality shall enhance its zoning regulations and building codes to encourage building outside of the flood zone and to minimize construction in flood prone areas to reconstruction of existing buildings. Flood zone area new construction or redevelopment of existing buildings should avoid high density concentration and areas of severe flooding. Placement of critical facilities and utilities in flood zones should be avoided whenever possible. Affordable housing should be sited to avoid flood zone and hazardous areas. | Planning Board | DEP (Bureau of Climate Resilience Planning) | 1-3 years After CCRHVA | Flood damage prevention ordinance date? The municipality needs to follow all regulations set forth by the NJDEP with regards to flood hazard area regulation, wetlands, etc. It does not site or recommend siting any affordable housing projects within a flood zone or a hazardous area. This activity is eligible for Highlands Council grant funding.
D4 | Land Use |  | Consider adopting an Accessory Dwelling Unit (ADU) Ordinance in residential zones | Planning Board | OPA/SJ
D5 | Land Use |  | Update the Open Space & Recreation Plan (OSRP). Explore open space and recreation opportunities with the State and County. Explore purchases of additional properties for active recreation, preservation and flood protection. | Work with County | Green Acres Funding, Highlands Council and County as applicable. | 1-3 years after CCRHVA | Petitioner will work closely with Green Acres, local advisory committee, County, County Improvement Authority, Highlands and property owners to negotiate the purchase of properties to be permanent open space. This activity is eligible for Highlands Council grant funding.
D6 | Land Use | * | Add appropriate Overlay Zones to Zoning Ordinance/Map. | Planning Board |  | After CCRHVA | The municipality's zoning ordinance should be updated to include overlays that address stormwater management, aquifer recharge, steep slopes, 100 year and 500 year flood zones and critical habitat and habitat corridors. This includes a CES overlay for structures in the 100 year and 500 year flood zone and environmentally sensitive areas (ESA). This activity is eligible for Highlands Council grant funding.
D7 | Land Use | * | Establish an affordable housing obligation and plan through a settlement agreement (if warranted), create a spending plan and work to meet it as needed. Be sure to avoid flood hazard areas when siting affordable housing. Also rehabilitation of deteriorated and non-code compliant housing stock. | Governing body, planning board | DCA, OPA | dependant on situation. | DCA can help municipality determine whether they meet the bar for PE - depending on community housing market, demographics, current need etc. This activity is eligible for Highlands Council grant funding.
D8 | Land Use | * | Reconcile and update Area in Need of Redevelopment and Area in Need of Rehabilitation Data | Planning Board | DCA, OPA | Reconcile after PE and update on going | Ensure that data is maintained and accurate
E1 | Sustainability |  | Develop green building and sustainable design guidelines for new development - consider requiring “green buildings” (LEED, Green Globes) in redevelopment areas, to the extent practicable. | Planning Board, Governing Body & Green Team | SJ, OPA |  | Sustainable Jersey points and support This activity is eligible for Highlands Council grant funding.
E2 | Sustainability | * | Streamline zoning code and permiting requirements to encourage solar and geothermal. | Planning Board, Governing Body & Green Team | DEP, BPU, SJ | 1-2 year | Sustainable Jersey points and support This activity is eligible for Highlands Council grant funding.
E3 | Sustainability |  | MLUL encourages municipalities to include a Green Building & Sustainability Element in their master plan to help establish policies and initiatives for achieving sustainability goals. Components include:• Define what sustainability and resilience mean to your community • Statutory basis for a sustainability element and how it relates to other elements of the plan • Document public engagement activities • Summarize existing conditions and trends, including any environmental justice (EJ) concerns and any available baseline assessment like greenhouse gas • Document community’s existing sustainability policies and programs and accomplishments inventories, energy use assessments, or public health inventories • Establish a vision for local sustainability and resilience, expressed in a succinct statement • Establish sustainability and resilience goals and objectives • Develop strategies and actions for achieving sustainability objectives, typically organized by topic area, such as land use, transportation, energy, water, waste, etc. • Establish performance measures and metrics for tracking progress toward objectives • Assign responsible parties for implementation actions • This could be expanded to be a Climate Action Plan if so desired. |  | DEP, Sustainable Jersey |  | Recommended. Report on progress in biennial review The Highlands Council guidance material discussed above under "Resiliency Planning," will include sustainability planning and incorporation of same into municipal master plans. As noted previously, this activity will be eligible for Highlands Council grant funding. See contact info above.
E4 | Sustainability |  | Statement of consistency and recycling ordinance |  | SJ, OPA, Clean Communities |  | (Seeking clarity on what a 'statement of consistency' is…)
F1 | Conservation | * | Tree Protection Ordinance , Tree Risk Assessment Plan as needed. Consider NJUCG accreditation | Planning Board, Governing Body & Green Team | DEP - Bureau of Sustainability; NJDEP Parks and Forestry; NJ Forest Fire Service; Sustainable Jersey | 2-3 years | Compare to Woolwich (https://ecode360.com/14140851) or Haddonfield (https://ecode360.com/10200060). Also, NJDEP Urban and Community Forestry guidelines are here: https://www.state.nj.us/dep/parksandforests/forest/community/Information_for_Municipalities.html
F2 | Conservation | * | Adopt a wellhead protection ordinance in addition to the Environmentally Critical Area protection with specifics to protect water quality and public health. | Planning Board, Governing Body & Green Team | DEP | 2-3 years | sample provided This activity is eligible for Highlands Council grant funding.
F3 | Conservation | * | Develop and adopt a Water Conservation Ordinance that is mutually agreeable to the Township and DEP | Planning Board, Governing Body & Green Team | DEP | 2-3 years | Sample provided This activity is eligible for Highlands Council grant funding.
F4 | Conservation |  | Prepare and adopt a Habitat Conservation Plan and protection measures to maintain habitat. Coordinate with county and surrounding municipalities to expand corridors of open space and natural features to support habitat connectivity. | Planning Board, Governing Body & Green Team | DEP technical assistance and funding | 2-3 years | The Habitat Conservation may potentially be included as part of the Conservation Plan rather than an individual plan. NJDEP Connecting Habitats Across NJ (CHANJ) mapping can be of assistance to identify potential corridors https://www.njfishandwildlife.com/ensp/chanj.htm This activity is eligible for Highlands Council grant funding.
F5 | Conservation |  | Once Habitat Conservation Plan adopted. Consider adding to Master Plan as a Conservation Plan Element | Planning Board, Governing Body & Green Team | DEP technical assistance and funding | After Habittat Conservatiuon Adopted and before Master Plan Reexamination | https://www.njfishandwildlife.com/ensp/chanj.htm This activity is eligible for Highlands Council grant funding.
F6 | Conservation | * | Review and update as necessary the Natural Resource Inventory, including climate change observations and concerns as they are relevant. DEP can assist with identifying what to update. | Planning Board, Governing Body & Green Team | DEP | 1-3 years After CCRHVA | Incorporate findings from the CCRHVA, and CES overlays as appropriate. Update the natural resources inventory documents to account for any changes since the last inventory as well as climate change considerations. The Highlands Council has developed an interactive Environmental Resource Inventory tool that could assist significantly in addressing this task (see: https://www.highlandseri.com/). This activity is eligible for Highlands Council grant funding.
F7 | Conservation | * | Review and update as necessary the inventory of contaminated sites, identify if any of these Known Contaminated Sites (KCS) are within the proposed center and/or are vulnerable to climate change. | Planning Board, Governing Body & Green Team |  | 1-3 years After CCRHVA | Review and update with climate impact considerations, findings from the CCRHVA, and CES overlays as appropriate. The Township follows the mapping and inventory provided by the NJDEP. This activity could be undertaken as a component of the ERI task above and is also eligible for Highlands Council grant funding. S
F8 | Conservation | * | Adopt a streem corridor/Riparian Zone protection ordinance | Planning Board, Governing Body & Green Team |  | 1-3 years After CCRHVA | Pay particular attention to the C1 waters in the Township. Review and update with climate impact considerations, findings from the CCRHVA, and CES overlays as appropriate. This activity is eligible for Highlands Council grant funding.
F9 | Conservation | * | Update ROSI since it is almost 10 years since last updated | Planning Board, Governing Body & Green Team | Somerset County, DEP | Within 4 years from recieiving PE | https://dep.nj.gov/otpla/rosi/
F10 | Conservation | * | Contine to work with County to provide and expand corridors of open space and natural features to protect historic structures, support habitat connectivity and adapt to changing climate condition | Planning Board, Governing Body & Green Team | Somerset County, DEP Green Acres | ongoing | Provide update during biennial review
GI | Transportation & Circulation | * | Incorporate Complete and Green Streets policy and Implementation Plan into the Circulation Element of the Master Plan All new transportation projects that impact any Right-of-Way made within Bedminster will be consistent with this plan and the adopted Complete Streets Policy. | Planning Board, Governing Body & Green Team | NJDOT, NJ TPA, Somerset County | 2-3 years | Samples provided Township will seek funding to implement Safe Streets plan Complete and Green Streets updates to master plan, development regulations, and local government policies are eligible for Highlands Council grant funding.
G3 | Transportation & Circulation |  | Implement expansion of bike/ped network. | Governing Body, Planning Board | NJDOT, NJ TPA, Somerset County |  | This activity is eligible for Highlands Council grant funding.
G4 | Transportation & Circulation |  | Seek coordination of services for commuters to train station | Governing Body, Planning Board | NJ Transit, NJDOT, NJ TPA, SCOOT, Somerset County | ongoing | Bedminster mentioned in MSA
G5 | Transportation & Circulation | * | Explore ways to manage goods movement in the community and incorporate into future Master Plan updates. | Planning Board, Governing Body | NJDOT, NJ TPA, Somerset County | When updating Master Plan | NJDOT can offer guidance
H1 | Highlands |  | Continue speaking with the Highland Planning Council to ensure the Township and the Highlands are working effectively | Governing Body, Planning Board | Highlands Council | ongoing | Recommended. Report on progress in biennial review
H2 | Agriculture |  | Update its 2003 Farmland Preservation Plan and continue its farmland preservation efforts. Incorporate standards and priorities for protection of Important Farmland Soils across the Township. | Governing Body, Planning Board | NJ AG, SADC, Highlands | 1 Year | Recommended. Report on progress in biennial review. This activity is eligible for Highlands Council grant funding.
H3 | Agriculture |  | Develop an Agriculture Retention Plan focused on retaining, supporting the Township agricultural base and promoting it as an important economic and food supply resource - one that may grow more important to the community and the region as climae change takes its toll on agriculture more broadly. | Governing Body, Planning Board | NJ AG, SADC, Highlands | ongoing | This activity is eligible for Highlands Council grant funding.
I1 | Energy | * | Develop a community GHG Reduction Action Plan, including GHG reduction targets. GHG reduction actions should be incorporated into land use element of master plan. 1) Conduct Local Government Energy Audit (LGEA) of municipal facilities and operations, at a minimum, and community-wide audits, if feasible, and 2) using the results of these audits, develop action plans for reducing municipal energy consumption and GHG emissions - use NJ’s 2020 GHG emissions reduction target as a goal | Township Committee & Planning Board | Bd of Public Utilities (BPU) Clean Energy Program provides funding for municipal energy audits: (http://www.njcleanenergy.com/commercial-industrial/programs/local-government-energy-audit/local-government-energy-audit | Timeline as provided PE guidelines (2 years with phasing) | The MPO prepared a greenhouse gas (GHG) inventory. (insert appropriate link here XXX) https://www.sjtpo.org/Documents/AirQuality/GreenhouseGasInventoryReport.pdf This inventory provides county and municipal-level GHG emissions information for various major community sectors/activities (e.g., residential, transportation, waste generation) (See Appendix A pages 1-4). XXX can acquire its local inventory data and use it as a baseline Sustainable Jersey points and support
I2 | Energy | * | Energy Tracking & Management - establish energy use baselines, tracking, mgt & reporting systems | Township Committee |  | Year 1 | https://www.sustainablejersey.com/actions/#open/action/482
I3 | Energy | * | Implement energy efficiency Measure for facilities | Township Committee |  | 2 years and phased | Sustainable Jersey points and support
I4 | Energy |  | Greening the municipal fleet: • Fleet Inventory and target for green fleet conversion. | Township Committee | Sustainable Jersey points and support | must do year 1 | (Community status XXX.)
I5 | Energy | * | Greening the municipal fleet: • purchase electric vehicles to achieve 20% reduction in fuel use w/in 4 years . | Township Committee | BPU, DEP, SJ possible $$ | must initiate by yr. 2 (can be multi-year) | (Community status XXX.)
I6 | Energy |  | Greening the municipal fleet: * Trip optimization software * Proper vehicle maintenance * Driver training *purchase electric vehicles to achieve 20% reduction in fuel use w/in 4 years . | Township Committee | BPU, DEP, SJ possible $$ | recommended | Sustainable Jersey points and support
I7 | Energy | * | Renewable Energy Generation: *Onsite Solar or *Geothermal system or *buy electric from a renewable source or *community solar project or *Renewable Energy Aggregation | Township Committee | BPU, DEP, SJ possible $$ | must do 3 within 4 years | Sustainable Jersey points and support
I8 | Energy | * | • Public EV charging infrastructure feasibility and supporting ordinances | Township Committee & Planning Board | BPU, DEP, SJ possible $$ | 1-2 years | Sustainable Jersey points and support The Township adopted the EV ordinance. Planning for EV infrastructure will be included in the Highlands Council Climate Resiliency Planning guidance; also eligible for Highlands Council grant funding
I9 | Energy |  | Make your town EV Friendly (choose 3) *update zoning ordinances to require pre-wiring for EV chargers as part of a redevelopment plan or for a specific zone(1-2 yrs.); *Adopt a PEV ordinance to include regulation and design standards for EVSE, EV parking spaces and design guidelines for installation of EVSE (1-2 yrs.); * Training for local officials and require local first responders to participate in education on PE and EVSE(1-2 yrs.); *Incentivize EV ready by reducing or waiving permit fees and providing recognition for businesses/entities that do it (2-3 yrs.); *Commitment from 3 or more partners for workplace or multi-family chargers (2-5 yrs.). | Township Committee & Planning Board | BPU, DEP, SJ possible $$ | (Endorsed communities must do at least 3 | Sustainable Jersey points and support The ordinance upates discussed under this activity will be eligible for Highlands Council grant funding in furtherance of resiliency planning efforts.
J1 | Infrastructure | * | Review and update as necessary Utilities Element of the Master Plan. Confirm the condition and capacity of the stormwater drainage system and water supply. Incorporate climate change implications. | Planning Board, NJ American Water. | DEP | 1-3 years after CCRHVA | New utility lines and associated infrastructure should be planned to avoid flood prone areas and existing utility infrastructure currently in or projected to be flood prone in the future should be addressed.
J2 | Infrastructure | * | Confirm that Somerset County has submitted a WMP with a Bedminster Chapter and a new FWSA map pursuant to 7:15-4.2 (c) | Somerset County | NJDEP
J4 | Infrastructure |  | Adopt an Impervious Surface Reduction Ordinance. It is strongly recommended that Bedminster incorporate expected increases in precipitation and temperature related to adverse impacts of climate change into an impervious surface reduction ordinance o Include measures to manage stormwater on-site rather than as runoff o Future redevelopment projects shall incorporate means to minimize and/or reduce new and/or existing impervious surfaces. | Township Committee | NJDEP |  | This activity is eligible for Highlands Council grant funding.
J5 | Infrastructure/ Utilities | * | Evaluate and update regularly the Stormwater Management Plan and Ordinance for consistency with the current Stormwater Management Rules. Be sure to submit MS-4 Permit reports each May. | Engineer, Township Committee and Planning Board | DEP and Somerset County technical assistance | 1-2 years | Updates to the Stormwater Mgmt Plan and Ordinance are eligible for Highlands Council grant funding
K1 | Economic Development |  | Promote Bedminster and Pluckemin Centers though coordinated planning efforts with business and property owners. Develop plans for center-based /walkability improvements in the Town Center and support economic development initiatives including façade and rehabilitation grant program, wayfinding signs, coordinated marketing efforts, etc. |  |  | ongoing | Report in biennial review Sustainable economic development planning is eligible for Highlands Council grant funding.
K2 | Economic Development |  | Apply for EMERGE and any other economic incentive programs to support economic development, particularly for the former AT&T property | Township Committee | NJ EDA | Make applications when appropriate | Report in biennial review
L1 | Historic Resources |  | Develop or Review and update Historic Preservation Ordinance, Inventory and Plan. Historic structures should be protected with enhanced stormwater management plans and flood minimization plans. | Historic Preservation Commission and Township Committee | SHPO, Somerset County | Report on progress in biennial review | (Status of Historic Preservation...) Review the NJ Historical Commission’s (NJ Department of State) grant program at http://www.nj.gov/state/divisions/historical/grants. Work with SHPO to develop planning documents some guidance is provided at : https://www.nj.gov/dep/hpo/images/_MULT_DG_32_v2_ID14078r.pdf Eligible for Highlands Council grant
M1 | Planning | * | Update the Community Facilities Plan | Planning Board | Technical assistance | 3 years
N1 | Environmental Justice | * | Follow the requirements of EO23 pursuant to NJDEP guidelines to review, identify, and update documents as necessary. |  | NJDEP | 1-3 years after provision of guidance | Monitor for changes in municipality that may warrant more environmental justice actions in the future.

## Sheet4
adopt a Flood Mitigation Plan and an All Hazards Mitigation Plan and Flood Ordinance
Bound Brook has not adopted a Wildfire Protection Plan (CWPP) with NJ Forest Fire Service and should update their Community Forest Management Plan and street tree species inventory in the town center and proposed redevelopment areas. Bound Brook should also consider initiating a Community Stewardship Incentive Program.