## INSTRUCTIONS
This Microsoft EXCEL 2007 version of the DPMC-11-2, Monthly Estimate For Payment To Contractor, and DPMC-12a, Unit Schedule Breakdown, will calculate the amounts you need to transfer to the DPMC-11, Invoice form.
First fill in the DPMC-12a, Unit Schedule Breakdown, and submit it to the Design Consultant or Construction Management firm for approval. The line items will automatically transfer to the DPMC-11-2 form in the left hand columns. If your Unit Schedule Breakdown requires more lines, insert rows in the body of the spreadsheet. Add an equal number of lines to the body of the DPMC-11-2 form and copy the formulas to the new lines.
Each month update the Work in Place columns of the DPMC-11-2 form, the retainage percentage (if changed), and the amount previously billed. All other totals will automatically calculate.
Transfer the totals to a DPMC-11 Invoice form, print and sign both forms before submitting them to DPMC for approval and processing.
INFORMATION FOR CONTRACTOR
DPMC-12a
UNIT SCHEDULE BREAKDOWN
USE OF THIS FORM
Use this form only when the billing for work completed will be presented in two or more partial payment invoices exclusive of retainage.
Submit this form for approval at the very outset of the contract. Submit it only once. The DPMC Project Manager must approve this breakdown before you submit any partial payments.
This form shows for each contract a detailed breakdown that will be the basis for the Contractor's entries on the Periodic Estimate for Partial Payment (DPMC-11 and DPMC-11-2) each time a partial payment is invoiced.
PREPARATION
The DPMC Project Manager or the Architect/Engineer/CM can provide assistance or further instructions. The Contractor will prepare the schedule for a lump-sum contract by breaking down the total contract price into units in sufficient detail to correspond with the construction operations. For a unit price contract, the items will correspond to the items stated in the contract. In some cases, it will be permissible to enter certain lump-sum items (such as "landscaping") in which entries will appear only in columns (1), (2), and (9).
Column (1) Item No.: Enter a number for each item, numbering consecutively. In the case of unit price contracts, where the items are already numbered in the contract, enter those numbers in this column.
Column (2) Description of Item: Provide a general description of the individual units or types of work performed and/or materials provided. Do not forget those elements of the General Conditions relevant to this contract (Bond, insurance, supervision, etc).
Column (3) Quantity: Show quantity of work.
Column (4) Unit of Measure: Show usual unit of measure for each item as, cu.yds., bd.ft., tons, etc.
Column (5) Cost per Unit: Show for each item that total in column (9) divided by the number of units in column (3), rounded to the nearest dollar or cent as appropriate.
Column (6) and (7) Material Cost and Labor Cost: Show only Labor and Material costs in these columns. Show such costs separately where this is common practice. If labor and material costs are combined, show total in column (6) and indicate that the figure is a total.
Column (8) Other Cost: Other operating costs including profit, taxes, overhead, bonds, insurance, building permits, small tools and supplies, plant rental or depreciation, contingencies, and similar costs shall be distributed proportionally to some or all of the items listed. Profits need not be shown separately. The ratio of "Other Costs" to "Total Cost of Item" may be determined for a contract and the apportionment of "Other Costs" to each item in the contract made on a percentage basis. In some cases certain other costs such as plant charges may apply only to a few items; it will be proper to distribute such changes only to those items.
Column (9) Total Cost of Item: Show the total of columns (6), (7) and (8).
NOTE: For Columns (6), (7), (8), & (9) do not show cents. Show dollar amounts only dispensing with the decimal and two zeros.
CERTIFICATIONS
The Contractor, the Architect/Engineer or Construction Manager, and the District Supervisor must sign all copies.

## DPMC-11-2
CONTRACTOR: |  |  |  | INVOICE #: |  | INVOICE PERIOD: |  |  | PROJECT #:
ITEM # | ITEM DESCRIPTION |  | CONTRACT TOTALS |  |  |  | COMPLETED THIS PERIOD |  | WORK IN PLACE/COMPLETE
|  |  | QUANTITY | UNIT | UNIT PRICE | AMOUNT | QUANTITY | AMOUNT | QUANTITY | AMOUNT
1 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
2 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
3 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
4 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
5 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
6 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
7 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
8 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
9 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
10 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
11 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
12 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
13 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
14 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
15 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
16 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
17 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
18 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
19 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
20 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
21 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
22 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
23 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
24 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
25 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
26 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
27 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
28 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
29 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
30 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
31 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
32 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
33 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
34 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
35 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
36 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
37 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
38 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
39 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
40 | 0 |  | 0 | 0 | #DIV/0! | 0 |  | #DIV/0! |  | #DIV/0!
TOTALS |  |  |  |  | (1) | 0 | (6) | #DIV/0! | (2) | #DIV/0!
CONTRACTOR CERTIFICATION |  | DESIGN CONSULTANT CERTIFICATION |  |  | PERCENTAGE OF CONSTRUCTION PROGRESS MADE AS OF THIS ESTIMATE: |  |  |  |  | #DIV/0!
As an authorized representative of the Contractor, I certify this Estimate to be correct and just and that payment therefor has not been received. I further certify that the Contractor and all its project subcontractors have complied with the Labor Standards of the contract; that the percentage of construction progress shown above is representative of the as-built conditions; and I also certify that all previous payments made under this contract have been applied by the Contractor to discharge in full all its obligations in connection with work covered by all prior payment estimates as required by N.J.S.A. 2A:44-148. |  | I certify that I have checked the quantities and amounts covered by this Estimate, that such are correct and consistent with all previous computations as actually checked and are wholly consistent with the requirements of the contract; and that the percentage of construction progress as shown is consistent with the as-built conditions.
[7 empty] | (3) AMOUNT RETAINED |  | 10% | #DIV/0!
(4) PREVIOUSLY BILLED
[7 empty] | (5) TOTAL DEDUCTIONS (3) + (4) |  |  | #DIV/0!
[7 empty] | (6) NET PAYMENT DUE THIS PERIOD (2) - (5) |  |  | #DIV/0!
|  | A/E FIRM NAME: __________________________________________________ |  |  |  |  | STATE OF NEW JERSEY USE ONLY
SIGN: ___________________________________________________________ |  | SIGN: ___________________________________________________________ |  |  |  |  | APPROVED FOR PAYMENT: $ _____________________________
TITLE: ___________________________________ DATE: ______________ |  | TITLE: ___________________________________ DATE: ____________ |  |  |  |  | STATE REPRESENTATIVE: _______________________________________ DATE: _____________

## DPMC-12a
NEW JERSEY DEPARTMENT OF TREASURY | [6 empty] | PROJECT #:
DPMC BUREAU OF DESIGN & CONSTRUCTION
SCHEDULE OF AMOUNTS FOR CONTRACT PAYMENTS | [6 empty] | TRADE:
(UNIT SCHEDULE BREAKDOWN)
NAME & ADDRESS OF CONTRACTOR
PROJECT DESCRIPTION
ITEM # | DESCRIPTION OF ITEM | QUANTITY | UNIT OF MEASURE | COST PER UNIT | MATERIALS COST | LABOR COST | OTHER COST | TOTAL COST OF ITEM
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9)
1 |  |  |  | #DIV/0! |  |  |  | 0
2 |  |  |  | #DIV/0! |  |  |  | 0
3 |  |  |  | #DIV/0! |  |  |  | 0
4 |  |  |  | #DIV/0! |  |  |  | 0
5 |  |  |  | #DIV/0! |  |  |  | 0
6 |  |  |  | #DIV/0! |  |  |  | 0
7 |  |  |  | #DIV/0! |  |  |  | 0
8 |  |  |  | #DIV/0! |  |  |  | 0
9 |  |  |  | #DIV/0! |  |  |  | 0
10 |  |  |  | #DIV/0! |  |  |  | 0
11 |  |  |  | #DIV/0! |  |  |  | 0
12 |  |  |  | #DIV/0! |  |  |  | 0
13 |  |  |  | #DIV/0! |  |  |  | 0
14 |  |  |  | #DIV/0! |  |  |  | 0
15 |  |  |  | #DIV/0! |  |  |  | 0
16 |  |  |  | #DIV/0! |  |  |  | 0
17 |  |  |  | #DIV/0! |  |  |  | 0
18 |  |  |  | #DIV/0! |  |  |  | 0
19 |  |  |  | #DIV/0! |  |  |  | 0
20 |  |  |  | #DIV/0! |  |  |  | 0
21 |  |  |  | #DIV/0! |  |  |  | 0
22 |  |  |  | #DIV/0! |  |  |  | 0
23 |  |  |  | #DIV/0! |  |  |  | 0
24 |  |  |  | #DIV/0! |  |  |  | 0
25 |  |  |  | #DIV/0! |  |  |  | 0
26 |  |  |  | #DIV/0! |  |  |  | 0
27 |  |  |  | #DIV/0! |  |  |  | 0
28 |  |  |  | #DIV/0! |  |  |  | 0
29 |  |  |  | #DIV/0! |  |  |  | 0
30 |  |  |  | #DIV/0! |  |  |  | 0
31 |  |  |  | #DIV/0! |  |  |  | 0
32 |  |  |  | #DIV/0! |  |  |  | 0
33 |  |  |  | #DIV/0! |  |  |  | 0
34 |  |  |  | #DIV/0! |  |  |  | 0
35 |  |  |  | #DIV/0! |  |  |  | 0
36 |  |  |  | #DIV/0! |  |  |  | 0
37 |  |  |  | #DIV/0! |  |  |  | 0
38 |  |  |  | #DIV/0! |  |  |  | 0
39 |  |  |  | #DIV/0! |  |  |  | 0
40 |  |  |  | #DIV/0! |  |  |  | 0
|  |  |  | TOTALS | 0 | 0 | 0 | 0
SUBMITTED BY: |  |  |  |  | RECOMMENDED BY:
CONTRACTOR SIGNATURE |  |  |  | DATE | DESIGN CONSULTANT OR CONSTRUCTION MANAGER |  |  | DATE
APPROVED BY:
|  | BDC/OCS DISTRICT SUPERVISOR |  |  |  | DATE